## DATES
villaID | Civil-1 | Civil-2 | Civil-3 | Civil-4 | Mechanical-1 | Civil-5 | Civil-6 | Civil-7 | Mechanical-2 | Civil-8 | Civil-9 | Civil-10 | Civil-11 | Architectural-1 | Mechanical-3 | Electerical-1 | Architectural-2 | Mechanical-4 | Architectural-3 | Mechanical-5 | Electerical-2 | Architectural-4 | Architectural-5 | Architectural-6 | Architectural-7 | Architectural-8 | Electerical-3 | Architectural-9 | Architectural-10 | Architectural-11 | Architectural-12 | Architectural-13 | Architectural-14 | Architectural-15 | Mechanical-6 | Architectural-16 | Architectural-17 | Electerical-4 | Mechanical-7 | Architectural-18 | Architectural-19 | Architectural-20 | Fence-1 | Fence-2 | Fence-3 | Electerical-5 | Fence-4 | Fence-5 | Fence-6 | Fence-7 | Fence-8 | Mechanical-8 | Fence-9 | Electerical-6 | Electerical-7 | Fence-10 | Fence-11 | Fence-12 | Architectural-21 | Fence-13 | Fence-14 | Fence-15 | Architectural-22 | Architectural-23 | Architectural-24 | Architectural-25 | Architectural-26 | Mechanical-9 | Architectural-27 | Fence-16 | Fence-17 | Architectural-28 | Electerical-8 | Mechanical-10 | Architectural-29 | Architectural-30 | Electerical-9 | Mechanical-11 | Architectural-31 | Electerical-10 | Architectural-32 | Architectural-33
name | Excavation&Compaction of Fondation | Pouring Concrete For Bedding | Reinforcement Concrete For Foundation | Steel Fixing& Carpenter work for Beams | Mech&Elec Establishment for Beams | Pouring Concrete For Beams | Bitmen Coating For Fondation&Beams | Backfilling Inside Fondations | Mech Works Under Grond Slap | Steel Fixing& Carpenter work for Ground Slap | Anti Termite Treatment For Ground Slap | Pouring Concrete For Ground Slap | Precast Constrction | Block Work For GF & Estabishment 1F | L.L & H.L Drainage | Elec Establishment For GF & 1F | Screed Work For 1F & Roof | Water Tank & Heater Foundations | Block Works For 1F | Water Line Network | Continue Elec Establishment For GF & 1F | Thermal Insulation For Roof | Roof Floor Tiles | Plaster Work For Villa | Marbale Stairs & Handrails | Water Proofing Of Bathrooms | Pulling The Elec Wires | Bathroom Tiles | Structure For Gypsum | Gypsum Board For Room | Installation Of Gypsum Board For Bathroom & Kitchen | Putty Filler For Gypsm Board Ceiling | Fixing Shower Glass | Interior Wall Putty Filler | Installation Of Sanitry Fixture | 1st Face Paint | Installation Of Aluminum Windows | Installation Of Elec Fixture & Accessories | Installation Of Water Tank-Heater & Pumps | Installation Of Parquet | Installation Of Wooden Doors | Final Face Paint | Pouring Bedding Concrete For Fence Fondations | RC Concrete For Fence Fondations | Steel Fixing & Carpentry For Fence Columns | Establishing Elec For Fence Columns | Pouring Concrete For Fence Columns | Installation Precast Panel For Fence | Bitumen Coating For Fence Fondations | Pouring Bedding Concrete For 'Front' Fence Fondations | RC Concrete For 'Front' Fence Fondations | Outdoor Drainage & Water Line | Steel Fixing & Carpentry For 'Front' Fence Columns | Establishing Elec For 'Front' Fence Columns | Establishing Elec For Fence & Yard | Backfilling the Yard | Pouring Concrete Wall Of 'Front' Fence Columns | Pouring Concrete Crown Of 'Front' Fence Columns | Bardoura Works For Yard | Pouring Concrete Flower Basin Of 'Front' Fence Columns | Antitermite Treatment For Yard | Pouring Concrete For Yard | Block Work For Flower Basin | Plastering Work For Flower Basin | Interlock Works For The Yard | External Grading Works For The Villa | Installation The Exterior Door & Garage Door | Fixing Floor Drain For The Yard | Granite Surronds Around The Villa | Painting The Base Surface Of The Fence | Painting The Final Face Of The Fence | Exterior Painting Of The Villa | Installation Elec Fixtures & Accessories For The Yard | Connection The Drain To The Piblic Network | Pardora Works For The External Sidewalk | Interlock Works For The Exerrnal Sidewalk | Pulling The Villa's Main Elec Cable | Mech Work Testing & Handover | Arch Snaglist & Handover | ElecWork Testing & Handover | Final Handover Of The Villa To The Consltant | Customer Delivery
nameArabic | انشائي - الحفر ودمك الأساس | انشائي - صب الخرسانة للفرشة | انشائي - خرسانة مسلحة للأساس | انشائي - تركيب حديد ونجارة للكمرات | ميكانيك - التأسيس الميكانيكي والكهربائي للكمرات | انشائي - صب الخرسانة للكمرات | انشائي - طلاء بيتومين للأساس والكمرات | انشائي - ردم داخل الأساسات | ميكانيك - أعمال ميكانيكية تحت البلاطة الأرضية | انشائي - تركيب حديد ونجارة للبلاطة الأرضية | انشائي - معالجة ضد النمل الأبيض للبلاطة الأرضية | انشائي - صب الخرسانة للبلاطة الأرضية | انشائي - إنشاء مسبق الصنع | معماري - بناء الطابق الأرضي والأول | ميكانيك - صرف الدور الارضي والعلوي | كهرباء - التأسيس الكهربائي للطابق الأرضي والأول | معماري - أعمال التسوية للطابق الأول والسقف | ميكانيك - أساسات خزان المياه والسخان | معماري - بناء الطابق الأول | ميكانيك - شبكة خطوط المياه | كهرباء - استكمال التأسيس الكهربائي للطابق الأرضي والأول | معماري - عزل حراري للسقف | معماري - بلاط الأسطح | معماري - لياسة الفيلا | معماري - السلالم الرخامية والدرابزين | معماري - عزل مائي للحمامات | كهرباء - سحب الأسلاك الكهربائية | معماري - بلاط الحمامات | معماري - هيكل الجبس | معماري - ألواح الجبس للغرف | معماري - تركيب ألواح الجبس للحمام والمطبخ | معماري - معجون سقف ألواح الجبس | معماري - تركيب زجاج الحمام | معماري - معجون الجدران الداخلية | ميكانيك - تركيب الأدوات الصحية | معماري - الدهان الأولي | معماري - تركيب نوافذ الألمنيوم | كهرباء - تركيب الأدوات الكهربائية والملحقات | ميكانيك - تركيب خزان المياه والسخان والمضخات | معماري - تركيب الباركيه | معماري - تركيب الأبواب الخشبية | معماري - الدهان النهائي | سور - صب الخرسانة للفرشة لأساسات السور | سور - خرسانة مسلحة لأساسات السور | سور - تركيب حديد ونجارة لأعمدة السور | كهرباء - التأسيس الكهربائي لأعمدة السور | سور - صب الخرسانة لأعمدة السور | سور - تركيب ألواح مسبقة الصنع للسور | سور - طلاء بيتومين لأساسات السور | سور - صب الخرسانة للفرشة لأساسات السور الأمامي | سور - خرسانة مسلحة لأساسات السور الأمامي | ميكانيك - صرف المياه الخارجي وخطوط المياه | سور - تركيب حديد ونجارة لأعمدة السور الأمامي | كهرباء - التأسيس الكهربائي لأعمدة السور الأمامي | كهرباء - التأسيس الكهربائي للسور والفناء | سور - ردم الفناء | سور - صب الخرسانة لجدار أعمدة السور الأمامي | سور - صب الخرسانة لتاج أعمدة السور الأمامي | معماري - أعمال الباردورا للفناء | سور - صب الخرسانة لحوض الزهور لأعمدة السور الأمامي | سور - معالجة ضد النمل الأبيض للفناء | سور - صب الخرسانة للفناء | معماري - بناء حوض الزهور | معماري - لياسة حوض الزهور | معماري - أعمال الإنترلوك للفناء | معماري - أعمال التسوية الخارجية للفيلا | معماري - تركيب الباب الخارجي وباب الجراج | ميكانيك - تركيب الصرف للفناء | معماري - أعمال الجرانيت حول الفيلا | سور - دهان السطح الأساسي للسور | سور - دهان الوجه النهائي للسور | معماري - دهان الواجهة الخارجية للفيلا | كهرباء - تركيب الأدوات الكهربائية والملحقات للفناء | ميكانيك - ربط الصرف والمياه بالشبكة العامة | معماري - أعمال الباردورا للرصيف الخارجي | معماري - أعمال الإنترلوك للرصيف الخارجي | كهرباء - سحب الكابل الكهربائي الرئيسي للفيلا | ميكانيك - اختبار الأعمال الميكانيكية وتسليمها | معماري - قائمة الأعمال المتبقية وتسليمها | كهرباء - اختبار الأعمال الكهربائية وتسليمها | معماري - التسليم النهائي للفيلا للعميل | معماري - تسليم العميل
id | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82
predecessors | [] | [1] | [2] | [3] | [4] | [5] | [6] | [7] | [8] | [9] | [10] | [11, 10] | [12] | [13] | [14] | [14] | [15, 16] | [17] | [17] | [19] | [19] | [18] | [22] | [20, 21] | [24] | [24] | [24] | [26, 23] | [28] | [29, 27] | [30] | [31] | [32] | [32, 25] | [33] | [34] | [34] | [32, 34, 27] | [35, 23] | [36] | [40] | [37, 41] | [13] | [43] | [44] | [45] | [46] | [47] | [48] | [48] | [50] | [49, 15] | [51] | [53] | [52] | [55] | [54] | [57] | [56] | [58] | [59] | [61] | [62] | [63] | [64] | [65] | [65] | [65] | [66] | [76] | [70] | [69, 71, 67, 68] | [71, 72] | [52, 60] | [65, 74] | [75] | [76, 73] | [74, 35, 39] | [76, 72, 41] | [77, 38] | [79, 80, 78, 42] | [81]
V_1 | [15 empty] | 2024-03-06 | 2024-03-13 | 2024-03-20 | 2024-03-20 | 2024-03-24 | 2024-03-24 | 2024-03-25 | 2024-03-31 | 2024-03-31 | 2024-04-07 | 2024-04-07 | 2024-04-07 | 2024-04-12 | 2024-04-16 | 2024-04-23 | 2024-04-28 | 2024-05-03 | 2024-05-10 | 2024-05-10 | 2024-05-14 | 2024-05-17 | 2024-05-17 | 2024-05-17 | 2024-05-22 | 2024-05-24 | 2024-05-28 | 2024-06-05 | 2024-02-28 | 2024-03-02 | 2024-03-09 | 2024-03-16 | 2024-03-20 | 2024-03-22 | 2024-03-27 | 2024-03-27 | 2024-03-29 | 2024-04-01 | 2024-04-02 | 2024-04-07 | 2024-04-07 | 2024-04-09 | 2024-04-12 | 2024-04-14 | 2024-04-14 | 2024-04-17 | 2024-04-20 | 2024-04-21 | 2024-04-22 | 2024-04-28 | 2024-05-03 | 2024-05-10 | 2024-05-10 | 2024-05-10 | 2024-05-14 | 2024-05-14 | 2024-05-17 | 2024-05-21 | 2024-05-29 | 2024-04-22 | 2024-05-10 | 2024-05-12 | 2024-06-03 | 2024-05-31 | 2024-06-05 | 2024-06-08 | 2024-06-14 | 2024-06-19
V_2 | [15 empty] | 2024-03-06 | 2024-03-13 | 2024-03-20 | 2024-03-20 | 2024-03-24 | 2024-03-24 | 2024-03-25 | 2024-03-31 | 2024-03-31 | 2024-04-07 | 2024-04-07 | 2024-04-07 | 2024-04-12 | 2024-04-16 | 2024-04-23 | 2024-04-28 | 2024-05-03 | 2024-05-10 | 2024-05-10 | 2024-05-14 | 2024-05-17 | 2024-05-17 | 2024-05-17 | 2024-05-22 | 2024-05-24 | 2024-05-28 | 2024-06-05 | 2024-02-28 | 2024-03-02 | 2024-03-09 | 2024-03-16 | 2024-03-20 | 2024-03-22 | 2024-03-27 | 2024-03-27 | 2024-03-29 | 2024-04-01 | 2024-04-02 | 2024-04-07 | 2024-04-07 | 2024-04-09 | 2024-04-12 | 2024-04-14 | 2024-04-14 | 2024-04-17 | 2024-04-20 | 2024-04-21 | 2024-04-22 | 2024-04-28 | 2024-05-03 | 2024-05-10 | 2024-05-10 | 2024-05-10 | 2024-05-14 | 2024-05-14 | 2024-05-17 | 2024-05-21 | 2024-05-29 | 2024-04-22 | 2024-05-10 | 2024-05-12 | 2024-06-03 | 2024-05-31 | 2024-06-05 | 2024-06-08 | 2024-06-14 | 2024-06-19
V_3 | [15 empty] | 2024-03-06 | 2024-03-13 | 2024-03-20 | 2024-03-20 | 2024-03-24 | 2024-03-24 | 2024-03-25 | 2024-03-31 | 2024-03-31 | 2024-04-07 | 2024-04-07 | 2024-04-07 | 2024-04-12 | 2024-04-16 | 2024-04-23 | 2024-04-28 | 2024-05-03 | 2024-05-10 | 2024-05-10 | 2024-05-14 | 2024-05-17 | 2024-05-17 | 2024-05-17 | 2024-05-22 | 2024-05-24 | 2024-05-28 | 2024-06-05 | 2024-02-28 | 2024-03-02 | 2024-03-09 | 2024-03-16 | 2024-03-20 | 2024-03-22 | 2024-03-27 | 2024-03-27 | 2024-03-29 | 2024-04-01 | 2024-04-02 | 2024-04-07 | 2024-04-07 | 2024-04-09 | 2024-04-12 | 2024-04-14 | 2024-04-14 | 2024-04-17 | 2024-04-20 | 2024-04-21 | 2024-04-22 | 2024-04-28 | 2024-05-03 | 2024-05-10 | 2024-05-10 | 2024-05-10 | 2024-05-14 | 2024-05-14 | 2024-05-17 | 2024-05-21 | 2024-05-29 | 2024-04-22 | 2024-05-10 | 2024-05-12 | 2024-06-03 | 2024-05-31 | 2024-06-05 | 2024-06-08 | 2024-06-14 | 2024-06-19
V_4 | 2024-01-21 | 2024-01-26 | 2024-01-28 | 2024-02-02 | 2024-02-06 | 2024-02-10 | 2024-02-11 | 2024-02-12 | 2024-02-14 | 2024-02-17 | 2024-02-19 | 2024-02-19 | 2024-02-20 | 2024-02-28 | 2024-03-06 | 2024-03-06 | 2024-03-13 | 2024-03-20 | 2024-03-20 | 2024-03-24 | 2024-03-24 | 2024-03-25 | 2024-03-31 | 2024-03-31 | 2024-04-07 | 2024-04-07 | 2024-04-07 | 2024-04-12 | 2024-04-16 | 2024-04-23 | 2024-04-28 | 2024-05-03 | 2024-05-10 | 2024-05-10 | 2024-05-14 | 2024-05-17 | 2024-05-17 | 2024-05-17 | 2024-05-22 | 2024-05-24 | 2024-05-28 | 2024-06-05 | 2024-02-28 | 2024-03-02 | 2024-03-09 | 2024-03-16 | 2024-03-20 | 2024-03-22 | 2024-03-27 | 2024-03-27 | 2024-03-29 | 2024-04-01 | 2024-04-02 | 2024-04-07 | 2024-04-07 | 2024-04-09 | 2024-04-12 | 2024-04-14 | 2024-04-14 | 2024-04-17 | 2024-04-20 | 2024-04-21 | 2024-04-22 | 2024-04-28 | 2024-05-03 | 2024-05-10 | 2024-05-10 | 2024-05-10 | 2024-05-14 | 2024-05-14 | 2024-05-17 | 2024-05-21 | 2024-05-29 | 2024-04-22 | 2024-05-10 | 2024-05-12 | 2024-06-03 | 2024-05-31 | 2024-06-05 | 2024-06-08 | 2024-06-14 | 2024-06-19
V_5 | 2024-01-21 | 2024-01-26 | 2024-01-28 | 2024-02-02 | 2024-02-06 | 2024-02-10 | 2024-02-11 | 2024-02-12 | 2024-02-14 | 2024-02-17 | 2024-02-19 | 2024-02-19 | 2024-02-20 | 2024-02-28 | 2024-03-06 | 2024-03-06 | 2024-03-13 | 2024-03-20 | 2024-03-20 | 2024-03-24 | 2024-03-24 | 2024-03-25 | 2024-03-31 | 2024-03-31 | 2024-04-07 | 2024-04-07 | 2024-04-07 | 2024-04-12 | 2024-04-16 | 2024-04-23 | 2024-04-28 | 2024-05-03 | 2024-05-10 | 2024-05-10 | 2024-05-14 | 2024-05-17 | 2024-05-17 | 2024-05-17 | 2024-05-22 | 2024-05-24 | 2024-05-28 | 2024-06-05 | 2024-02-28 | 2024-03-02 | 2024-03-09 | 2024-03-16 | 2024-03-20 | 2024-03-22 | 2024-03-27 | 2024-03-27 | 2024-03-29 | 2024-04-01 | 2024-04-02 | 2024-04-07 | 2024-04-07 | 2024-04-09 | 2024-04-12 | 2024-04-14 | 2024-04-14 | 2024-04-17 | 2024-04-20 | 2024-04-21 | 2024-04-22 | 2024-04-28 | 2024-05-03 | 2024-05-10 | 2024-05-10 | 2024-05-10 | 2024-05-14 | 2024-05-14 | 2024-05-17 | 2024-05-21 | 2024-05-29 | 2024-04-22 | 2024-05-10 | 2024-05-12 | 2024-06-03 | 2024-05-31 | 2024-06-05 | 2024-06-08 | 2024-06-14 | 2024-06-19
V_6 | 2024-01-21 | 2024-01-26 | 2024-01-28 | 2024-02-02 | 2024-02-06 | 2024-02-10 | 2024-02-11 | 2024-02-12 | 2024-02-14 | 2024-02-17 | 2024-02-19 | 2024-02-19 | 2024-02-20 | 2024-02-28 | 2024-03-06 | 2024-03-06 | 2024-03-13 | 2024-03-20 | 2024-03-20 | 2024-03-24 | 2024-03-24 | 2024-03-25 | 2024-03-31 | 2024-03-31 | 2024-04-07 | 2024-04-07 | 2024-04-07 | 2024-04-12 | 2024-04-16 | 2024-04-23 | 2024-04-28 | 2024-05-03 | 2024-05-10 | 2024-05-10 | 2024-05-14 | 2024-05-17 | 2024-05-17 | 2024-05-17 | 2024-05-22 | 2024-05-24 | 2024-05-28 | 2024-06-05 | 2024-02-28 | 2024-03-02 | 2024-03-09 | 2024-03-16 | 2024-03-20 | 2024-03-22 | 2024-03-27 | 2024-03-27 | 2024-03-29 | 2024-04-01 | 2024-04-02 | 2024-04-07 | 2024-04-07 | 2024-04-09 | 2024-04-12 | 2024-04-14 | 2024-04-14 | 2024-04-17 | 2024-04-20 | 2024-04-21 | 2024-04-22 | 2024-04-28 | 2024-05-03 | 2024-05-10 | 2024-05-10 | 2024-05-10 | 2024-05-14 | 2024-05-14 | 2024-05-17 | 2024-05-21 | 2024-05-29 | 2024-04-22 | 2024-05-10 | 2024-05-12 | 2024-06-03 | 2024-05-31 | 2024-06-05 | 2024-06-08 | 2024-06-14 | 2024-06-19
V_7 | 2024-01-21 | 2024-01-26 | 2024-01-28 | 2024-02-02 | 2024-02-06 | 2024-02-10 | 2024-02-11 | 2024-02-12 | 2024-02-14 | 2024-02-17 | 2024-02-19 | 2024-02-19 | 2024-02-20 | 2024-02-28 | 2024-03-06 | 2024-03-06 | 2024-03-13 | 2024-03-20 | 2024-03-20 | 2024-03-24 | 2024-03-24 | 2024-03-25 | 2024-03-31 | 2024-03-31 | 2024-04-07 | 2024-04-07 | 2024-04-07 | 2024-04-12 | 2024-04-16 | 2024-04-23 | 2024-04-28 | 2024-05-03 | 2024-05-10 | 2024-05-10 | 2024-05-14 | 2024-05-17 | 2024-05-17 | 2024-05-17 | 2024-05-22 | 2024-05-24 | 2024-05-28 | 2024-06-05 | 2024-02-28 | 2024-03-02 | 2024-03-09 | 2024-03-16 | 2024-03-20 | 2024-03-22 | 2024-03-27 | 2024-03-27 | 2024-03-29 | 2024-04-01 | 2024-04-02 | 2024-04-07 | 2024-04-07 | 2024-04-09 | 2024-04-12 | 2024-04-14 | 2024-04-14 | 2024-04-17 | 2024-04-20 | 2024-04-21 | 2024-04-22 | 2024-04-28 | 2024-05-03 | 2024-05-10 | 2024-05-10 | 2024-05-10 | 2024-05-14 | 2024-05-14 | 2024-05-17 | 2024-05-21 | 2024-05-29 | 2024-04-22 | 2024-05-10 | 2024-05-12 | 2024-06-03 | 2024-05-31 | 2024-06-05 | 2024-06-08 | 2024-06-14 | 2024-06-19
V_8 | 2024-01-21 | 2024-01-26 | 2024-01-28 | 2024-02-02 | 2024-02-06 | 2024-02-10 | 2024-02-11 | 2024-02-12 | 2024-02-14 | 2024-02-17 | 2024-02-19 | 2024-02-19 | 2024-02-20 | 2024-02-28 | 2024-03-06 | 2024-03-06 | 2024-03-13 | 2024-03-20 | 2024-03-20 | 2024-03-24 | 2024-03-24 | 2024-03-25 | 2024-03-31 | 2024-03-31 | 2024-04-07 | 2024-04-07 | 2024-04-07 | 2024-04-12 | 2024-04-16 | 2024-04-23 | 2024-04-28 | 2024-05-03 | 2024-05-10 | 2024-05-10 | 2024-05-14 | 2024-05-17 | 2024-05-17 | 2024-05-17 | 2024-05-22 | 2024-05-24 | 2024-05-28 | 2024-06-05 | 2024-02-28 | 2024-03-02 | 2024-03-09 | 2024-03-16 | 2024-03-20 | 2024-03-22 | 2024-03-27 | 2024-03-27 | 2024-03-29 | 2024-04-01 | 2024-04-02 | 2024-04-07 | 2024-04-07 | 2024-04-09 | 2024-04-12 | 2024-04-14 | 2024-04-14 | 2024-04-17 | 2024-04-20 | 2024-04-21 | 2024-04-22 | 2024-04-28 | 2024-05-03 | 2024-05-10 | 2024-05-10 | 2024-05-10 | 2024-05-14 | 2024-05-14 | 2024-05-17 | 2024-05-21 | 2024-05-29 | 2024-04-22 | 2024-05-10 | 2024-05-12 | 2024-06-03 | 2024-05-31 | 2024-06-05 | 2024-06-08 | 2024-06-14 | 2024-06-19
V_9 | 2024-01-26 | 2024-01-30 | 2024-02-02 | 2024-02-06 | 2024-02-11 | 2024-02-14 | 2024-02-16 | 2024-02-18 | 2024-02-20 | 2024-02-24 | 2024-02-26 | 2024-02-26 | 2024-02-28 | 2024-03-08 | 2024-03-15 | 2024-03-15 | 2024-03-22 | 2024-03-29 | 2024-03-29 | 2024-04-01 | 2024-04-01 | 2024-04-02 | 2024-04-08 | 2024-04-08 | 2024-04-15 | 2024-04-15 | 2024-04-15 | 2024-04-20 | 2024-04-24 | 2024-05-01 | 2024-05-06 | 2024-05-11 | 2024-05-18 | 2024-05-18 | 2024-05-22 | 2024-05-25 | 2024-05-25 | 2024-05-25 | 2024-05-31 | 2024-06-01 | 2024-06-05 | 2024-06-14 | 2024-03-08 | 2024-03-10 | 2024-03-17 | 2024-03-24 | 2024-03-29 | 2024-03-30 | 2024-04-05 | 2024-04-05 | 2024-04-06 | 2024-04-09 | 2024-04-10 | 2024-04-15 | 2024-04-15 | 2024-04-17 | 2024-04-20 | 2024-04-22 | 2024-04-22 | 2024-04-26 | 2024-04-28 | 2024-04-29 | 2024-04-30 | 2024-05-06 | 2024-05-11 | 2024-05-18 | 2024-05-18 | 2024-05-18 | 2024-05-22 | 2024-05-22 | 2024-05-25 | 2024-05-29 | 2024-06-07 | 2024-04-30 | 2024-05-18 | 2024-05-20 | 2024-06-11 | 2024-06-08 | 2024-06-14 | 2024-06-16 | 2024-06-22 | 2024-06-28
V_10 | 2024-01-26 | 2024-01-30 | 2024-02-02 | 2024-02-06 | 2024-02-11 | 2024-02-14 | 2024-02-16 | 2024-02-18 | 2024-02-20 | 2024-02-24 | 2024-02-26 | 2024-02-26 | 2024-02-28 | [16 empty] | 2024-05-01 | 2024-05-06 | 2024-05-11 | 2024-05-18 | 2024-05-18 | 2024-05-22 | 2024-05-25 | 2024-05-25 | 2024-05-25 | 2024-05-31 | 2024-06-01 | 2024-06-05 | 2024-06-14 | 2024-03-08 | 2024-03-10 | 2024-03-17 | 2024-03-24 | 2024-03-29 | 2024-03-30 | 2024-04-05 | 2024-04-05 | 2024-04-06 | 2024-04-09 | 2024-04-10 | 2024-04-15 | 2024-04-15 | 2024-04-17 | 2024-04-20 | 2024-04-22 | 2024-04-22 | 2024-04-26 | 2024-04-28 | 2024-04-29 | 2024-04-30 | 2024-05-06 | 2024-05-11 | 2024-05-18 | 2024-05-18 | 2024-05-18 | 2024-05-22 | 2024-05-22 | 2024-05-25 | 2024-05-29 | 2024-06-07 | 2024-04-30 | 2024-05-18 | 2024-05-20 | 2024-06-11 | 2024-06-08 | 2024-06-14 | 2024-06-16 | 2024-06-22 | 2024-06-28
V_11 | 2024-01-26 | 2024-01-30 | 2024-02-02 | 2024-02-06 | 2024-02-11 | 2024-02-14 | 2024-02-16 | 2024-02-18 | 2024-02-20 | 2024-02-24 | 2024-02-26 | 2024-02-26 | 2024-02-28 | [16 empty] | 2024-05-01 | 2024-05-06 | 2024-05-11 | 2024-05-18 | 2024-05-18 | 2024-05-22 | 2024-05-25 | 2024-05-25 | 2024-05-25 | 2024-05-31 | 2024-06-01 | 2024-06-05 | 2024-06-14 | 2024-03-08 | 2024-03-10 | 2024-03-17 | 2024-03-24 | 2024-03-29 | 2024-03-30 | 2024-04-05 | 2024-04-05 | 2024-04-06 | 2024-04-09 | 2024-04-10 | 2024-04-15 | 2024-04-15 | 2024-04-17 | 2024-04-20 | 2024-04-22 | 2024-04-22 | 2024-04-26 | 2024-04-28 | 2024-04-29 | 2024-04-30 | 2024-05-06 | 2024-05-11 | 2024-05-18 | 2024-05-18 | 2024-05-18 | 2024-05-22 | 2024-05-22 | 2024-05-25 | 2024-05-29 | 2024-06-07 | 2024-04-30 | 2024-05-18 | 2024-05-20 | 2024-06-11 | 2024-06-08 | 2024-06-14 | 2024-06-16 | 2024-06-22 | 2024-06-28
V_12 | 2024-01-26 | 2024-01-30 | 2024-02-02 | 2024-02-06 | 2024-02-11 | 2024-02-14 | 2024-02-16 | 2024-02-18 | 2024-02-20 | 2024-02-24 | 2024-02-26 | 2024-02-26 | 2024-02-28 | [16 empty] | 2024-05-01 | 2024-05-06 | 2024-05-11 | 2024-05-18 | 2024-05-18 | 2024-05-22 | 2024-05-25 | 2024-05-25 | 2024-05-25 | 2024-05-31 | 2024-06-01 | 2024-06-05 | 2024-06-14 | 2024-03-08 | 2024-03-10 | 2024-03-17 | 2024-03-24 | 2024-03-29 | 2024-03-30 | 2024-04-05 | 2024-04-05 | 2024-04-06 | 2024-04-09 | 2024-04-10 | 2024-04-15 | 2024-04-15 | 2024-04-17 | 2024-04-20 | 2024-04-22 | 2024-04-22 | 2024-04-26 | 2024-04-28 | 2024-04-29 | 2024-04-30 | 2024-05-06 | 2024-05-11 | 2024-05-18 | 2024-05-18 | 2024-05-18 | 2024-05-22 | 2024-05-22 | 2024-05-25 | 2024-05-29 | 2024-06-07 | 2024-04-30 | 2024-05-18 | 2024-05-20 | 2024-06-11 | 2024-06-08 | 2024-06-14 | 2024-06-16 | 2024-06-22 | 2024-06-28
V_13 | 2024-01-26 | 2024-01-30 | 2024-02-02 | 2024-02-06 | 2024-02-11 | 2024-02-14 | 2024-02-16 | 2024-02-18 | 2024-02-20 | 2024-02-24 | 2024-02-26 | 2024-02-26 | 2024-02-28 | [16 empty] | 2024-05-01 | 2024-05-06 | 2024-05-11 | 2024-05-18 | 2024-05-18 | 2024-05-22 | 2024-05-25 | 2024-05-25 | 2024-05-25 | 2024-05-31 | 2024-06-01 | 2024-06-05 | 2024-06-14 | 2024-03-08 | 2024-03-10 | 2024-03-17 | 2024-03-24 | 2024-03-29 | 2024-03-30 | 2024-04-05 | 2024-04-05 | 2024-04-06 | 2024-04-09 | 2024-04-10 | 2024-04-15 | 2024-04-15 | 2024-04-17 | 2024-04-20 | 2024-04-22 | 2024-04-22 | 2024-04-26 | 2024-04-28 | 2024-04-29 | 2024-04-30 | 2024-05-06 | 2024-05-11 | 2024-05-18 | 2024-05-18 | 2024-05-18 | 2024-05-22 | 2024-05-22 | 2024-05-25 | 2024-05-29 | 2024-06-07 | 2024-04-30 | 2024-05-18 | 2024-05-20 | 2024-06-11 | 2024-06-08 | 2024-06-14 | 2024-06-16 | 2024-06-22 | 2024-06-28
V_14 | 2024-01-26 | 2024-01-30 | 2024-02-02 | 2024-02-06 | 2024-02-11 | 2024-02-14 | 2024-02-16 | 2024-02-18 | 2024-02-20 | 2024-02-24 | 2024-02-26 | 2024-02-26 | 2024-02-28 | [16 empty] | 2024-05-01 | 2024-05-06 | 2024-05-11 | 2024-05-18 | 2024-05-18 | 2024-05-22 | 2024-05-25 | 2024-05-25 | 2024-05-25 | 2024-05-31 | 2024-06-01 | 2024-06-05 | 2024-06-14 | 2024-03-08 | 2024-03-10 | 2024-03-17 | 2024-03-24 | 2024-03-29 | 2024-03-30 | 2024-04-05 | 2024-04-05 | 2024-04-06 | 2024-04-09 | 2024-04-10 | 2024-04-15 | 2024-04-15 | 2024-04-17 | 2024-04-20 | 2024-04-22 | 2024-04-22 | 2024-04-26 | 2024-04-28 | 2024-04-29 | 2024-04-30 | 2024-05-06 | 2024-05-11 | 2024-05-18 | 2024-05-18 | 2024-05-18 | 2024-05-22 | 2024-05-22 | 2024-05-25 | 2024-05-29 | 2024-06-07 | 2024-04-30 | 2024-05-18 | 2024-05-20 | 2024-06-11 | 2024-06-08 | 2024-06-14 | 2024-06-16 | 2024-06-22 | 2024-06-28
V_15 | 2024-01-26 | 2024-01-30 | 2024-02-02 | 2024-02-06 | 2024-02-11 | 2024-02-14 | 2024-02-16 | 2024-02-18 | 2024-02-20 | 2024-02-24 | 2024-02-26 | 2024-02-26 | 2024-02-28 | [16 empty] | 2024-05-01 | 2024-05-06 | 2024-05-11 | 2024-05-18 | 2024-05-18 | 2024-05-22 | 2024-05-25 | 2024-05-25 | 2024-05-25 | 2024-05-31 | 2024-06-01 | 2024-06-05 | 2024-06-14 | 2024-03-08 | 2024-03-10 | 2024-03-17 | 2024-03-24 | 2024-03-29 | 2024-03-30 | 2024-04-05 | 2024-04-05 | 2024-04-06 | 2024-04-09 | 2024-04-10 | 2024-04-15 | 2024-04-15 | 2024-04-17 | 2024-04-20 | 2024-04-22 | 2024-04-22 | 2024-04-26 | 2024-04-28 | 2024-04-29 | 2024-04-30 | 2024-05-06 | 2024-05-11 | 2024-05-18 | 2024-05-18 | 2024-05-18 | 2024-05-22 | 2024-05-22 | 2024-05-25 | 2024-05-29 | 2024-06-07 | 2024-04-30 | 2024-05-18 | 2024-05-20 | 2024-06-11 | 2024-06-08 | 2024-06-14 | 2024-06-16 | 2024-06-22 | 2024-06-28
V_16 | 2024-01-26 | 2024-01-30 | 2024-02-02 | 2024-02-06 | 2024-02-11 | 2024-02-14 | 2024-02-16 | 2024-02-18 | 2024-02-20 | 2024-02-24 | 2024-02-26 | 2024-02-26 | 2024-02-28 | [16 empty] | 2024-05-01 | 2024-05-06 | 2024-05-11 | 2024-05-18 | 2024-05-18 | 2024-05-22 | 2024-05-25 | 2024-05-25 | 2024-05-25 | 2024-05-31 | 2024-06-01 | 2024-06-05 | 2024-06-14 | 2024-03-08 | 2024-03-10 | 2024-03-17 | 2024-03-24 | 2024-03-29 | 2024-03-30 | 2024-04-05 | 2024-04-05 | 2024-04-06 | 2024-04-09 | 2024-04-10 | 2024-04-15 | 2024-04-15 | 2024-04-17 | 2024-04-20 | 2024-04-22 | 2024-04-22 | 2024-04-26 | 2024-04-28 | 2024-04-29 | 2024-04-30 | 2024-05-06 | 2024-05-11 | 2024-05-18 | 2024-05-18 | 2024-05-18 | 2024-05-22 | 2024-05-22 | 2024-05-25 | 2024-05-29 | 2024-06-07 | 2024-04-30 | 2024-05-18 | 2024-05-20 | 2024-06-11 | 2024-06-08 | 2024-06-14 | 2024-06-16 | 2024-06-22 | 2024-06-28
V_17 | 2024-01-30 | 2024-02-04 | 2024-02-06 | 2024-02-11 | 2024-02-16 | 2024-02-19 | 2024-02-20 | 2024-02-23 | 2024-02-25 | 2024-02-28 | 2024-03-02 | 2024-03-02 | 2024-03-08 | [16 empty] | 2024-05-10 | 2024-05-14 | 2024-05-19 | 2024-05-26 | 2024-05-26 | 2024-05-31 | 2024-06-02 | 2024-06-02 | 2024-06-02 | 2024-06-08 | 2024-06-09 | 2024-06-14 | 2024-06-22 | 2024-03-16 | 2024-03-18 | 2024-03-25 | 2024-04-01 | 2024-04-06 | 2024-04-07 | 2024-04-13 | 2024-04-13 | 2024-04-14 | 2024-04-17 | 2024-04-19 | 2024-04-23 | 2024-04-23 | 2024-04-26 | 2024-04-28 | 2024-04-30 | 2024-04-30 | 2024-05-04 | 2024-05-06 | 2024-05-07 | 2024-05-08 | 2024-05-14 | 2024-05-19 | 2024-05-26 | 2024-05-26 | 2024-05-26 | 2024-05-31 | 2024-05-31 | 2024-06-02 | 2024-06-07 | 2024-06-15 | 2024-05-08 | 2024-05-26 | 2024-05-28 | 2024-06-19 | 2024-06-16 | 2024-06-22 | 2024-06-24 | 2024-06-30 | 2024-07-06
V_18 | 2024-01-30 | 2024-02-04 | 2024-02-06 | 2024-02-11 | 2024-02-16 | 2024-02-19 | 2024-02-20 | 2024-02-23 | 2024-02-25 | 2024-02-28 | 2024-03-02 | 2024-03-02 | 2024-03-08 | [16 empty] | 2024-05-10 | 2024-05-14 | 2024-05-19 | 2024-05-26 | 2024-05-26 | 2024-05-31 | 2024-06-02 | 2024-06-02 | 2024-06-02 | 2024-06-08 | 2024-06-09 | 2024-06-14 | 2024-06-22 | 2024-03-16 | 2024-03-18 | 2024-03-25 | 2024-04-01 | 2024-04-06 | 2024-04-07 | 2024-04-13 | 2024-04-13 | 2024-04-14 | 2024-04-17 | 2024-04-19 | 2024-04-23 | 2024-04-23 | 2024-04-26 | 2024-04-28 | 2024-04-30 | 2024-04-30 | 2024-05-04 | 2024-05-06 | 2024-05-07 | 2024-05-08 | 2024-05-14 | 2024-05-19 | 2024-05-26 | 2024-05-26 | 2024-05-26 | 2024-05-31 | 2024-05-31 | 2024-06-02 | 2024-06-07 | 2024-06-15 | 2024-05-08 | 2024-05-26 | 2024-05-28 | 2024-06-19 | 2024-06-16 | 2024-06-22 | 2024-06-24 | 2024-06-30 | 2024-07-06
V_19 | 2024-01-30 | 2024-02-04 | 2024-02-06 | 2024-02-11 | 2024-02-16 | 2024-02-19 | 2024-02-20 | 2024-02-23 | 2024-02-25 | 2024-02-28 | 2024-03-02 | 2024-03-02 | 2024-03-08 | 2024-03-16 | 2024-03-23 | 2024-03-23 | 2024-03-30 | 2024-04-06 | 2024-04-06 | 2024-04-09 | 2024-04-09 | 2024-04-10 | 2024-04-16 | 2024-04-16 | 2024-04-23 | 2024-04-23 | 2024-04-23 | 2024-04-28 | 2024-05-03 | 2024-05-10 | 2024-05-14 | 2024-05-19 | 2024-05-26 | 2024-05-26 | 2024-05-31 | 2024-06-02 | 2024-06-02 | 2024-06-02 | 2024-06-08 | 2024-06-09 | 2024-06-14 | 2024-06-22 | 2024-03-16 | 2024-03-18 | 2024-03-25 | 2024-04-01 | 2024-04-06 | 2024-04-07 | 2024-04-13 | 2024-04-13 | 2024-04-14 | 2024-04-17 | 2024-04-19 | 2024-04-23 | 2024-04-23 | 2024-04-26 | 2024-04-28 | 2024-04-30 | 2024-04-30 | 2024-05-04 | 2024-05-06 | 2024-05-07 | 2024-05-08 | 2024-05-14 | 2024-05-19 | 2024-05-26 | 2024-05-26 | 2024-05-26 | 2024-05-31 | 2024-05-31 | 2024-06-02 | 2024-06-07 | 2024-06-15 | 2024-05-08 | 2024-05-26 | 2024-05-28 | 2024-06-19 | 2024-06-16 | 2024-06-22 | 2024-06-24 | 2024-06-30 | 2024-07-06
V_20 | 2024-01-30 | 2024-02-04 | 2024-02-06 | 2024-02-11 | 2024-02-16 | 2024-02-19 | 2024-02-20 | 2024-02-23 | 2024-02-25 | 2024-02-28 | 2024-03-02 | 2024-03-02 | 2024-03-08 | 2024-03-16 | 2024-03-23 | 2024-03-23 | 2024-03-30 | 2024-04-06 | 2024-04-06 | 2024-04-09 | 2024-04-09 | 2024-04-10 | 2024-04-16 | 2024-04-16 | 2024-04-23 | 2024-04-23 | 2024-04-23 | 2024-04-28 | 2024-05-03 | 2024-05-10 | 2024-05-14 | 2024-05-19 | 2024-05-26 | 2024-05-26 | 2024-05-31 | 2024-06-02 | 2024-06-02 | 2024-06-02 | 2024-06-08 | 2024-06-09 | 2024-06-14 | 2024-06-22 | 2024-03-16 | 2024-03-18 | 2024-03-25 | 2024-04-01 | 2024-04-06 | 2024-04-07 | 2024-04-13 | 2024-04-13 | 2024-04-14 | 2024-04-17 | 2024-04-19 | 2024-04-23 | 2024-04-23 | 2024-04-26 | 2024-04-28 | 2024-04-30 | 2024-04-30 | 2024-05-04 | 2024-05-06 | 2024-05-07 | 2024-05-08 | 2024-05-14 | 2024-05-19 | 2024-05-26 | 2024-05-26 | 2024-05-26 | 2024-05-31 | 2024-05-31 | 2024-06-02 | 2024-06-07 | 2024-06-15 | 2024-05-08 | 2024-05-26 | 2024-05-28 | 2024-06-19 | 2024-06-16 | 2024-06-22 | 2024-06-24 | 2024-06-30 | 2024-07-06
V_21 | 2024-01-30 | 2024-02-04 | 2024-02-06 | 2024-02-11 | 2024-02-16 | 2024-02-19 | 2024-02-20 | 2024-02-23 | 2024-02-25 | 2024-02-28 | 2024-03-02 | 2024-03-02 | 2024-03-08 | 2024-03-16 | 2024-03-23 | 2024-03-23 | 2024-03-30 | 2024-04-06 | 2024-04-06 | 2024-04-09 | 2024-04-09 | 2024-04-10 | 2024-04-16 | 2024-04-16 | 2024-04-23 | 2024-04-23 | 2024-04-23 | 2024-04-28 | 2024-05-03 | 2024-05-10 | 2024-05-14 | 2024-05-19 | 2024-05-26 | 2024-05-26 | 2024-05-31 | 2024-06-02 | 2024-06-02 | 2024-06-02 | 2024-06-08 | 2024-06-09 | 2024-06-14 | 2024-06-22 | 2024-03-16 | 2024-03-18 | 2024-03-25 | 2024-04-01 | 2024-04-06 | 2024-04-07 | 2024-04-13 | 2024-04-13 | 2024-04-14 | 2024-04-17 | 2024-04-19 | 2024-04-23 | 2024-04-23 | 2024-04-26 | 2024-04-28 | 2024-04-30 | 2024-04-30 | 2024-05-04 | 2024-05-06 | 2024-05-07 | 2024-05-08 | 2024-05-14 | 2024-05-19 | 2024-05-26 | 2024-05-26 | 2024-05-26 | 2024-05-31 | 2024-05-31 | 2024-06-02 | 2024-06-07 | 2024-06-15 | 2024-05-08 | 2024-05-26 | 2024-05-28 | 2024-06-19 | 2024-06-16 | 2024-06-22 | 2024-06-24 | 2024-06-30 | 2024-07-06
V_22 | 2024-01-30 | 2024-02-04 | 2024-02-06 | 2024-02-11 | 2024-02-16 | 2024-02-19 | 2024-02-20 | 2024-02-23 | 2024-02-25 | 2024-02-28 | 2024-03-02 | 2024-03-02 | 2024-03-08 | 2024-03-16 | 2024-03-23 | 2024-03-23 | 2024-03-30 | 2024-04-06 | 2024-04-06 | 2024-04-09 | 2024-04-09 | 2024-04-10 | 2024-04-16 | 2024-04-16 | 2024-04-23 | 2024-04-23 | 2024-04-23 | 2024-04-28 | 2024-05-03 | 2024-05-10 | 2024-05-14 | 2024-05-19 | 2024-05-26 | 2024-05-26 | 2024-05-31 | 2024-06-02 | 2024-06-02 | 2024-06-02 | 2024-06-08 | 2024-06-09 | 2024-06-14 | 2024-06-22 | 2024-03-16 | 2024-03-18 | 2024-03-25 | 2024-04-01 | 2024-04-06 | 2024-04-07 | 2024-04-13 | 2024-04-13 | 2024-04-14 | 2024-04-17 | 2024-04-19 | 2024-04-23 | 2024-04-23 | 2024-04-26 | 2024-04-28 | 2024-04-30 | 2024-04-30 | 2024-05-04 | 2024-05-06 | 2024-05-07 | 2024-05-08 | 2024-05-14 | 2024-05-19 | 2024-05-26 | 2024-05-26 | 2024-05-26 | 2024-05-31 | 2024-05-31 | 2024-06-02 | 2024-06-07 | 2024-06-15 | 2024-05-08 | 2024-05-26 | 2024-05-28 | 2024-06-19 | 2024-06-16 | 2024-06-22 | 2024-06-24 | 2024-06-30 | 2024-07-06
V_23 | 2024-01-30 | 2024-02-04 | 2024-02-06 | 2024-02-11 | 2024-02-16 | 2024-02-19 | 2024-02-20 | 2024-02-23 | 2024-02-25 | 2024-02-28 | 2024-03-02 | 2024-03-02 | 2024-03-08 | 2024-03-16 | 2024-03-23 | 2024-03-23 | 2024-03-30 | 2024-04-06 | 2024-04-06 | 2024-04-09 | 2024-04-09 | 2024-04-10 | 2024-04-16 | 2024-04-16 | 2024-04-23 | 2024-04-23 | 2024-04-23 | 2024-04-28 | 2024-05-03 | 2024-05-10 | 2024-05-14 | 2024-05-19 | 2024-05-26 | 2024-05-26 | 2024-05-31 | 2024-06-02 | 2024-06-02 | 2024-06-02 | 2024-06-08 | 2024-06-09 | 2024-06-14 | 2024-06-22 | 2024-03-16 | 2024-03-18 | 2024-03-25 | 2024-04-01 | 2024-04-06 | 2024-04-07 | 2024-04-13 | 2024-04-13 | 2024-04-14 | 2024-04-17 | 2024-04-19 | 2024-04-23 | 2024-04-23 | 2024-04-26 | 2024-04-28 | 2024-04-30 | 2024-04-30 | 2024-05-04 | 2024-05-06 | 2024-05-07 | 2024-05-08 | 2024-05-14 | 2024-05-19 | 2024-05-26 | 2024-05-26 | 2024-05-26 | 2024-05-31 | 2024-05-31 | 2024-06-02 | 2024-06-07 | 2024-06-15 | 2024-05-08 | 2024-05-26 | 2024-05-28 | 2024-06-19 | 2024-06-16 | 2024-06-22 | 2024-06-24 | 2024-06-30 | 2024-07-06
V_24 | 2024-01-30 | 2024-02-04 | 2024-02-06 | 2024-02-11 | 2024-02-16 | 2024-02-19 | 2024-02-20 | 2024-02-23 | 2024-02-25 | 2024-02-28 | 2024-03-02 | 2024-03-02 | 2024-03-08 | 2024-03-16 | 2024-03-23 | 2024-03-23 | 2024-03-30 | 2024-04-06 | 2024-04-06 | 2024-04-09 | 2024-04-09 | 2024-04-10 | 2024-04-16 | 2024-04-16 | 2024-04-23 | 2024-04-23 | 2024-04-23 | 2024-04-28 | 2024-05-03 | 2024-05-10 | 2024-05-14 | 2024-05-19 | 2024-05-26 | 2024-05-26 | 2024-05-31 | 2024-06-02 | 2024-06-02 | 2024-06-02 | 2024-06-08 | 2024-06-09 | 2024-06-14 | 2024-06-22 | 2024-03-16 | 2024-03-18 | 2024-03-25 | 2024-04-01 | 2024-04-06 | 2024-04-07 | 2024-04-13 | 2024-04-13 | 2024-04-14 | 2024-04-17 | 2024-04-19 | 2024-04-23 | 2024-04-23 | 2024-04-26 | 2024-04-28 | 2024-04-30 | 2024-04-30 | 2024-05-04 | 2024-05-06 | 2024-05-07 | 2024-05-08 | 2024-05-14 | 2024-05-19 | 2024-05-26 | 2024-05-26 | 2024-05-26 | 2024-05-31 | 2024-05-31 | 2024-06-02 | 2024-06-07 | 2024-06-15 | 2024-05-08 | 2024-05-26 | 2024-05-28 | 2024-06-19 | 2024-06-16 | 2024-06-22 | 2024-06-24 | 2024-06-30 | 2024-07-06
V_25 | 2024-02-04 | 2024-02-09 | 2024-02-11 | 2024-02-16 | 2024-02-20 | 2024-02-24 | 2024-02-25 | 2024-02-27 | 2024-03-01 | 2024-03-04 | 2024-03-06 | 2024-03-06 | 2024-03-16 | 2024-03-24 | 2024-03-31 | 2024-03-31 | 2024-04-07 | 2024-04-14 | 2024-04-14 | 2024-04-17 | 2024-04-17 | 2024-04-19 | 2024-04-24 | 2024-04-24 | 2024-05-01 | 2024-05-01 | 2024-05-01 | 2024-05-06 | 2024-05-11 | 2024-05-18 | 2024-05-22 | 2024-05-27 | 2024-06-03 | 2024-06-03 | 2024-06-08 | 2024-06-10 | 2024-06-10 | 2024-06-10 | 2024-06-16 | 2024-06-17 | 2024-06-22 | 2024-06-30 | 2024-03-24 | 2024-03-26 | 2024-04-02 | 2024-04-09 | 2024-04-14 | 2024-04-15 | 2024-04-21 | 2024-04-21 | 2024-04-22 | 2024-04-26 | 2024-04-27 | 2024-05-01 | 2024-05-01 | 2024-05-04 | 2024-05-06 | 2024-05-08 | 2024-05-08 | 2024-05-12 | 2024-05-14 | 2024-05-15 | 2024-05-17 | 2024-05-22 | 2024-05-27 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2024-06-08 | 2024-06-08 | 2024-06-10 | 2024-06-15 | 2024-06-23 | 2024-05-17 | 2024-06-03 | 2024-06-05 | 2024-06-28 | 2024-06-24 | 2024-06-30 | 2024-07-02 | 2024-07-08 | 2024-07-14
V_26 | 2024-02-04 | 2024-02-09 | 2024-02-11 | 2024-02-16 | 2024-02-20 | 2024-02-24 | 2024-02-25 | 2024-02-27 | 2024-03-01 | 2024-03-04 | 2024-03-06 | 2024-03-06 | 2024-03-16 | 2024-03-24 | 2024-03-31 | 2024-03-31 | 2024-04-07 | 2024-04-14 | 2024-04-14 | 2024-04-17 | 2024-04-17 | 2024-04-19 | 2024-04-24 | 2024-04-24 | 2024-05-01 | 2024-05-01 | 2024-05-01 | 2024-05-06 | 2024-05-11 | 2024-05-18 | 2024-05-22 | 2024-05-27 | 2024-06-03 | 2024-06-03 | 2024-06-08 | 2024-06-10 | 2024-06-10 | 2024-06-10 | 2024-06-16 | 2024-06-17 | 2024-06-22 | 2024-06-30 | 2024-03-24 | 2024-03-26 | 2024-04-02 | 2024-04-09 | 2024-04-14 | 2024-04-15 | 2024-04-21 | 2024-04-21 | 2024-04-22 | 2024-04-26 | 2024-04-27 | 2024-05-01 | 2024-05-01 | 2024-05-04 | 2024-05-06 | 2024-05-08 | 2024-05-08 | 2024-05-12 | 2024-05-14 | 2024-05-15 | 2024-05-17 | 2024-05-22 | 2024-05-27 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2024-06-08 | 2024-06-08 | 2024-06-10 | 2024-06-15 | 2024-06-23 | 2024-05-17 | 2024-06-03 | 2024-06-05 | 2024-06-28 | 2024-06-24 | 2024-06-30 | 2024-07-02 | 2024-07-08 | 2024-07-14
V_27 | 2024-02-04 | 2024-02-09 | 2024-02-11 | 2024-02-16 | 2024-02-20 | 2024-02-24 | 2024-02-25 | 2024-02-27 | 2024-03-01 | 2024-03-04 | 2024-03-06 | 2024-03-06 | 2024-03-16 | 2024-03-24 | 2024-03-31 | 2024-03-31 | 2024-04-07 | 2024-04-14 | 2024-04-14 | 2024-04-17 | 2024-04-17 | 2024-04-19 | 2024-04-24 | 2024-04-24 | 2024-05-01 | 2024-05-01 | 2024-05-01 | 2024-05-06 | 2024-05-11 | 2024-05-18 | 2024-05-22 | 2024-05-27 | 2024-06-03 | 2024-06-03 | 2024-06-08 | 2024-06-10 | 2024-06-10 | 2024-06-10 | 2024-06-16 | 2024-06-17 | 2024-06-22 | 2024-06-30 | 2024-03-24 | 2024-03-26 | 2024-04-02 | 2024-04-09 | 2024-04-14 | 2024-04-15 | 2024-04-21 | 2024-04-21 | 2024-04-22 | 2024-04-26 | 2024-04-27 | 2024-05-01 | 2024-05-01 | 2024-05-04 | 2024-05-06 | 2024-05-08 | 2024-05-08 | 2024-05-12 | 2024-05-14 | 2024-05-15 | 2024-05-17 | 2024-05-22 | 2024-05-27 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2024-06-08 | 2024-06-08 | 2024-06-10 | 2024-06-15 | 2024-06-23 | 2024-05-17 | 2024-06-03 | 2024-06-05 | 2024-06-28 | 2024-06-24 | 2024-06-30 | 2024-07-02 | 2024-07-08 | 2024-07-14
V_28 | 2024-02-04 | 2024-02-09 | 2024-02-11 | 2024-02-16 | 2024-02-20 | 2024-02-24 | 2024-02-25 | 2024-02-27 | 2024-03-01 | 2024-03-04 | 2024-03-06 | 2024-03-06 | 2024-03-16 | 2024-03-24 | 2024-03-31 | 2024-03-31 | 2024-04-07 | 2024-04-14 | 2024-04-14 | 2024-04-17 | 2024-04-17 | 2024-04-19 | 2024-04-24 | 2024-04-24 | 2024-05-01 | 2024-05-01 | 2024-05-01 | 2024-05-06 | 2024-05-11 | 2024-05-18 | 2024-05-22 | 2024-05-27 | 2024-06-03 | 2024-06-03 | 2024-06-08 | 2024-06-10 | 2024-06-10 | 2024-06-10 | 2024-06-16 | 2024-06-17 | 2024-06-22 | 2024-06-30 | 2024-03-24 | 2024-03-26 | 2024-04-02 | 2024-04-09 | 2024-04-14 | 2024-04-15 | 2024-04-21 | 2024-04-21 | 2024-04-22 | 2024-04-26 | 2024-04-27 | 2024-05-01 | 2024-05-01 | 2024-05-04 | 2024-05-06 | 2024-05-08 | 2024-05-08 | 2024-05-12 | 2024-05-14 | 2024-05-15 | 2024-05-17 | 2024-05-22 | 2024-05-27 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2024-06-08 | 2024-06-08 | 2024-06-10 | 2024-06-15 | 2024-06-23 | 2024-05-17 | 2024-06-03 | 2024-06-05 | 2024-06-28 | 2024-06-24 | 2024-06-30 | 2024-07-02 | 2024-07-08 | 2024-07-14
V_29 | 2024-02-04 | 2024-02-09 | 2024-02-11 | 2024-02-16 | 2024-02-20 | 2024-02-24 | 2024-02-25 | 2024-02-27 | 2024-03-01 | 2024-03-04 | 2024-03-06 | 2024-03-06 | 2024-03-16 | 2024-03-24 | 2024-03-31 | 2024-03-31 | 2024-04-07 | 2024-04-14 | 2024-04-14 | 2024-04-17 | 2024-04-17 | 2024-04-19 | 2024-04-24 | [24 empty] | 2024-04-15 | 2024-04-21 | 2024-04-21 | 2024-04-22 | 2024-04-26 | 2024-04-27 | 2024-05-01 | 2024-05-01 | 2024-05-04 | 2024-05-06 | 2024-05-08 | 2024-05-08 | 2024-05-12 | 2024-05-14 | 2024-05-15 | 2024-05-17 | 2024-05-22 | 2024-05-27 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2024-06-08 | 2024-06-08 | 2024-06-10 | 2024-06-15 | 2024-06-23 | 2024-05-17 | 2024-06-03 | 2024-06-05 | 2024-06-28 | 2024-06-24 | 2024-06-30 | 2024-07-02 | 2024-07-08 | 2024-07-14
V_30 | 2024-02-04 | 2024-02-09 | 2024-02-11 | 2024-02-16 | 2024-02-20 | 2024-02-24 | 2024-02-25 | 2024-02-27 | 2024-03-01 | 2024-03-04 | 2024-03-06 | 2024-03-06 | 2024-03-16 | 2024-03-24 | 2024-03-31 | 2024-03-31 | 2024-04-07 | 2024-04-14 | 2024-04-14 | 2024-04-17 | 2024-04-17 | 2024-04-19 | 2024-04-24 | [24 empty] | 2024-04-15 | 2024-04-21 | 2024-04-21 | 2024-04-22 | 2024-04-26 | 2024-04-27 | 2024-05-01 | 2024-05-01 | 2024-05-04 | 2024-05-06 | 2024-05-08 | 2024-05-08 | 2024-05-12 | 2024-05-14 | 2024-05-15 | 2024-05-17 | 2024-05-22 | 2024-05-27 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2024-06-08 | 2024-06-08 | 2024-06-10 | 2024-06-15 | 2024-06-23 | 2024-05-17 | 2024-06-03 | 2024-06-05 | 2024-06-28 | 2024-06-24 | 2024-06-30 | 2024-07-02 | 2024-07-08 | 2024-07-14
V_31 | 2024-02-04 | 2024-02-09 | 2024-02-11 | 2024-02-16 | 2024-02-20 | 2024-02-24 | 2024-02-25 | 2024-02-27 | 2024-03-01 | 2024-03-04 | 2024-03-06 | 2024-03-06 | 2024-03-16 | 2024-03-24 | 2024-03-31 | 2024-03-31 | 2024-04-07 | 2024-04-14 | 2024-04-14 | 2024-04-17 | 2024-04-17 | 2024-04-19 | 2024-04-24 | [24 empty] | 2024-04-15 | 2024-04-21 | 2024-04-21 | 2024-04-22 | 2024-04-26 | 2024-04-27 | 2024-05-01 | 2024-05-01 | 2024-05-04 | 2024-05-06 | 2024-05-08 | 2024-05-08 | 2024-05-12 | 2024-05-14 | 2024-05-15 | 2024-05-17 | 2024-05-22 | 2024-05-27 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2024-06-08 | 2024-06-08 | 2024-06-10 | 2024-06-15 | 2024-06-23 | 2024-05-17 | 2024-06-03 | 2024-06-05 | 2024-06-28 | 2024-06-24 | 2024-06-30 | 2024-07-02 | 2024-07-08 | 2024-07-14
V_32 | 2024-02-04 | 2024-02-09 | 2024-02-11 | 2024-02-16 | 2024-02-20 | 2024-02-24 | 2024-02-25 | 2024-02-27 | 2024-03-01 | 2024-03-04 | 2024-03-06 | 2024-03-06 | 2024-03-16 | 2024-03-24 | 2024-03-31 | 2024-03-31 | 2024-04-07 | 2024-04-14 | 2024-04-14 | 2024-04-17 | 2024-04-17 | 2024-04-19 | 2024-04-24 | [24 empty] | 2024-04-15 | 2024-04-21 | 2024-04-21 | 2024-04-22 | 2024-04-26 | 2024-04-27 | 2024-05-01 | 2024-05-01 | 2024-05-04 | 2024-05-06 | 2024-05-08 | 2024-05-08 | 2024-05-12 | 2024-05-14 | 2024-05-15 | 2024-05-17 | 2024-05-22 | 2024-05-27 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2024-06-08 | 2024-06-08 | 2024-06-10 | 2024-06-15 | 2024-06-23 | 2024-05-17 | 2024-06-03 | 2024-06-05 | 2024-06-28 | 2024-06-24 | 2024-06-30 | 2024-07-02 | 2024-07-08 | 2024-07-14
V_33 | 2024-02-09 | 2024-02-13 | 2024-02-16 | 2024-02-20 | 2024-02-25 | 2024-02-28 | 2024-03-01 | 2024-03-03 | 2024-03-05 | 2024-03-09 | 2024-03-11 | 2024-03-11 | 2024-03-24 | 2024-04-01 | 2024-04-08 | 2024-04-08 | 2024-04-15 | 2024-04-22 | 2024-04-22 | 2024-04-26 | 2024-04-26 | 2024-04-27 | 2024-05-03 | [24 empty] | 2024-04-23 | 2024-04-29 | 2024-04-29 | 2024-04-30 | 2024-05-04 | 2024-05-05 | 2024-05-10 | 2024-05-10 | 2024-05-12 | 2024-05-14 | 2024-05-17 | 2024-05-17 | 2024-05-20 | 2024-05-22 | 2024-05-24 | 2024-05-25 | 2024-05-31 | 2024-06-04 | 2024-06-11 | 2024-06-11 | 2024-06-11 | 2024-06-16 | 2024-06-16 | 2024-06-18 | 2024-06-23 | 2024-07-01 | 2024-05-25 | 2024-06-11 | 2024-06-14 | 2024-07-06 | 2024-07-02 | 2024-07-08 | 2024-07-10 | 2024-07-16 | 2024-07-22
V_34 | 2024-02-09 | 2024-02-13 | 2024-02-16 | 2024-02-20 | 2024-02-25 | 2024-02-28 | 2024-03-01 | 2024-03-03 | 2024-03-05 | 2024-03-09 | 2024-03-11 | 2024-03-11 | 2024-03-24 | 2024-04-01 | 2024-04-08 | 2024-04-08 | 2024-04-15 | 2024-04-22 | 2024-04-22 | 2024-04-26 | 2024-04-26 | 2024-04-27 | 2024-05-03 | [24 empty] | 2024-04-23 | 2024-04-29 | 2024-04-29 | 2024-04-30 | 2024-05-04 | 2024-05-05 | 2024-05-10 | 2024-05-10 | 2024-05-12 | 2024-05-14 | 2024-05-17 | 2024-05-17 | 2024-05-20 | 2024-05-22 | 2024-05-24 | 2024-05-25 | 2024-05-31 | 2024-06-04 | 2024-06-11 | 2024-06-11 | 2024-06-11 | 2024-06-16 | 2024-06-16 | 2024-06-18 | 2024-06-23 | 2024-07-01 | 2024-05-25 | 2024-06-11 | 2024-06-14 | 2024-07-06 | 2024-07-02 | 2024-07-08 | 2024-07-10 | 2024-07-16 | 2024-07-22
V_35 | 2024-02-09 | 2024-02-13 | 2024-02-16 | 2024-02-20 | 2024-02-25 | 2024-02-28 | 2024-03-01 | 2024-03-03 | 2024-03-05 | 2024-03-09 | 2024-03-11 | 2024-03-11 | 2024-03-24 | 2024-04-01 | 2024-04-08 | 2024-04-08 | 2024-04-15 | 2024-04-22 | 2024-04-22 | 2024-04-26 | 2024-04-26 | 2024-04-27 | 2024-05-03 | [24 empty] | 2024-04-23 | 2024-04-29 | 2024-04-29 | 2024-04-30 | 2024-05-04 | 2024-05-05 | 2024-05-10 | 2024-05-10 | 2024-05-12 | 2024-05-14 | 2024-05-17 | 2024-05-17 | 2024-05-20 | 2024-05-22 | 2024-05-24 | 2024-05-25 | 2024-05-31 | 2024-06-04 | 2024-06-11 | 2024-06-11 | 2024-06-11 | 2024-06-16 | 2024-06-16 | 2024-06-18 | 2024-06-23 | 2024-07-01 | 2024-05-25 | 2024-06-11 | 2024-06-14 | 2024-07-06 | 2024-07-02 | 2024-07-08 | 2024-07-10 | 2024-07-16 | 2024-07-22
V_36 | 2024-02-09 | 2024-02-13 | 2024-02-16 | 2024-02-20 | 2024-02-25 | 2024-02-28 | 2024-03-01 | 2024-03-03 | 2024-03-05 | 2024-03-09 | 2024-03-11 | 2024-03-11 | 2024-03-24 | 2024-04-01 | 2024-04-08 | 2024-04-08 | 2024-04-15 | 2024-04-22 | 2024-04-22 | 2024-04-26 | 2024-04-26 | 2024-04-27 | 2024-05-03 | 2024-05-03 | 2024-05-10 | 2024-05-10 | 2024-05-10 | 2024-05-14 | 2024-05-19 | 2024-05-26 | 2024-05-31 | 2024-06-04 | 2024-06-11 | 2024-06-11 | 2024-06-16 | 2024-06-18 | 2024-06-18 | 2024-06-18 | 2024-06-24 | 2024-06-25 | 2024-06-30 | 2024-07-08 | 2024-04-01 | 2024-04-03 | 2024-04-10 | 2024-04-17 | 2024-04-22 | 2024-04-23 | 2024-04-29 | 2024-04-29 | 2024-04-30 | 2024-05-04 | 2024-05-05 | 2024-05-10 | 2024-05-10 | 2024-05-12 | 2024-05-14 | 2024-05-17 | 2024-05-17 | 2024-05-20 | 2024-05-22 | 2024-05-24 | 2024-05-25 | 2024-05-31 | 2024-06-04 | 2024-06-11 | 2024-06-11 | 2024-06-11 | 2024-06-16 | 2024-06-16 | 2024-06-18 | 2024-06-23 | 2024-07-01 | 2024-05-25 | 2024-06-11 | 2024-06-14 | 2024-07-06 | 2024-07-02 | 2024-07-08 | 2024-07-10 | 2024-07-16 | 2024-07-22
V_37 | 2024-02-09 | 2024-02-13 | 2024-02-16 | 2024-02-20 | 2024-02-25 | 2024-02-28 | 2024-03-01 | 2024-03-03 | 2024-03-05 | 2024-03-09 | 2024-03-11 | 2024-03-11 | 2024-03-24 | 2024-04-01 | 2024-04-08 | 2024-04-08 | 2024-04-15 | 2024-04-22 | 2024-04-22 | 2024-04-26 | 2024-04-26 | 2024-04-27 | 2024-05-03 | 2024-05-03 | 2024-05-10 | 2024-05-10 | 2024-05-10 | 2024-05-14 | 2024-05-19 | 2024-05-26 | 2024-05-31 | 2024-06-04 | 2024-06-11 | 2024-06-11 | 2024-06-16 | 2024-06-18 | 2024-06-18 | 2024-06-18 | 2024-06-24 | 2024-06-25 | 2024-06-30 | 2024-07-08 | 2024-04-01 | 2024-04-03 | 2024-04-10 | 2024-04-17 | 2024-04-22 | 2024-04-23 | 2024-04-29 | 2024-04-29 | 2024-04-30 | 2024-05-04 | 2024-05-05 | 2024-05-10 | 2024-05-10 | 2024-05-12 | 2024-05-14 | 2024-05-17 | 2024-05-17 | 2024-05-20 | 2024-05-22 | 2024-05-24 | 2024-05-25 | 2024-05-31 | 2024-06-04 | 2024-06-11 | 2024-06-11 | 2024-06-11 | 2024-06-16 | 2024-06-16 | 2024-06-18 | 2024-06-23 | 2024-07-01 | 2024-05-25 | 2024-06-11 | 2024-06-14 | 2024-07-06 | 2024-07-02 | 2024-07-08 | 2024-07-10 | 2024-07-16 | 2024-07-22
V_38 | 2024-02-09 | 2024-02-13 | 2024-02-16 | 2024-02-20 | 2024-02-25 | 2024-02-28 | 2024-03-01 | 2024-03-03 | 2024-03-05 | 2024-03-09 | 2024-03-11 | 2024-03-11 | 2024-03-24 | 2024-04-01 | 2024-04-08 | 2024-04-08 | 2024-04-15 | 2024-04-22 | 2024-04-22 | 2024-04-26 | 2024-04-26 | 2024-04-27 | 2024-05-03 | 2024-05-03 | 2024-05-10 | 2024-05-10 | 2024-05-10 | 2024-05-14 | 2024-05-19 | 2024-05-26 | 2024-05-31 | 2024-06-04 | 2024-06-11 | 2024-06-11 | 2024-06-16 | 2024-06-18 | 2024-06-18 | 2024-06-18 | 2024-06-24 | 2024-06-25 | 2024-06-30 | 2024-07-08 | 2024-04-01 | 2024-04-03 | 2024-04-10 | 2024-04-17 | 2024-04-22 | 2024-04-23 | 2024-04-29 | 2024-04-29 | 2024-04-30 | 2024-05-04 | 2024-05-05 | 2024-05-10 | 2024-05-10 | 2024-05-12 | 2024-05-14 | 2024-05-17 | 2024-05-17 | 2024-05-20 | 2024-05-22 | 2024-05-24 | 2024-05-25 | 2024-05-31 | 2024-06-04 | 2024-06-11 | 2024-06-11 | 2024-06-11 | 2024-06-16 | 2024-06-16 | 2024-06-18 | 2024-06-23 | 2024-07-01 | 2024-05-25 | 2024-06-11 | 2024-06-14 | 2024-07-06 | 2024-07-02 | 2024-07-08 | 2024-07-10 | 2024-07-16 | 2024-07-22
V_39 | 2024-02-09 | 2024-02-13 | 2024-02-16 | 2024-02-20 | 2024-02-25 | 2024-02-28 | 2024-03-01 | 2024-03-03 | 2024-03-05 | 2024-03-09 | 2024-03-11 | 2024-03-11 | 2024-03-24 | 2024-04-01 | 2024-04-08 | 2024-04-08 | 2024-04-15 | 2024-04-22 | 2024-04-22 | 2024-04-26 | 2024-04-26 | 2024-04-27 | 2024-05-03 | 2024-05-03 | 2024-05-10 | 2024-05-10 | 2024-05-10 | 2024-05-14 | 2024-05-19 | 2024-05-26 | 2024-05-31 | 2024-06-04 | 2024-06-11 | 2024-06-11 | 2024-06-16 | 2024-06-18 | 2024-06-18 | 2024-06-18 | 2024-06-24 | 2024-06-25 | 2024-06-30 | 2024-07-08 | 2024-04-01 | 2024-04-03 | 2024-04-10 | 2024-04-17 | 2024-04-22 | 2024-04-23 | 2024-04-29 | 2024-04-29 | 2024-04-30 | 2024-05-04 | 2024-05-05 | 2024-05-10 | 2024-05-10 | 2024-05-12 | 2024-05-14 | 2024-05-17 | 2024-05-17 | 2024-05-20 | 2024-05-22 | 2024-05-24 | 2024-05-25 | 2024-05-31 | 2024-06-04 | 2024-06-11 | 2024-06-11 | 2024-06-11 | 2024-06-16 | 2024-06-16 | 2024-06-18 | 2024-06-23 | 2024-07-01 | 2024-05-25 | 2024-06-11 | 2024-06-14 | 2024-07-06 | 2024-07-02 | 2024-07-08 | 2024-07-10 | 2024-07-16 | 2024-07-22
V_40 | 2024-02-09 | 2024-02-13 | 2024-02-16 | 2024-02-20 | 2024-02-25 | 2024-02-28 | 2024-03-01 | 2024-03-03 | 2024-03-05 | 2024-03-09 | 2024-03-11 | 2024-03-11 | 2024-03-24 | 2024-04-01 | 2024-04-08 | 2024-04-08 | 2024-04-15 | 2024-04-22 | 2024-04-22 | 2024-04-26 | 2024-04-26 | 2024-04-27 | 2024-05-03 | 2024-05-03 | 2024-05-10 | 2024-05-10 | 2024-05-10 | 2024-05-14 | 2024-05-19 | 2024-05-26 | 2024-05-31 | 2024-06-04 | 2024-06-11 | 2024-06-11 | 2024-06-16 | 2024-06-18 | 2024-06-18 | 2024-06-18 | 2024-06-24 | 2024-06-25 | 2024-06-30 | 2024-07-08 | 2024-04-01 | 2024-04-03 | 2024-04-10 | 2024-04-17 | 2024-04-22 | 2024-04-23 | 2024-04-29 | 2024-04-29 | 2024-04-30 | 2024-05-04 | 2024-05-05 | 2024-05-10 | 2024-05-10 | 2024-05-12 | 2024-05-14 | 2024-05-17 | 2024-05-17 | 2024-05-20 | 2024-05-22 | 2024-05-24 | 2024-05-25 | 2024-05-31 | 2024-06-04 | 2024-06-11 | 2024-06-11 | 2024-06-11 | 2024-06-16 | 2024-06-16 | 2024-06-18 | 2024-06-23 | 2024-07-01 | 2024-05-25 | 2024-06-11 | 2024-06-14 | 2024-07-06 | 2024-07-02 | 2024-07-08 | 2024-07-10 | 2024-07-16 | 2024-07-22
V_41 | 2024-02-13 | 2024-02-18 | 2024-02-20 | 2024-02-25 | 2024-03-01 | 2024-03-04 | 2024-03-05 | 2024-03-08 | 2024-03-10 | 2024-03-13 | 2024-03-16 | 2024-03-16 | 2024-04-01 | 2024-04-09 | 2024-04-16 | 2024-04-16 | 2024-04-23 | 2024-04-30 | 2024-04-30 | 2024-05-04 | 2024-05-04 | 2024-05-05 | 2024-05-11 | 2024-05-11 | 2024-05-18 | 2024-05-18 | 2024-05-18 | 2024-05-22 | 2024-05-27 | 2024-06-03 | 2024-06-08 | 2024-06-12 | 2024-06-19 | 2024-06-19 | 2024-06-24 | 2024-06-26 | 2024-06-26 | 2024-06-26 | 2024-07-02 | 2024-07-03 | 2024-07-08 | 2024-07-16 | 2024-04-09 | 2024-04-12 | 2024-04-19 | 2024-04-26 | 2024-04-30 | 2024-05-01 | 2024-05-07 | 2024-05-07 | 2024-05-08 | 2024-05-12 | 2024-05-13 | 2024-05-18 | 2024-05-18 | 2024-05-20 | 2024-05-22 | 2024-05-25 | 2024-05-25 | 2024-05-28 | 2024-05-31 | 2024-06-01 | 2024-06-02 | 2024-06-08 | 2024-06-12 | 2024-06-19 | 2024-06-19 | 2024-06-19 | 2024-06-24 | 2024-06-24 | 2024-06-26 | 2024-07-01 | 2024-07-09 | 2024-06-02 | 2024-06-19 | 2024-06-22 | 2024-07-14 | 2024-07-10 | 2024-07-16 | 2024-07-19 | 2024-07-24 | 2024-07-30
V_42 | 2024-02-13 | 2024-02-18 | 2024-02-20 | 2024-02-25 | 2024-03-01 | 2024-03-04 | 2024-03-05 | 2024-03-08 | 2024-03-10 | 2024-03-13 | 2024-03-16 | 2024-03-16 | 2024-04-01 | 2024-04-09 | 2024-04-16 | 2024-04-16 | 2024-04-23 | 2024-04-30 | 2024-04-30 | 2024-05-04 | 2024-05-04 | 2024-05-05 | 2024-05-11 | 2024-05-11 | 2024-05-18 | 2024-05-18 | 2024-05-18 | 2024-05-22 | 2024-05-27 | 2024-06-03 | 2024-06-08 | 2024-06-12 | 2024-06-19 | 2024-06-19 | 2024-06-24 | 2024-06-26 | 2024-06-26 | 2024-06-26 | 2024-07-02 | 2024-07-03 | 2024-07-08 | 2024-07-16 | 2024-04-09 | 2024-04-12 | 2024-04-19 | 2024-04-26 | 2024-04-30 | 2024-05-01 | 2024-05-07 | 2024-05-07 | 2024-05-08 | 2024-05-12 | 2024-05-13 | 2024-05-18 | 2024-05-18 | 2024-05-20 | 2024-05-22 | 2024-05-25 | 2024-05-25 | 2024-05-28 | 2024-05-31 | 2024-06-01 | 2024-06-02 | 2024-06-08 | 2024-06-12 | 2024-06-19 | 2024-06-19 | 2024-06-19 | 2024-06-24 | 2024-06-24 | 2024-06-26 | 2024-07-01 | 2024-07-09 | 2024-06-02 | 2024-06-19 | 2024-06-22 | 2024-07-14 | 2024-07-10 | 2024-07-16 | 2024-07-19 | 2024-07-24 | 2024-07-30
V_43 | 2024-02-13 | 2024-02-18 | 2024-02-20 | 2024-02-25 | 2024-03-01 | 2024-03-04 | 2024-03-05 | 2024-03-08 | 2024-03-10 | 2024-03-13 | 2024-03-16 | 2024-03-16 | 2024-04-01 | 2024-04-09 | 2024-04-16 | 2024-04-16 | 2024-04-23 | 2024-04-30 | 2024-04-30 | 2024-05-04 | 2024-05-04 | 2024-05-05 | 2024-05-11 | 2024-05-11 | 2024-05-18 | 2024-05-18 | 2024-05-18 | 2024-05-22 | 2024-05-27 | 2024-06-03 | 2024-06-08 | 2024-06-12 | 2024-06-19 | 2024-06-19 | 2024-06-24 | 2024-06-26 | 2024-06-26 | 2024-06-26 | 2024-07-02 | 2024-07-03 | 2024-07-08 | 2024-07-16 | 2024-04-09 | 2024-04-12 | 2024-04-19 | 2024-04-26 | 2024-04-30 | 2024-05-01 | 2024-05-07 | 2024-05-07 | 2024-05-08 | 2024-05-12 | 2024-05-13 | 2024-05-18 | 2024-05-18 | 2024-05-20 | 2024-05-22 | 2024-05-25 | 2024-05-25 | 2024-05-28 | 2024-05-31 | 2024-06-01 | 2024-06-02 | 2024-06-08 | 2024-06-12 | 2024-06-19 | 2024-06-19 | 2024-06-19 | 2024-06-24 | 2024-06-24 | 2024-06-26 | 2024-07-01 | 2024-07-09 | 2024-06-02 | 2024-06-19 | 2024-06-22 | 2024-07-14 | 2024-07-10 | 2024-07-16 | 2024-07-19 | 2024-07-24 | 2024-07-30
V_44 | 2024-02-13 | 2024-02-18 | 2024-02-20 | 2024-02-25 | 2024-03-01 | 2024-03-04 | 2024-03-05 | 2024-03-08 | 2024-03-10 | 2024-03-13 | 2024-03-16 | 2024-03-16 | 2024-04-01 | 2024-04-09 | 2024-04-16 | 2024-04-16 | 2024-04-23 | 2024-04-30 | 2024-04-30 | 2024-05-04 | 2024-05-04 | 2024-05-05 | 2024-05-11 | 2024-05-11 | 2024-05-18 | 2024-05-18 | 2024-05-18 | 2024-05-22 | 2024-05-27 | 2024-06-03 | 2024-06-08 | 2024-06-12 | 2024-06-19 | 2024-06-19 | 2024-06-24 | 2024-06-26 | 2024-06-26 | 2024-06-26 | 2024-07-02 | 2024-07-03 | 2024-07-08 | 2024-07-16 | 2024-04-09 | 2024-04-12 | 2024-04-19 | 2024-04-26 | 2024-04-30 | 2024-05-01 | 2024-05-07 | 2024-05-07 | 2024-05-08 | 2024-05-12 | 2024-05-13 | 2024-05-18 | 2024-05-18 | 2024-05-20 | 2024-05-22 | 2024-05-25 | 2024-05-25 | 2024-05-28 | 2024-05-31 | 2024-06-01 | 2024-06-02 | 2024-06-08 | 2024-06-12 | 2024-06-19 | 2024-06-19 | 2024-06-19 | 2024-06-24 | 2024-06-24 | 2024-06-26 | 2024-07-01 | 2024-07-09 | 2024-06-02 | 2024-06-19 | 2024-06-22 | 2024-07-14 | 2024-07-10 | 2024-07-16 | 2024-07-19 | 2024-07-24 | 2024-07-30
V_45 | 2024-02-13 | 2024-02-18 | 2024-02-20 | 2024-02-25 | 2024-03-01 | 2024-03-04 | 2024-03-05 | 2024-03-08 | 2024-03-10 | 2024-03-13 | 2024-03-16 | 2024-03-16 | 2024-04-01 | 2024-04-09 | 2024-04-16 | 2024-04-16 | 2024-04-23 | 2024-04-30 | 2024-04-30 | 2024-05-04 | 2024-05-04 | 2024-05-05 | 2024-05-11 | 2024-05-11 | 2024-05-18 | 2024-05-18 | 2024-05-18 | 2024-05-22 | 2024-05-27 | 2024-06-03 | 2024-06-08 | 2024-06-12 | 2024-06-19 | 2024-06-19 | 2024-06-24 | 2024-06-26 | 2024-06-26 | 2024-06-26 | 2024-07-02 | 2024-07-03 | 2024-07-08 | 2024-07-16 | 2024-04-09 | 2024-04-12 | 2024-04-19 | 2024-04-26 | 2024-04-30 | 2024-05-01 | 2024-05-07 | 2024-05-07 | 2024-05-08 | 2024-05-12 | 2024-05-13 | 2024-05-18 | 2024-05-18 | 2024-05-20 | 2024-05-22 | 2024-05-25 | 2024-05-25 | 2024-05-28 | 2024-05-31 | 2024-06-01 | 2024-06-02 | 2024-06-08 | 2024-06-12 | 2024-06-19 | 2024-06-19 | 2024-06-19 | 2024-06-24 | 2024-06-24 | 2024-06-26 | 2024-07-01 | 2024-07-09 | 2024-06-02 | 2024-06-19 | 2024-06-22 | 2024-07-14 | 2024-07-10 | 2024-07-16 | 2024-07-19 | 2024-07-24 | 2024-07-30
V_46 | 2024-02-13 | 2024-02-18 | 2024-02-20 | 2024-02-25 | 2024-03-01 | 2024-03-04 | 2024-03-05 | 2024-03-08 | 2024-03-10 | 2024-03-13 | 2024-03-16 | 2024-03-16 | 2024-04-01 | 2024-04-09 | 2024-04-16 | 2024-04-16 | 2024-04-23 | 2024-04-30 | 2024-04-30 | 2024-05-04 | 2024-05-04 | 2024-05-05 | 2024-05-11 | 2024-05-11 | 2024-05-18 | 2024-05-18 | 2024-05-18 | 2024-05-22 | 2024-05-27 | 2024-06-03 | 2024-06-08 | 2024-06-12 | 2024-06-19 | 2024-06-19 | 2024-06-24 | 2024-06-26 | 2024-06-26 | 2024-06-26 | 2024-07-02 | 2024-07-03 | 2024-07-08 | 2024-07-16 | 2024-04-09 | 2024-04-12 | 2024-04-19 | 2024-04-26 | 2024-04-30 | 2024-05-01 | 2024-05-07 | 2024-05-07 | 2024-05-08 | 2024-05-12 | 2024-05-13 | 2024-05-18 | 2024-05-18 | 2024-05-20 | 2024-05-22 | 2024-05-25 | 2024-05-25 | 2024-05-28 | 2024-05-31 | 2024-06-01 | 2024-06-02 | 2024-06-08 | 2024-06-12 | 2024-06-19 | 2024-06-19 | 2024-06-19 | 2024-06-24 | 2024-06-24 | 2024-06-26 | 2024-07-01 | 2024-07-09 | 2024-06-02 | 2024-06-19 | 2024-06-22 | 2024-07-14 | 2024-07-10 | 2024-07-16 | 2024-07-19 | 2024-07-24 | 2024-07-30
V_47 | 2024-02-13 | 2024-02-18 | 2024-02-20 | 2024-02-25 | 2024-03-01 | 2024-03-04 | 2024-03-05 | 2024-03-08 | 2024-03-10 | 2024-03-13 | 2024-03-16 | 2024-03-16 | 2024-04-01 | 2024-04-09 | 2024-04-16 | 2024-04-16 | 2024-04-23 | 2024-04-30 | 2024-04-30 | 2024-05-04 | 2024-05-04 | 2024-05-05 | 2024-05-11 | 2024-05-11 | 2024-05-18 | 2024-05-18 | 2024-05-18 | 2024-05-22 | 2024-05-27 | 2024-06-03 | 2024-06-08 | 2024-06-12 | 2024-06-19 | 2024-06-19 | 2024-06-24 | 2024-06-26 | 2024-06-26 | 2024-06-26 | 2024-07-02 | 2024-07-03 | 2024-07-08 | 2024-07-16 | 2024-04-09 | 2024-04-12 | 2024-04-19 | 2024-04-26 | 2024-04-30 | 2024-05-01 | 2024-05-07 | 2024-05-07 | 2024-05-08 | 2024-05-12 | 2024-05-13 | 2024-05-18 | 2024-05-18 | 2024-05-20 | 2024-05-22 | 2024-05-25 | 2024-05-25 | 2024-05-28 | 2024-05-31 | 2024-06-01 | 2024-06-02 | 2024-06-08 | 2024-06-12 | 2024-06-19 | 2024-06-19 | 2024-06-19 | 2024-06-24 | 2024-06-24 | 2024-06-26 | 2024-07-01 | 2024-07-09 | 2024-06-02 | 2024-06-19 | 2024-06-22 | 2024-07-14 | 2024-07-10 | 2024-07-16 | 2024-07-19 | 2024-07-24 | 2024-07-30
V_48 | 2024-02-13 | 2024-02-18 | 2024-02-20 | 2024-02-25 | 2024-03-01 | 2024-03-04 | 2024-03-05 | 2024-03-08 | 2024-03-10 | 2024-03-13 | 2024-03-16 | 2024-03-16 | 2024-04-01 | 2024-04-09 | 2024-04-16 | 2024-04-16 | 2024-04-23 | 2024-04-30 | 2024-04-30 | 2024-05-04 | 2024-05-04 | 2024-05-05 | 2024-05-11 | 2024-05-11 | 2024-05-18 | 2024-05-18 | 2024-05-18 | 2024-05-22 | 2024-05-27 | 2024-06-03 | 2024-06-08 | 2024-06-12 | 2024-06-19 | 2024-06-19 | 2024-06-24 | 2024-06-26 | 2024-06-26 | 2024-06-26 | 2024-07-02 | 2024-07-03 | 2024-07-08 | 2024-07-16 | 2024-04-09 | 2024-04-12 | 2024-04-19 | 2024-04-26 | 2024-04-30 | 2024-05-01 | 2024-05-07 | 2024-05-07 | 2024-05-08 | 2024-05-12 | 2024-05-13 | 2024-05-18 | 2024-05-18 | 2024-05-20 | 2024-05-22 | 2024-05-25 | 2024-05-25 | 2024-05-28 | 2024-05-31 | 2024-06-01 | 2024-06-02 | 2024-06-08 | 2024-06-12 | 2024-06-19 | 2024-06-19 | 2024-06-19 | 2024-06-24 | 2024-06-24 | 2024-06-26 | 2024-07-01 | 2024-07-09 | 2024-06-02 | 2024-06-19 | 2024-06-22 | 2024-07-14 | 2024-07-10 | 2024-07-16 | 2024-07-19 | 2024-07-24 | 2024-07-30
V_49 | 2024-02-18 | 2024-02-25 | 2024-02-27 | 2024-03-03 | 2024-03-08 | 2024-03-11 | 2024-03-12 | 2024-03-15 | 2024-03-18 | 2024-03-22 | 2024-03-24 | 2024-03-24 | 2024-04-09 | 2024-04-17 | 2024-04-24 | 2024-04-24 | 2024-05-01 | 2024-05-08 | 2024-05-08 | 2024-05-12 | 2024-05-12 | 2024-05-13 | 2024-05-19 | 2024-05-19 | 2024-05-26 | 2024-05-26 | 2024-05-26 | 2024-05-31 | 2024-06-04 | 2024-06-11 | 2024-06-16 | 2024-06-21 | 2024-06-28 | 2024-06-28 | 2024-07-02 | 2024-07-05 | 2024-07-05 | 2024-07-05 | 2024-07-10 | 2024-07-12 | 2024-07-16 | 2024-07-24 | 2024-04-17 | 2024-04-20 | 2024-04-27 | 2024-05-04 | 2024-05-08 | 2024-05-10 | 2024-05-15 | 2024-05-15 | 2024-05-17 | 2024-05-20 | 2024-05-21 | 2024-05-26 | 2024-05-26 | 2024-05-28 | 2024-05-31 | 2024-06-02 | 2024-06-02 | 2024-06-05 | 2024-06-08 | 2024-06-09 | 2024-06-10 | 2024-06-16 | 2024-06-21 | 2024-06-28 | 2024-06-28 | 2024-06-28 | 2024-07-02 | 2024-07-02 | 2024-07-05 | 2024-07-09 | 2024-07-17 | 2024-06-10 | 2024-06-28 | 2024-06-30 | 2024-07-22 | 2024-07-19 | 2024-07-24 | 2024-07-27 | 2024-08-02 | 2024-08-07
V_50 | 2024-02-18 | 2024-02-25 | 2024-02-27 | 2024-03-03 | 2024-03-08 | 2024-03-11 | 2024-03-12 | 2024-03-15 | 2024-03-18 | 2024-03-22 | 2024-03-24 | 2024-03-24 | 2024-04-09 | 2024-04-17 | 2024-04-24 | 2024-04-24 | 2024-05-01 | 2024-05-08 | 2024-05-08 | 2024-05-12 | 2024-05-12 | 2024-05-13 | 2024-05-19 | 2024-05-19 | 2024-05-26 | 2024-05-26 | 2024-05-26 | [40 empty] | 2024-06-28 | 2024-07-02 | 2024-07-02 | 2024-07-05 | 2024-07-09 | 2024-07-17 | 2024-06-10 | 2024-06-28 | 2024-06-30 | 2024-07-22 | 2024-07-19 | 2024-07-24 | 2024-07-27 | 2024-08-02 | 2024-08-07
V_51 | 2024-02-18 | 2024-02-25 | 2024-02-27 | 2024-03-03 | 2024-03-08 | 2024-03-11 | 2024-03-12 | 2024-03-15 | 2024-03-18 | 2024-03-22 | 2024-03-24 | 2024-03-24 | 2024-04-09 | 2024-04-17 | 2024-04-24 | 2024-04-24 | 2024-05-01 | 2024-05-08 | 2024-05-08 | 2024-05-12 | 2024-05-12 | 2024-05-13 | 2024-05-19 | 2024-05-19 | 2024-05-26 | 2024-05-26 | 2024-05-26 | [40 empty] | 2024-06-28 | 2024-07-02 | 2024-07-02 | 2024-07-05 | 2024-07-09 | 2024-07-17 | 2024-06-10 | 2024-06-28 | 2024-06-30 | 2024-07-22 | 2024-07-19 | 2024-07-24 | 2024-07-27 | 2024-08-02 | 2024-08-07
V_52 | 2024-02-18 | 2024-02-25 | 2024-02-27 | 2024-03-03 | 2024-03-08 | 2024-03-11 | 2024-03-12 | 2024-03-15 | 2024-03-18 | 2024-03-22 | 2024-03-24 | 2024-03-24 | 2024-04-09 | 2024-04-17 | 2024-04-24 | 2024-04-24 | 2024-05-01 | 2024-05-08 | 2024-05-08 | 2024-05-12 | 2024-05-12 | 2024-05-13 | 2024-05-19 | 2024-05-19 | 2024-05-26 | 2024-05-26 | 2024-05-26 | [40 empty] | 2024-06-28 | 2024-07-02 | 2024-07-02 | 2024-07-05 | 2024-07-09 | 2024-07-17 | 2024-06-10 | 2024-06-28 | 2024-06-30 | 2024-07-22 | 2024-07-19 | 2024-07-24 | 2024-07-27 | 2024-08-02 | 2024-08-07
V_53 | 2024-02-18 | 2024-02-25 | 2024-02-27 | 2024-03-03 | 2024-03-08 | 2024-03-11 | 2024-03-12 | 2024-03-15 | 2024-03-18 | 2024-03-22 | 2024-03-24 | 2024-03-24 | 2024-04-09 | 2024-04-17 | 2024-04-24 | 2024-04-24 | 2024-05-01 | 2024-05-08 | 2024-05-08 | 2024-05-12 | 2024-05-12 | 2024-05-13 | 2024-05-19 | 2024-05-19 | 2024-05-26 | 2024-05-26 | 2024-05-26 | [40 empty] | 2024-06-28 | 2024-07-02 | 2024-07-02 | 2024-07-05 | 2024-07-09 | 2024-07-17 | 2024-06-10 | 2024-06-28 | 2024-06-30 | 2024-07-22 | 2024-07-19 | 2024-07-24 | 2024-07-27 | 2024-08-02 | 2024-08-07
V_54 | 2024-02-18 | 2024-02-25 | 2024-02-27 | 2024-03-03 | 2024-03-08 | 2024-03-11 | 2024-03-12 | 2024-03-15 | 2024-03-18 | 2024-03-22 | 2024-03-24 | 2024-03-24 | 2024-04-09 | 2024-04-17 | 2024-04-24 | 2024-04-24 | 2024-05-01 | 2024-05-08 | 2024-05-08 | 2024-05-12 | 2024-05-12 | 2024-05-13 | 2024-05-19 | 2024-05-19 | 2024-05-26 | 2024-05-26 | 2024-05-26 | [40 empty] | 2024-06-28 | 2024-07-02 | 2024-07-02 | 2024-07-05 | 2024-07-09 | 2024-07-17 | 2024-06-10 | 2024-06-28 | 2024-06-30 | 2024-07-22 | 2024-07-19 | 2024-07-24 | 2024-07-27 | 2024-08-02 | 2024-08-07
V_55 | 2024-02-18 | 2024-02-25 | 2024-02-27 | 2024-03-03 | 2024-03-08 | 2024-03-11 | 2024-03-12 | 2024-03-15 | 2024-03-18 | 2024-03-22 | 2024-03-24 | 2024-03-24 | 2024-04-09 | 2024-04-17 | 2024-04-24 | 2024-04-24 | 2024-05-01 | 2024-05-08 | 2024-05-08 | 2024-05-12 | 2024-05-12 | 2024-05-13 | 2024-05-19 | 2024-05-19 | 2024-05-26 | 2024-05-26 | 2024-05-26 | [40 empty] | 2024-06-28 | 2024-07-02 | 2024-07-02 | 2024-07-05 | 2024-07-09 | 2024-07-17 | 2024-06-10 | 2024-06-28 | 2024-06-30 | 2024-07-22 | 2024-07-19 | 2024-07-24 | 2024-07-27 | 2024-08-02 | 2024-08-07
V_56 | 2024-02-18 | 2024-02-25 | 2024-02-27 | 2024-03-03 | 2024-03-08 | 2024-03-11 | 2024-03-12 | 2024-03-15 | 2024-03-18 | 2024-03-22 | 2024-03-24 | 2024-03-24 | 2024-04-09 | 2024-04-17 | 2024-04-24 | 2024-04-24 | 2024-05-01 | 2024-05-08 | 2024-05-08 | 2024-05-12 | 2024-05-12 | 2024-05-13 | 2024-05-19 | 2024-05-19 | 2024-05-26 | 2024-05-26 | 2024-05-26 | [40 empty] | 2024-06-28 | 2024-07-02 | 2024-07-02 | 2024-07-05 | 2024-07-09 | 2024-07-17 | 2024-06-10 | 2024-06-28 | 2024-06-30 | 2024-07-22 | 2024-07-19 | 2024-07-24 | 2024-07-27 | 2024-08-02 | 2024-08-07
V_57 | 2024-02-25 | 2024-03-03 | 2024-03-05 | 2024-03-10 | 2024-03-15 | 2024-03-18 | 2024-03-19 | 2024-03-22 | 2024-03-25 | 2024-03-29 | 2024-03-31 | 2024-03-31 | 2024-04-17 | 2024-04-26 | 2024-05-03 | 2024-05-03 | 2024-05-10 | 2024-05-17 | 2024-05-17 | 2024-05-20 | 2024-05-20 | 2024-05-21 | 2024-05-27 | 2024-05-27 | 2024-06-03 | 2024-06-03 | 2024-06-03 | [40 empty] | 2024-07-06 | 2024-07-10 | 2024-07-10 | 2024-07-13 | 2024-07-17 | 2024-07-26 | 2024-06-18 | 2024-07-06 | 2024-07-08 | 2024-07-30 | 2024-07-27 | 2024-08-02 | 2024-08-04 | 2024-08-10 | 2024-08-16
V_58 | 2024-02-25 | 2024-03-03 | 2024-03-05 | 2024-03-10 | 2024-03-15 | 2024-03-18 | 2024-03-19 | 2024-03-22 | 2024-03-25 | 2024-03-29 | 2024-03-31 | 2024-03-31 | 2024-04-17 | 2024-04-26 | 2024-05-03 | 2024-05-03 | 2024-05-10 | 2024-05-17 | 2024-05-17 | 2024-05-20 | 2024-05-20 | 2024-05-21 | 2024-05-27 | 2024-05-27 | 2024-06-03 | 2024-06-03 | 2024-06-03 | [40 empty] | 2024-07-06 | 2024-07-10 | 2024-07-10 | 2024-07-13 | 2024-07-17 | 2024-07-26 | 2024-06-18 | 2024-07-06 | 2024-07-08 | 2024-07-30 | 2024-07-27 | 2024-08-02 | 2024-08-04 | 2024-08-10 | 2024-08-16
V_59 | 2024-02-25 | 2024-03-03 | 2024-03-05 | 2024-03-10 | 2024-03-15 | 2024-03-18 | 2024-03-19 | 2024-03-22 | 2024-03-25 | 2024-03-29 | 2024-03-31 | 2024-03-31 | 2024-04-17 | 2024-04-26 | 2024-05-03 | 2024-05-03 | 2024-05-10 | 2024-05-17 | 2024-05-17 | 2024-05-20 | 2024-05-20 | 2024-05-21 | 2024-05-27 | 2024-05-27 | 2024-06-03 | 2024-06-03 | 2024-06-03 | [40 empty] | 2024-07-06 | 2024-07-10 | 2024-07-10 | 2024-07-13 | 2024-07-17 | 2024-07-26 | 2024-06-18 | 2024-07-06 | 2024-07-08 | 2024-07-30 | 2024-07-27 | 2024-08-02 | 2024-08-04 | 2024-08-10 | 2024-08-16
V_60 | 2024-02-25 | 2024-03-03 | 2024-03-05 | 2024-03-10 | 2024-03-15 | 2024-03-18 | 2024-03-19 | 2024-03-22 | 2024-03-25 | 2024-03-29 | 2024-03-31 | 2024-03-31 | 2024-04-17 | 2024-04-26 | 2024-05-03 | 2024-05-03 | 2024-05-10 | 2024-05-17 | 2024-05-17 | 2024-05-20 | 2024-05-20 | 2024-05-21 | 2024-05-27 | 2024-05-27 | 2024-06-03 | 2024-06-03 | 2024-06-03 | [40 empty] | 2024-07-06 | 2024-07-10 | 2024-07-10 | 2024-07-13 | 2024-07-17 | 2024-07-26 | 2024-06-18 | 2024-07-06 | 2024-07-08 | 2024-07-30 | 2024-07-27 | 2024-08-02 | 2024-08-04 | 2024-08-10 | 2024-08-16
V_61 | 2024-02-25 | 2024-03-03 | 2024-03-05 | 2024-03-10 | 2024-03-15 | 2024-03-18 | 2024-03-19 | 2024-03-22 | 2024-03-25 | 2024-03-29 | 2024-03-31 | 2024-03-31 | 2024-04-17 | 2024-04-26 | 2024-05-03 | 2024-05-03 | 2024-05-10 | 2024-05-17 | 2024-05-17 | 2024-05-20 | 2024-05-20 | 2024-05-21 | 2024-05-27 | 2024-05-27 | 2024-06-03 | 2024-06-03 | 2024-06-03 | [40 empty] | 2024-07-06 | 2024-07-10 | 2024-07-10 | 2024-07-13 | 2024-07-17 | 2024-07-26 | 2024-06-18 | 2024-07-06 | 2024-07-08 | 2024-07-30 | 2024-07-27 | 2024-08-02 | 2024-08-04 | 2024-08-10 | 2024-08-16
V_62 | 2024-02-25 | 2024-03-03 | 2024-03-05 | 2024-03-10 | 2024-03-15 | 2024-03-18 | 2024-03-19 | 2024-03-22 | 2024-03-25 | 2024-03-29 | 2024-03-31 | 2024-03-31 | 2024-04-17 | 2024-04-26 | 2024-05-03 | 2024-05-03 | 2024-05-10 | 2024-05-17 | 2024-05-17 | 2024-05-20 | 2024-05-20 | 2024-05-21 | 2024-05-27 | 2024-05-27 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2024-06-08 | 2024-06-12 | 2024-06-19 | 2024-06-24 | 2024-06-29 | 2024-07-06 | 2024-07-06 | 2024-07-10 | 2024-07-13 | 2024-07-13 | 2024-07-13 | 2024-07-19 | 2024-07-20 | 2024-07-24 | 2024-08-02 | 2024-04-26 | 2024-04-28 | 2024-05-05 | 2024-05-12 | 2024-05-17 | 2024-05-18 | 2024-05-24 | 2024-05-24 | 2024-05-25 | 2024-05-28 | 2024-05-29 | 2024-06-03 | 2024-06-03 | 2024-06-05 | 2024-06-08 | 2024-06-10 | 2024-06-10 | 2024-06-14 | 2024-06-16 | 2024-06-17 | 2024-06-18 | 2024-06-24 | 2024-06-29 | 2024-07-06 | 2024-07-06 | 2024-07-06 | 2024-07-10 | 2024-07-10 | 2024-07-13 | 2024-07-17 | 2024-07-26 | 2024-06-18 | 2024-07-06 | 2024-07-08 | 2024-07-30 | 2024-07-27 | 2024-08-02 | 2024-08-04 | 2024-08-10 | 2024-08-16
V_63 | 2024-02-25 | 2024-03-03 | 2024-03-05 | 2024-03-10 | 2024-03-15 | 2024-03-18 | 2024-03-19 | 2024-03-22 | 2024-03-25 | 2024-03-29 | 2024-03-31 | 2024-03-31 | 2024-04-17 | 2024-04-26 | 2024-05-03 | 2024-05-03 | 2024-05-10 | 2024-05-17 | 2024-05-17 | 2024-05-20 | 2024-05-20 | 2024-05-21 | 2024-05-27 | 2024-05-27 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2024-06-08 | 2024-06-12 | 2024-06-19 | 2024-06-24 | 2024-06-29 | 2024-07-06 | 2024-07-06 | 2024-07-10 | 2024-07-13 | 2024-07-13 | 2024-07-13 | 2024-07-19 | 2024-07-20 | 2024-07-24 | 2024-08-02 | 2024-04-26 | 2024-04-28 | 2024-05-05 | 2024-05-12 | 2024-05-17 | 2024-05-18 | 2024-05-24 | 2024-05-24 | 2024-05-25 | 2024-05-28 | 2024-05-29 | 2024-06-03 | 2024-06-03 | 2024-06-05 | 2024-06-08 | 2024-06-10 | 2024-06-10 | 2024-06-14 | 2024-06-16 | 2024-06-17 | 2024-06-18 | 2024-06-24 | 2024-06-29 | 2024-07-06 | 2024-07-06 | 2024-07-06 | 2024-07-10 | 2024-07-10 | 2024-07-13 | 2024-07-17 | 2024-07-26 | 2024-06-18 | 2024-07-06 | 2024-07-08 | 2024-07-30 | 2024-07-27 | 2024-08-02 | 2024-08-04 | 2024-08-10 | 2024-08-16
V_64 | 2024-02-25 | 2024-03-03 | 2024-03-05 | 2024-03-10 | 2024-03-15 | 2024-03-18 | 2024-03-19 | 2024-03-22 | 2024-03-25 | 2024-03-29 | 2024-03-31 | 2024-03-31 | 2024-04-17 | 2024-04-26 | 2024-05-03 | 2024-05-03 | 2024-05-10 | 2024-05-17 | 2024-05-17 | 2024-05-20 | 2024-05-20 | 2024-05-21 | 2024-05-27 | 2024-05-27 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2024-06-08 | 2024-06-12 | 2024-06-19 | 2024-06-24 | 2024-06-29 | 2024-07-06 | 2024-07-06 | 2024-07-10 | 2024-07-13 | 2024-07-13 | 2024-07-13 | 2024-07-19 | 2024-07-20 | 2024-07-24 | 2024-08-02 | 2024-04-26 | 2024-04-28 | 2024-05-05 | 2024-05-12 | 2024-05-17 | 2024-05-18 | 2024-05-24 | 2024-05-24 | 2024-05-25 | 2024-05-28 | 2024-05-29 | 2024-06-03 | 2024-06-03 | 2024-06-05 | 2024-06-08 | 2024-06-10 | 2024-06-10 | 2024-06-14 | 2024-06-16 | 2024-06-17 | 2024-06-18 | 2024-06-24 | 2024-06-29 | 2024-07-06 | 2024-07-06 | 2024-07-06 | 2024-07-10 | 2024-07-10 | 2024-07-13 | 2024-07-17 | 2024-07-26 | 2024-06-18 | 2024-07-06 | 2024-07-08 | 2024-07-30 | 2024-07-27 | 2024-08-02 | 2024-08-04 | 2024-08-10 | 2024-08-16
V_65 | 2024-03-03 | 2024-03-10 | 2024-03-12 | 2024-03-18 | 2024-03-23 | 2024-03-26 | 2024-03-27 | 2024-03-31 | 2024-04-05 | 2024-04-08 | 2024-04-12 | 2024-04-12 | 2024-04-26 | 2024-05-04 | 2024-05-11 | 2024-05-11 | 2024-05-18 | 2024-05-25 | 2024-05-25 | 2024-05-28 | 2024-05-28 | 2024-05-29 | 2024-06-04 | 2024-06-04 | 2024-06-11 | 2024-06-11 | 2024-06-11 | 2024-06-16 | 2024-06-21 | 2024-06-28 | 2024-07-02 | 2024-07-07 | 2024-07-14 | 2024-07-14 | 2024-07-19 | 2024-07-21 | 2024-07-21 | 2024-07-21 | 2024-07-27 | 2024-07-28 | 2024-08-02 | 2024-08-10 | 2024-05-04 | 2024-05-06 | 2024-05-13 | 2024-05-20 | 2024-05-25 | 2024-05-26 | 2024-06-01 | 2024-06-01 | 2024-06-02 | 2024-06-05 | 2024-06-07 | 2024-06-11 | 2024-06-11 | 2024-06-14 | 2024-06-16 | 2024-06-18 | 2024-06-18 | 2024-06-22 | 2024-06-24 | 2024-06-25 | 2024-06-26 | 2024-07-02 | 2024-07-07 | 2024-07-14 | 2024-07-14 | 2024-07-14 | 2024-07-19 | 2024-07-19 | 2024-07-21 | 2024-07-26 | 2024-08-03 | 2024-06-26 | 2024-07-14 | 2024-07-16 | 2024-08-07 | 2024-08-04 | 2024-08-10 | 2024-08-12 | 2024-08-18 | 2024-08-24
V_66 | 2024-03-03 | 2024-03-10 | 2024-03-12 | 2024-03-18 | 2024-03-23 | 2024-03-26 | 2024-03-27 | 2024-03-31 | 2024-04-05 | 2024-04-08 | 2024-04-12 | 2024-04-12 | 2024-04-26 | 2024-05-04 | 2024-05-11 | 2024-05-11 | 2024-05-18 | 2024-05-25 | 2024-05-25 | 2024-05-28 | 2024-05-28 | 2024-05-29 | 2024-06-04 | 2024-06-04 | 2024-06-11 | 2024-06-11 | 2024-06-11 | 2024-06-16 | 2024-06-21 | 2024-06-28 | 2024-07-02 | 2024-07-07 | 2024-07-14 | 2024-07-14 | 2024-07-19 | 2024-07-21 | 2024-07-21 | 2024-07-21 | 2024-07-27 | 2024-07-28 | 2024-08-02 | 2024-08-10 | 2024-05-04 | 2024-05-06 | 2024-05-13 | 2024-05-20 | 2024-05-25 | 2024-05-26 | 2024-06-01 | 2024-06-01 | 2024-06-02 | 2024-06-05 | 2024-06-07 | 2024-06-11 | 2024-06-11 | 2024-06-14 | 2024-06-16 | 2024-06-18 | 2024-06-18 | 2024-06-22 | 2024-06-24 | 2024-06-25 | 2024-06-26 | 2024-07-02 | 2024-07-07 | 2024-07-14 | 2024-07-14 | 2024-07-14 | 2024-07-19 | 2024-07-19 | 2024-07-21 | 2024-07-26 | 2024-08-03 | 2024-06-26 | 2024-07-14 | 2024-07-16 | 2024-08-07 | 2024-08-04 | 2024-08-10 | 2024-08-12 | 2024-08-18 | 2024-08-24
V_67 | 2024-03-03 | 2024-03-10 | 2024-03-12 | 2024-03-18 | 2024-03-23 | 2024-03-26 | 2024-03-27 | 2024-03-31 | 2024-04-05 | 2024-04-08 | 2024-04-12 | 2024-04-12 | 2024-04-26 | 2024-05-04 | 2024-05-11 | 2024-05-11 | 2024-05-18 | 2024-05-25 | 2024-05-25 | 2024-05-28 | 2024-05-28 | 2024-05-29 | 2024-06-04 | 2024-06-04 | 2024-06-11 | 2024-06-11 | 2024-06-11 | 2024-06-16 | 2024-06-21 | 2024-06-28 | 2024-07-02 | 2024-07-07 | 2024-07-14 | 2024-07-14 | 2024-07-19 | 2024-07-21 | 2024-07-21 | 2024-07-21 | 2024-07-27 | 2024-07-28 | 2024-08-02 | 2024-08-10 | 2024-05-04 | 2024-05-06 | 2024-05-13 | 2024-05-20 | 2024-05-25 | 2024-05-26 | 2024-06-01 | 2024-06-01 | 2024-06-02 | 2024-06-05 | 2024-06-07 | 2024-06-11 | 2024-06-11 | 2024-06-14 | 2024-06-16 | 2024-06-18 | 2024-06-18 | 2024-06-22 | 2024-06-24 | 2024-06-25 | 2024-06-26 | 2024-07-02 | 2024-07-07 | 2024-07-14 | 2024-07-14 | 2024-07-14 | 2024-07-19 | 2024-07-19 | 2024-07-21 | 2024-07-26 | 2024-08-03 | 2024-06-26 | 2024-07-14 | 2024-07-16 | 2024-08-07 | 2024-08-04 | 2024-08-10 | 2024-08-12 | 2024-08-18 | 2024-08-24
V_68 | 2024-03-03 | 2024-03-10 | 2024-03-12 | 2024-03-18 | 2024-03-23 | 2024-03-26 | 2024-03-27 | 2024-03-31 | 2024-04-05 | 2024-04-08 | 2024-04-12 | 2024-04-12 | 2024-04-26 | 2024-05-04 | 2024-05-11 | 2024-05-11 | 2024-05-18 | 2024-05-25 | 2024-05-25 | 2024-05-28 | 2024-05-28 | 2024-05-29 | 2024-06-04 | 2024-06-04 | 2024-06-11 | 2024-06-11 | 2024-06-11 | 2024-06-16 | 2024-06-21 | 2024-06-28 | 2024-07-02 | 2024-07-07 | 2024-07-14 | 2024-07-14 | 2024-07-19 | 2024-07-21 | 2024-07-21 | 2024-07-21 | 2024-07-27 | 2024-07-28 | 2024-08-02 | 2024-08-10 | 2024-05-04 | 2024-05-06 | 2024-05-13 | 2024-05-20 | 2024-05-25 | 2024-05-26 | 2024-06-01 | 2024-06-01 | 2024-06-02 | 2024-06-05 | 2024-06-07 | 2024-06-11 | 2024-06-11 | 2024-06-14 | 2024-06-16 | 2024-06-18 | 2024-06-18 | 2024-06-22 | 2024-06-24 | 2024-06-25 | 2024-06-26 | 2024-07-02 | 2024-07-07 | 2024-07-14 | 2024-07-14 | 2024-07-14 | 2024-07-19 | 2024-07-19 | 2024-07-21 | 2024-07-26 | 2024-08-03 | 2024-06-26 | 2024-07-14 | 2024-07-16 | 2024-08-07 | 2024-08-04 | 2024-08-10 | 2024-08-12 | 2024-08-18 | 2024-08-24
V_69 | 2024-03-03 | 2024-03-10 | 2024-03-12 | 2024-03-18 | 2024-03-23 | 2024-03-26 | 2024-03-27 | 2024-03-31 | 2024-04-05 | 2024-04-08 | 2024-04-12 | 2024-04-12 | 2024-04-26 | 2024-05-04 | 2024-05-11 | 2024-05-11 | 2024-05-18 | 2024-05-25 | 2024-05-25 | 2024-05-28 | 2024-05-28 | 2024-05-29 | 2024-06-04 | 2024-06-04 | 2024-06-11 | 2024-06-11 | 2024-06-11 | 2024-06-16 | 2024-06-21 | 2024-06-28 | 2024-07-02 | 2024-07-07 | 2024-07-14 | 2024-07-14 | 2024-07-19 | 2024-07-21 | 2024-07-21 | 2024-07-21 | 2024-07-27 | 2024-07-28 | 2024-08-02 | 2024-08-10 | 2024-05-04 | 2024-05-06 | 2024-05-13 | 2024-05-20 | 2024-05-25 | 2024-05-26 | 2024-06-01 | 2024-06-01 | 2024-06-02 | 2024-06-05 | 2024-06-07 | 2024-06-11 | 2024-06-11 | 2024-06-14 | 2024-06-16 | 2024-06-18 | 2024-06-18 | 2024-06-22 | 2024-06-24 | 2024-06-25 | 2024-06-26 | 2024-07-02 | 2024-07-07 | 2024-07-14 | 2024-07-14 | 2024-07-14 | 2024-07-19 | 2024-07-19 | 2024-07-21 | 2024-07-26 | 2024-08-03 | 2024-06-26 | 2024-07-14 | 2024-07-16 | 2024-08-07 | 2024-08-04 | 2024-08-10 | 2024-08-12 | 2024-08-18 | 2024-08-24
V_70 | 2024-03-03 | 2024-03-10 | 2024-03-12 | 2024-03-18 | 2024-03-23 | 2024-03-26 | 2024-03-27 | 2024-03-31 | 2024-04-05 | 2024-04-08 | 2024-04-12 | 2024-04-12 | 2024-04-26 | 2024-05-04 | 2024-05-11 | 2024-05-11 | 2024-05-18 | 2024-05-25 | 2024-05-25 | 2024-05-28 | 2024-05-28 | 2024-05-29 | 2024-06-04 | 2024-06-04 | 2024-06-11 | 2024-06-11 | 2024-06-11 | 2024-06-16 | 2024-06-21 | 2024-06-28 | 2024-07-02 | 2024-07-07 | 2024-07-14 | 2024-07-14 | 2024-07-19 | 2024-07-21 | 2024-07-21 | 2024-07-21 | 2024-07-27 | 2024-07-28 | 2024-08-02 | 2024-08-10 | 2024-05-04 | 2024-05-06 | 2024-05-13 | 2024-05-20 | 2024-05-25 | 2024-05-26 | 2024-06-01 | 2024-06-01 | 2024-06-02 | 2024-06-05 | 2024-06-07 | 2024-06-11 | 2024-06-11 | 2024-06-14 | 2024-06-16 | 2024-06-18 | 2024-06-18 | 2024-06-22 | 2024-06-24 | 2024-06-25 | 2024-06-26 | 2024-07-02 | 2024-07-07 | 2024-07-14 | 2024-07-14 | 2024-07-14 | 2024-07-19 | 2024-07-19 | 2024-07-21 | 2024-07-26 | 2024-08-03 | 2024-06-26 | 2024-07-14 | 2024-07-16 | 2024-08-07 | 2024-08-04 | 2024-08-10 | 2024-08-12 | 2024-08-18 | 2024-08-24
V_71 | 2024-03-03 | 2024-03-10 | 2024-03-12 | 2024-03-18 | 2024-03-23 | 2024-03-26 | 2024-03-27 | 2024-03-31 | 2024-04-05 | 2024-04-08 | 2024-04-12 | 2024-04-12 | 2024-04-26 | 2024-05-04 | 2024-05-11 | 2024-05-11 | 2024-05-18 | 2024-05-25 | 2024-05-25 | 2024-05-28 | 2024-05-28 | 2024-05-29 | 2024-06-04 | 2024-06-04 | 2024-06-11 | 2024-06-11 | 2024-06-11 | 2024-06-16 | 2024-06-21 | 2024-06-28 | 2024-07-02 | 2024-07-07 | 2024-07-14 | 2024-07-14 | 2024-07-19 | 2024-07-21 | 2024-07-21 | 2024-07-21 | 2024-07-27 | 2024-07-28 | 2024-08-02 | 2024-08-10 | 2024-05-04 | 2024-05-06 | 2024-05-13 | 2024-05-20 | 2024-05-25 | 2024-05-26 | 2024-06-01 | 2024-06-01 | 2024-06-02 | 2024-06-05 | 2024-06-07 | 2024-06-11 | 2024-06-11 | 2024-06-14 | 2024-06-16 | 2024-06-18 | 2024-06-18 | 2024-06-22 | 2024-06-24 | 2024-06-25 | 2024-06-26 | 2024-07-02 | 2024-07-07 | 2024-07-14 | 2024-07-14 | 2024-07-14 | 2024-07-19 | 2024-07-19 | 2024-07-21 | 2024-07-26 | 2024-08-03 | 2024-06-26 | 2024-07-14 | 2024-07-16 | 2024-08-07 | 2024-08-04 | 2024-08-10 | 2024-08-12 | 2024-08-18 | 2024-08-24
V_72 | 2024-03-03 | 2024-03-10 | 2024-03-12 | 2024-03-18 | 2024-03-23 | 2024-03-26 | 2024-03-27 | 2024-03-31 | 2024-04-05 | 2024-04-08 | 2024-04-12 | 2024-04-12 | 2024-04-26 | 2024-05-04 | 2024-05-11 | 2024-05-11 | 2024-05-18 | 2024-05-25 | 2024-05-25 | 2024-05-28 | 2024-05-28 | 2024-05-29 | 2024-06-04 | 2024-06-04 | 2024-06-11 | 2024-06-11 | 2024-06-11 | 2024-06-16 | 2024-06-21 | 2024-06-28 | 2024-07-02 | 2024-07-07 | 2024-07-14 | 2024-07-14 | 2024-07-19 | 2024-07-21 | 2024-07-21 | 2024-07-21 | 2024-07-27 | 2024-07-28 | 2024-08-02 | 2024-08-10 | 2024-05-04 | 2024-05-06 | 2024-05-13 | 2024-05-20 | 2024-05-25 | 2024-05-26 | 2024-06-01 | 2024-06-01 | 2024-06-02 | 2024-06-05 | 2024-06-07 | 2024-06-11 | 2024-06-11 | 2024-06-14 | 2024-06-16 | 2024-06-18 | 2024-06-18 | 2024-06-22 | 2024-06-24 | 2024-06-25 | 2024-06-26 | 2024-07-02 | 2024-07-07 | 2024-07-14 | 2024-07-14 | 2024-07-14 | 2024-07-19 | 2024-07-19 | 2024-07-21 | 2024-07-26 | 2024-08-03 | 2024-06-26 | 2024-07-14 | 2024-07-16 | 2024-08-07 | 2024-08-04 | 2024-08-10 | 2024-08-12 | 2024-08-18 | 2024-08-24
V_73 | 2024-03-10 | 2024-03-17 | 2024-03-19 | 2024-03-25 | 2024-03-30 | 2024-04-02 | 2024-04-03 | 2024-04-07 | 2024-04-12 | 2024-04-15 | 2024-04-19 | 2024-04-19 | 2024-05-04 | 2024-05-12 | 2024-05-19 | 2024-05-19 | 2024-05-26 | 2024-06-02 | 2024-06-02 | 2024-06-05 | 2024-06-05 | 2024-06-07 | 2024-06-12 | 2024-06-12 | 2024-06-19 | 2024-06-19 | 2024-06-19 | 2024-06-24 | 2024-06-29 | 2024-07-06 | 2024-07-10 | 2024-07-15 | 2024-07-22 | 2024-07-22 | 2024-07-27 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-08-04 | 2024-08-05 | 2024-08-10 | 2024-08-18 | 2024-05-12 | 2024-05-14 | 2024-05-21 | 2024-05-28 | 2024-06-02 | 2024-06-03 | 2024-06-09 | 2024-06-09 | 2024-06-10 | 2024-06-14 | 2024-06-15 | 2024-06-19 | 2024-06-19 | 2024-06-22 | 2024-06-24 | 2024-06-26 | 2024-06-26 | 2024-06-30 | 2024-07-02 | 2024-07-03 | 2024-07-05 | 2024-07-10 | 2024-07-15 | 2024-07-22 | 2024-07-22 | 2024-07-22 | 2024-07-27 | 2024-07-27 | 2024-07-29 | 2024-08-03 | 2024-08-11 | 2024-07-05 | 2024-07-22 | 2024-07-24 | 2024-08-16 | 2024-08-12 | 2024-08-18 | 2024-08-20 | 2024-08-26 | 2024-09-01
V_74 | 2024-03-10 | 2024-03-17 | 2024-03-19 | 2024-03-25 | 2024-03-30 | 2024-04-02 | 2024-04-03 | 2024-04-07 | 2024-04-12 | 2024-04-15 | [19 empty] | 2024-07-06 | 2024-07-10 | 2024-07-15 | 2024-07-22 | 2024-07-22 | 2024-07-27 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-08-04 | 2024-08-05 | 2024-08-10 | 2024-08-18 | 2024-05-12 | 2024-05-14 | 2024-05-21 | 2024-05-28 | 2024-06-02 | 2024-06-03 | 2024-06-09 | 2024-06-09 | 2024-06-10 | 2024-06-14 | 2024-06-15 | 2024-06-19 | 2024-06-19 | 2024-06-22 | 2024-06-24 | 2024-06-26 | 2024-06-26 | 2024-06-30 | 2024-07-02 | 2024-07-03 | 2024-07-05 | 2024-07-10 | 2024-07-15 | 2024-07-22 | 2024-07-22 | 2024-07-22 | 2024-07-27 | 2024-07-27 | 2024-07-29 | 2024-08-03 | 2024-08-11 | 2024-07-05 | 2024-07-22 | 2024-07-24 | 2024-08-16 | 2024-08-12 | 2024-08-18 | 2024-08-20 | 2024-08-26 | 2024-09-01
V_75 | 2024-03-10 | 2024-03-17 | 2024-03-19 | 2024-03-25 | 2024-03-30 | 2024-04-02 | 2024-04-03 | 2024-04-07 | 2024-04-12 | 2024-04-15 | [19 empty] | 2024-07-06 | 2024-07-10 | 2024-07-15 | 2024-07-22 | 2024-07-22 | 2024-07-27 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-08-04 | 2024-08-05 | 2024-08-10 | 2024-08-18 | 2024-05-12 | 2024-05-14 | 2024-05-21 | 2024-05-28 | 2024-06-02 | 2024-06-03 | 2024-06-09 | 2024-06-09 | 2024-06-10 | 2024-06-14 | 2024-06-15 | 2024-06-19 | 2024-06-19 | 2024-06-22 | 2024-06-24 | 2024-06-26 | 2024-06-26 | 2024-06-30 | 2024-07-02 | 2024-07-03 | 2024-07-05 | 2024-07-10 | 2024-07-15 | 2024-07-22 | 2024-07-22 | 2024-07-22 | 2024-07-27 | 2024-07-27 | 2024-07-29 | 2024-08-03 | 2024-08-11 | 2024-07-05 | 2024-07-22 | 2024-07-24 | 2024-08-16 | 2024-08-12 | 2024-08-18 | 2024-08-20 | 2024-08-26 | 2024-09-01
V_76 | 2024-03-10 | 2024-03-17 | 2024-03-19 | 2024-03-25 | 2024-03-30 | 2024-04-02 | 2024-04-03 | 2024-04-07 | 2024-04-12 | 2024-04-15 | [19 empty] | 2024-07-06 | 2024-07-10 | 2024-07-15 | 2024-07-22 | 2024-07-22 | 2024-07-27 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-08-04 | 2024-08-05 | 2024-08-10 | 2024-08-18 | 2024-05-12 | 2024-05-14 | 2024-05-21 | 2024-05-28 | 2024-06-02 | 2024-06-03 | 2024-06-09 | 2024-06-09 | 2024-06-10 | 2024-06-14 | 2024-06-15 | 2024-06-19 | 2024-06-19 | 2024-06-22 | 2024-06-24 | 2024-06-26 | 2024-06-26 | 2024-06-30 | 2024-07-02 | 2024-07-03 | 2024-07-05 | 2024-07-10 | 2024-07-15 | 2024-07-22 | 2024-07-22 | 2024-07-22 | 2024-07-27 | 2024-07-27 | 2024-07-29 | 2024-08-03 | 2024-08-11 | 2024-07-05 | 2024-07-22 | 2024-07-24 | 2024-08-16 | 2024-08-12 | 2024-08-18 | 2024-08-20 | 2024-08-26 | 2024-09-01
V_77 | 2024-03-10 | 2024-03-17 | 2024-03-19 | 2024-03-25 | 2024-03-30 | 2024-04-02 | 2024-04-03 | 2024-04-07 | 2024-04-12 | 2024-04-15 | [19 empty] | 2024-07-06 | 2024-07-10 | 2024-07-15 | 2024-07-22 | 2024-07-22 | 2024-07-27 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-08-04 | 2024-08-05 | 2024-08-10 | 2024-08-18 | 2024-05-12 | 2024-05-14 | 2024-05-21 | 2024-05-28 | 2024-06-02 | 2024-06-03 | 2024-06-09 | 2024-06-09 | 2024-06-10 | 2024-06-14 | 2024-06-15 | 2024-06-19 | 2024-06-19 | 2024-06-22 | 2024-06-24 | 2024-06-26 | 2024-06-26 | 2024-06-30 | 2024-07-02 | 2024-07-03 | 2024-07-05 | 2024-07-10 | 2024-07-15 | 2024-07-22 | 2024-07-22 | 2024-07-22 | 2024-07-27 | 2024-07-27 | 2024-07-29 | 2024-08-03 | 2024-08-11 | 2024-07-05 | 2024-07-22 | 2024-07-24 | 2024-08-16 | 2024-08-12 | 2024-08-18 | 2024-08-20 | 2024-08-26 | 2024-09-01
V_78 | 2024-03-10 | 2024-03-17 | 2024-03-19 | 2024-03-25 | 2024-03-30 | 2024-04-02 | 2024-04-03 | 2024-04-07 | 2024-04-12 | 2024-04-15 | [19 empty] | 2024-07-06 | 2024-07-10 | 2024-07-15 | 2024-07-22 | 2024-07-22 | 2024-07-27 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-08-04 | 2024-08-05 | 2024-08-10 | 2024-08-18 | 2024-05-12 | 2024-05-14 | 2024-05-21 | 2024-05-28 | 2024-06-02 | 2024-06-03 | 2024-06-09 | 2024-06-09 | 2024-06-10 | 2024-06-14 | 2024-06-15 | 2024-06-19 | 2024-06-19 | 2024-06-22 | 2024-06-24 | 2024-06-26 | 2024-06-26 | 2024-06-30 | 2024-07-02 | 2024-07-03 | 2024-07-05 | 2024-07-10 | 2024-07-15 | 2024-07-22 | 2024-07-22 | 2024-07-22 | 2024-07-27 | 2024-07-27 | 2024-07-29 | 2024-08-03 | 2024-08-11 | 2024-07-05 | 2024-07-22 | 2024-07-24 | 2024-08-16 | 2024-08-12 | 2024-08-18 | 2024-08-20 | 2024-08-26 | 2024-09-01
V_79 | 2024-03-10 | 2024-03-17 | 2024-03-19 | 2024-03-25 | 2024-03-30 | 2024-04-02 | 2024-04-03 | 2024-04-07 | 2024-04-12 | 2024-04-15 | 2024-04-19 | 2024-04-19 | 2024-05-04 | 2024-05-12 | 2024-05-19 | 2024-05-19 | 2024-05-26 | 2024-06-02 | 2024-06-02 | 2024-06-05 | 2024-06-05 | 2024-06-07 | 2024-06-12 | 2024-06-12 | 2024-06-19 | 2024-06-19 | 2024-06-19 | 2024-06-24 | 2024-06-29 | 2024-07-06 | 2024-07-10 | 2024-07-15 | 2024-07-22 | 2024-07-22 | 2024-07-27 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-08-04 | 2024-08-05 | 2024-08-10 | 2024-08-18 | 2024-05-12 | 2024-05-14 | 2024-05-21 | 2024-05-28 | 2024-06-02 | 2024-06-03 | 2024-06-09 | 2024-06-09 | 2024-06-10 | 2024-06-14 | 2024-06-15 | 2024-06-19 | 2024-06-19 | 2024-06-22 | 2024-06-24 | 2024-06-26 | 2024-06-26 | 2024-06-30 | 2024-07-02 | 2024-07-03 | 2024-07-05 | 2024-07-10 | 2024-07-15 | 2024-07-22 | 2024-07-22 | 2024-07-22 | 2024-07-27 | 2024-07-27 | 2024-07-29 | 2024-08-03 | 2024-08-11 | 2024-07-05 | 2024-07-22 | 2024-07-24 | 2024-08-16 | 2024-08-12 | 2024-08-18 | 2024-08-20 | 2024-08-26 | 2024-09-01
V_80 | 2024-03-10 | 2024-03-17 | 2024-03-19 | 2024-03-25 | 2024-03-30 | 2024-04-02 | 2024-04-03 | 2024-04-07 | 2024-04-12 | 2024-04-15 | 2024-04-19 | 2024-04-19 | 2024-05-04 | 2024-05-12 | 2024-05-19 | 2024-05-19 | 2024-05-26 | 2024-06-02 | 2024-06-02 | 2024-06-05 | 2024-06-05 | 2024-06-07 | 2024-06-12 | 2024-06-12 | 2024-06-19 | 2024-06-19 | 2024-06-19 | 2024-06-24 | 2024-06-29 | 2024-07-06 | 2024-07-10 | 2024-07-15 | 2024-07-22 | 2024-07-22 | 2024-07-27 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-08-04 | 2024-08-05 | 2024-08-10 | 2024-08-18 | 2024-05-12 | 2024-05-14 | 2024-05-21 | 2024-05-28 | 2024-06-02 | 2024-06-03 | 2024-06-09 | 2024-06-09 | 2024-06-10 | 2024-06-14 | 2024-06-15 | 2024-06-19 | 2024-06-19 | 2024-06-22 | 2024-06-24 | 2024-06-26 | 2024-06-26 | 2024-06-30 | 2024-07-02 | 2024-07-03 | 2024-07-05 | 2024-07-10 | 2024-07-15 | 2024-07-22 | 2024-07-22 | 2024-07-22 | 2024-07-27 | 2024-07-27 | 2024-07-29 | 2024-08-03 | 2024-08-11 | 2024-07-05 | 2024-07-22 | 2024-07-24 | 2024-08-16 | 2024-08-12 | 2024-08-18 | 2024-08-20 | 2024-08-26 | 2024-09-01
V_81 | 2024-03-17 | 2024-03-24 | 2024-03-26 | 2024-04-01 | 2024-04-06 | 2024-04-09 | 2024-04-10 | 2024-04-14 | 2024-04-19 | 2024-04-22 | 2024-04-26 | 2024-04-26 | 2024-05-12 | 2024-05-20 | 2024-05-27 | 2024-05-27 | 2024-06-03 | 2024-06-10 | 2024-06-10 | 2024-06-14 | 2024-06-14 | 2024-06-15 | 2024-06-21 | 2024-06-21 | 2024-06-28 | 2024-06-28 | 2024-06-28 | 2024-07-02 | 2024-07-07 | 2024-07-14 | 2024-07-19 | 2024-07-23 | 2024-07-30 | 2024-07-30 | 2024-08-04 | 2024-08-06 | 2024-08-06 | 2024-08-06 | 2024-08-12 | 2024-08-13 | 2024-08-18 | 2024-08-26 | 2024-05-20 | 2024-05-22 | 2024-05-29 | 2024-06-05 | 2024-06-10 | 2024-06-11 | 2024-06-17 | 2024-06-17 | 2024-06-18 | 2024-06-22 | 2024-06-23 | 2024-06-28 | 2024-06-28 | 2024-06-30 | 2024-07-02 | 2024-07-05 | 2024-07-05 | 2024-07-08 | 2024-07-10 | 2024-07-12 | 2024-07-13 | 2024-07-19 | 2024-07-23 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-08-04 | 2024-08-04 | 2024-08-06 | 2024-08-11 | 2024-08-19 | 2024-07-13 | 2024-07-30 | 2024-08-02 | 2024-08-24 | 2024-08-20 | 2024-08-26 | 2024-08-28 | 2024-09-03 | 2024-09-09
V_82 | 2024-03-17 | 2024-03-24 | 2024-03-26 | 2024-04-01 | 2024-04-06 | 2024-04-09 | 2024-04-10 | 2024-04-14 | 2024-04-19 | 2024-04-22 | 2024-04-26 | 2024-04-26 | 2024-05-12 | 2024-05-20 | 2024-05-27 | 2024-05-27 | 2024-06-03 | 2024-06-10 | 2024-06-10 | 2024-06-14 | 2024-06-14 | 2024-06-15 | 2024-06-21 | 2024-06-21 | 2024-06-28 | 2024-06-28 | 2024-06-28 | 2024-07-02 | 2024-07-07 | 2024-07-14 | 2024-07-19 | 2024-07-23 | 2024-07-30 | 2024-07-30 | 2024-08-04 | 2024-08-06 | 2024-08-06 | 2024-08-06 | 2024-08-12 | 2024-08-13 | 2024-08-18 | 2024-08-26 | 2024-05-20 | 2024-05-22 | 2024-05-29 | 2024-06-05 | 2024-06-10 | 2024-06-11 | 2024-06-17 | 2024-06-17 | 2024-06-18 | 2024-06-22 | 2024-06-23 | 2024-06-28 | 2024-06-28 | 2024-06-30 | 2024-07-02 | 2024-07-05 | 2024-07-05 | 2024-07-08 | 2024-07-10 | 2024-07-12 | 2024-07-13 | 2024-07-19 | 2024-07-23 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-08-04 | 2024-08-04 | 2024-08-06 | 2024-08-11 | 2024-08-19 | 2024-07-13 | 2024-07-30 | 2024-08-02 | 2024-08-24 | 2024-08-20 | 2024-08-26 | 2024-08-28 | 2024-09-03 | 2024-09-09
V_83 | 2024-03-17 | 2024-03-24 | 2024-03-26 | 2024-04-01 | 2024-04-06 | 2024-04-09 | 2024-04-10 | 2024-04-14 | 2024-04-19 | 2024-04-22 | 2024-04-26 | 2024-04-26 | 2024-05-12 | 2024-05-20 | 2024-05-27 | 2024-05-27 | 2024-06-03 | 2024-06-10 | 2024-06-10 | 2024-06-14 | 2024-06-14 | 2024-06-15 | 2024-06-21 | 2024-06-21 | 2024-06-28 | 2024-06-28 | 2024-06-28 | 2024-07-02 | 2024-07-07 | 2024-07-14 | 2024-07-19 | 2024-07-23 | 2024-07-30 | 2024-07-30 | 2024-08-04 | 2024-08-06 | 2024-08-06 | 2024-08-06 | 2024-08-12 | 2024-08-13 | 2024-08-18 | 2024-08-26 | 2024-05-20 | 2024-05-22 | 2024-05-29 | 2024-06-05 | 2024-06-10 | 2024-06-11 | 2024-06-17 | 2024-06-17 | 2024-06-18 | 2024-06-22 | 2024-06-23 | 2024-06-28 | 2024-06-28 | 2024-06-30 | 2024-07-02 | 2024-07-05 | 2024-07-05 | 2024-07-08 | 2024-07-10 | 2024-07-12 | 2024-07-13 | 2024-07-19 | 2024-07-23 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-08-04 | 2024-08-04 | 2024-08-06 | 2024-08-11 | 2024-08-19 | 2024-07-13 | 2024-07-30 | 2024-08-02 | 2024-08-24 | 2024-08-20 | 2024-08-26 | 2024-08-28 | 2024-09-03 | 2024-09-09
V_84 | 2024-03-17 | 2024-03-24 | 2024-03-26 | 2024-04-01 | 2024-04-06 | 2024-04-09 | 2024-04-10 | 2024-04-14 | 2024-04-19 | 2024-04-22 | 2024-04-26 | 2024-04-26 | 2024-05-12 | 2024-05-20 | 2024-05-27 | 2024-05-27 | 2024-06-03 | 2024-06-10 | 2024-06-10 | 2024-06-14 | 2024-06-14 | 2024-06-15 | 2024-06-21 | 2024-06-21 | 2024-06-28 | 2024-06-28 | 2024-06-28 | 2024-07-02 | 2024-07-07 | 2024-07-14 | 2024-07-19 | 2024-07-23 | 2024-07-30 | 2024-07-30 | 2024-08-04 | 2024-08-06 | 2024-08-06 | 2024-08-06 | 2024-08-12 | 2024-08-13 | 2024-08-18 | 2024-08-26 | 2024-05-20 | 2024-05-22 | 2024-05-29 | 2024-06-05 | 2024-06-10 | 2024-06-11 | 2024-06-17 | 2024-06-17 | 2024-06-18 | 2024-06-22 | 2024-06-23 | 2024-06-28 | 2024-06-28 | 2024-06-30 | 2024-07-02 | 2024-07-05 | 2024-07-05 | 2024-07-08 | 2024-07-10 | 2024-07-12 | 2024-07-13 | 2024-07-19 | 2024-07-23 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-08-04 | 2024-08-04 | 2024-08-06 | 2024-08-11 | 2024-08-19 | 2024-07-13 | 2024-07-30 | 2024-08-02 | 2024-08-24 | 2024-08-20 | 2024-08-26 | 2024-08-28 | 2024-09-03 | 2024-09-09
V_85 | 2024-03-17 | 2024-03-24 | 2024-03-26 | 2024-04-01 | 2024-04-06 | 2024-04-09 | 2024-04-10 | 2024-04-14 | 2024-04-19 | 2024-04-22 | 2024-04-26 | 2024-04-26 | 2024-05-12 | 2024-05-20 | 2024-05-27 | 2024-05-27 | 2024-06-03 | 2024-06-10 | 2024-06-10 | 2024-06-14 | 2024-06-14 | 2024-06-15 | 2024-06-21 | 2024-06-21 | 2024-06-28 | 2024-06-28 | 2024-06-28 | 2024-07-02 | 2024-07-07 | 2024-07-14 | 2024-07-19 | 2024-07-23 | 2024-07-30 | 2024-07-30 | 2024-08-04 | 2024-08-06 | 2024-08-06 | 2024-08-06 | 2024-08-12 | 2024-08-13 | 2024-08-18 | 2024-08-26 | 2024-05-20 | 2024-05-22 | 2024-05-29 | 2024-06-05 | 2024-06-10 | 2024-06-11 | 2024-06-17 | 2024-06-17 | 2024-06-18 | 2024-06-22 | 2024-06-23 | 2024-06-28 | 2024-06-28 | 2024-06-30 | 2024-07-02 | 2024-07-05 | 2024-07-05 | 2024-07-08 | 2024-07-10 | 2024-07-12 | 2024-07-13 | 2024-07-19 | 2024-07-23 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-08-04 | 2024-08-04 | 2024-08-06 | 2024-08-11 | 2024-08-19 | 2024-07-13 | 2024-07-30 | 2024-08-02 | 2024-08-24 | 2024-08-20 | 2024-08-26 | 2024-08-28 | 2024-09-03 | 2024-09-09
V_86 | 2024-03-17 | 2024-03-24 | 2024-03-26 | 2024-04-01 | 2024-04-06 | 2024-04-09 | 2024-04-10 | 2024-04-14 | 2024-04-19 | 2024-04-22 | 2024-04-26 | 2024-04-26 | 2024-05-12 | 2024-05-20 | 2024-05-27 | 2024-05-27 | 2024-06-03 | 2024-06-10 | 2024-06-10 | [41 empty] | 2024-07-10 | 2024-07-12 | 2024-07-13 | 2024-07-19 | 2024-07-23 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-08-04 | 2024-08-04 | 2024-08-06 | 2024-08-11 | 2024-08-19 | 2024-07-13 | 2024-07-30 | 2024-08-02 | 2024-08-24 | 2024-08-20 | 2024-08-26 | 2024-08-28 | 2024-09-03 | 2024-09-09
V_87 | 2024-03-17 | 2024-03-24 | 2024-03-26 | 2024-04-01 | 2024-04-06 | 2024-04-09 | 2024-04-10 | 2024-04-14 | 2024-04-19 | 2024-04-22 | 2024-04-26 | 2024-04-26 | 2024-05-12 | 2024-05-20 | 2024-05-27 | 2024-05-27 | 2024-06-03 | 2024-06-10 | 2024-06-10 | [41 empty] | 2024-07-10 | 2024-07-12 | 2024-07-13 | 2024-07-19 | 2024-07-23 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-08-04 | 2024-08-04 | 2024-08-06 | 2024-08-11 | 2024-08-19 | 2024-07-13 | 2024-07-30 | 2024-08-02 | 2024-08-24 | 2024-08-20 | 2024-08-26 | 2024-08-28 | 2024-09-03 | 2024-09-09
V_88 | 2024-03-17 | 2024-03-24 | 2024-03-26 | 2024-04-01 | 2024-04-06 | 2024-04-09 | 2024-04-10 | 2024-04-14 | 2024-04-19 | 2024-04-22 | 2024-04-26 | 2024-04-26 | 2024-05-12 | 2024-05-20 | 2024-05-27 | 2024-05-27 | 2024-06-03 | 2024-06-10 | 2024-06-10 | [41 empty] | 2024-07-10 | 2024-07-12 | 2024-07-13 | 2024-07-19 | 2024-07-23 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-08-04 | 2024-08-04 | 2024-08-06 | 2024-08-11 | 2024-08-19 | 2024-07-13 | 2024-07-30 | 2024-08-02 | 2024-08-24 | 2024-08-20 | 2024-08-26 | 2024-08-28 | 2024-09-03 | 2024-09-09
V_89 | 2024-03-24 | 2024-03-31 | 2024-04-02 | 2024-04-08 | 2024-04-13 | 2024-04-16 | 2024-04-17 | 2024-04-21 | 2024-04-26 | 2024-04-29 | 2024-05-03 | 2024-05-03 | 2024-05-20 | 2024-05-28 | 2024-06-04 | 2024-06-04 | 2024-06-11 | 2024-06-18 | 2024-06-18 | [41 empty] | 2024-07-19 | 2024-07-20 | 2024-07-21 | 2024-07-27 | 2024-07-31 | 2024-08-07 | 2024-08-07 | 2024-08-07 | 2024-08-12 | 2024-08-12 | 2024-08-14 | 2024-08-19 | 2024-08-27 | 2024-07-21 | 2024-08-07 | 2024-08-10 | 2024-09-01 | 2024-08-28 | 2024-09-03 | 2024-09-06 | 2024-09-11 | 2024-09-17
V_90 | 2024-03-24 | 2024-03-31 | 2024-04-02 | 2024-04-08 | 2024-04-13 | 2024-04-16 | 2024-04-17 | 2024-04-21 | 2024-04-26 | 2024-04-29 | 2024-05-03 | 2024-05-03 | 2024-05-20 | 2024-05-28 | 2024-06-04 | 2024-06-04 | 2024-06-11 | 2024-06-18 | 2024-06-18 | [41 empty] | 2024-07-19 | 2024-07-20 | 2024-07-21 | 2024-07-27 | 2024-07-31 | 2024-08-07 | 2024-08-07 | 2024-08-07 | 2024-08-12 | 2024-08-12 | 2024-08-14 | 2024-08-19 | 2024-08-27 | 2024-07-21 | 2024-08-07 | 2024-08-10 | 2024-09-01 | 2024-08-28 | 2024-09-03 | 2024-09-06 | 2024-09-11 | 2024-09-17
V_91 | 2024-03-24 | 2024-03-31 | 2024-04-02 | 2024-04-08 | 2024-04-13 | 2024-04-16 | 2024-04-17 | 2024-04-21 | 2024-04-26 | 2024-04-29 | 2024-05-03 | 2024-05-03 | 2024-05-20 | 2024-05-28 | 2024-06-04 | 2024-06-04 | 2024-06-11 | 2024-06-18 | 2024-06-18 | [41 empty] | 2024-07-19 | 2024-07-20 | 2024-07-21 | 2024-07-27 | 2024-07-31 | 2024-08-07 | 2024-08-07 | 2024-08-07 | 2024-08-12 | 2024-08-12 | 2024-08-14 | 2024-08-19 | 2024-08-27 | 2024-07-21 | 2024-08-07 | 2024-08-10 | 2024-09-01 | 2024-08-28 | 2024-09-03 | 2024-09-06 | 2024-09-11 | 2024-09-17
V_92 | 2024-03-24 | 2024-03-31 | 2024-04-02 | 2024-04-08 | 2024-04-13 | 2024-04-16 | 2024-04-17 | 2024-04-21 | 2024-04-26 | 2024-04-29 | 2024-05-03 | 2024-05-03 | 2024-05-20 | 2024-05-28 | 2024-06-04 | 2024-06-04 | 2024-06-11 | 2024-06-18 | 2024-06-18 | [41 empty] | 2024-07-19 | 2024-07-20 | 2024-07-21 | 2024-07-27 | 2024-07-31 | 2024-08-07 | 2024-08-07 | 2024-08-07 | 2024-08-12 | 2024-08-12 | 2024-08-14 | 2024-08-19 | 2024-08-27 | 2024-07-21 | 2024-08-07 | 2024-08-10 | 2024-09-01 | 2024-08-28 | 2024-09-03 | 2024-09-06 | 2024-09-11 | 2024-09-17
V_93 | 2024-03-24 | 2024-03-31 | 2024-04-02 | 2024-04-08 | 2024-04-13 | 2024-04-16 | 2024-04-17 | 2024-04-21 | 2024-04-26 | 2024-04-29 | 2024-05-03 | 2024-05-03 | 2024-05-20 | 2024-05-28 | 2024-06-04 | 2024-06-04 | 2024-06-11 | 2024-06-18 | 2024-06-18 | [41 empty] | 2024-07-19 | 2024-07-20 | 2024-07-21 | 2024-07-27 | 2024-07-31 | 2024-08-07 | 2024-08-07 | 2024-08-07 | 2024-08-12 | 2024-08-12 | 2024-08-14 | 2024-08-19 | 2024-08-27 | 2024-07-21 | 2024-08-07 | 2024-08-10 | 2024-09-01 | 2024-08-28 | 2024-09-03 | 2024-09-06 | 2024-09-11 | 2024-09-17
V_94 | 2024-03-24 | 2024-03-31 | 2024-04-02 | 2024-04-08 | 2024-04-13 | 2024-04-16 | 2024-04-17 | 2024-04-21 | 2024-04-26 | 2024-04-29 | 2024-05-03 | 2024-05-03 | 2024-05-20 | 2024-05-28 | 2024-06-04 | 2024-06-04 | 2024-06-11 | 2024-06-18 | 2024-06-18 | [41 empty] | 2024-07-19 | 2024-07-20 | 2024-07-21 | 2024-07-27 | 2024-07-31 | 2024-08-07 | 2024-08-07 | 2024-08-07 | 2024-08-12 | 2024-08-12 | 2024-08-14 | 2024-08-19 | 2024-08-27 | 2024-07-21 | 2024-08-07 | 2024-08-10 | 2024-09-01 | 2024-08-28 | 2024-09-03 | 2024-09-06 | 2024-09-11 | 2024-09-17
V_95 | 2024-03-14 | 2024-03-21 | 2024-03-23 | 2024-03-29 | 2024-04-03 | 2024-04-06 | 2024-04-07 | 2024-04-11 | 2024-04-16 | 2024-04-19 | 2024-04-23 | 2024-04-23 | 2024-05-10 | 2024-05-18 | 2024-05-25 | 2024-05-25 | 2024-06-01 | 2024-06-08 | 2024-06-08 | [41 empty] | 2024-07-09 | 2024-07-10 | 2024-07-11 | 2024-07-17 | 2024-07-21 | 2024-07-28 | 2024-07-28 | 2024-07-28 | 2024-08-02 | 2024-08-02 | 2024-08-04 | 2024-08-09 | 2024-08-17 | 2024-07-11 | 2024-07-28 | 2024-07-31 | 2024-08-22 | 2024-08-18 | 2024-08-24 | 2024-08-27 | 2024-09-01 | 2024-09-07
V_96 | 2024-03-14 | 2024-03-21 | 2024-03-23 | 2024-03-29 | 2024-04-03 | 2024-04-06 | 2024-04-07 | 2024-04-11 | 2024-04-16 | 2024-04-19 | 2024-04-23 | 2024-04-23 | 2024-05-10 | 2024-05-18 | 2024-05-25 | 2024-05-25 | 2024-06-01 | 2024-06-08 | 2024-06-08 | [41 empty] | 2024-07-09 | 2024-07-10 | 2024-07-11 | 2024-07-17 | 2024-07-21 | 2024-07-28 | 2024-07-28 | 2024-07-28 | 2024-08-02 | 2024-08-02 | 2024-08-04 | 2024-08-09 | 2024-08-17 | 2024-07-11 | 2024-07-28 | 2024-07-31 | 2024-08-22 | 2024-08-18 | 2024-08-24 | 2024-08-27 | 2024-09-01 | 2024-09-07
V_97 | 2024-03-21 | 2024-03-28 | 2024-03-30 | 2024-04-05 | 2024-04-10 | 2024-04-13 | 2024-04-14 | 2024-04-18 | 2024-04-23 | 2024-04-26 | 2024-04-30 | 2024-04-30 | 2024-05-18 | 2024-05-26 | 2024-06-02 | 2024-06-02 | 2024-06-09 | 2024-06-16 | 2024-06-16 | [41 empty] | 2024-07-17 | 2024-07-18 | 2024-07-19 | 2024-07-25 | 2024-07-30 | 2024-08-06 | 2024-08-06 | 2024-08-06 | 2024-08-10 | 2024-08-10 | 2024-08-13 | 2024-08-17 | 2024-08-25 | 2024-07-19 | 2024-08-06 | 2024-08-08 | 2024-08-30 | 2024-08-27 | 2024-09-01 | 2024-09-04 | 2024-09-10 | 2024-09-15
V_98 | 2024-03-21 | 2024-03-28 | 2024-03-30 | 2024-04-05 | 2024-04-10 | 2024-04-13 | 2024-04-14 | 2024-04-18 | 2024-04-23 | 2024-04-26 | 2024-04-30 | 2024-04-30 | 2024-05-18 | 2024-05-26 | 2024-06-02 | 2024-06-02 | 2024-06-09 | 2024-06-16 | 2024-06-16 | [41 empty] | 2024-07-17 | 2024-07-18 | 2024-07-19 | 2024-07-25 | 2024-07-30 | 2024-08-06 | 2024-08-06 | 2024-08-06 | 2024-08-10 | 2024-08-10 | 2024-08-13 | 2024-08-17 | 2024-08-25 | 2024-07-19 | 2024-08-06 | 2024-08-08 | 2024-08-30 | 2024-08-27 | 2024-09-01 | 2024-09-04 | 2024-09-10 | 2024-09-15
V_99 | 2024-03-21 | 2024-03-28 | 2024-03-30 | 2024-04-05 | 2024-04-10 | 2024-04-13 | 2024-04-14 | 2024-04-18 | 2024-04-23 | 2024-04-26 | 2024-04-30 | 2024-04-30 | 2024-05-18 | 2024-05-26 | 2024-06-02 | 2024-06-02 | 2024-06-09 | 2024-06-16 | 2024-06-16 | [41 empty] | 2024-07-17 | 2024-07-18 | 2024-07-19 | 2024-07-25 | 2024-07-30 | 2024-08-06 | 2024-08-06 | 2024-08-06 | 2024-08-10 | 2024-08-10 | 2024-08-13 | 2024-08-17 | 2024-08-25 | 2024-07-19 | 2024-08-06 | 2024-08-08 | 2024-08-30 | 2024-08-27 | 2024-09-01 | 2024-09-04 | 2024-09-10 | 2024-09-15
V_100 | 2024-03-21 | 2024-03-28 | 2024-03-30 | 2024-04-05 | 2024-04-10 | 2024-04-13 | 2024-04-14 | 2024-04-18 | 2024-04-23 | 2024-04-26 | 2024-04-30 | 2024-04-30 | 2024-05-18 | 2024-05-26 | 2024-06-02 | 2024-06-02 | 2024-06-09 | 2024-06-16 | 2024-06-16 | [41 empty] | 2024-07-17 | 2024-07-18 | 2024-07-19 | 2024-07-25 | 2024-07-30 | 2024-08-06 | 2024-08-06 | 2024-08-06 | 2024-08-10 | 2024-08-10 | 2024-08-13 | 2024-08-17 | 2024-08-25 | 2024-07-19 | 2024-08-06 | 2024-08-08 | 2024-08-30 | 2024-08-27 | 2024-09-01 | 2024-09-04 | 2024-09-10 | 2024-09-15
V_101 | 2024-03-21 | 2024-03-28 | 2024-03-30 | 2024-04-05 | 2024-04-10 | 2024-04-13 | 2024-04-14 | 2024-04-18 | 2024-04-23 | 2024-04-26 | 2024-04-30 | 2024-04-30 | 2024-05-18 | 2024-05-26 | 2024-06-02 | 2024-06-02 | 2024-06-09 | 2024-06-16 | 2024-06-16 | [41 empty] | 2024-07-17 | 2024-07-18 | 2024-07-19 | 2024-07-25 | 2024-07-30 | 2024-08-06 | 2024-08-06 | 2024-08-06 | 2024-08-10 | 2024-08-10 | 2024-08-13 | 2024-08-17 | 2024-08-25 | 2024-07-19 | 2024-08-06 | 2024-08-08 | 2024-08-30 | 2024-08-27 | 2024-09-01 | 2024-09-04 | 2024-09-10 | 2024-09-15
V_102 | 2024-03-21 | 2024-03-28 | 2024-03-30 | 2024-04-05 | 2024-04-10 | 2024-04-13 | 2024-04-14 | 2024-04-18 | 2024-04-23 | 2024-04-26 | 2024-04-30 | 2024-04-30 | 2024-05-18 | 2024-05-26 | 2024-06-02 | 2024-06-02 | 2024-06-09 | 2024-06-16 | 2024-06-16 | [41 empty] | 2024-07-17 | 2024-07-18 | 2024-07-19 | 2024-07-25 | 2024-07-30 | 2024-08-06 | 2024-08-06 | 2024-08-06 | 2024-08-10 | 2024-08-10 | 2024-08-13 | 2024-08-17 | 2024-08-25 | 2024-07-19 | 2024-08-06 | 2024-08-08 | 2024-08-30 | 2024-08-27 | 2024-09-01 | 2024-09-04 | 2024-09-10 | 2024-09-15
V_103 | 2024-03-21 | 2024-03-28 | 2024-03-30 | 2024-04-05 | 2024-04-10 | 2024-04-13 | 2024-04-14 | 2024-04-18 | 2024-04-23 | 2024-04-26 | 2024-04-30 | 2024-04-30 | 2024-05-18 | 2024-05-26 | 2024-06-02 | 2024-06-02 | 2024-06-09 | 2024-06-16 | 2024-06-16 | [41 empty] | 2024-07-17 | 2024-07-18 | 2024-07-19 | 2024-07-25 | 2024-07-30 | 2024-08-06 | 2024-08-06 | 2024-08-06 | 2024-08-10 | 2024-08-10 | 2024-08-13 | 2024-08-17 | 2024-08-25 | 2024-07-19 | 2024-08-06 | 2024-08-08 | 2024-08-30 | 2024-08-27 | 2024-09-01 | 2024-09-04 | 2024-09-10 | 2024-09-15
V_104 | 2024-03-21 | 2024-03-28 | 2024-03-30 | 2024-04-05 | 2024-04-10 | 2024-04-13 | 2024-04-14 | 2024-04-18 | 2024-04-23 | 2024-04-26 | 2024-04-30 | 2024-04-30 | 2024-05-18 | 2024-05-26 | 2024-06-02 | 2024-06-02 | 2024-06-09 | 2024-06-16 | 2024-06-16 | [41 empty] | 2024-07-17 | 2024-07-18 | 2024-07-19 | 2024-07-25 | 2024-07-30 | 2024-08-06 | 2024-08-06 | 2024-08-06 | 2024-08-10 | 2024-08-10 | 2024-08-13 | 2024-08-17 | 2024-08-25 | 2024-07-19 | 2024-08-06 | 2024-08-08 | 2024-08-30 | 2024-08-27 | 2024-09-01 | 2024-09-04 | 2024-09-10 | 2024-09-15
V_105 | 2024-03-28 | 2024-04-04 | 2024-04-06 | 2024-04-12 | 2024-04-17 | 2024-04-20 | 2024-04-21 | 2024-04-25 | 2024-04-30 | 2024-05-03 | 2024-05-07 | 2024-05-07 | 2024-05-26 | 2024-06-04 | 2024-06-11 | 2024-06-11 | 2024-06-18 | 2024-06-25 | 2024-06-25 | [41 empty] | 2024-07-25 | 2024-07-26 | 2024-07-27 | 2024-08-02 | 2024-08-07 | 2024-08-14 | 2024-08-14 | 2024-08-14 | 2024-08-18 | 2024-08-18 | 2024-08-21 | 2024-08-25 | 2024-09-03 | 2024-07-27 | 2024-08-14 | 2024-08-16 | 2024-09-07 | 2024-09-04 | 2024-09-10 | 2024-09-12 | 2024-09-18 | 2024-09-24
V_106 | 2024-03-28 | 2024-04-04 | 2024-04-06 | 2024-04-12 | 2024-04-17 | 2024-04-20 | 2024-04-21 | 2024-04-25 | 2024-04-30 | 2024-05-03 | 2024-05-07 | 2024-05-07 | 2024-05-26 | 2024-06-04 | 2024-06-11 | 2024-06-11 | 2024-06-18 | 2024-06-25 | 2024-06-25 | [41 empty] | 2024-07-25 | 2024-07-26 | 2024-07-27 | 2024-08-02 | 2024-08-07 | 2024-08-14 | 2024-08-14 | 2024-08-14 | 2024-08-18 | 2024-08-18 | 2024-08-21 | 2024-08-25 | 2024-09-03 | 2024-07-27 | 2024-08-14 | 2024-08-16 | 2024-09-07 | 2024-09-04 | 2024-09-10 | 2024-09-12 | 2024-09-18 | 2024-09-24
V_107 | 2024-03-28 | 2024-04-04 | 2024-04-06 | 2024-04-12 | 2024-04-17 | 2024-04-20 | 2024-04-21 | 2024-04-25 | 2024-04-30 | 2024-05-03 | 2024-05-07 | 2024-05-07 | 2024-05-26 | 2024-06-04 | 2024-06-11 | 2024-06-11 | 2024-06-18 | 2024-06-25 | 2024-06-25 | [41 empty] | 2024-07-25 | 2024-07-26 | 2024-07-27 | 2024-08-02 | 2024-08-07 | 2024-08-14 | 2024-08-14 | 2024-08-14 | 2024-08-18 | 2024-08-18 | 2024-08-21 | 2024-08-25 | 2024-09-03 | 2024-07-27 | 2024-08-14 | 2024-08-16 | 2024-09-07 | 2024-09-04 | 2024-09-10 | 2024-09-12 | 2024-09-18 | 2024-09-24
V_108 | 2024-03-28 | 2024-04-04 | 2024-04-06 | 2024-04-12 | 2024-04-17 | 2024-04-20 | 2024-04-21 | 2024-04-25 | 2024-04-30 | 2024-05-03 | 2024-05-07 | 2024-05-07 | 2024-05-26 | 2024-06-04 | 2024-06-11 | 2024-06-11 | 2024-06-18 | 2024-06-25 | 2024-06-25 | [41 empty] | 2024-07-25 | 2024-07-26 | 2024-07-27 | 2024-08-02 | 2024-08-07 | 2024-08-14 | 2024-08-14 | 2024-08-14 | 2024-08-18 | 2024-08-18 | 2024-08-21 | 2024-08-25 | 2024-09-03 | 2024-07-27 | 2024-08-14 | 2024-08-16 | 2024-09-07 | 2024-09-04 | 2024-09-10 | 2024-09-12 | 2024-09-18 | 2024-09-24
V_109 | 2024-03-28 | 2024-04-04 | 2024-04-06 | 2024-04-12 | 2024-04-17 | 2024-04-20 | 2024-04-21 | 2024-04-25 | 2024-04-30 | 2024-05-03 | 2024-05-07 | 2024-05-07 | 2024-05-26 | 2024-06-04 | 2024-06-11 | 2024-06-11 | 2024-06-18 | 2024-06-25 | 2024-06-25 | [41 empty] | 2024-07-25 | 2024-07-26 | 2024-07-27 | 2024-08-02 | 2024-08-07 | 2024-08-14 | 2024-08-14 | 2024-08-14 | 2024-08-18 | 2024-08-18 | 2024-08-21 | 2024-08-25 | 2024-09-03 | 2024-07-27 | 2024-08-14 | 2024-08-16 | 2024-09-07 | 2024-09-04 | 2024-09-10 | 2024-09-12 | 2024-09-18 | 2024-09-24
V_110 | 2024-03-28 | 2024-04-04 | 2024-04-06 | 2024-04-12 | 2024-04-17 | 2024-04-20 | 2024-04-21 | 2024-04-25 | 2024-04-30 | 2024-05-03 | 2024-05-07 | 2024-05-07 | 2024-05-26 | 2024-06-04 | 2024-06-11 | 2024-06-11 | 2024-06-18 | 2024-06-25 | 2024-06-25 | [41 empty] | 2024-07-25 | 2024-07-26 | 2024-07-27 | 2024-08-02 | 2024-08-07 | 2024-08-14 | 2024-08-14 | 2024-08-14 | 2024-08-18 | 2024-08-18 | 2024-08-21 | 2024-08-25 | 2024-09-03 | 2024-07-27 | 2024-08-14 | 2024-08-16 | 2024-09-07 | 2024-09-04 | 2024-09-10 | 2024-09-12 | 2024-09-18 | 2024-09-24
V_111 | 2024-03-28 | 2024-04-04 | 2024-04-06 | 2024-04-12 | 2024-04-17 | 2024-04-20 | 2024-04-21 | 2024-04-25 | 2024-04-30 | 2024-05-03 | 2024-05-07 | 2024-05-07 | 2024-05-26 | 2024-06-04 | 2024-06-11 | 2024-06-11 | 2024-06-18 | 2024-06-25 | 2024-06-25 | 2024-06-28 | 2024-06-28 | 2024-06-29 | 2024-07-05 | 2024-07-05 | 2024-07-12 | 2024-07-12 | 2024-07-12 | 2024-07-17 | 2024-07-21 | 2024-07-28 | 2024-08-02 | 2024-08-07 | 2024-08-14 | 2024-08-14 | 2024-08-18 | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2024-08-27 | 2024-08-28 | 2024-09-01 | 2024-09-10 | 2024-06-04 | 2024-06-06 | 2024-06-13 | 2024-06-20 | 2024-06-25 | 2024-06-26 | 2024-07-02 | 2024-07-02 | 2024-07-03 | 2024-07-06 | 2024-07-07 | 2024-07-12 | 2024-07-12 | 2024-07-14 | 2024-07-17 | 2024-07-19 | 2024-07-19 | 2024-07-23 | 2024-07-25 | 2024-07-26 | 2024-07-27 | 2024-08-02 | 2024-08-07 | 2024-08-14 | 2024-08-14 | 2024-08-14 | 2024-08-18 | 2024-08-18 | 2024-08-21 | 2024-08-25 | 2024-09-03 | 2024-07-27 | 2024-08-14 | 2024-08-16 | 2024-09-07 | 2024-09-04 | 2024-09-10 | 2024-09-12 | 2024-09-18 | 2024-09-24
V_112 | 2024-03-28 | 2024-04-04 | 2024-04-06 | 2024-04-12 | 2024-04-17 | 2024-04-20 | 2024-04-21 | 2024-04-25 | 2024-04-30 | 2024-05-03 | 2024-05-07 | 2024-05-07 | 2024-05-26 | 2024-06-04 | 2024-06-11 | 2024-06-11 | 2024-06-18 | 2024-06-25 | 2024-06-25 | 2024-06-28 | 2024-06-28 | 2024-06-29 | 2024-07-05 | 2024-07-05 | 2024-07-12 | 2024-07-12 | 2024-07-12 | 2024-07-17 | 2024-07-21 | 2024-07-28 | 2024-08-02 | 2024-08-07 | 2024-08-14 | 2024-08-14 | 2024-08-18 | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2024-08-27 | 2024-08-28 | 2024-09-01 | 2024-09-10 | 2024-06-04 | 2024-06-06 | 2024-06-13 | 2024-06-20 | 2024-06-25 | 2024-06-26 | 2024-07-02 | 2024-07-02 | 2024-07-03 | 2024-07-06 | 2024-07-07 | 2024-07-12 | 2024-07-12 | 2024-07-14 | 2024-07-17 | 2024-07-19 | 2024-07-19 | 2024-07-23 | 2024-07-25 | 2024-07-26 | 2024-07-27 | 2024-08-02 | 2024-08-07 | 2024-08-14 | 2024-08-14 | 2024-08-14 | 2024-08-18 | 2024-08-18 | 2024-08-21 | 2024-08-25 | 2024-09-03 | 2024-07-27 | 2024-08-14 | 2024-08-16 | 2024-09-07 | 2024-09-04 | 2024-09-10 | 2024-09-12 | 2024-09-18 | 2024-09-24
V_113 | 2024-04-04 | 2024-04-11 | 2024-04-13 | 2024-04-19 | 2024-04-24 | 2024-04-27 | 2024-04-28 | 2024-05-02 | 2024-05-07 | 2024-05-10 | 2024-05-14 | 2024-05-14 | 2024-06-04 | 2024-06-12 | 2024-06-19 | 2024-06-19 | 2024-06-26 | 2024-07-03 | 2024-07-03 | 2024-07-06 | 2024-07-06 | 2024-07-07 | 2024-07-13 | 2024-07-13 | 2024-07-20 | 2024-07-20 | 2024-07-20 | 2024-07-25 | 2024-07-30 | 2024-08-06 | 2024-08-10 | 2024-08-15 | 2024-08-22 | 2024-08-22 | 2024-08-27 | 2024-08-29 | 2024-08-29 | 2024-08-29 | 2024-09-04 | 2024-09-05 | 2024-09-10 | 2024-09-18 | 2024-06-12 | 2024-06-14 | 2024-06-21 | 2024-06-28 | 2024-07-03 | 2024-07-04 | 2024-07-10 | 2024-07-10 | 2024-07-11 | 2024-07-14 | 2024-07-16 | 2024-07-20 | 2024-07-20 | 2024-07-23 | 2024-07-25 | 2024-07-27 | 2024-07-27 | 2024-07-31 | 2024-08-02 | 2024-08-03 | 2024-08-04 | 2024-08-10 | 2024-08-15 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-27 | 2024-08-27 | 2024-08-29 | 2024-09-03 | 2024-09-11 | 2024-08-04 | 2024-08-22 | 2024-08-24 | 2024-09-15 | 2024-09-12 | 2024-09-18 | 2024-09-20 | 2024-09-26 | 2024-10-02
V_114 | 2024-04-04 | 2024-04-11 | 2024-04-13 | 2024-04-19 | 2024-04-24 | 2024-04-27 | 2024-04-28 | 2024-05-02 | 2024-05-07 | 2024-05-10 | 2024-05-14 | 2024-05-14 | 2024-06-04 | 2024-06-12 | 2024-06-19 | 2024-06-19 | 2024-06-26 | 2024-07-03 | 2024-07-03 | 2024-07-06 | 2024-07-06 | 2024-07-07 | 2024-07-13 | 2024-07-13 | 2024-07-20 | 2024-07-20 | 2024-07-20 | 2024-07-25 | 2024-07-30 | 2024-08-06 | 2024-08-10 | 2024-08-15 | 2024-08-22 | 2024-08-22 | 2024-08-27 | 2024-08-29 | 2024-08-29 | 2024-08-29 | 2024-09-04 | 2024-09-05 | 2024-09-10 | 2024-09-18 | 2024-06-12 | 2024-06-14 | 2024-06-21 | 2024-06-28 | 2024-07-03 | 2024-07-04 | 2024-07-10 | 2024-07-10 | 2024-07-11 | 2024-07-14 | 2024-07-16 | 2024-07-20 | 2024-07-20 | 2024-07-23 | 2024-07-25 | 2024-07-27 | 2024-07-27 | 2024-07-31 | 2024-08-02 | 2024-08-03 | 2024-08-04 | 2024-08-10 | 2024-08-15 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-27 | 2024-08-27 | 2024-08-29 | 2024-09-03 | 2024-09-11 | 2024-08-04 | 2024-08-22 | 2024-08-24 | 2024-09-15 | 2024-09-12 | 2024-09-18 | 2024-09-20 | 2024-09-26 | 2024-10-02
V_115 | 2024-04-04 | 2024-04-11 | 2024-04-13 | 2024-04-19 | 2024-04-24 | 2024-04-27 | 2024-04-28 | 2024-05-02 | 2024-05-07 | 2024-05-10 | 2024-05-14 | 2024-05-14 | 2024-06-04 | 2024-06-12 | 2024-06-19 | 2024-06-19 | 2024-06-26 | 2024-07-03 | 2024-07-03 | 2024-07-06 | 2024-07-06 | 2024-07-07 | 2024-07-13 | 2024-07-13 | 2024-07-20 | 2024-07-20 | 2024-07-20 | 2024-07-25 | 2024-07-30 | 2024-08-06 | 2024-08-10 | 2024-08-15 | 2024-08-22 | 2024-08-22 | 2024-08-27 | 2024-08-29 | 2024-08-29 | 2024-08-29 | 2024-09-04 | 2024-09-05 | 2024-09-10 | 2024-09-18 | 2024-06-12 | 2024-06-14 | 2024-06-21 | 2024-06-28 | 2024-07-03 | 2024-07-04 | 2024-07-10 | 2024-07-10 | 2024-07-11 | 2024-07-14 | 2024-07-16 | 2024-07-20 | 2024-07-20 | 2024-07-23 | 2024-07-25 | 2024-07-27 | 2024-07-27 | 2024-07-31 | 2024-08-02 | 2024-08-03 | 2024-08-04 | 2024-08-10 | 2024-08-15 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-27 | 2024-08-27 | 2024-08-29 | 2024-09-03 | 2024-09-11 | 2024-08-04 | 2024-08-22 | 2024-08-24 | 2024-09-15 | 2024-09-12 | 2024-09-18 | 2024-09-20 | 2024-09-26 | 2024-10-02
V_116 | 2024-04-04 | 2024-04-11 | 2024-04-13 | 2024-04-19 | 2024-04-24 | 2024-04-27 | 2024-04-28 | 2024-05-02 | 2024-05-07 | 2024-05-10 | 2024-05-14 | 2024-05-14 | 2024-06-04 | 2024-06-12 | 2024-06-19 | 2024-06-19 | 2024-06-26 | 2024-07-03 | 2024-07-03 | 2024-07-06 | 2024-07-06 | 2024-07-07 | 2024-07-13 | 2024-07-13 | 2024-07-20 | 2024-07-20 | 2024-07-20 | 2024-07-25 | 2024-07-30 | 2024-08-06 | 2024-08-10 | 2024-08-15 | 2024-08-22 | 2024-08-22 | 2024-08-27 | 2024-08-29 | 2024-08-29 | 2024-08-29 | 2024-09-04 | 2024-09-05 | 2024-09-10 | 2024-09-18 | 2024-06-12 | 2024-06-14 | 2024-06-21 | 2024-06-28 | 2024-07-03 | 2024-07-04 | 2024-07-10 | 2024-07-10 | 2024-07-11 | 2024-07-14 | 2024-07-16 | 2024-07-20 | 2024-07-20 | 2024-07-23 | 2024-07-25 | 2024-07-27 | 2024-07-27 | 2024-07-31 | 2024-08-02 | 2024-08-03 | 2024-08-04 | 2024-08-10 | 2024-08-15 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-27 | 2024-08-27 | 2024-08-29 | 2024-09-03 | 2024-09-11 | 2024-08-04 | 2024-08-22 | 2024-08-24 | 2024-09-15 | 2024-09-12 | 2024-09-18 | 2024-09-20 | 2024-09-26 | 2024-10-02
V_117 | 2024-04-04 | 2024-04-11 | 2024-04-13 | 2024-04-19 | 2024-04-24 | 2024-04-27 | 2024-04-28 | 2024-05-02 | 2024-05-07 | 2024-05-10 | 2024-05-14 | 2024-05-14 | 2024-06-04 | 2024-06-12 | 2024-06-19 | 2024-06-19 | 2024-06-26 | 2024-07-03 | 2024-07-03 | 2024-07-06 | 2024-07-06 | 2024-07-07 | 2024-07-13 | 2024-07-13 | 2024-07-20 | 2024-07-20 | 2024-07-20 | 2024-07-25 | 2024-07-30 | 2024-08-06 | 2024-08-10 | 2024-08-15 | 2024-08-22 | 2024-08-22 | 2024-08-27 | 2024-08-29 | 2024-08-29 | 2024-08-29 | 2024-09-04 | 2024-09-05 | 2024-09-10 | 2024-09-18 | 2024-06-12 | 2024-06-14 | 2024-06-21 | 2024-06-28 | 2024-07-03 | 2024-07-04 | 2024-07-10 | 2024-07-10 | 2024-07-11 | 2024-07-14 | 2024-07-16 | 2024-07-20 | 2024-07-20 | 2024-07-23 | 2024-07-25 | 2024-07-27 | 2024-07-27 | 2024-07-31 | 2024-08-02 | 2024-08-03 | 2024-08-04 | 2024-08-10 | 2024-08-15 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-27 | 2024-08-27 | 2024-08-29 | 2024-09-03 | 2024-09-11 | 2024-08-04 | 2024-08-22 | 2024-08-24 | 2024-09-15 | 2024-09-12 | 2024-09-18 | 2024-09-20 | 2024-09-26 | 2024-10-02
V_118 | 2024-04-04 | 2024-04-11 | 2024-04-13 | 2024-04-19 | 2024-04-24 | 2024-04-27 | 2024-04-28 | 2024-05-02 | 2024-05-07 | 2024-05-10 | 2024-05-14 | 2024-05-14 | 2024-06-04 | 2024-06-12 | 2024-06-19 | 2024-06-19 | 2024-06-26 | 2024-07-03 | 2024-07-03 | 2024-07-06 | 2024-07-06 | 2024-07-07 | 2024-07-13 | 2024-07-13 | 2024-07-20 | 2024-07-20 | 2024-07-20 | 2024-07-25 | 2024-07-30 | 2024-08-06 | 2024-08-10 | 2024-08-15 | 2024-08-22 | 2024-08-22 | 2024-08-27 | 2024-08-29 | 2024-08-29 | 2024-08-29 | 2024-09-04 | 2024-09-05 | 2024-09-10 | 2024-09-18 | 2024-06-12 | 2024-06-14 | 2024-06-21 | 2024-06-28 | 2024-07-03 | 2024-07-04 | 2024-07-10 | 2024-07-10 | 2024-07-11 | 2024-07-14 | 2024-07-16 | 2024-07-20 | 2024-07-20 | 2024-07-23 | 2024-07-25 | 2024-07-27 | 2024-07-27 | 2024-07-31 | 2024-08-02 | 2024-08-03 | 2024-08-04 | 2024-08-10 | 2024-08-15 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-27 | 2024-08-27 | 2024-08-29 | 2024-09-03 | 2024-09-11 | 2024-08-04 | 2024-08-22 | 2024-08-24 | 2024-09-15 | 2024-09-12 | 2024-09-18 | 2024-09-20 | 2024-09-26 | 2024-10-02
V_119 | 2024-04-04 | 2024-04-11 | 2024-04-13 | 2024-04-19 | 2024-04-24 | 2024-04-27 | 2024-04-28 | 2024-05-02 | 2024-05-07 | 2024-05-10 | 2024-05-14 | 2024-05-14 | 2024-06-04 | 2024-06-12 | 2024-06-19 | 2024-06-19 | 2024-06-26 | 2024-07-03 | 2024-07-03 | 2024-07-06 | 2024-07-06 | 2024-07-07 | 2024-07-13 | 2024-07-13 | 2024-07-20 | 2024-07-20 | 2024-07-20 | 2024-07-25 | 2024-07-30 | 2024-08-06 | 2024-08-10 | 2024-08-15 | 2024-08-22 | 2024-08-22 | 2024-08-27 | 2024-08-29 | 2024-08-29 | 2024-08-29 | 2024-09-04 | 2024-09-05 | 2024-09-10 | 2024-09-18 | 2024-06-12 | 2024-06-14 | 2024-06-21 | 2024-06-28 | 2024-07-03 | 2024-07-04 | 2024-07-10 | 2024-07-10 | 2024-07-11 | 2024-07-14 | 2024-07-16 | 2024-07-20 | 2024-07-20 | 2024-07-23 | 2024-07-25 | 2024-07-27 | 2024-07-27 | 2024-07-31 | 2024-08-02 | 2024-08-03 | 2024-08-04 | 2024-08-10 | 2024-08-15 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-27 | 2024-08-27 | 2024-08-29 | 2024-09-03 | 2024-09-11 | 2024-08-04 | 2024-08-22 | 2024-08-24 | 2024-09-15 | 2024-09-12 | 2024-09-18 | 2024-09-20 | 2024-09-26 | 2024-10-02
V_120 | 2024-04-04 | 2024-04-11 | 2024-04-13 | 2024-04-19 | 2024-04-24 | 2024-04-27 | 2024-04-28 | 2024-05-02 | 2024-05-07 | 2024-05-10 | 2024-05-14 | 2024-05-14 | 2024-06-04 | 2024-06-12 | 2024-06-19 | 2024-06-19 | 2024-06-26 | 2024-07-03 | 2024-07-03 | 2024-07-06 | 2024-07-06 | 2024-07-07 | 2024-07-13 | 2024-07-13 | 2024-07-20 | 2024-07-20 | 2024-07-20 | 2024-07-25 | 2024-07-30 | 2024-08-06 | 2024-08-10 | 2024-08-15 | 2024-08-22 | 2024-08-22 | 2024-08-27 | 2024-08-29 | 2024-08-29 | 2024-08-29 | 2024-09-04 | 2024-09-05 | 2024-09-10 | 2024-09-18 | 2024-06-12 | 2024-06-14 | 2024-06-21 | 2024-06-28 | 2024-07-03 | 2024-07-04 | 2024-07-10 | 2024-07-10 | 2024-07-11 | 2024-07-14 | 2024-07-16 | 2024-07-20 | 2024-07-20 | 2024-07-23 | 2024-07-25 | 2024-07-27 | 2024-07-27 | 2024-07-31 | 2024-08-02 | 2024-08-03 | 2024-08-04 | 2024-08-10 | 2024-08-15 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-27 | 2024-08-27 | 2024-08-29 | 2024-09-03 | 2024-09-11 | 2024-08-04 | 2024-08-22 | 2024-08-24 | 2024-09-15 | 2024-09-12 | 2024-09-18 | 2024-09-20 | 2024-09-26 | 2024-10-02
V_121 | 2024-04-11 | 2024-04-18 | 2024-04-20 | 2024-04-26 | 2024-05-01 | 2024-05-04 | 2024-05-05 | 2024-05-09 | 2024-05-14 | 2024-05-17 | 2024-05-21 | 2024-05-21 | 2024-06-12 | 2024-06-20 | 2024-06-27 | 2024-06-27 | 2024-07-04 | 2024-07-11 | 2024-07-11 | 2024-07-14 | 2024-07-14 | 2024-07-16 | 2024-07-21 | 2024-07-21 | 2024-07-28 | 2024-07-28 | 2024-07-28 | 2024-08-02 | 2024-08-07 | 2024-08-14 | 2024-08-18 | 2024-08-23 | 2024-08-30 | 2024-08-30 | 2024-09-04 | 2024-09-06 | 2024-09-06 | 2024-09-06 | 2024-09-12 | 2024-09-13 | 2024-09-18 | 2024-09-26 | 2024-06-20 | 2024-06-22 | 2024-06-29 | 2024-07-06 | 2024-07-11 | 2024-07-12 | 2024-07-18 | 2024-07-18 | 2024-07-19 | 2024-07-23 | 2024-07-24 | 2024-07-28 | 2024-07-28 | 2024-07-31 | 2024-08-02 | 2024-08-04 | 2024-08-04 | 2024-08-08 | 2024-08-10 | 2024-08-11 | 2024-08-13 | 2024-08-18 | 2024-08-23 | 2024-08-30 | 2024-08-30 | 2024-08-30 | 2024-09-04 | 2024-09-04 | 2024-09-06 | 2024-09-11 | 2024-09-19 | 2024-08-13 | 2024-08-30 | 2024-09-01 | 2024-09-24 | 2024-09-20 | 2024-09-26 | 2024-09-28 | 2024-10-04 | 2024-10-10
V_122 | 2024-04-11 | 2024-04-18 | 2024-04-20 | 2024-04-26 | 2024-05-01 | 2024-05-04 | 2024-05-05 | 2024-05-09 | 2024-05-14 | 2024-05-17 | 2024-05-21 | 2024-05-21 | 2024-06-12 | 2024-06-20 | 2024-06-27 | 2024-06-27 | 2024-07-04 | 2024-07-11 | 2024-07-11 | 2024-07-14 | 2024-07-14 | 2024-07-16 | 2024-07-21 | 2024-07-21 | 2024-07-28 | 2024-07-28 | 2024-07-28 | 2024-08-02 | 2024-08-07 | 2024-08-14 | 2024-08-18 | 2024-08-23 | 2024-08-30 | 2024-08-30 | 2024-09-04 | 2024-09-06 | 2024-09-06 | 2024-09-06 | 2024-09-12 | 2024-09-13 | 2024-09-18 | 2024-09-26 | 2024-06-20 | 2024-06-22 | 2024-06-29 | 2024-07-06 | 2024-07-11 | 2024-07-12 | 2024-07-18 | 2024-07-18 | 2024-07-19 | 2024-07-23 | 2024-07-24 | 2024-07-28 | 2024-07-28 | 2024-07-31 | 2024-08-02 | 2024-08-04 | 2024-08-04 | 2024-08-08 | 2024-08-10 | 2024-08-11 | 2024-08-13 | 2024-08-18 | 2024-08-23 | 2024-08-30 | 2024-08-30 | 2024-08-30 | 2024-09-04 | 2024-09-04 | 2024-09-06 | 2024-09-11 | 2024-09-19 | 2024-08-13 | 2024-08-30 | 2024-09-01 | 2024-09-24 | 2024-09-20 | 2024-09-26 | 2024-09-28 | 2024-10-04 | 2024-10-10
V_123 | 2024-04-11 | 2024-04-18 | 2024-04-20 | 2024-04-26 | 2024-05-01 | 2024-05-04 | 2024-05-05 | 2024-05-09 | 2024-05-14 | 2024-05-17 | 2024-05-21 | 2024-05-21 | 2024-06-12 | 2024-06-20 | 2024-06-27 | 2024-06-27 | 2024-07-04 | 2024-07-11 | 2024-07-11 | 2024-07-14 | 2024-07-14 | 2024-07-16 | 2024-07-21 | 2024-07-21 | 2024-07-28 | 2024-07-28 | 2024-07-28 | 2024-08-02 | 2024-08-07 | 2024-08-14 | 2024-08-18 | 2024-08-23 | 2024-08-30 | 2024-08-30 | 2024-09-04 | 2024-09-06 | 2024-09-06 | 2024-09-06 | 2024-09-12 | 2024-09-13 | 2024-09-18 | 2024-09-26 | 2024-06-20 | 2024-06-22 | 2024-06-29 | 2024-07-06 | 2024-07-11 | 2024-07-12 | 2024-07-18 | 2024-07-18 | 2024-07-19 | 2024-07-23 | 2024-07-24 | 2024-07-28 | 2024-07-28 | 2024-07-31 | 2024-08-02 | 2024-08-04 | 2024-08-04 | 2024-08-08 | 2024-08-10 | 2024-08-11 | 2024-08-13 | 2024-08-18 | 2024-08-23 | 2024-08-30 | 2024-08-30 | 2024-08-30 | 2024-09-04 | 2024-09-04 | 2024-09-06 | 2024-09-11 | 2024-09-19 | 2024-08-13 | 2024-08-30 | 2024-09-01 | 2024-09-24 | 2024-09-20 | 2024-09-26 | 2024-09-28 | 2024-10-04 | 2024-10-10
V_124 | 2024-04-11 | 2024-04-18 | 2024-04-20 | 2024-04-26 | 2024-05-01 | 2024-05-04 | 2024-05-05 | 2024-05-09 | 2024-05-14 | 2024-05-17 | 2024-05-21 | 2024-05-21 | 2024-06-12 | 2024-06-20 | 2024-06-27 | 2024-06-27 | 2024-07-04 | 2024-07-11 | 2024-07-11 | 2024-07-14 | 2024-07-14 | 2024-07-16 | 2024-07-21 | 2024-07-21 | 2024-07-28 | 2024-07-28 | 2024-07-28 | 2024-08-02 | 2024-08-07 | 2024-08-14 | 2024-08-18 | 2024-08-23 | 2024-08-30 | 2024-08-30 | 2024-09-04 | 2024-09-06 | 2024-09-06 | 2024-09-06 | 2024-09-12 | 2024-09-13 | 2024-09-18 | 2024-09-26 | 2024-06-20 | 2024-06-22 | 2024-06-29 | 2024-07-06 | 2024-07-11 | 2024-07-12 | 2024-07-18 | 2024-07-18 | 2024-07-19 | 2024-07-23 | 2024-07-24 | 2024-07-28 | 2024-07-28 | 2024-07-31 | 2024-08-02 | 2024-08-04 | 2024-08-04 | 2024-08-08 | 2024-08-10 | 2024-08-11 | 2024-08-13 | 2024-08-18 | 2024-08-23 | 2024-08-30 | 2024-08-30 | 2024-08-30 | 2024-09-04 | 2024-09-04 | 2024-09-06 | 2024-09-11 | 2024-09-19 | 2024-08-13 | 2024-08-30 | 2024-09-01 | 2024-09-24 | 2024-09-20 | 2024-09-26 | 2024-09-28 | 2024-10-04 | 2024-10-10
V_125 | 2024-04-11 | 2024-04-18 | 2024-04-20 | 2024-04-26 | 2024-05-01 | 2024-05-04 | 2024-05-05 | 2024-05-09 | 2024-05-14 | 2024-05-17 | 2024-05-21 | 2024-05-21 | 2024-06-12 | 2024-06-20 | 2024-06-27 | 2024-06-27 | 2024-07-04 | 2024-07-11 | 2024-07-11 | 2024-07-14 | 2024-07-14 | 2024-07-16 | 2024-07-21 | 2024-07-21 | 2024-07-28 | 2024-07-28 | 2024-07-28 | 2024-08-02 | 2024-08-07 | 2024-08-14 | 2024-08-18 | 2024-08-23 | 2024-08-30 | 2024-08-30 | 2024-09-04 | 2024-09-06 | 2024-09-06 | 2024-09-06 | 2024-09-12 | 2024-09-13 | 2024-09-18 | 2024-09-26 | 2024-06-20 | 2024-06-22 | 2024-06-29 | 2024-07-06 | 2024-07-11 | 2024-07-12 | 2024-07-18 | 2024-07-18 | 2024-07-19 | 2024-07-23 | 2024-07-24 | 2024-07-28 | 2024-07-28 | 2024-07-31 | 2024-08-02 | 2024-08-04 | 2024-08-04 | 2024-08-08 | 2024-08-10 | 2024-08-11 | 2024-08-13 | 2024-08-18 | 2024-08-23 | 2024-08-30 | 2024-08-30 | 2024-08-30 | 2024-09-04 | 2024-09-04 | 2024-09-06 | 2024-09-11 | 2024-09-19 | 2024-08-13 | 2024-08-30 | 2024-09-01 | 2024-09-24 | 2024-09-20 | 2024-09-26 | 2024-09-28 | 2024-10-04 | 2024-10-10
V_126 | 2024-04-11 | 2024-04-18 | 2024-04-20 | 2024-04-26 | 2024-05-01 | 2024-05-04 | 2024-05-05 | 2024-05-09 | 2024-05-14 | 2024-05-17 | 2024-05-21 | 2024-05-21 | 2024-06-12 | 2024-06-20 | 2024-06-27 | 2024-06-27 | 2024-07-04 | 2024-07-11 | 2024-07-11 | 2024-07-14 | 2024-07-14 | 2024-07-16 | 2024-07-21 | 2024-07-21 | 2024-07-28 | 2024-07-28 | 2024-07-28 | 2024-08-02 | 2024-08-07 | 2024-08-14 | 2024-08-18 | 2024-08-23 | 2024-08-30 | 2024-08-30 | 2024-09-04 | 2024-09-06 | 2024-09-06 | 2024-09-06 | 2024-09-12 | 2024-09-13 | 2024-09-18 | 2024-09-26 | 2024-06-20 | 2024-06-22 | 2024-06-29 | 2024-07-06 | 2024-07-11 | 2024-07-12 | 2024-07-18 | 2024-07-18 | 2024-07-19 | 2024-07-23 | 2024-07-24 | 2024-07-28 | 2024-07-28 | 2024-07-31 | 2024-08-02 | 2024-08-04 | 2024-08-04 | 2024-08-08 | 2024-08-10 | 2024-08-11 | 2024-08-13 | 2024-08-18 | 2024-08-23 | 2024-08-30 | 2024-08-30 | 2024-08-30 | 2024-09-04 | 2024-09-04 | 2024-09-06 | 2024-09-11 | 2024-09-19 | 2024-08-13 | 2024-08-30 | 2024-09-01 | 2024-09-24 | 2024-09-20 | 2024-09-26 | 2024-09-28 | 2024-10-04 | 2024-10-10
V_127 | 2024-04-11 | 2024-04-18 | 2024-04-20 | 2024-04-26 | 2024-05-01 | 2024-05-04 | 2024-05-05 | 2024-05-09 | 2024-05-14 | 2024-05-17 | 2024-05-21 | 2024-05-21 | 2024-06-12 | 2024-06-20 | 2024-06-27 | 2024-06-27 | 2024-07-04 | 2024-07-11 | 2024-07-11 | 2024-07-14 | 2024-07-14 | 2024-07-16 | 2024-07-21 | 2024-07-21 | 2024-07-28 | 2024-07-28 | 2024-07-28 | 2024-08-02 | 2024-08-07 | 2024-08-14 | 2024-08-18 | 2024-08-23 | 2024-08-30 | 2024-08-30 | 2024-09-04 | 2024-09-06 | 2024-09-06 | 2024-09-06 | 2024-09-12 | 2024-09-13 | 2024-09-18 | 2024-09-26 | 2024-06-20 | 2024-06-22 | 2024-06-29 | 2024-07-06 | 2024-07-11 | 2024-07-12 | 2024-07-18 | 2024-07-18 | 2024-07-19 | 2024-07-23 | 2024-07-24 | 2024-07-28 | 2024-07-28 | 2024-07-31 | 2024-08-02 | 2024-08-04 | 2024-08-04 | 2024-08-08 | 2024-08-10 | 2024-08-11 | 2024-08-13 | 2024-08-18 | 2024-08-23 | 2024-08-30 | 2024-08-30 | 2024-08-30 | 2024-09-04 | 2024-09-04 | 2024-09-06 | 2024-09-11 | 2024-09-19 | 2024-08-13 | 2024-08-30 | 2024-09-01 | 2024-09-24 | 2024-09-20 | 2024-09-26 | 2024-09-28 | 2024-10-04 | 2024-10-10
V_128 | 2024-04-11 | 2024-04-18 | 2024-04-20 | 2024-04-26 | 2024-05-01 | 2024-05-04 | 2024-05-05 | 2024-05-09 | [18 empty] | 2024-07-28 | 2024-08-02 | 2024-08-07 | 2024-08-14 | 2024-08-18 | 2024-08-23 | 2024-08-30 | 2024-08-30 | 2024-09-04 | 2024-09-06 | 2024-09-06 | 2024-09-06 | 2024-09-12 | 2024-09-13 | 2024-09-18 | 2024-09-26 | 2024-06-20 | 2024-06-22 | 2024-06-29 | 2024-07-06 | 2024-07-11 | 2024-07-12 | 2024-07-18 | 2024-07-18 | 2024-07-19 | 2024-07-23 | 2024-07-24 | 2024-07-28 | 2024-07-28 | 2024-07-31 | 2024-08-02 | 2024-08-04 | 2024-08-04 | 2024-08-08 | 2024-08-10 | 2024-08-11 | 2024-08-13 | 2024-08-18 | 2024-08-23 | 2024-08-30 | 2024-08-30 | 2024-08-30 | 2024-09-04 | 2024-09-04 | 2024-09-06 | 2024-09-11 | 2024-09-19 | 2024-08-13 | 2024-08-30 | 2024-09-01 | 2024-09-24 | 2024-09-20 | 2024-09-26 | 2024-09-28 | 2024-10-04 | 2024-10-10
V_129 | 2024-04-18 | 2024-04-25 | 2024-04-27 | 2024-05-03 | 2024-05-08 | 2024-05-11 | 2024-05-12 | 2024-05-16 | [18 empty] | 2024-08-06 | 2024-08-10 | 2024-08-15 | 2024-08-22 | 2024-08-27 | 2024-08-31 | 2024-09-07 | 2024-09-07 | 2024-09-12 | 2024-09-14 | 2024-09-14 | 2024-09-14 | 2024-09-20 | 2024-09-21 | 2024-09-26 | 2024-10-04 | 2024-06-28 | 2024-06-30 | 2024-07-07 | 2024-07-14 | 2024-07-19 | 2024-07-20 | 2024-07-26 | 2024-07-26 | 2024-07-27 | 2024-07-31 | 2024-08-01 | 2024-08-06 | 2024-08-06 | 2024-08-08 | 2024-08-10 | 2024-08-13 | 2024-08-13 | 2024-08-16 | 2024-08-18 | 2024-08-20 | 2024-08-21 | 2024-08-27 | 2024-08-31 | 2024-09-07 | 2024-09-07 | 2024-09-07 | 2024-09-12 | 2024-09-12 | 2024-09-14 | 2024-09-19 | 2024-09-27 | 2024-08-21 | 2024-09-07 | 2024-09-10 | 2024-10-02 | 2024-09-28 | 2024-10-04 | 2024-10-06 | 2024-10-12 | 2024-10-18
V_130 | 2024-04-18 | 2024-04-25 | 2024-04-27 | 2024-05-03 | 2024-05-08 | 2024-05-11 | 2024-05-12 | 2024-05-16 | [18 empty] | 2024-08-06 | 2024-08-10 | 2024-08-15 | 2024-08-22 | 2024-08-27 | 2024-08-31 | 2024-09-07 | 2024-09-07 | 2024-09-12 | 2024-09-14 | 2024-09-14 | 2024-09-14 | 2024-09-20 | 2024-09-21 | 2024-09-26 | 2024-10-04 | 2024-06-28 | 2024-06-30 | 2024-07-07 | 2024-07-14 | 2024-07-19 | 2024-07-20 | 2024-07-26 | 2024-07-26 | 2024-07-27 | 2024-07-31 | 2024-08-01 | 2024-08-06 | 2024-08-06 | 2024-08-08 | 2024-08-10 | 2024-08-13 | 2024-08-13 | 2024-08-16 | 2024-08-18 | 2024-08-20 | 2024-08-21 | 2024-08-27 | 2024-08-31 | 2024-09-07 | 2024-09-07 | 2024-09-07 | 2024-09-12 | 2024-09-12 | 2024-09-14 | 2024-09-19 | 2024-09-27 | 2024-08-21 | 2024-09-07 | 2024-09-10 | 2024-10-02 | 2024-09-28 | 2024-10-04 | 2024-10-06 | 2024-10-12 | 2024-10-18
V_131 | 2024-04-18 | 2024-04-25 | 2024-04-27 | 2024-05-03 | 2024-05-08 | 2024-05-11 | 2024-05-12 | 2024-05-16 | [18 empty] | 2024-08-06 | 2024-08-10 | 2024-08-15 | 2024-08-22 | 2024-08-27 | 2024-08-31 | 2024-09-07 | 2024-09-07 | 2024-09-12 | 2024-09-14 | 2024-09-14 | 2024-09-14 | 2024-09-20 | 2024-09-21 | 2024-09-26 | 2024-10-04 | 2024-06-28 | 2024-06-30 | 2024-07-07 | 2024-07-14 | 2024-07-19 | 2024-07-20 | 2024-07-26 | 2024-07-26 | 2024-07-27 | 2024-07-31 | 2024-08-01 | 2024-08-06 | 2024-08-06 | 2024-08-08 | 2024-08-10 | 2024-08-13 | 2024-08-13 | 2024-08-16 | 2024-08-18 | 2024-08-20 | 2024-08-21 | 2024-08-27 | 2024-08-31 | 2024-09-07 | 2024-09-07 | 2024-09-07 | 2024-09-12 | 2024-09-12 | 2024-09-14 | 2024-09-19 | 2024-09-27 | 2024-08-21 | 2024-09-07 | 2024-09-10 | 2024-10-02 | 2024-09-28 | 2024-10-04 | 2024-10-06 | 2024-10-12 | 2024-10-18
V_132 | 2024-04-18 | 2024-04-25 | 2024-04-27 | 2024-05-03 | 2024-05-08 | 2024-05-11 | 2024-05-12 | 2024-05-16 | [18 empty] | 2024-08-06 | 2024-08-10 | 2024-08-15 | 2024-08-22 | 2024-08-27 | 2024-08-31 | 2024-09-07 | 2024-09-07 | 2024-09-12 | 2024-09-14 | 2024-09-14 | 2024-09-14 | 2024-09-20 | 2024-09-21 | 2024-09-26 | 2024-10-04 | 2024-06-28 | 2024-06-30 | 2024-07-07 | 2024-07-14 | 2024-07-19 | 2024-07-20 | 2024-07-26 | 2024-07-26 | 2024-07-27 | 2024-07-31 | 2024-08-01 | 2024-08-06 | 2024-08-06 | 2024-08-08 | 2024-08-10 | 2024-08-13 | 2024-08-13 | 2024-08-16 | 2024-08-18 | 2024-08-20 | 2024-08-21 | 2024-08-27 | 2024-08-31 | 2024-09-07 | 2024-09-07 | 2024-09-07 | 2024-09-12 | 2024-09-12 | 2024-09-14 | 2024-09-19 | 2024-09-27 | 2024-08-21 | 2024-09-07 | 2024-09-10 | 2024-10-02 | 2024-09-28 | 2024-10-04 | 2024-10-06 | 2024-10-12 | 2024-10-18
V_133 | 2024-04-18 | 2024-04-25 | 2024-04-27 | 2024-05-03 | 2024-05-08 | 2024-05-11 | 2024-05-12 | 2024-05-16 | [18 empty] | 2024-08-06 | 2024-08-10 | 2024-08-15 | 2024-08-22 | 2024-08-27 | 2024-08-31 | 2024-09-07 | 2024-09-07 | 2024-09-12 | 2024-09-14 | 2024-09-14 | 2024-09-14 | 2024-09-20 | 2024-09-21 | 2024-09-26 | 2024-10-04 | 2024-06-28 | 2024-06-30 | 2024-07-07 | 2024-07-14 | 2024-07-19 | 2024-07-20 | 2024-07-26 | 2024-07-26 | 2024-07-27 | 2024-07-31 | 2024-08-01 | 2024-08-06 | 2024-08-06 | 2024-08-08 | 2024-08-10 | 2024-08-13 | 2024-08-13 | 2024-08-16 | 2024-08-18 | 2024-08-20 | 2024-08-21 | 2024-08-27 | 2024-08-31 | 2024-09-07 | 2024-09-07 | 2024-09-07 | 2024-09-12 | 2024-09-12 | 2024-09-14 | 2024-09-19 | 2024-09-27 | 2024-08-21 | 2024-09-07 | 2024-09-10 | 2024-10-02 | 2024-09-28 | 2024-10-04 | 2024-10-06 | 2024-10-12 | 2024-10-18
V_134 | 2024-04-18 | 2024-04-25 | 2024-04-27 | 2024-05-03 | 2024-05-08 | 2024-05-11 | 2024-05-12 | 2024-05-16 | [18 empty] | 2024-08-06 | 2024-08-10 | 2024-08-15 | 2024-08-22 | 2024-08-27 | 2024-08-31 | 2024-09-07 | 2024-09-07 | 2024-09-12 | 2024-09-14 | 2024-09-14 | 2024-09-14 | 2024-09-20 | 2024-09-21 | 2024-09-26 | 2024-10-04 | 2024-06-28 | 2024-06-30 | 2024-07-07 | 2024-07-14 | 2024-07-19 | 2024-07-20 | 2024-07-26 | 2024-07-26 | 2024-07-27 | 2024-07-31 | 2024-08-01 | 2024-08-06 | 2024-08-06 | 2024-08-08 | 2024-08-10 | 2024-08-13 | 2024-08-13 | 2024-08-16 | 2024-08-18 | 2024-08-20 | 2024-08-21 | 2024-08-27 | 2024-08-31 | 2024-09-07 | 2024-09-07 | 2024-09-07 | 2024-09-12 | 2024-09-12 | 2024-09-14 | 2024-09-19 | 2024-09-27 | 2024-08-21 | 2024-09-07 | 2024-09-10 | 2024-10-02 | 2024-09-28 | 2024-10-04 | 2024-10-06 | 2024-10-12 | 2024-10-18
V_135 | 2024-04-18 | 2024-04-25 | 2024-04-27 | 2024-05-03 | 2024-05-08 | 2024-05-11 | 2024-05-12 | 2024-05-16 | [18 empty] | 2024-08-06 | 2024-08-10 | 2024-08-15 | 2024-08-22 | 2024-08-27 | 2024-08-31 | 2024-09-07 | 2024-09-07 | 2024-09-12 | 2024-09-14 | 2024-09-14 | 2024-09-14 | 2024-09-20 | 2024-09-21 | 2024-09-26 | 2024-10-04 | 2024-06-28 | 2024-06-30 | 2024-07-07 | 2024-07-14 | 2024-07-19 | 2024-07-20 | 2024-07-26 | 2024-07-26 | 2024-07-27 | 2024-07-31 | 2024-08-01 | 2024-08-06 | 2024-08-06 | 2024-08-08 | 2024-08-10 | 2024-08-13 | 2024-08-13 | 2024-08-16 | 2024-08-18 | 2024-08-20 | 2024-08-21 | 2024-08-27 | 2024-08-31 | 2024-09-07 | 2024-09-07 | 2024-09-07 | 2024-09-12 | 2024-09-12 | 2024-09-14 | 2024-09-19 | 2024-09-27 | 2024-08-21 | 2024-09-07 | 2024-09-10 | 2024-10-02 | 2024-09-28 | 2024-10-04 | 2024-10-06 | 2024-10-12 | 2024-10-18
V_136 | 2024-04-18 | 2024-04-25 | 2024-04-27 | 2024-05-03 | 2024-05-08 | 2024-05-11 | 2024-05-12 | 2024-05-16 | [18 empty] | 2024-08-06 | 2024-08-10 | 2024-08-15 | 2024-08-22 | 2024-08-27 | 2024-08-31 | 2024-09-07 | 2024-09-07 | 2024-09-12 | 2024-09-14 | 2024-09-14 | 2024-09-14 | 2024-09-20 | 2024-09-21 | 2024-09-26 | 2024-10-04 | 2024-06-28 | 2024-06-30 | 2024-07-07 | 2024-07-14 | 2024-07-19 | 2024-07-20 | 2024-07-26 | 2024-07-26 | 2024-07-27 | 2024-07-31 | 2024-08-01 | 2024-08-06 | 2024-08-06 | 2024-08-08 | 2024-08-10 | 2024-08-13 | 2024-08-13 | 2024-08-16 | 2024-08-18 | 2024-08-20 | 2024-08-21 | 2024-08-27 | 2024-08-31 | 2024-09-07 | 2024-09-07 | 2024-09-07 | 2024-09-12 | 2024-09-12 | 2024-09-14 | 2024-09-19 | 2024-09-27 | 2024-08-21 | 2024-09-07 | 2024-09-10 | 2024-10-02 | 2024-09-28 | 2024-10-04 | 2024-10-06 | 2024-10-12 | 2024-10-18
V_137 | 2024-04-25 | 2024-05-02 | 2024-05-04 | 2024-05-10 | 2024-05-15 | 2024-05-18 | 2024-05-19 | 2024-05-23 | [18 empty] | 2024-08-14 | 2024-08-18 | 2024-08-23 | 2024-08-30 | 2024-09-04 | 2024-09-08 | 2024-09-15 | 2024-09-15 | 2024-09-20 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-28 | 2024-09-29 | 2024-10-04 | 2024-10-12 | 2024-07-06 | 2024-07-09 | 2024-07-16 | 2024-07-23 | 2024-07-27 | 2024-07-28 | 2024-08-03 | 2024-08-03 | 2024-08-04 | 2024-08-08 | 2024-08-09 | 2024-08-14 | 2024-08-14 | 2024-08-16 | 2024-08-18 | 2024-08-21 | 2024-08-21 | 2024-08-24 | 2024-08-27 | 2024-08-28 | 2024-08-29 | 2024-09-04 | 2024-09-08 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-20 | 2024-09-20 | 2024-09-22 | 2024-09-27 | 2024-10-05 | 2024-08-29 | 2024-09-15 | 2024-09-18 | 2024-10-10 | 2024-10-06 | 2024-10-12 | 2024-10-15 | 2024-10-20 | 2024-10-26
V_138 | 2024-04-25 | 2024-05-02 | 2024-05-04 | 2024-05-10 | 2024-05-15 | 2024-05-18 | 2024-05-19 | 2024-05-23 | [18 empty] | 2024-08-14 | 2024-08-18 | 2024-08-23 | 2024-08-30 | 2024-09-04 | 2024-09-08 | 2024-09-15 | 2024-09-15 | 2024-09-20 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-28 | 2024-09-29 | 2024-10-04 | 2024-10-12 | 2024-07-06 | 2024-07-09 | 2024-07-16 | 2024-07-23 | 2024-07-27 | 2024-07-28 | 2024-08-03 | 2024-08-03 | 2024-08-04 | 2024-08-08 | 2024-08-09 | 2024-08-14 | 2024-08-14 | 2024-08-16 | 2024-08-18 | 2024-08-21 | 2024-08-21 | 2024-08-24 | 2024-08-27 | 2024-08-28 | 2024-08-29 | 2024-09-04 | 2024-09-08 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-20 | 2024-09-20 | 2024-09-22 | 2024-09-27 | 2024-10-05 | 2024-08-29 | 2024-09-15 | 2024-09-18 | 2024-10-10 | 2024-10-06 | 2024-10-12 | 2024-10-15 | 2024-10-20 | 2024-10-26
V_139 | 2024-04-25 | 2024-05-02 | 2024-05-04 | 2024-05-10 | 2024-05-15 | 2024-05-18 | 2024-05-19 | 2024-05-23 | [18 empty] | 2024-08-14 | 2024-08-18 | 2024-08-23 | 2024-08-30 | 2024-09-04 | 2024-09-08 | 2024-09-15 | 2024-09-15 | 2024-09-20 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-28 | 2024-09-29 | 2024-10-04 | 2024-10-12 | 2024-07-06 | 2024-07-09 | 2024-07-16 | 2024-07-23 | 2024-07-27 | 2024-07-28 | 2024-08-03 | 2024-08-03 | 2024-08-04 | 2024-08-08 | 2024-08-09 | 2024-08-14 | 2024-08-14 | 2024-08-16 | 2024-08-18 | 2024-08-21 | 2024-08-21 | 2024-08-24 | 2024-08-27 | 2024-08-28 | 2024-08-29 | 2024-09-04 | 2024-09-08 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-20 | 2024-09-20 | 2024-09-22 | 2024-09-27 | 2024-10-05 | 2024-08-29 | 2024-09-15 | 2024-09-18 | 2024-10-10 | 2024-10-06 | 2024-10-12 | 2024-10-15 | 2024-10-20 | 2024-10-26
V_140 | 2024-04-25 | 2024-05-02 | 2024-05-04 | 2024-05-10 | 2024-05-15 | 2024-05-18 | 2024-05-19 | 2024-05-23 | [18 empty] | 2024-08-14 | 2024-08-18 | 2024-08-23 | 2024-08-30 | 2024-09-04 | 2024-09-08 | 2024-09-15 | 2024-09-15 | 2024-09-20 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-28 | 2024-09-29 | 2024-10-04 | 2024-10-12 | 2024-07-06 | 2024-07-09 | 2024-07-16 | 2024-07-23 | 2024-07-27 | 2024-07-28 | 2024-08-03 | 2024-08-03 | 2024-08-04 | 2024-08-08 | 2024-08-09 | 2024-08-14 | 2024-08-14 | 2024-08-16 | 2024-08-18 | 2024-08-21 | 2024-08-21 | 2024-08-24 | 2024-08-27 | 2024-08-28 | 2024-08-29 | 2024-09-04 | 2024-09-08 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-20 | 2024-09-20 | 2024-09-22 | 2024-09-27 | 2024-10-05 | 2024-08-29 | 2024-09-15 | 2024-09-18 | 2024-10-10 | 2024-10-06 | 2024-10-12 | 2024-10-15 | 2024-10-20 | 2024-10-26
V_141 | 2024-04-25 | 2024-05-02 | 2024-05-04 | 2024-05-10 | 2024-05-15 | 2024-05-18 | 2024-05-19 | 2024-05-23 | [18 empty] | 2024-08-14 | 2024-08-18 | 2024-08-23 | 2024-08-30 | 2024-09-04 | 2024-09-08 | 2024-09-15 | 2024-09-15 | 2024-09-20 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-28 | 2024-09-29 | 2024-10-04 | 2024-10-12 | 2024-07-06 | 2024-07-09 | 2024-07-16 | 2024-07-23 | 2024-07-27 | 2024-07-28 | 2024-08-03 | 2024-08-03 | 2024-08-04 | 2024-08-08 | 2024-08-09 | 2024-08-14 | 2024-08-14 | 2024-08-16 | 2024-08-18 | 2024-08-21 | 2024-08-21 | 2024-08-24 | 2024-08-27 | 2024-08-28 | 2024-08-29 | 2024-09-04 | 2024-09-08 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-20 | 2024-09-20 | 2024-09-22 | 2024-09-27 | 2024-10-05 | 2024-08-29 | 2024-09-15 | 2024-09-18 | 2024-10-10 | 2024-10-06 | 2024-10-12 | 2024-10-15 | 2024-10-20 | 2024-10-26
V_142 | 2024-04-25 | 2024-05-02 | 2024-05-04 | 2024-05-10 | 2024-05-15 | 2024-05-18 | 2024-05-19 | 2024-05-23 | [18 empty] | 2024-08-14 | 2024-08-18 | 2024-08-23 | 2024-08-30 | 2024-09-04 | 2024-09-08 | 2024-09-15 | 2024-09-15 | 2024-09-20 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-28 | 2024-09-29 | 2024-10-04 | 2024-10-12 | 2024-07-06 | 2024-07-09 | 2024-07-16 | 2024-07-23 | 2024-07-27 | 2024-07-28 | 2024-08-03 | 2024-08-03 | 2024-08-04 | 2024-08-08 | 2024-08-09 | 2024-08-14 | 2024-08-14 | 2024-08-16 | 2024-08-18 | 2024-08-21 | 2024-08-21 | 2024-08-24 | 2024-08-27 | 2024-08-28 | 2024-08-29 | 2024-09-04 | 2024-09-08 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-20 | 2024-09-20 | 2024-09-22 | 2024-09-27 | 2024-10-05 | 2024-08-29 | 2024-09-15 | 2024-09-18 | 2024-10-10 | 2024-10-06 | 2024-10-12 | 2024-10-15 | 2024-10-20 | 2024-10-26
V_143 | 2024-04-25 | 2024-05-02 | 2024-05-04 | 2024-05-10 | 2024-05-15 | 2024-05-18 | 2024-05-19 | 2024-05-23 | [18 empty] | 2024-08-14 | 2024-08-18 | 2024-08-23 | 2024-08-30 | 2024-09-04 | 2024-09-08 | 2024-09-15 | 2024-09-15 | 2024-09-20 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-28 | 2024-09-29 | 2024-10-04 | 2024-10-12 | 2024-07-06 | 2024-07-09 | 2024-07-16 | 2024-07-23 | 2024-07-27 | 2024-07-28 | 2024-08-03 | 2024-08-03 | 2024-08-04 | 2024-08-08 | 2024-08-09 | 2024-08-14 | 2024-08-14 | 2024-08-16 | 2024-08-18 | 2024-08-21 | 2024-08-21 | 2024-08-24 | 2024-08-27 | 2024-08-28 | 2024-08-29 | 2024-09-04 | 2024-09-08 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-20 | 2024-09-20 | 2024-09-22 | 2024-09-27 | 2024-10-05 | 2024-08-29 | 2024-09-15 | 2024-09-18 | 2024-10-10 | 2024-10-06 | 2024-10-12 | 2024-10-15 | 2024-10-20 | 2024-10-26
V_144 | 2024-04-25 | 2024-05-02 | 2024-05-04 | 2024-05-10 | 2024-05-15 | 2024-05-18 | 2024-05-19 | 2024-05-23 | [18 empty] | 2024-08-14 | 2024-08-18 | 2024-08-23 | 2024-08-30 | 2024-09-04 | 2024-09-08 | 2024-09-15 | 2024-09-15 | 2024-09-20 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-28 | 2024-09-29 | 2024-10-04 | 2024-10-12 | 2024-07-06 | 2024-07-09 | 2024-07-16 | 2024-07-23 | 2024-07-27 | 2024-07-28 | 2024-08-03 | 2024-08-03 | 2024-08-04 | 2024-08-08 | 2024-08-09 | 2024-08-14 | 2024-08-14 | 2024-08-16 | 2024-08-18 | 2024-08-21 | 2024-08-21 | 2024-08-24 | 2024-08-27 | 2024-08-28 | 2024-08-29 | 2024-09-04 | 2024-09-08 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-20 | 2024-09-20 | 2024-09-22 | 2024-09-27 | 2024-10-05 | 2024-08-29 | 2024-09-15 | 2024-09-18 | 2024-10-10 | 2024-10-06 | 2024-10-12 | 2024-10-15 | 2024-10-20 | 2024-10-26
V_145 | 2024-05-02 | 2024-05-09 | 2024-05-11 | 2024-05-17 | 2024-05-22 | 2024-05-25 | 2024-05-26 | 2024-05-30 | [18 empty] | 2024-08-22 | 2024-08-27 | 2024-08-31 | 2024-09-07 | 2024-09-12 | 2024-09-17 | 2024-09-24 | 2024-09-24 | 2024-09-28 | 2024-10-01 | 2024-10-01 | 2024-10-01 | 2024-10-06 | 2024-10-08 | 2024-10-12 | 2024-10-20 | 2024-07-14 | 2024-07-17 | 2024-07-24 | 2024-07-31 | 2024-08-04 | 2024-08-06 | 2024-08-11 | 2024-08-11 | 2024-08-13 | 2024-08-16 | 2024-08-17 | 2024-08-22 | 2024-08-22 | 2024-08-24 | 2024-08-27 | 2024-08-29 | 2024-08-29 | 2024-09-01 | 2024-09-04 | 2024-09-05 | 2024-09-06 | 2024-09-12 | 2024-09-17 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2024-09-28 | 2024-09-28 | 2024-10-01 | 2024-10-05 | 2024-10-13 | 2024-09-06 | 2024-09-24 | 2024-09-26 | 2024-10-18 | 2024-10-15 | 2024-10-20 | 2024-10-23 | 2024-10-29 | 2024-11-03
V_146 | 2024-05-02 | 2024-05-09 | 2024-05-11 | 2024-05-17 | 2024-05-22 | 2024-05-25 | 2024-05-26 | 2024-05-30 | [18 empty] | 2024-08-22 | 2024-08-27 | 2024-08-31 | 2024-09-07 | 2024-09-12 | 2024-09-17 | 2024-09-24 | 2024-09-24 | 2024-09-28 | 2024-10-01 | 2024-10-01 | 2024-10-01 | 2024-10-06 | 2024-10-08 | 2024-10-12 | 2024-10-20 | 2024-07-14 | 2024-07-17 | 2024-07-24 | 2024-07-31 | 2024-08-04 | 2024-08-06 | 2024-08-11 | 2024-08-11 | 2024-08-13 | 2024-08-16 | 2024-08-17 | 2024-08-22 | 2024-08-22 | 2024-08-24 | 2024-08-27 | 2024-08-29 | 2024-08-29 | 2024-09-01 | 2024-09-04 | 2024-09-05 | 2024-09-06 | 2024-09-12 | 2024-09-17 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2024-09-28 | 2024-09-28 | 2024-10-01 | 2024-10-05 | 2024-10-13 | 2024-09-06 | 2024-09-24 | 2024-09-26 | 2024-10-18 | 2024-10-15 | 2024-10-20 | 2024-10-23 | 2024-10-29 | 2024-11-03
V_147 | 2024-05-02 | 2024-05-09 | 2024-05-11 | 2024-05-17 | 2024-05-22 | 2024-05-25 | 2024-05-26 | 2024-05-30 | [18 empty] | 2024-08-22 | 2024-08-27 | 2024-08-31 | 2024-09-07 | 2024-09-12 | 2024-09-17 | 2024-09-24 | 2024-09-24 | 2024-09-28 | 2024-10-01 | 2024-10-01 | 2024-10-01 | 2024-10-06 | 2024-10-08 | 2024-10-12 | 2024-10-20 | 2024-07-14 | 2024-07-17 | 2024-07-24 | 2024-07-31 | 2024-08-04 | 2024-08-06 | 2024-08-11 | 2024-08-11 | 2024-08-13 | 2024-08-16 | 2024-08-17 | 2024-08-22 | 2024-08-22 | 2024-08-24 | 2024-08-27 | 2024-08-29 | 2024-08-29 | 2024-09-01 | 2024-09-04 | 2024-09-05 | 2024-09-06 | 2024-09-12 | 2024-09-17 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2024-09-28 | 2024-09-28 | 2024-10-01 | 2024-10-05 | 2024-10-13 | 2024-09-06 | 2024-09-24 | 2024-09-26 | 2024-10-18 | 2024-10-15 | 2024-10-20 | 2024-10-23 | 2024-10-29 | 2024-11-03
V_148 | 2024-05-02 | 2024-05-09 | 2024-05-11 | 2024-05-17 | 2024-05-22 | 2024-05-25 | 2024-05-26 | 2024-05-30 | [18 empty] | 2024-08-22 | 2024-08-27 | 2024-08-31 | 2024-09-07 | 2024-09-12 | 2024-09-17 | 2024-09-24 | 2024-09-24 | 2024-09-28 | 2024-10-01 | 2024-10-01 | 2024-10-01 | 2024-10-06 | 2024-10-08 | 2024-10-12 | 2024-10-20 | 2024-07-14 | 2024-07-17 | 2024-07-24 | 2024-07-31 | 2024-08-04 | 2024-08-06 | 2024-08-11 | 2024-08-11 | 2024-08-13 | 2024-08-16 | 2024-08-17 | 2024-08-22 | 2024-08-22 | 2024-08-24 | 2024-08-27 | 2024-08-29 | 2024-08-29 | 2024-09-01 | 2024-09-04 | 2024-09-05 | 2024-09-06 | 2024-09-12 | 2024-09-17 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2024-09-28 | 2024-09-28 | 2024-10-01 | 2024-10-05 | 2024-10-13 | 2024-09-06 | 2024-09-24 | 2024-09-26 | 2024-10-18 | 2024-10-15 | 2024-10-20 | 2024-10-23 | 2024-10-29 | 2024-11-03
V_149 | 2024-05-02 | 2024-05-09 | 2024-05-11 | 2024-05-17 | 2024-05-22 | 2024-05-25 | 2024-05-26 | 2024-05-30 | [18 empty] | 2024-08-22 | 2024-08-27 | 2024-08-31 | 2024-09-07 | 2024-09-12 | 2024-09-17 | 2024-09-24 | 2024-09-24 | 2024-09-28 | 2024-10-01 | 2024-10-01 | 2024-10-01 | 2024-10-06 | 2024-10-08 | 2024-10-12 | 2024-10-20 | 2024-07-14 | 2024-07-17 | 2024-07-24 | 2024-07-31 | 2024-08-04 | 2024-08-06 | 2024-08-11 | 2024-08-11 | 2024-08-13 | 2024-08-16 | 2024-08-17 | 2024-08-22 | 2024-08-22 | 2024-08-24 | 2024-08-27 | 2024-08-29 | 2024-08-29 | 2024-09-01 | 2024-09-04 | 2024-09-05 | 2024-09-06 | 2024-09-12 | 2024-09-17 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2024-09-28 | 2024-09-28 | 2024-10-01 | 2024-10-05 | 2024-10-13 | 2024-09-06 | 2024-09-24 | 2024-09-26 | 2024-10-18 | 2024-10-15 | 2024-10-20 | 2024-10-23 | 2024-10-29 | 2024-11-03
V_150 | 2024-05-02 | 2024-05-09 | 2024-05-11 | 2024-05-17 | 2024-05-22 | 2024-05-25 | 2024-05-26 | 2024-05-30 | [18 empty] | 2024-08-22 | 2024-08-27 | 2024-08-31 | 2024-09-07 | 2024-09-12 | 2024-09-17 | 2024-09-24 | 2024-09-24 | 2024-09-28 | 2024-10-01 | 2024-10-01 | 2024-10-01 | 2024-10-06 | 2024-10-08 | 2024-10-12 | 2024-10-20 | 2024-07-14 | 2024-07-17 | 2024-07-24 | 2024-07-31 | 2024-08-04 | 2024-08-06 | 2024-08-11 | 2024-08-11 | 2024-08-13 | 2024-08-16 | 2024-08-17 | 2024-08-22 | 2024-08-22 | 2024-08-24 | 2024-08-27 | 2024-08-29 | 2024-08-29 | 2024-09-01 | 2024-09-04 | 2024-09-05 | 2024-09-06 | 2024-09-12 | 2024-09-17 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2024-09-28 | 2024-09-28 | 2024-10-01 | 2024-10-05 | 2024-10-13 | 2024-09-06 | 2024-09-24 | 2024-09-26 | 2024-10-18 | 2024-10-15 | 2024-10-20 | 2024-10-23 | 2024-10-29 | 2024-11-03
V_151 | 2024-05-02 | 2024-05-09 | 2024-05-11 | 2024-05-17 | 2024-05-22 | 2024-05-25 | 2024-05-26 | 2024-05-30 | [18 empty] | 2024-08-22 | 2024-08-27 | 2024-08-31 | 2024-09-07 | 2024-09-12 | 2024-09-17 | 2024-09-24 | 2024-09-24 | 2024-09-28 | 2024-10-01 | 2024-10-01 | 2024-10-01 | 2024-10-06 | 2024-10-08 | 2024-10-12 | 2024-10-20 | 2024-07-14 | 2024-07-17 | 2024-07-24 | 2024-07-31 | 2024-08-04 | 2024-08-06 | 2024-08-11 | 2024-08-11 | 2024-08-13 | 2024-08-16 | 2024-08-17 | 2024-08-22 | 2024-08-22 | 2024-08-24 | 2024-08-27 | 2024-08-29 | 2024-08-29 | 2024-09-01 | 2024-09-04 | 2024-09-05 | 2024-09-06 | 2024-09-12 | 2024-09-17 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2024-09-28 | 2024-09-28 | 2024-10-01 | 2024-10-05 | 2024-10-13 | 2024-09-06 | 2024-09-24 | 2024-09-26 | 2024-10-18 | 2024-10-15 | 2024-10-20 | 2024-10-23 | 2024-10-29 | 2024-11-03
V_152 | 2024-05-02 | 2024-05-09 | 2024-05-11 | 2024-05-17 | 2024-05-22 | 2024-05-25 | 2024-05-26 | 2024-05-30 | [18 empty] | 2024-08-22 | 2024-08-27 | 2024-08-31 | 2024-09-07 | 2024-09-12 | 2024-09-17 | 2024-09-24 | 2024-09-24 | 2024-09-28 | 2024-10-01 | 2024-10-01 | 2024-10-01 | 2024-10-06 | 2024-10-08 | 2024-10-12 | 2024-10-20 | 2024-07-14 | 2024-07-17 | 2024-07-24 | 2024-07-31 | 2024-08-04 | 2024-08-06 | 2024-08-11 | 2024-08-11 | 2024-08-13 | 2024-08-16 | 2024-08-17 | 2024-08-22 | 2024-08-22 | 2024-08-24 | 2024-08-27 | 2024-08-29 | 2024-08-29 | 2024-09-01 | 2024-09-04 | 2024-09-05 | 2024-09-06 | 2024-09-12 | 2024-09-17 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2024-09-28 | 2024-09-28 | 2024-10-01 | 2024-10-05 | 2024-10-13 | 2024-09-06 | 2024-09-24 | 2024-09-26 | 2024-10-18 | 2024-10-15 | 2024-10-20 | 2024-10-23 | 2024-10-29 | 2024-11-03
V_153 | 2024-05-09 | 2024-05-16 | 2024-05-18 | 2024-05-24 | 2024-05-29 | 2024-06-01 | 2024-06-02 | 2024-06-06 | [18 empty] | 2024-08-30 | 2024-09-04 | 2024-09-08 | 2024-09-15 | 2024-09-20 | 2024-09-25 | 2024-10-02 | 2024-10-02 | 2024-10-06 | 2024-10-09 | 2024-10-09 | 2024-10-09 | 2024-10-15 | 2024-10-16 | 2024-10-20 | 2024-10-29 | 2024-07-23 | 2024-07-25 | 2024-08-01 | 2024-08-08 | 2024-08-13 | 2024-08-14 | 2024-08-20 | 2024-08-20 | 2024-08-21 | 2024-08-24 | 2024-08-25 | 2024-08-30 | 2024-08-30 | 2024-09-01 | 2024-09-04 | 2024-09-06 | 2024-09-06 | 2024-09-10 | 2024-09-12 | 2024-09-13 | 2024-09-14 | 2024-09-20 | 2024-09-25 | 2024-10-02 | 2024-10-02 | 2024-10-02 | 2024-10-06 | 2024-10-06 | 2024-10-09 | 2024-10-13 | 2024-10-22 | 2024-09-14 | 2024-10-02 | 2024-10-04 | 2024-10-26 | 2024-10-23 | 2024-10-29 | 2024-10-31 | 2024-11-06 | 2024-11-12
V_154 | 2024-05-09 | 2024-05-16 | 2024-05-18 | 2024-05-24 | 2024-05-29 | 2024-06-01 | 2024-06-02 | 2024-06-06 | [18 empty] | 2024-08-30 | 2024-09-04 | 2024-09-08 | 2024-09-15 | 2024-09-20 | 2024-09-25 | 2024-10-02 | 2024-10-02 | 2024-10-06 | 2024-10-09 | 2024-10-09 | 2024-10-09 | 2024-10-15 | 2024-10-16 | 2024-10-20 | 2024-10-29 | 2024-07-23 | 2024-07-25 | 2024-08-01 | 2024-08-08 | 2024-08-13 | 2024-08-14 | 2024-08-20 | 2024-08-20 | 2024-08-21 | 2024-08-24 | 2024-08-25 | 2024-08-30 | 2024-08-30 | 2024-09-01 | 2024-09-04 | 2024-09-06 | 2024-09-06 | 2024-09-10 | 2024-09-12 | 2024-09-13 | 2024-09-14 | 2024-09-20 | 2024-09-25 | 2024-10-02 | 2024-10-02 | 2024-10-02 | 2024-10-06 | 2024-10-06 | 2024-10-09 | 2024-10-13 | 2024-10-22 | 2024-09-14 | 2024-10-02 | 2024-10-04 | 2024-10-26 | 2024-10-23 | 2024-10-29 | 2024-10-31 | 2024-11-06 | 2024-11-12
V_155 | 2024-05-09 | 2024-05-16 | 2024-05-18 | 2024-05-24 | 2024-05-29 | 2024-06-01 | 2024-06-02 | 2024-06-06 | [18 empty] | 2024-08-30 | 2024-09-04 | 2024-09-08 | 2024-09-15 | 2024-09-20 | 2024-09-25 | 2024-10-02 | 2024-10-02 | 2024-10-06 | 2024-10-09 | 2024-10-09 | 2024-10-09 | 2024-10-15 | 2024-10-16 | 2024-10-20 | 2024-10-29 | 2024-07-23 | 2024-07-25 | 2024-08-01 | 2024-08-08 | 2024-08-13 | 2024-08-14 | 2024-08-20 | 2024-08-20 | 2024-08-21 | 2024-08-24 | 2024-08-25 | 2024-08-30 | 2024-08-30 | 2024-09-01 | 2024-09-04 | 2024-09-06 | 2024-09-06 | 2024-09-10 | 2024-09-12 | 2024-09-13 | 2024-09-14 | 2024-09-20 | 2024-09-25 | 2024-10-02 | 2024-10-02 | 2024-10-02 | 2024-10-06 | 2024-10-06 | 2024-10-09 | 2024-10-13 | 2024-10-22 | 2024-09-14 | 2024-10-02 | 2024-10-04 | 2024-10-26 | 2024-10-23 | 2024-10-29 | 2024-10-31 | 2024-11-06 | 2024-11-12
V_156 | 2024-05-09 | 2024-05-16 | 2024-05-18 | 2024-05-24 | 2024-05-29 | 2024-06-01 | 2024-06-02 | 2024-06-06 | [18 empty] | 2024-08-30 | 2024-09-04 | 2024-09-08 | 2024-09-15 | 2024-09-20 | 2024-09-25 | 2024-10-02 | 2024-10-02 | 2024-10-06 | 2024-10-09 | 2024-10-09 | 2024-10-09 | 2024-10-15 | 2024-10-16 | 2024-10-20 | 2024-10-29 | 2024-07-23 | 2024-07-25 | 2024-08-01 | 2024-08-08 | 2024-08-13 | 2024-08-14 | 2024-08-20 | 2024-08-20 | 2024-08-21 | 2024-08-24 | 2024-08-25 | 2024-08-30 | 2024-08-30 | 2024-09-01 | 2024-09-04 | 2024-09-06 | 2024-09-06 | 2024-09-10 | 2024-09-12 | 2024-09-13 | 2024-09-14 | 2024-09-20 | 2024-09-25 | 2024-10-02 | 2024-10-02 | 2024-10-02 | 2024-10-06 | 2024-10-06 | 2024-10-09 | 2024-10-13 | 2024-10-22 | 2024-09-14 | 2024-10-02 | 2024-10-04 | 2024-10-26 | 2024-10-23 | 2024-10-29 | 2024-10-31 | 2024-11-06 | 2024-11-12
V_157 | 2024-05-09 | 2024-05-16 | 2024-05-18 | 2024-05-24 | 2024-05-29 | 2024-06-01 | 2024-06-02 | 2024-06-06 | [18 empty] | 2024-08-30 | 2024-09-04 | 2024-09-08 | 2024-09-15 | 2024-09-20 | 2024-09-25 | 2024-10-02 | 2024-10-02 | 2024-10-06 | 2024-10-09 | 2024-10-09 | 2024-10-09 | 2024-10-15 | 2024-10-16 | 2024-10-20 | 2024-10-29 | 2024-07-23 | 2024-07-25 | 2024-08-01 | 2024-08-08 | 2024-08-13 | 2024-08-14 | 2024-08-20 | 2024-08-20 | 2024-08-21 | 2024-08-24 | 2024-08-25 | 2024-08-30 | 2024-08-30 | 2024-09-01 | 2024-09-04 | 2024-09-06 | 2024-09-06 | 2024-09-10 | 2024-09-12 | 2024-09-13 | 2024-09-14 | 2024-09-20 | 2024-09-25 | 2024-10-02 | 2024-10-02 | 2024-10-02 | 2024-10-06 | 2024-10-06 | 2024-10-09 | 2024-10-13 | 2024-10-22 | 2024-09-14 | 2024-10-02 | 2024-10-04 | 2024-10-26 | 2024-10-23 | 2024-10-29 | 2024-10-31 | 2024-11-06 | 2024-11-12
V_158 | 2024-05-09 | 2024-05-16 | 2024-05-18 | 2024-05-24 | 2024-05-29 | 2024-06-01 | 2024-06-02 | 2024-06-06 | [18 empty] | 2024-08-30 | 2024-09-04 | 2024-09-08 | 2024-09-15 | 2024-09-20 | 2024-09-25 | 2024-10-02 | 2024-10-02 | 2024-10-06 | 2024-10-09 | 2024-10-09 | 2024-10-09 | 2024-10-15 | 2024-10-16 | 2024-10-20 | 2024-10-29 | 2024-07-23 | 2024-07-25 | 2024-08-01 | 2024-08-08 | 2024-08-13 | 2024-08-14 | 2024-08-20 | 2024-08-20 | 2024-08-21 | 2024-08-24 | 2024-08-25 | 2024-08-30 | 2024-08-30 | 2024-09-01 | 2024-09-04 | 2024-09-06 | 2024-09-06 | 2024-09-10 | 2024-09-12 | 2024-09-13 | 2024-09-14 | 2024-09-20 | 2024-09-25 | 2024-10-02 | 2024-10-02 | 2024-10-02 | 2024-10-06 | 2024-10-06 | 2024-10-09 | 2024-10-13 | 2024-10-22 | 2024-09-14 | 2024-10-02 | 2024-10-04 | 2024-10-26 | 2024-10-23 | 2024-10-29 | 2024-10-31 | 2024-11-06 | 2024-11-12
V_159 | 2024-05-09 | 2024-05-16 | 2024-05-18 | 2024-05-24 | 2024-05-29 | 2024-06-01 | 2024-06-02 | 2024-06-06 | [18 empty] | 2024-08-30 | 2024-09-04 | 2024-09-08 | 2024-09-15 | 2024-09-20 | 2024-09-25 | 2024-10-02 | 2024-10-02 | 2024-10-06 | 2024-10-09 | 2024-10-09 | 2024-10-09 | 2024-10-15 | 2024-10-16 | 2024-10-20 | 2024-10-29 | 2024-07-23 | 2024-07-25 | 2024-08-01 | 2024-08-08 | 2024-08-13 | 2024-08-14 | 2024-08-20 | 2024-08-20 | 2024-08-21 | 2024-08-24 | 2024-08-25 | 2024-08-30 | 2024-08-30 | 2024-09-01 | 2024-09-04 | 2024-09-06 | 2024-09-06 | 2024-09-10 | 2024-09-12 | 2024-09-13 | 2024-09-14 | 2024-09-20 | 2024-09-25 | 2024-10-02 | 2024-10-02 | 2024-10-02 | 2024-10-06 | 2024-10-06 | 2024-10-09 | 2024-10-13 | 2024-10-22 | 2024-09-14 | 2024-10-02 | 2024-10-04 | 2024-10-26 | 2024-10-23 | 2024-10-29 | 2024-10-31 | 2024-11-06 | 2024-11-12
V_160 | 2024-05-09 | 2024-05-16 | 2024-05-18 | 2024-05-24 | 2024-05-29 | 2024-06-01 | 2024-06-02 | 2024-06-06 | [18 empty] | 2024-08-30 | 2024-09-04 | 2024-09-08 | 2024-09-15 | 2024-09-20 | 2024-09-25 | 2024-10-02 | 2024-10-02 | 2024-10-06 | 2024-10-09 | 2024-10-09 | 2024-10-09 | 2024-10-15 | 2024-10-16 | 2024-10-20 | 2024-10-29 | 2024-07-23 | 2024-07-25 | 2024-08-01 | 2024-08-08 | 2024-08-13 | 2024-08-14 | 2024-08-20 | 2024-08-20 | 2024-08-21 | 2024-08-24 | 2024-08-25 | 2024-08-30 | 2024-08-30 | 2024-09-01 | 2024-09-04 | 2024-09-06 | 2024-09-06 | 2024-09-10 | 2024-09-12 | 2024-09-13 | 2024-09-14 | 2024-09-20 | 2024-09-25 | 2024-10-02 | 2024-10-02 | 2024-10-02 | 2024-10-06 | 2024-10-06 | 2024-10-09 | 2024-10-13 | 2024-10-22 | 2024-09-14 | 2024-10-02 | 2024-10-04 | 2024-10-26 | 2024-10-23 | 2024-10-29 | 2024-10-31 | 2024-11-06 | 2024-11-12
V_161 | 2024-05-16 | 2024-05-23 | 2024-05-25 | 2024-05-31 | 2024-06-05 | 2024-06-08 | 2024-06-09 | 2024-06-13 | [18 empty] | 2024-09-07 | 2024-09-12 | 2024-09-17 | 2024-09-24 | 2024-09-28 | 2024-10-03 | 2024-10-10 | 2024-10-10 | 2024-10-15 | 2024-10-17 | 2024-10-17 | 2024-10-17 | 2024-10-23 | 2024-10-24 | 2024-10-29 | 2024-11-06 | 2024-07-31 | 2024-08-02 | 2024-08-09 | 2024-08-16 | 2024-08-21 | 2024-08-22 | 2024-08-28 | 2024-08-28 | 2024-08-29 | 2024-09-01 | 2024-09-03 | 2024-09-07 | 2024-09-07 | 2024-09-10 | 2024-09-12 | 2024-09-14 | 2024-09-14 | 2024-09-18 | 2024-09-20 | 2024-09-21 | 2024-09-22 | 2024-09-28 | 2024-10-03 | 2024-10-10 | 2024-10-10 | 2024-10-10 | 2024-10-15 | 2024-10-15 | 2024-10-17 | 2024-10-22 | 2024-10-30 | 2024-09-22 | 2024-10-10 | 2024-10-12 | 2024-11-03 | 2024-10-31 | 2024-11-06 | 2024-11-08 | 2024-11-14 | 2024-11-20
V_162 | 2024-05-16 | 2024-05-23 | 2024-05-25 | 2024-05-31 | 2024-06-05 | 2024-06-08 | 2024-06-09 | 2024-06-13 | [18 empty] | 2024-09-07 | 2024-09-12 | 2024-09-17 | 2024-09-24 | 2024-09-28 | 2024-10-03 | 2024-10-10 | 2024-10-10 | 2024-10-15 | 2024-10-17 | 2024-10-17 | 2024-10-17 | 2024-10-23 | 2024-10-24 | 2024-10-29 | 2024-11-06 | 2024-07-31 | 2024-08-02 | 2024-08-09 | 2024-08-16 | 2024-08-21 | 2024-08-22 | 2024-08-28 | 2024-08-28 | 2024-08-29 | 2024-09-01 | 2024-09-03 | 2024-09-07 | 2024-09-07 | 2024-09-10 | 2024-09-12 | 2024-09-14 | 2024-09-14 | 2024-09-18 | 2024-09-20 | 2024-09-21 | 2024-09-22 | 2024-09-28 | 2024-10-03 | 2024-10-10 | 2024-10-10 | 2024-10-10 | 2024-10-15 | 2024-10-15 | 2024-10-17 | 2024-10-22 | 2024-10-30 | 2024-09-22 | 2024-10-10 | 2024-10-12 | 2024-11-03 | 2024-10-31 | 2024-11-06 | 2024-11-08 | 2024-11-14 | 2024-11-20
V_163 | 2024-05-16 | 2024-05-23 | 2024-05-25 | 2024-05-31 | 2024-06-05 | 2024-06-08 | 2024-06-09 | 2024-06-13 | [18 empty] | 2024-09-07 | 2024-09-12 | 2024-09-17 | 2024-09-24 | 2024-09-28 | 2024-10-03 | 2024-10-10 | 2024-10-10 | 2024-10-15 | 2024-10-17 | 2024-10-17 | 2024-10-17 | 2024-10-23 | 2024-10-24 | 2024-10-29 | 2024-11-06 | 2024-07-31 | 2024-08-02 | 2024-08-09 | 2024-08-16 | 2024-08-21 | 2024-08-22 | 2024-08-28 | 2024-08-28 | 2024-08-29 | 2024-09-01 | 2024-09-03 | 2024-09-07 | 2024-09-07 | 2024-09-10 | 2024-09-12 | 2024-09-14 | 2024-09-14 | 2024-09-18 | 2024-09-20 | 2024-09-21 | 2024-09-22 | 2024-09-28 | 2024-10-03 | 2024-10-10 | 2024-10-10 | 2024-10-10 | 2024-10-15 | 2024-10-15 | 2024-10-17 | 2024-10-22 | 2024-10-30 | 2024-09-22 | 2024-10-10 | 2024-10-12 | 2024-11-03 | 2024-10-31 | 2024-11-06 | 2024-11-08 | 2024-11-14 | 2024-11-20
V_164 | 2024-05-16 | 2024-05-23 | 2024-05-25 | 2024-05-31 | 2024-06-05 | 2024-06-08 | 2024-06-09 | 2024-06-13 | [18 empty] | 2024-09-07 | 2024-09-12 | 2024-09-17 | 2024-09-24 | 2024-09-28 | 2024-10-03 | 2024-10-10 | 2024-10-10 | 2024-10-15 | 2024-10-17 | 2024-10-17 | 2024-10-17 | 2024-10-23 | 2024-10-24 | 2024-10-29 | 2024-11-06 | 2024-07-31 | 2024-08-02 | 2024-08-09 | 2024-08-16 | 2024-08-21 | 2024-08-22 | 2024-08-28 | 2024-08-28 | 2024-08-29 | 2024-09-01 | 2024-09-03 | 2024-09-07 | 2024-09-07 | 2024-09-10 | 2024-09-12 | 2024-09-14 | 2024-09-14 | 2024-09-18 | 2024-09-20 | 2024-09-21 | 2024-09-22 | 2024-09-28 | 2024-10-03 | 2024-10-10 | 2024-10-10 | 2024-10-10 | 2024-10-15 | 2024-10-15 | 2024-10-17 | 2024-10-22 | 2024-10-30 | 2024-09-22 | 2024-10-10 | 2024-10-12 | 2024-11-03 | 2024-10-31 | 2024-11-06 | 2024-11-08 | 2024-11-14 | 2024-11-20
V_165 | 2024-05-16 | 2024-05-23 | 2024-05-25 | 2024-05-31 | 2024-06-05 | 2024-06-08 | 2024-06-09 | 2024-06-13 | [18 empty] | 2024-09-07 | 2024-09-12 | 2024-09-17 | 2024-09-24 | 2024-09-28 | 2024-10-03 | 2024-10-10 | 2024-10-10 | 2024-10-15 | 2024-10-17 | 2024-10-17 | 2024-10-17 | 2024-10-23 | 2024-10-24 | 2024-10-29 | 2024-11-06 | 2024-07-31 | 2024-08-02 | 2024-08-09 | 2024-08-16 | 2024-08-21 | 2024-08-22 | 2024-08-28 | 2024-08-28 | 2024-08-29 | 2024-09-01 | 2024-09-03 | 2024-09-07 | 2024-09-07 | 2024-09-10 | 2024-09-12 | 2024-09-14 | 2024-09-14 | 2024-09-18 | 2024-09-20 | 2024-09-21 | 2024-09-22 | 2024-09-28 | 2024-10-03 | 2024-10-10 | 2024-10-10 | 2024-10-10 | 2024-10-15 | 2024-10-15 | 2024-10-17 | 2024-10-22 | 2024-10-30 | 2024-09-22 | 2024-10-10 | 2024-10-12 | 2024-11-03 | 2024-10-31 | 2024-11-06 | 2024-11-08 | 2024-11-14 | 2024-11-20
V_166 | 2024-05-16 | 2024-05-23 | 2024-05-25 | 2024-05-31 | 2024-06-05 | 2024-06-08 | 2024-06-09 | 2024-06-13 | [18 empty] | 2024-09-07 | 2024-09-12 | 2024-09-17 | 2024-09-24 | 2024-09-28 | 2024-10-03 | 2024-10-10 | 2024-10-10 | 2024-10-15 | 2024-10-17 | 2024-10-17 | 2024-10-17 | 2024-10-23 | 2024-10-24 | 2024-10-29 | 2024-11-06 | 2024-07-31 | 2024-08-02 | 2024-08-09 | 2024-08-16 | 2024-08-21 | 2024-08-22 | 2024-08-28 | 2024-08-28 | 2024-08-29 | 2024-09-01 | 2024-09-03 | 2024-09-07 | 2024-09-07 | 2024-09-10 | 2024-09-12 | 2024-09-14 | 2024-09-14 | 2024-09-18 | 2024-09-20 | 2024-09-21 | 2024-09-22 | 2024-09-28 | 2024-10-03 | 2024-10-10 | 2024-10-10 | 2024-10-10 | 2024-10-15 | 2024-10-15 | 2024-10-17 | 2024-10-22 | 2024-10-30 | 2024-09-22 | 2024-10-10 | 2024-10-12 | 2024-11-03 | 2024-10-31 | 2024-11-06 | 2024-11-08 | 2024-11-14 | 2024-11-20
V_167 | 2024-05-16 | 2024-05-23 | 2024-05-25 | 2024-05-31 | 2024-06-05 | 2024-06-08 | 2024-06-09 | 2024-06-13 | [18 empty] | 2024-09-07 | 2024-09-12 | 2024-09-17 | 2024-09-24 | 2024-09-28 | 2024-10-03 | 2024-10-10 | 2024-10-10 | 2024-10-15 | 2024-10-17 | 2024-10-17 | 2024-10-17 | 2024-10-23 | 2024-10-24 | 2024-10-29 | 2024-11-06 | 2024-07-31 | 2024-08-02 | 2024-08-09 | 2024-08-16 | 2024-08-21 | 2024-08-22 | 2024-08-28 | 2024-08-28 | 2024-08-29 | 2024-09-01 | 2024-09-03 | 2024-09-07 | 2024-09-07 | 2024-09-10 | 2024-09-12 | 2024-09-14 | 2024-09-14 | 2024-09-18 | 2024-09-20 | 2024-09-21 | 2024-09-22 | 2024-09-28 | 2024-10-03 | 2024-10-10 | 2024-10-10 | 2024-10-10 | 2024-10-15 | 2024-10-15 | 2024-10-17 | 2024-10-22 | 2024-10-30 | 2024-09-22 | 2024-10-10 | 2024-10-12 | 2024-11-03 | 2024-10-31 | 2024-11-06 | 2024-11-08 | 2024-11-14 | 2024-11-20
V_168 | 2024-05-16 | 2024-05-23 | 2024-05-25 | 2024-05-31 | 2024-06-05 | 2024-06-08 | 2024-06-09 | 2024-06-13 | [18 empty] | 2024-09-07 | 2024-09-12 | 2024-09-17 | 2024-09-24 | 2024-09-28 | 2024-10-03 | 2024-10-10 | 2024-10-10 | 2024-10-15 | 2024-10-17 | 2024-10-17 | 2024-10-17 | 2024-10-23 | 2024-10-24 | 2024-10-29 | 2024-11-06 | 2024-07-31 | 2024-08-02 | 2024-08-09 | 2024-08-16 | 2024-08-21 | 2024-08-22 | 2024-08-28 | 2024-08-28 | 2024-08-29 | 2024-09-01 | 2024-09-03 | 2024-09-07 | 2024-09-07 | 2024-09-10 | 2024-09-12 | 2024-09-14 | 2024-09-14 | 2024-09-18 | 2024-09-20 | 2024-09-21 | 2024-09-22 | 2024-09-28 | 2024-10-03 | 2024-10-10 | 2024-10-10 | 2024-10-10 | 2024-10-15 | 2024-10-15 | 2024-10-17 | 2024-10-22 | 2024-10-30 | 2024-09-22 | 2024-10-10 | 2024-10-12 | 2024-11-03 | 2024-10-31 | 2024-11-06 | 2024-11-08 | 2024-11-14 | 2024-11-20
V_169 | 2024-05-23 | 2024-05-30 | 2024-06-01 | 2024-06-07 | 2024-06-12 | 2024-06-15 | 2024-06-16 | 2024-06-20 | [18 empty] | 2024-09-15 | 2024-09-20 | 2024-09-25 | 2024-10-02 | 2024-10-06 | 2024-10-11 | 2024-10-18 | 2024-10-18 | 2024-10-23 | 2024-10-25 | 2024-10-25 | 2024-10-25 | 2024-10-31 | 2024-11-01 | 2024-11-06 | 2024-11-14 | 2024-08-08 | 2024-08-10 | 2024-08-17 | 2024-08-24 | 2024-08-29 | 2024-08-30 | 2024-09-05 | 2024-09-05 | 2024-09-06 | 2024-09-10 | 2024-09-11 | 2024-09-15 | 2024-09-15 | 2024-09-18 | 2024-09-20 | 2024-09-22 | 2024-09-22 | 2024-09-26 | 2024-09-28 | 2024-09-29 | 2024-10-01 | 2024-10-06 | 2024-10-11 | 2024-10-18 | 2024-10-18 | 2024-10-18 | 2024-10-23 | 2024-10-23 | 2024-10-25 | 2024-10-30 | 2024-11-07 | 2024-10-01 | 2024-10-18 | 2024-10-20 | 2024-11-12 | 2024-11-08 | 2024-11-14 | 2024-11-16 | 2024-11-22 | 2024-11-28
V_170 | 2024-05-23 | 2024-05-30 | 2024-06-01 | 2024-06-07 | 2024-06-12 | 2024-06-15 | 2024-06-16 | 2024-06-20 | [18 empty] | 2024-09-15 | 2024-09-20 | 2024-09-25 | 2024-10-02 | 2024-10-06 | 2024-10-11 | 2024-10-18 | 2024-10-18 | 2024-10-23 | 2024-10-25 | 2024-10-25 | 2024-10-25 | 2024-10-31 | 2024-11-01 | 2024-11-06 | 2024-11-14 | 2024-08-08 | 2024-08-10 | 2024-08-17 | 2024-08-24 | 2024-08-29 | 2024-08-30 | 2024-09-05 | 2024-09-05 | 2024-09-06 | 2024-09-10 | 2024-09-11 | 2024-09-15 | 2024-09-15 | 2024-09-18 | 2024-09-20 | 2024-09-22 | 2024-09-22 | 2024-09-26 | 2024-09-28 | 2024-09-29 | 2024-10-01 | 2024-10-06 | 2024-10-11 | 2024-10-18 | 2024-10-18 | 2024-10-18 | 2024-10-23 | 2024-10-23 | 2024-10-25 | 2024-10-30 | 2024-11-07 | 2024-10-01 | 2024-10-18 | 2024-10-20 | 2024-11-12 | 2024-11-08 | 2024-11-14 | 2024-11-16 | 2024-11-22 | 2024-11-28
V_171 | 2024-05-23 | 2024-05-30 | 2024-06-01 | 2024-06-07 | 2024-06-12 | 2024-06-15 | 2024-06-16 | 2024-06-20 | [18 empty] | 2024-09-15 | 2024-09-20 | 2024-09-25 | 2024-10-02 | 2024-10-06 | 2024-10-11 | 2024-10-18 | 2024-10-18 | 2024-10-23 | 2024-10-25 | 2024-10-25 | 2024-10-25 | 2024-10-31 | 2024-11-01 | 2024-11-06 | 2024-11-14 | 2024-08-08 | 2024-08-10 | 2024-08-17 | 2024-08-24 | 2024-08-29 | 2024-08-30 | 2024-09-05 | 2024-09-05 | 2024-09-06 | 2024-09-10 | 2024-09-11 | 2024-09-15 | 2024-09-15 | 2024-09-18 | 2024-09-20 | 2024-09-22 | 2024-09-22 | 2024-09-26 | 2024-09-28 | 2024-09-29 | 2024-10-01 | 2024-10-06 | 2024-10-11 | 2024-10-18 | 2024-10-18 | 2024-10-18 | 2024-10-23 | 2024-10-23 | 2024-10-25 | 2024-10-30 | 2024-11-07 | 2024-10-01 | 2024-10-18 | 2024-10-20 | 2024-11-12 | 2024-11-08 | 2024-11-14 | 2024-11-16 | 2024-11-22 | 2024-11-28
V_172 | 2024-05-23 | 2024-05-30 | 2024-06-01 | 2024-06-07 | 2024-06-12 | 2024-06-15 | 2024-06-16 | 2024-06-20 | [18 empty] | 2024-09-15 | 2024-09-20 | 2024-09-25 | 2024-10-02 | 2024-10-06 | 2024-10-11 | 2024-10-18 | 2024-10-18 | 2024-10-23 | 2024-10-25 | 2024-10-25 | 2024-10-25 | 2024-10-31 | 2024-11-01 | 2024-11-06 | 2024-11-14 | 2024-08-08 | 2024-08-10 | 2024-08-17 | 2024-08-24 | 2024-08-29 | 2024-08-30 | 2024-09-05 | 2024-09-05 | 2024-09-06 | 2024-09-10 | 2024-09-11 | 2024-09-15 | 2024-09-15 | 2024-09-18 | 2024-09-20 | 2024-09-22 | 2024-09-22 | 2024-09-26 | 2024-09-28 | 2024-09-29 | 2024-10-01 | 2024-10-06 | 2024-10-11 | 2024-10-18 | 2024-10-18 | 2024-10-18 | 2024-10-23 | 2024-10-23 | 2024-10-25 | 2024-10-30 | 2024-11-07 | 2024-10-01 | 2024-10-18 | 2024-10-20 | 2024-11-12 | 2024-11-08 | 2024-11-14 | 2024-11-16 | 2024-11-22 | 2024-11-28
V_173 | 2024-05-23 | 2024-05-30 | 2024-06-01 | 2024-06-07 | 2024-06-12 | 2024-06-15 | 2024-06-16 | 2024-06-20 | [18 empty] | 2024-09-15 | 2024-09-20 | 2024-09-25 | 2024-10-02 | 2024-10-06 | 2024-10-11 | 2024-10-18 | 2024-10-18 | 2024-10-23 | 2024-10-25 | 2024-10-25 | 2024-10-25 | 2024-10-31 | 2024-11-01 | 2024-11-06 | 2024-11-14 | 2024-08-08 | 2024-08-10 | 2024-08-17 | 2024-08-24 | 2024-08-29 | 2024-08-30 | 2024-09-05 | 2024-09-05 | 2024-09-06 | 2024-09-10 | 2024-09-11 | 2024-09-15 | 2024-09-15 | 2024-09-18 | 2024-09-20 | 2024-09-22 | 2024-09-22 | 2024-09-26 | 2024-09-28 | 2024-09-29 | 2024-10-01 | 2024-10-06 | 2024-10-11 | 2024-10-18 | 2024-10-18 | 2024-10-18 | 2024-10-23 | 2024-10-23 | 2024-10-25 | 2024-10-30 | 2024-11-07 | 2024-10-01 | 2024-10-18 | 2024-10-20 | 2024-11-12 | 2024-11-08 | 2024-11-14 | 2024-11-16 | 2024-11-22 | 2024-11-28
V_174 | 2024-05-23 | 2024-05-30 | 2024-06-01 | 2024-06-07 | 2024-06-12 | 2024-06-15 | 2024-06-16 | 2024-06-20 | [18 empty] | 2024-09-15 | 2024-09-20 | 2024-09-25 | 2024-10-02 | 2024-10-06 | 2024-10-11 | 2024-10-18 | 2024-10-18 | 2024-10-23 | 2024-10-25 | 2024-10-25 | 2024-10-25 | 2024-10-31 | 2024-11-01 | 2024-11-06 | 2024-11-14 | 2024-08-08 | 2024-08-10 | 2024-08-17 | 2024-08-24 | 2024-08-29 | 2024-08-30 | 2024-09-05 | 2024-09-05 | 2024-09-06 | 2024-09-10 | 2024-09-11 | 2024-09-15 | 2024-09-15 | 2024-09-18 | 2024-09-20 | 2024-09-22 | 2024-09-22 | 2024-09-26 | 2024-09-28 | 2024-09-29 | 2024-10-01 | 2024-10-06 | 2024-10-11 | 2024-10-18 | 2024-10-18 | 2024-10-18 | 2024-10-23 | 2024-10-23 | 2024-10-25 | 2024-10-30 | 2024-11-07 | 2024-10-01 | 2024-10-18 | 2024-10-20 | 2024-11-12 | 2024-11-08 | 2024-11-14 | 2024-11-16 | 2024-11-22 | 2024-11-28
V_175 | 2024-05-23 | 2024-05-30 | 2024-06-01 | 2024-06-07 | 2024-06-12 | 2024-06-15 | 2024-06-16 | 2024-06-20 | [18 empty] | 2024-09-15 | 2024-09-20 | 2024-09-25 | 2024-10-02 | 2024-10-06 | 2024-10-11 | 2024-10-18 | 2024-10-18 | 2024-10-23 | 2024-10-25 | 2024-10-25 | 2024-10-25 | 2024-10-31 | 2024-11-01 | 2024-11-06 | 2024-11-14 | 2024-08-08 | 2024-08-10 | 2024-08-17 | 2024-08-24 | 2024-08-29 | 2024-08-30 | 2024-09-05 | 2024-09-05 | 2024-09-06 | 2024-09-10 | 2024-09-11 | 2024-09-15 | 2024-09-15 | 2024-09-18 | 2024-09-20 | 2024-09-22 | 2024-09-22 | 2024-09-26 | 2024-09-28 | 2024-09-29 | 2024-10-01 | 2024-10-06 | 2024-10-11 | 2024-10-18 | 2024-10-18 | 2024-10-18 | 2024-10-23 | 2024-10-23 | 2024-10-25 | 2024-10-30 | 2024-11-07 | 2024-10-01 | 2024-10-18 | 2024-10-20 | 2024-11-12 | 2024-11-08 | 2024-11-14 | 2024-11-16 | 2024-11-22 | 2024-11-28
V_176 | 2024-05-23 | 2024-05-30 | 2024-06-01 | 2024-06-07 | 2024-06-12 | 2024-06-15 | 2024-06-16 | 2024-06-20 | [18 empty] | 2024-09-15 | 2024-09-20 | 2024-09-25 | 2024-10-02 | 2024-10-06 | 2024-10-11 | 2024-10-18 | 2024-10-18 | 2024-10-23 | 2024-10-25 | 2024-10-25 | 2024-10-25 | 2024-10-31 | 2024-11-01 | 2024-11-06 | 2024-11-14 | 2024-08-08 | 2024-08-10 | 2024-08-17 | 2024-08-24 | 2024-08-29 | 2024-08-30 | 2024-09-05 | 2024-09-05 | 2024-09-06 | 2024-09-10 | 2024-09-11 | 2024-09-15 | 2024-09-15 | 2024-09-18 | 2024-09-20 | 2024-09-22 | 2024-09-22 | 2024-09-26 | 2024-09-28 | 2024-09-29 | 2024-10-01 | 2024-10-06 | 2024-10-11 | 2024-10-18 | 2024-10-18 | 2024-10-18 | 2024-10-23 | 2024-10-23 | 2024-10-25 | 2024-10-30 | 2024-11-07 | 2024-10-01 | 2024-10-18 | 2024-10-20 | 2024-11-12 | 2024-11-08 | 2024-11-14 | 2024-11-16 | 2024-11-22 | 2024-11-28
V_177 | 2024-05-30 | 2024-06-06 | 2024-06-08 | 2024-06-14 | 2024-06-19 | 2024-06-22 | 2024-06-23 | 2024-06-27 | [18 empty] | 2024-09-24 | 2024-09-28 | 2024-10-03 | 2024-10-10 | 2024-10-15 | 2024-10-19 | 2024-10-26 | 2024-10-26 | 2024-10-31 | 2024-11-02 | 2024-11-02 | 2024-11-02 | 2024-11-08 | 2024-11-09 | 2024-11-14 | 2024-11-22 | 2024-08-16 | 2024-08-18 | 2024-08-25 | 2024-09-01 | 2024-09-06 | 2024-09-07 | 2024-09-13 | 2024-09-13 | 2024-09-14 | 2024-09-18 | 2024-09-19 | 2024-09-24 | 2024-09-24 | 2024-09-26 | 2024-09-28 | 2024-10-01 | 2024-10-01 | 2024-10-04 | 2024-10-06 | 2024-10-08 | 2024-10-09 | 2024-10-15 | 2024-10-19 | 2024-10-26 | 2024-10-26 | 2024-10-26 | 2024-10-31 | 2024-10-31 | 2024-11-02 | 2024-11-07 | 2024-11-15 | 2024-10-09 | 2024-10-26 | 2024-10-29 | 2024-11-20 | 2024-11-16 | 2024-11-22 | 2024-11-24 | 2024-11-30 | 2024-12-06
V_178 | 2024-05-30 | 2024-06-06 | 2024-06-08 | 2024-06-14 | 2024-06-19 | 2024-06-22 | 2024-06-23 | 2024-06-27 | [18 empty] | 2024-09-24 | 2024-09-28 | 2024-10-03 | 2024-10-10 | 2024-10-15 | 2024-10-19 | 2024-10-26 | 2024-10-26 | 2024-10-31 | 2024-11-02 | 2024-11-02 | 2024-11-02 | 2024-11-08 | 2024-11-09 | 2024-11-14 | 2024-11-22 | 2024-08-16 | 2024-08-18 | 2024-08-25 | 2024-09-01 | 2024-09-06 | 2024-09-07 | 2024-09-13 | 2024-09-13 | 2024-09-14 | 2024-09-18 | 2024-09-19 | 2024-09-24 | 2024-09-24 | 2024-09-26 | 2024-09-28 | 2024-10-01 | 2024-10-01 | 2024-10-04 | 2024-10-06 | 2024-10-08 | 2024-10-09 | 2024-10-15 | 2024-10-19 | 2024-10-26 | 2024-10-26 | 2024-10-26 | 2024-10-31 | 2024-10-31 | 2024-11-02 | 2024-11-07 | 2024-11-15 | 2024-10-09 | 2024-10-26 | 2024-10-29 | 2024-11-20 | 2024-11-16 | 2024-11-22 | 2024-11-24 | 2024-11-30 | 2024-12-06
V_179 | 2024-05-30 | 2024-06-06 | 2024-06-08 | 2024-06-14 | 2024-06-19 | 2024-06-22 | 2024-06-23 | 2024-06-27 | [18 empty] | 2024-09-24 | 2024-09-28 | 2024-10-03 | 2024-10-10 | 2024-10-15 | 2024-10-19 | 2024-10-26 | 2024-10-26 | 2024-10-31 | 2024-11-02 | 2024-11-02 | 2024-11-02 | 2024-11-08 | 2024-11-09 | 2024-11-14 | 2024-11-22 | 2024-08-16 | 2024-08-18 | 2024-08-25 | 2024-09-01 | 2024-09-06 | 2024-09-07 | 2024-09-13 | 2024-09-13 | 2024-09-14 | 2024-09-18 | 2024-09-19 | 2024-09-24 | 2024-09-24 | 2024-09-26 | 2024-09-28 | 2024-10-01 | 2024-10-01 | 2024-10-04 | 2024-10-06 | 2024-10-08 | 2024-10-09 | 2024-10-15 | 2024-10-19 | 2024-10-26 | 2024-10-26 | 2024-10-26 | 2024-10-31 | 2024-10-31 | 2024-11-02 | 2024-11-07 | 2024-11-15 | 2024-10-09 | 2024-10-26 | 2024-10-29 | 2024-11-20 | 2024-11-16 | 2024-11-22 | 2024-11-24 | 2024-11-30 | 2024-12-06
V_180 | 2024-05-30 | 2024-06-06 | 2024-06-08 | 2024-06-14 | 2024-06-19 | 2024-06-22 | 2024-06-23 | 2024-06-27 | [18 empty] | 2024-09-24 | 2024-09-28 | 2024-10-03 | 2024-10-10 | 2024-10-15 | 2024-10-19 | 2024-10-26 | 2024-10-26 | 2024-10-31 | 2024-11-02 | 2024-11-02 | 2024-11-02 | 2024-11-08 | 2024-11-09 | 2024-11-14 | 2024-11-22 | 2024-08-16 | 2024-08-18 | 2024-08-25 | 2024-09-01 | 2024-09-06 | 2024-09-07 | 2024-09-13 | 2024-09-13 | 2024-09-14 | 2024-09-18 | 2024-09-19 | 2024-09-24 | 2024-09-24 | 2024-09-26 | 2024-09-28 | 2024-10-01 | 2024-10-01 | 2024-10-04 | 2024-10-06 | 2024-10-08 | 2024-10-09 | 2024-10-15 | 2024-10-19 | 2024-10-26 | 2024-10-26 | 2024-10-26 | 2024-10-31 | 2024-10-31 | 2024-11-02 | 2024-11-07 | 2024-11-15 | 2024-10-09 | 2024-10-26 | 2024-10-29 | 2024-11-20 | 2024-11-16 | 2024-11-22 | 2024-11-24 | 2024-11-30 | 2024-12-06
V_181 | 2024-05-30 | 2024-06-06 | 2024-06-08 | 2024-06-14 | 2024-06-19 | 2024-06-22 | 2024-06-23 | 2024-06-27 | [18 empty] | 2024-09-24 | 2024-09-28 | 2024-10-03 | 2024-10-10 | 2024-10-15 | 2024-10-19 | 2024-10-26 | 2024-10-26 | 2024-10-31 | 2024-11-02 | 2024-11-02 | 2024-11-02 | 2024-11-08 | 2024-11-09 | 2024-11-14 | 2024-11-22 | 2024-08-16 | 2024-08-18 | 2024-08-25 | 2024-09-01 | 2024-09-06 | 2024-09-07 | 2024-09-13 | 2024-09-13 | 2024-09-14 | 2024-09-18 | 2024-09-19 | 2024-09-24 | 2024-09-24 | 2024-09-26 | 2024-09-28 | 2024-10-01 | 2024-10-01 | 2024-10-04 | 2024-10-06 | 2024-10-08 | 2024-10-09 | 2024-10-15 | 2024-10-19 | 2024-10-26 | 2024-10-26 | 2024-10-26 | 2024-10-31 | 2024-10-31 | 2024-11-02 | 2024-11-07 | 2024-11-15 | 2024-10-09 | 2024-10-26 | 2024-10-29 | 2024-11-20 | 2024-11-16 | 2024-11-22 | 2024-11-24 | 2024-11-30 | 2024-12-06
V_182 | 2024-05-30 | 2024-06-06 | 2024-06-08 | 2024-06-14 | 2024-06-19 | 2024-06-22 | 2024-06-23 | 2024-06-27 | [18 empty] | 2024-09-24 | 2024-09-28 | 2024-10-03 | 2024-10-10 | 2024-10-15 | 2024-10-19 | 2024-10-26 | 2024-10-26 | 2024-10-31 | 2024-11-02 | 2024-11-02 | 2024-11-02 | 2024-11-08 | 2024-11-09 | 2024-11-14 | 2024-11-22 | 2024-08-16 | 2024-08-18 | 2024-08-25 | 2024-09-01 | 2024-09-06 | 2024-09-07 | 2024-09-13 | 2024-09-13 | 2024-09-14 | 2024-09-18 | 2024-09-19 | 2024-09-24 | 2024-09-24 | 2024-09-26 | 2024-09-28 | 2024-10-01 | 2024-10-01 | 2024-10-04 | 2024-10-06 | 2024-10-08 | 2024-10-09 | 2024-10-15 | 2024-10-19 | 2024-10-26 | 2024-10-26 | 2024-10-26 | 2024-10-31 | 2024-10-31 | 2024-11-02 | 2024-11-07 | 2024-11-15 | 2024-10-09 | 2024-10-26 | 2024-10-29 | 2024-11-20 | 2024-11-16 | 2024-11-22 | 2024-11-24 | 2024-11-30 | 2024-12-06
V_183 | 2024-05-30 | 2024-06-06 | 2024-06-08 | 2024-06-14 | 2024-06-19 | 2024-06-22 | 2024-06-23 | 2024-06-27 | [18 empty] | 2024-09-24 | 2024-09-28 | 2024-10-03 | 2024-10-10 | 2024-10-15 | 2024-10-19 | 2024-10-26 | 2024-10-26 | 2024-10-31 | 2024-11-02 | 2024-11-02 | 2024-11-02 | 2024-11-08 | 2024-11-09 | 2024-11-14 | 2024-11-22 | 2024-08-16 | 2024-08-18 | 2024-08-25 | 2024-09-01 | 2024-09-06 | 2024-09-07 | 2024-09-13 | 2024-09-13 | 2024-09-14 | 2024-09-18 | 2024-09-19 | 2024-09-24 | 2024-09-24 | 2024-09-26 | 2024-09-28 | 2024-10-01 | 2024-10-01 | 2024-10-04 | 2024-10-06 | 2024-10-08 | 2024-10-09 | 2024-10-15 | 2024-10-19 | 2024-10-26 | 2024-10-26 | 2024-10-26 | 2024-10-31 | 2024-10-31 | 2024-11-02 | 2024-11-07 | 2024-11-15 | 2024-10-09 | 2024-10-26 | 2024-10-29 | 2024-11-20 | 2024-11-16 | 2024-11-22 | 2024-11-24 | 2024-11-30 | 2024-12-06
V_184 | 2024-05-30 | 2024-06-06 | 2024-06-08 | 2024-06-14 | 2024-06-19 | 2024-06-22 | 2024-06-23 | 2024-06-27 | [18 empty] | 2024-09-24 | 2024-09-28 | 2024-10-03 | 2024-10-10 | 2024-10-15 | 2024-10-19 | 2024-10-26 | 2024-10-26 | 2024-10-31 | 2024-11-02 | 2024-11-02 | 2024-11-02 | 2024-11-08 | 2024-11-09 | 2024-11-14 | 2024-11-22 | 2024-08-16 | 2024-08-18 | 2024-08-25 | 2024-09-01 | 2024-09-06 | 2024-09-07 | 2024-09-13 | 2024-09-13 | 2024-09-14 | 2024-09-18 | 2024-09-19 | 2024-09-24 | 2024-09-24 | 2024-09-26 | 2024-09-28 | 2024-10-01 | 2024-10-01 | 2024-10-04 | 2024-10-06 | 2024-10-08 | 2024-10-09 | 2024-10-15 | 2024-10-19 | 2024-10-26 | 2024-10-26 | 2024-10-26 | 2024-10-31 | 2024-10-31 | 2024-11-02 | 2024-11-07 | 2024-11-15 | 2024-10-09 | 2024-10-26 | 2024-10-29 | 2024-11-20 | 2024-11-16 | 2024-11-22 | 2024-11-24 | 2024-11-30 | 2024-12-06
V_185 | 2024-06-06 | 2024-06-13 | 2024-06-15 | 2024-06-21 | 2024-06-26 | 2024-06-29 | 2024-06-30 | 2024-07-04 | [18 empty] | 2024-10-02 | 2024-10-06 | 2024-10-11 | 2024-10-18 | 2024-10-23 | 2024-10-27 | 2024-11-03 | 2024-11-03 | 2024-11-08 | 2024-11-10 | 2024-11-10 | 2024-11-10 | 2024-11-16 | 2024-11-17 | 2024-11-22 | 2024-11-30 | 2024-08-24 | 2024-08-27 | 2024-09-03 | 2024-09-10 | 2024-09-14 | 2024-09-15 | 2024-09-21 | 2024-09-21 | 2024-09-22 | 2024-09-26 | 2024-09-27 | 2024-10-02 | 2024-10-02 | 2024-10-04 | 2024-10-06 | 2024-10-09 | 2024-10-09 | 2024-10-12 | 2024-10-15 | 2024-10-16 | 2024-10-17 | 2024-10-23 | 2024-10-27 | 2024-11-03 | 2024-11-03 | 2024-11-03 | 2024-11-08 | 2024-11-08 | 2024-11-10 | 2024-11-15 | 2024-11-23 | 2024-10-17 | 2024-11-03 | 2024-11-06 | 2024-11-28 | 2024-11-24 | 2024-11-30 | 2024-12-03 | 2024-12-08 | 2024-12-14
V_186 | 2024-06-06 | 2024-06-13 | 2024-06-15 | 2024-06-21 | 2024-06-26 | 2024-06-29 | 2024-06-30 | 2024-07-04 | [18 empty] | 2024-10-02 | 2024-10-06 | 2024-10-11 | 2024-10-18 | 2024-10-23 | 2024-10-27 | 2024-11-03 | 2024-11-03 | 2024-11-08 | 2024-11-10 | 2024-11-10 | 2024-11-10 | 2024-11-16 | 2024-11-17 | 2024-11-22 | 2024-11-30 | 2024-08-24 | 2024-08-27 | 2024-09-03 | 2024-09-10 | 2024-09-14 | 2024-09-15 | 2024-09-21 | 2024-09-21 | 2024-09-22 | 2024-09-26 | 2024-09-27 | 2024-10-02 | 2024-10-02 | 2024-10-04 | 2024-10-06 | 2024-10-09 | 2024-10-09 | 2024-10-12 | 2024-10-15 | 2024-10-16 | 2024-10-17 | 2024-10-23 | 2024-10-27 | 2024-11-03 | 2024-11-03 | 2024-11-03 | 2024-11-08 | 2024-11-08 | 2024-11-10 | 2024-11-15 | 2024-11-23 | 2024-10-17 | 2024-11-03 | 2024-11-06 | 2024-11-28 | 2024-11-24 | 2024-11-30 | 2024-12-03 | 2024-12-08 | 2024-12-14
V_187 | 2024-06-06 | 2024-06-13 | 2024-06-15 | 2024-06-21 | 2024-06-26 | 2024-06-29 | 2024-06-30 | 2024-07-04 | [18 empty] | 2024-10-02 | 2024-10-06 | 2024-10-11 | 2024-10-18 | 2024-10-23 | 2024-10-27 | 2024-11-03 | 2024-11-03 | 2024-11-08 | 2024-11-10 | 2024-11-10 | 2024-11-10 | 2024-11-16 | 2024-11-17 | 2024-11-22 | 2024-11-30 | 2024-08-24 | 2024-08-27 | 2024-09-03 | 2024-09-10 | 2024-09-14 | 2024-09-15 | 2024-09-21 | 2024-09-21 | 2024-09-22 | 2024-09-26 | 2024-09-27 | 2024-10-02 | 2024-10-02 | 2024-10-04 | 2024-10-06 | 2024-10-09 | 2024-10-09 | 2024-10-12 | 2024-10-15 | 2024-10-16 | 2024-10-17 | 2024-10-23 | 2024-10-27 | 2024-11-03 | 2024-11-03 | 2024-11-03 | 2024-11-08 | 2024-11-08 | 2024-11-10 | 2024-11-15 | 2024-11-23 | 2024-10-17 | 2024-11-03 | 2024-11-06 | 2024-11-28 | 2024-11-24 | 2024-11-30 | 2024-12-03 | 2024-12-08 | 2024-12-14
V_188 | 2024-06-06 | 2024-06-13 | 2024-06-15 | 2024-06-21 | 2024-06-26 | 2024-06-29 | 2024-06-30 | 2024-07-04 | [18 empty] | 2024-10-02 | 2024-10-06 | 2024-10-11 | 2024-10-18 | 2024-10-23 | 2024-10-27 | 2024-11-03 | 2024-11-03 | 2024-11-08 | 2024-11-10 | 2024-11-10 | 2024-11-10 | 2024-11-16 | 2024-11-17 | 2024-11-22 | 2024-11-30 | 2024-08-24 | 2024-08-27 | 2024-09-03 | 2024-09-10 | 2024-09-14 | 2024-09-15 | 2024-09-21 | 2024-09-21 | 2024-09-22 | 2024-09-26 | 2024-09-27 | 2024-10-02 | 2024-10-02 | 2024-10-04 | 2024-10-06 | 2024-10-09 | 2024-10-09 | 2024-10-12 | 2024-10-15 | 2024-10-16 | 2024-10-17 | 2024-10-23 | 2024-10-27 | 2024-11-03 | 2024-11-03 | 2024-11-03 | 2024-11-08 | 2024-11-08 | 2024-11-10 | 2024-11-15 | 2024-11-23 | 2024-10-17 | 2024-11-03 | 2024-11-06 | 2024-11-28 | 2024-11-24 | 2024-11-30 | 2024-12-03 | 2024-12-08 | 2024-12-14
V_189 | 2024-06-06 | 2024-06-13 | 2024-06-15 | 2024-06-21 | 2024-06-26 | 2024-06-29 | 2024-06-30 | 2024-07-04 | [18 empty] | 2024-10-02 | 2024-10-06 | 2024-10-11 | 2024-10-18 | 2024-10-23 | 2024-10-27 | 2024-11-03 | 2024-11-03 | 2024-11-08 | 2024-11-10 | 2024-11-10 | 2024-11-10 | 2024-11-16 | 2024-11-17 | 2024-11-22 | 2024-11-30 | 2024-08-24 | 2024-08-27 | 2024-09-03 | 2024-09-10 | 2024-09-14 | 2024-09-15 | 2024-09-21 | 2024-09-21 | 2024-09-22 | 2024-09-26 | 2024-09-27 | 2024-10-02 | 2024-10-02 | 2024-10-04 | 2024-10-06 | 2024-10-09 | 2024-10-09 | 2024-10-12 | 2024-10-15 | 2024-10-16 | 2024-10-17 | 2024-10-23 | 2024-10-27 | 2024-11-03 | 2024-11-03 | 2024-11-03 | 2024-11-08 | 2024-11-08 | 2024-11-10 | 2024-11-15 | 2024-11-23 | 2024-10-17 | 2024-11-03 | 2024-11-06 | 2024-11-28 | 2024-11-24 | 2024-11-30 | 2024-12-03 | 2024-12-08 | 2024-12-14
V_190 | 2024-06-06 | 2024-06-13 | 2024-06-15 | 2024-06-21 | 2024-06-26 | 2024-06-29 | 2024-06-30 | 2024-07-04 | [18 empty] | 2024-10-02 | 2024-10-06 | 2024-10-11 | 2024-10-18 | 2024-10-23 | 2024-10-27 | 2024-11-03 | 2024-11-03 | 2024-11-08 | 2024-11-10 | 2024-11-10 | 2024-11-10 | 2024-11-16 | 2024-11-17 | 2024-11-22 | 2024-11-30 | 2024-08-24 | 2024-08-27 | 2024-09-03 | 2024-09-10 | 2024-09-14 | 2024-09-15 | 2024-09-21 | 2024-09-21 | 2024-09-22 | 2024-09-26 | 2024-09-27 | 2024-10-02 | 2024-10-02 | 2024-10-04 | 2024-10-06 | 2024-10-09 | 2024-10-09 | 2024-10-12 | 2024-10-15 | 2024-10-16 | 2024-10-17 | 2024-10-23 | 2024-10-27 | 2024-11-03 | 2024-11-03 | 2024-11-03 | 2024-11-08 | 2024-11-08 | 2024-11-10 | 2024-11-15 | 2024-11-23 | 2024-10-17 | 2024-11-03 | 2024-11-06 | 2024-11-28 | 2024-11-24 | 2024-11-30 | 2024-12-03 | 2024-12-08 | 2024-12-14
V_191 | 2024-06-06 | 2024-06-13 | 2024-06-15 | 2024-06-21 | 2024-06-26 | 2024-06-29 | 2024-06-30 | 2024-07-04 | [18 empty] | 2024-10-02 | 2024-10-06 | 2024-10-11 | 2024-10-18 | 2024-10-23 | 2024-10-27 | 2024-11-03 | 2024-11-03 | 2024-11-08 | 2024-11-10 | 2024-11-10 | 2024-11-10 | 2024-11-16 | 2024-11-17 | 2024-11-22 | 2024-11-30 | 2024-08-24 | 2024-08-27 | 2024-09-03 | 2024-09-10 | 2024-09-14 | 2024-09-15 | 2024-09-21 | 2024-09-21 | 2024-09-22 | 2024-09-26 | 2024-09-27 | 2024-10-02 | 2024-10-02 | 2024-10-04 | 2024-10-06 | 2024-10-09 | 2024-10-09 | 2024-10-12 | 2024-10-15 | 2024-10-16 | 2024-10-17 | 2024-10-23 | 2024-10-27 | 2024-11-03 | 2024-11-03 | 2024-11-03 | 2024-11-08 | 2024-11-08 | 2024-11-10 | 2024-11-15 | 2024-11-23 | 2024-10-17 | 2024-11-03 | 2024-11-06 | 2024-11-28 | 2024-11-24 | 2024-11-30 | 2024-12-03 | 2024-12-08 | 2024-12-14
V_192 | 2024-06-06 | 2024-06-13 | 2024-06-15 | 2024-06-21 | 2024-06-26 | 2024-06-29 | 2024-06-30 | 2024-07-04 | [18 empty] | 2024-10-02 | 2024-10-06 | 2024-10-11 | 2024-10-18 | 2024-10-23 | 2024-10-27 | 2024-11-03 | 2024-11-03 | 2024-11-08 | 2024-11-10 | 2024-11-10 | 2024-11-10 | 2024-11-16 | 2024-11-17 | 2024-11-22 | 2024-11-30 | 2024-08-24 | 2024-08-27 | 2024-09-03 | 2024-09-10 | 2024-09-14 | 2024-09-15 | 2024-09-21 | 2024-09-21 | 2024-09-22 | 2024-09-26 | 2024-09-27 | 2024-10-02 | 2024-10-02 | 2024-10-04 | 2024-10-06 | 2024-10-09 | 2024-10-09 | 2024-10-12 | 2024-10-15 | 2024-10-16 | 2024-10-17 | 2024-10-23 | 2024-10-27 | 2024-11-03 | 2024-11-03 | 2024-11-03 | 2024-11-08 | 2024-11-08 | 2024-11-10 | 2024-11-15 | 2024-11-23 | 2024-10-17 | 2024-11-03 | 2024-11-06 | 2024-11-28 | 2024-11-24 | 2024-11-30 | 2024-12-03 | 2024-12-08 | 2024-12-14
V_193 | 2024-06-13 | 2024-06-20 | 2024-06-22 | 2024-06-28 | 2024-07-03 | 2024-07-06 | 2024-07-07 | 2024-07-11 | [18 empty] | 2024-10-10 | 2024-10-15 | 2024-10-19 | 2024-10-26 | 2024-10-31 | 2024-11-05 | 2024-11-12 | 2024-11-12 | 2024-11-16 | 2024-11-19 | 2024-11-19 | 2024-11-19 | 2024-11-24 | 2024-11-26 | 2024-11-30 | 2024-12-08 | 2024-09-01 | 2024-09-04 | 2024-09-11 | 2024-09-18 | 2024-09-22 | 2024-09-24 | 2024-09-29 | 2024-09-29 | 2024-10-01 | 2024-10-04 | 2024-10-05 | 2024-10-10 | 2024-10-10 | 2024-10-12 | 2024-10-15 | 2024-10-17 | 2024-10-17 | 2024-10-20 | 2024-10-23 | 2024-10-24 | 2024-10-25 | 2024-10-31 | 2024-11-05 | 2024-11-12 | 2024-11-12 | 2024-11-12 | 2024-11-16 | 2024-11-16 | 2024-11-19 | 2024-11-23 | 2024-12-01 | 2024-10-25 | 2024-11-12 | 2024-11-14 | 2024-12-06 | 2024-12-03 | 2024-12-08 | 2024-12-11 | 2024-12-17 | 2024-12-22
V_194 | 2024-06-13 | 2024-06-20 | 2024-06-22 | 2024-06-28 | 2024-07-03 | 2024-07-06 | 2024-07-07 | 2024-07-11 | [18 empty] | 2024-10-10 | 2024-10-15 | 2024-10-19 | 2024-10-26 | 2024-10-31 | 2024-11-05 | 2024-11-12 | 2024-11-12 | 2024-11-16 | 2024-11-19 | 2024-11-19 | 2024-11-19 | 2024-11-24 | 2024-11-26 | 2024-11-30 | 2024-12-08 | 2024-09-01 | 2024-09-04 | 2024-09-11 | 2024-09-18 | 2024-09-22 | 2024-09-24 | 2024-09-29 | 2024-09-29 | 2024-10-01 | 2024-10-04 | 2024-10-05 | 2024-10-10 | 2024-10-10 | 2024-10-12 | 2024-10-15 | 2024-10-17 | 2024-10-17 | 2024-10-20 | 2024-10-23 | 2024-10-24 | 2024-10-25 | 2024-10-31 | 2024-11-05 | 2024-11-12 | 2024-11-12 | 2024-11-12 | 2024-11-16 | 2024-11-16 | 2024-11-19 | 2024-11-23 | 2024-12-01 | 2024-10-25 | 2024-11-12 | 2024-11-14 | 2024-12-06 | 2024-12-03 | 2024-12-08 | 2024-12-11 | 2024-12-17 | 2024-12-22
V_195 | 2024-06-13 | 2024-06-20 | 2024-06-22 | 2024-06-28 | 2024-07-03 | 2024-07-06 | 2024-07-07 | 2024-07-11 | [18 empty] | 2024-10-10 | 2024-10-15 | 2024-10-19 | 2024-10-26 | 2024-10-31 | 2024-11-05 | 2024-11-12 | 2024-11-12 | 2024-11-16 | 2024-11-19 | 2024-11-19 | 2024-11-19 | 2024-11-24 | 2024-11-26 | 2024-11-30 | 2024-12-08 | 2024-09-01 | 2024-09-04 | 2024-09-11 | 2024-09-18 | 2024-09-22 | 2024-09-24 | 2024-09-29 | 2024-09-29 | 2024-10-01 | 2024-10-04 | 2024-10-05 | 2024-10-10 | 2024-10-10 | 2024-10-12 | 2024-10-15 | 2024-10-17 | 2024-10-17 | 2024-10-20 | 2024-10-23 | 2024-10-24 | 2024-10-25 | 2024-10-31 | 2024-11-05 | 2024-11-12 | 2024-11-12 | 2024-11-12 | 2024-11-16 | 2024-11-16 | 2024-11-19 | 2024-11-23 | 2024-12-01 | 2024-10-25 | 2024-11-12 | 2024-11-14 | 2024-12-06 | 2024-12-03 | 2024-12-08 | 2024-12-11 | 2024-12-17 | 2024-12-22
V_196 | 2024-06-13 | 2024-06-20 | 2024-06-22 | 2024-06-28 | 2024-07-03 | 2024-07-06 | 2024-07-07 | 2024-07-11 | [18 empty] | 2024-10-10 | 2024-10-15 | 2024-10-19 | 2024-10-26 | 2024-10-31 | 2024-11-05 | 2024-11-12 | 2024-11-12 | 2024-11-16 | 2024-11-19 | 2024-11-19 | 2024-11-19 | 2024-11-24 | 2024-11-26 | 2024-11-30 | 2024-12-08 | 2024-09-01 | 2024-09-04 | 2024-09-11 | 2024-09-18 | 2024-09-22 | 2024-09-24 | 2024-09-29 | 2024-09-29 | 2024-10-01 | 2024-10-04 | 2024-10-05 | 2024-10-10 | 2024-10-10 | 2024-10-12 | 2024-10-15 | 2024-10-17 | 2024-10-17 | 2024-10-20 | 2024-10-23 | 2024-10-24 | 2024-10-25 | 2024-10-31 | 2024-11-05 | 2024-11-12 | 2024-11-12 | 2024-11-12 | 2024-11-16 | 2024-11-16 | 2024-11-19 | 2024-11-23 | 2024-12-01 | 2024-10-25 | 2024-11-12 | 2024-11-14 | 2024-12-06 | 2024-12-03 | 2024-12-08 | 2024-12-11 | 2024-12-17 | 2024-12-22
V_197 | 2024-06-13 | 2024-06-20 | 2024-06-22 | 2024-06-28 | 2024-07-03 | 2024-07-06 | 2024-07-07 | 2024-07-11 | [18 empty] | 2024-10-10 | 2024-10-15 | 2024-10-19 | 2024-10-26 | 2024-10-31 | 2024-11-05 | 2024-11-12 | 2024-11-12 | 2024-11-16 | 2024-11-19 | 2024-11-19 | 2024-11-19 | 2024-11-24 | 2024-11-26 | 2024-11-30 | 2024-12-08 | 2024-09-01 | 2024-09-04 | 2024-09-11 | 2024-09-18 | 2024-09-22 | 2024-09-24 | 2024-09-29 | 2024-09-29 | 2024-10-01 | 2024-10-04 | 2024-10-05 | 2024-10-10 | 2024-10-10 | 2024-10-12 | 2024-10-15 | 2024-10-17 | 2024-10-17 | 2024-10-20 | 2024-10-23 | 2024-10-24 | 2024-10-25 | 2024-10-31 | 2024-11-05 | 2024-11-12 | 2024-11-12 | 2024-11-12 | 2024-11-16 | 2024-11-16 | 2024-11-19 | 2024-11-23 | 2024-12-01 | 2024-10-25 | 2024-11-12 | 2024-11-14 | 2024-12-06 | 2024-12-03 | 2024-12-08 | 2024-12-11 | 2024-12-17 | 2024-12-22
V_198 | 2024-06-13 | 2024-06-20 | 2024-06-22 | 2024-06-28 | 2024-07-03 | 2024-07-06 | 2024-07-07 | 2024-07-11 | [18 empty] | 2024-10-10 | 2024-10-15 | 2024-10-19 | 2024-10-26 | 2024-10-31 | 2024-11-05 | 2024-11-12 | 2024-11-12 | 2024-11-16 | 2024-11-19 | 2024-11-19 | 2024-11-19 | 2024-11-24 | 2024-11-26 | 2024-11-30 | 2024-12-08 | 2024-09-01 | 2024-09-04 | 2024-09-11 | 2024-09-18 | 2024-09-22 | 2024-09-24 | 2024-09-29 | 2024-09-29 | 2024-10-01 | 2024-10-04 | 2024-10-05 | 2024-10-10 | 2024-10-10 | 2024-10-12 | 2024-10-15 | 2024-10-17 | 2024-10-17 | 2024-10-20 | 2024-10-23 | 2024-10-24 | 2024-10-25 | 2024-10-31 | 2024-11-05 | 2024-11-12 | 2024-11-12 | 2024-11-12 | 2024-11-16 | 2024-11-16 | 2024-11-19 | 2024-11-23 | 2024-12-01 | 2024-10-25 | 2024-11-12 | 2024-11-14 | 2024-12-06 | 2024-12-03 | 2024-12-08 | 2024-12-11 | 2024-12-17 | 2024-12-22
V_199 | 2024-06-13 | 2024-06-20 | 2024-06-22 | 2024-06-28 | 2024-07-03 | 2024-07-06 | 2024-07-07 | 2024-07-11 | [18 empty] | 2024-10-10 | 2024-10-15 | 2024-10-19 | 2024-10-26 | 2024-10-31 | 2024-11-05 | 2024-11-12 | 2024-11-12 | 2024-11-16 | 2024-11-19 | 2024-11-19 | 2024-11-19 | 2024-11-24 | 2024-11-26 | 2024-11-30 | 2024-12-08 | 2024-09-01 | 2024-09-04 | 2024-09-11 | 2024-09-18 | 2024-09-22 | 2024-09-24 | 2024-09-29 | 2024-09-29 | 2024-10-01 | 2024-10-04 | 2024-10-05 | 2024-10-10 | 2024-10-10 | 2024-10-12 | 2024-10-15 | 2024-10-17 | 2024-10-17 | 2024-10-20 | 2024-10-23 | 2024-10-24 | 2024-10-25 | 2024-10-31 | 2024-11-05 | 2024-11-12 | 2024-11-12 | 2024-11-12 | 2024-11-16 | 2024-11-16 | 2024-11-19 | 2024-11-23 | 2024-12-01 | 2024-10-25 | 2024-11-12 | 2024-11-14 | 2024-12-06 | 2024-12-03 | 2024-12-08 | 2024-12-11 | 2024-12-17 | 2024-12-22
V_200 | 2024-06-13 | 2024-06-20 | 2024-06-22 | 2024-06-28 | 2024-07-03 | 2024-07-06 | 2024-07-07 | 2024-07-11 | [18 empty] | 2024-10-10 | 2024-10-15 | 2024-10-19 | 2024-10-26 | 2024-10-31 | 2024-11-05 | 2024-11-12 | 2024-11-12 | 2024-11-16 | 2024-11-19 | 2024-11-19 | 2024-11-19 | 2024-11-24 | 2024-11-26 | 2024-11-30 | 2024-12-08 | 2024-09-01 | 2024-09-04 | 2024-09-11 | 2024-09-18 | 2024-09-22 | 2024-09-24 | 2024-09-29 | 2024-09-29 | 2024-10-01 | 2024-10-04 | 2024-10-05 | 2024-10-10 | 2024-10-10 | 2024-10-12 | 2024-10-15 | 2024-10-17 | 2024-10-17 | 2024-10-20 | 2024-10-23 | 2024-10-24 | 2024-10-25 | 2024-10-31 | 2024-11-05 | 2024-11-12 | 2024-11-12 | 2024-11-12 | 2024-11-16 | 2024-11-16 | 2024-11-19 | 2024-11-23 | 2024-12-01 | 2024-10-25 | 2024-11-12 | 2024-11-14 | 2024-12-06 | 2024-12-03 | 2024-12-08 | 2024-12-11 | 2024-12-17 | 2024-12-22
V_201 | 2024-06-20 | 2024-06-27 | 2024-06-29 | 2024-07-05 | 2024-07-10 | 2024-07-13 | 2024-07-14 | 2024-07-18 | [18 empty] | 2024-10-18 | 2024-10-23 | 2024-10-27 | 2024-11-03 | 2024-11-08 | 2024-11-13 | 2024-11-20 | 2024-11-20 | 2024-11-24 | 2024-11-27 | 2024-11-27 | 2024-11-27 | 2024-12-03 | 2024-12-04 | 2024-12-08 | 2024-12-17 | 2024-09-10 | 2024-09-12 | 2024-09-19 | 2024-09-26 | 2024-10-01 | 2024-10-02 | 2024-10-08 | 2024-10-08 | 2024-10-09 | 2024-10-12 | 2024-10-13 | 2024-10-18 | 2024-10-18 | 2024-10-20 | 2024-10-23 | 2024-10-25 | 2024-10-25 | 2024-10-29 | 2024-10-31 | 2024-11-01 | 2024-11-02 | 2024-11-08 | 2024-11-13 | 2024-11-20 | 2024-11-20 | 2024-11-20 | 2024-11-24 | 2024-11-24 | 2024-11-27 | 2024-12-01 | 2024-12-10 | 2024-11-02 | 2024-11-20 | 2024-11-22 | 2024-12-14 | 2024-12-11 | 2024-12-17 | 2024-12-19 | 2024-12-25 | 2024-12-31
V_202 | 2024-06-20 | 2024-06-27 | 2024-06-29 | 2024-07-05 | 2024-07-10 | 2024-07-13 | 2024-07-14 | 2024-07-18 | [18 empty] | 2024-10-18 | 2024-10-23 | 2024-10-27 | 2024-11-03 | 2024-11-08 | 2024-11-13 | 2024-11-20 | 2024-11-20 | 2024-11-24 | 2024-11-27 | 2024-11-27 | 2024-11-27 | 2024-12-03 | 2024-12-04 | 2024-12-08 | 2024-12-17 | 2024-09-10 | 2024-09-12 | 2024-09-19 | 2024-09-26 | 2024-10-01 | 2024-10-02 | 2024-10-08 | 2024-10-08 | 2024-10-09 | 2024-10-12 | 2024-10-13 | 2024-10-18 | 2024-10-18 | 2024-10-20 | 2024-10-23 | 2024-10-25 | 2024-10-25 | 2024-10-29 | 2024-10-31 | 2024-11-01 | 2024-11-02 | 2024-11-08 | 2024-11-13 | 2024-11-20 | 2024-11-20 | 2024-11-20 | 2024-11-24 | 2024-11-24 | 2024-11-27 | 2024-12-01 | 2024-12-10 | 2024-11-02 | 2024-11-20 | 2024-11-22 | 2024-12-14 | 2024-12-11 | 2024-12-17 | 2024-12-19 | 2024-12-25 | 2024-12-31
V_203 | 2024-06-20 | 2024-06-27 | 2024-06-29 | 2024-07-05 | 2024-07-10 | 2024-07-13 | 2024-07-14 | 2024-07-18 | [18 empty] | 2024-10-18 | 2024-10-23 | 2024-10-27 | 2024-11-03 | 2024-11-08 | 2024-11-13 | 2024-11-20 | 2024-11-20 | 2024-11-24 | 2024-11-27 | 2024-11-27 | 2024-11-27 | 2024-12-03 | 2024-12-04 | 2024-12-08 | 2024-12-17 | 2024-09-10 | 2024-09-12 | 2024-09-19 | 2024-09-26 | 2024-10-01 | 2024-10-02 | 2024-10-08 | 2024-10-08 | 2024-10-09 | 2024-10-12 | 2024-10-13 | 2024-10-18 | 2024-10-18 | 2024-10-20 | 2024-10-23 | 2024-10-25 | 2024-10-25 | 2024-10-29 | 2024-10-31 | 2024-11-01 | 2024-11-02 | 2024-11-08 | 2024-11-13 | 2024-11-20 | 2024-11-20 | 2024-11-20 | 2024-11-24 | 2024-11-24 | 2024-11-27 | 2024-12-01 | 2024-12-10 | 2024-11-02 | 2024-11-20 | 2024-11-22 | 2024-12-14 | 2024-12-11 | 2024-12-17 | 2024-12-19 | 2024-12-25 | 2024-12-31
V_204 | 2024-06-20 | 2024-06-27 | 2024-06-29 | 2024-07-05 | 2024-07-10 | 2024-07-13 | 2024-07-14 | 2024-07-18 | [18 empty] | 2024-10-18 | 2024-10-23 | 2024-10-27 | 2024-11-03 | 2024-11-08 | 2024-11-13 | 2024-11-20 | 2024-11-20 | 2024-11-24 | 2024-11-27 | 2024-11-27 | 2024-11-27 | 2024-12-03 | 2024-12-04 | 2024-12-08 | 2024-12-17 | 2024-09-10 | 2024-09-12 | 2024-09-19 | 2024-09-26 | 2024-10-01 | 2024-10-02 | 2024-10-08 | 2024-10-08 | 2024-10-09 | 2024-10-12 | 2024-10-13 | 2024-10-18 | 2024-10-18 | 2024-10-20 | 2024-10-23 | 2024-10-25 | 2024-10-25 | 2024-10-29 | 2024-10-31 | 2024-11-01 | 2024-11-02 | 2024-11-08 | 2024-11-13 | 2024-11-20 | 2024-11-20 | 2024-11-20 | 2024-11-24 | 2024-11-24 | 2024-11-27 | 2024-12-01 | 2024-12-10 | 2024-11-02 | 2024-11-20 | 2024-11-22 | 2024-12-14 | 2024-12-11 | 2024-12-17 | 2024-12-19 | 2024-12-25 | 2024-12-31
V_205 | 2024-06-20 | 2024-06-27 | 2024-06-29 | 2024-07-05 | 2024-07-10 | 2024-07-13 | 2024-07-14 | 2024-07-18 | [18 empty] | 2024-10-18 | 2024-10-23 | 2024-10-27 | 2024-11-03 | 2024-11-08 | 2024-11-13 | 2024-11-20 | 2024-11-20 | 2024-11-24 | 2024-11-27 | 2024-11-27 | 2024-11-27 | 2024-12-03 | 2024-12-04 | 2024-12-08 | 2024-12-17 | 2024-09-10 | 2024-09-12 | 2024-09-19 | 2024-09-26 | 2024-10-01 | 2024-10-02 | 2024-10-08 | 2024-10-08 | 2024-10-09 | 2024-10-12 | 2024-10-13 | 2024-10-18 | 2024-10-18 | 2024-10-20 | 2024-10-23 | 2024-10-25 | 2024-10-25 | 2024-10-29 | 2024-10-31 | 2024-11-01 | 2024-11-02 | 2024-11-08 | 2024-11-13 | 2024-11-20 | 2024-11-20 | 2024-11-20 | 2024-11-24 | 2024-11-24 | 2024-11-27 | 2024-12-01 | 2024-12-10 | 2024-11-02 | 2024-11-20 | 2024-11-22 | 2024-12-14 | 2024-12-11 | 2024-12-17 | 2024-12-19 | 2024-12-25 | 2024-12-31
V_206 | 2024-06-20 | 2024-06-27 | 2024-06-29 | 2024-07-05 | 2024-07-10 | 2024-07-13 | 2024-07-14 | 2024-07-18 | [18 empty] | 2024-10-18 | 2024-10-23 | 2024-10-27 | 2024-11-03 | 2024-11-08 | 2024-11-13 | 2024-11-20 | 2024-11-20 | 2024-11-24 | 2024-11-27 | 2024-11-27 | 2024-11-27 | 2024-12-03 | 2024-12-04 | 2024-12-08 | 2024-12-17 | 2024-09-10 | 2024-09-12 | 2024-09-19 | 2024-09-26 | 2024-10-01 | 2024-10-02 | 2024-10-08 | 2024-10-08 | 2024-10-09 | 2024-10-12 | 2024-10-13 | 2024-10-18 | 2024-10-18 | 2024-10-20 | 2024-10-23 | 2024-10-25 | 2024-10-25 | 2024-10-29 | 2024-10-31 | 2024-11-01 | 2024-11-02 | 2024-11-08 | 2024-11-13 | 2024-11-20 | 2024-11-20 | 2024-11-20 | 2024-11-24 | 2024-11-24 | 2024-11-27 | 2024-12-01 | 2024-12-10 | 2024-11-02 | 2024-11-20 | 2024-11-22 | 2024-12-14 | 2024-12-11 | 2024-12-17 | 2024-12-19 | 2024-12-25 | 2024-12-31
V_207 | 2024-06-20 | 2024-06-27 | 2024-06-29 | 2024-07-05 | 2024-07-10 | 2024-07-13 | 2024-07-14 | 2024-07-18 | [18 empty] | 2024-10-18 | 2024-10-23 | 2024-10-27 | 2024-11-03 | 2024-11-08 | 2024-11-13 | 2024-11-20 | 2024-11-20 | 2024-11-24 | 2024-11-27 | 2024-11-27 | 2024-11-27 | 2024-12-03 | 2024-12-04 | 2024-12-08 | 2024-12-17 | 2024-09-10 | 2024-09-12 | 2024-09-19 | 2024-09-26 | 2024-10-01 | 2024-10-02 | 2024-10-08 | 2024-10-08 | 2024-10-09 | 2024-10-12 | 2024-10-13 | 2024-10-18 | 2024-10-18 | 2024-10-20 | 2024-10-23 | 2024-10-25 | 2024-10-25 | 2024-10-29 | 2024-10-31 | 2024-11-01 | 2024-11-02 | 2024-11-08 | 2024-11-13 | 2024-11-20 | 2024-11-20 | 2024-11-20 | 2024-11-24 | 2024-11-24 | 2024-11-27 | 2024-12-01 | 2024-12-10 | 2024-11-02 | 2024-11-20 | 2024-11-22 | 2024-12-14 | 2024-12-11 | 2024-12-17 | 2024-12-19 | 2024-12-25 | 2024-12-31
V_208 | 2024-06-20 | 2024-06-27 | 2024-06-29 | 2024-07-05 | 2024-07-10 | 2024-07-13 | 2024-07-14 | 2024-07-18 | [18 empty] | 2024-10-18 | 2024-10-23 | 2024-10-27 | 2024-11-03 | 2024-11-08 | 2024-11-13 | 2024-11-20 | 2024-11-20 | 2024-11-24 | 2024-11-27 | 2024-11-27 | 2024-11-27 | 2024-12-03 | 2024-12-04 | 2024-12-08 | 2024-12-17 | 2024-09-10 | 2024-09-12 | 2024-09-19 | 2024-09-26 | 2024-10-01 | 2024-10-02 | 2024-10-08 | 2024-10-08 | 2024-10-09 | 2024-10-12 | 2024-10-13 | 2024-10-18 | 2024-10-18 | 2024-10-20 | 2024-10-23 | 2024-10-25 | 2024-10-25 | 2024-10-29 | 2024-10-31 | 2024-11-01 | 2024-11-02 | 2024-11-08 | 2024-11-13 | 2024-11-20 | 2024-11-20 | 2024-11-20 | 2024-11-24 | 2024-11-24 | 2024-11-27 | 2024-12-01 | 2024-12-10 | 2024-11-02 | 2024-11-20 | 2024-11-22 | 2024-12-14 | 2024-12-11 | 2024-12-17 | 2024-12-19 | 2024-12-25 | 2024-12-31
V_209 | 2024-06-27 | 2024-07-04 | 2024-07-06 | 2024-07-12 | 2024-07-17 | 2024-07-20 | 2024-07-21 | 2024-07-25 | [18 empty] | 2024-10-26 | 2024-10-31 | 2024-11-05 | 2024-11-12 | 2024-11-16 | 2024-11-21 | 2024-11-28 | 2024-11-28 | 2024-12-03 | 2024-12-05 | 2024-12-05 | 2024-12-05 | 2024-12-11 | 2024-12-12 | 2024-12-17 | 2024-12-25 | 2024-09-18 | 2024-09-20 | 2024-09-27 | 2024-10-04 | 2024-10-09 | 2024-10-10 | 2024-10-16 | 2024-10-16 | 2024-10-17 | 2024-10-20 | 2024-10-22 | 2024-10-26 | 2024-10-26 | 2024-10-29 | 2024-10-31 | 2024-11-02 | 2024-11-02 | 2024-11-06 | 2024-11-08 | 2024-11-09 | 2024-11-10 | 2024-11-16 | 2024-11-21 | 2024-11-28 | 2024-11-28 | 2024-11-28 | 2024-12-03 | 2024-12-03 | 2024-12-05 | 2024-12-10 | 2024-12-18 | 2024-11-10 | 2024-11-28 | 2024-11-30 | 2024-12-22 | 2024-12-19 | 2024-12-25 | 2024-12-27 | 2025-01-02 | 2025-01-08
V_210 | 2024-06-27 | 2024-07-04 | 2024-07-06 | 2024-07-12 | 2024-07-17 | 2024-07-20 | 2024-07-21 | 2024-07-25 | [18 empty] | 2024-10-26 | 2024-10-31 | 2024-11-05 | 2024-11-12 | 2024-11-16 | 2024-11-21 | 2024-11-28 | 2024-11-28 | 2024-12-03 | 2024-12-05 | 2024-12-05 | 2024-12-05 | 2024-12-11 | 2024-12-12 | 2024-12-17 | 2024-12-25 | 2024-09-18 | 2024-09-20 | 2024-09-27 | 2024-10-04 | 2024-10-09 | 2024-10-10 | 2024-10-16 | 2024-10-16 | 2024-10-17 | 2024-10-20 | 2024-10-22 | 2024-10-26 | 2024-10-26 | 2024-10-29 | 2024-10-31 | 2024-11-02 | 2024-11-02 | 2024-11-06 | 2024-11-08 | 2024-11-09 | 2024-11-10 | 2024-11-16 | 2024-11-21 | 2024-11-28 | 2024-11-28 | 2024-11-28 | 2024-12-03 | 2024-12-03 | 2024-12-05 | 2024-12-10 | 2024-12-18 | 2024-11-10 | 2024-11-28 | 2024-11-30 | 2024-12-22 | 2024-12-19 | 2024-12-25 | 2024-12-27 | 2025-01-02 | 2025-01-08
V_211 | 2024-06-27 | 2024-07-04 | 2024-07-06 | 2024-07-12 | 2024-07-17 | 2024-07-20 | 2024-07-21 | 2024-07-25 | [18 empty] | 2024-10-26 | 2024-10-31 | 2024-11-05 | 2024-11-12 | 2024-11-16 | 2024-11-21 | 2024-11-28 | 2024-11-28 | 2024-12-03 | 2024-12-05 | 2024-12-05 | 2024-12-05 | 2024-12-11 | 2024-12-12 | 2024-12-17 | 2024-12-25 | 2024-09-18 | 2024-09-20 | 2024-09-27 | 2024-10-04 | 2024-10-09 | 2024-10-10 | 2024-10-16 | 2024-10-16 | 2024-10-17 | 2024-10-20 | 2024-10-22 | 2024-10-26 | 2024-10-26 | 2024-10-29 | 2024-10-31 | 2024-11-02 | 2024-11-02 | 2024-11-06 | 2024-11-08 | 2024-11-09 | 2024-11-10 | 2024-11-16 | 2024-11-21 | 2024-11-28 | 2024-11-28 | 2024-11-28 | 2024-12-03 | 2024-12-03 | 2024-12-05 | 2024-12-10 | 2024-12-18 | 2024-11-10 | 2024-11-28 | 2024-11-30 | 2024-12-22 | 2024-12-19 | 2024-12-25 | 2024-12-27 | 2025-01-02 | 2025-01-08
V_212 | 2024-06-27 | 2024-07-04 | 2024-07-06 | 2024-07-12 | 2024-07-17 | 2024-07-20 | 2024-07-21 | 2024-07-25 | [18 empty] | 2024-10-26 | 2024-10-31 | 2024-11-05 | 2024-11-12 | 2024-11-16 | 2024-11-21 | 2024-11-28 | 2024-11-28 | 2024-12-03 | 2024-12-05 | 2024-12-05 | 2024-12-05 | 2024-12-11 | 2024-12-12 | 2024-12-17 | 2024-12-25 | 2024-09-18 | 2024-09-20 | 2024-09-27 | 2024-10-04 | 2024-10-09 | 2024-10-10 | 2024-10-16 | 2024-10-16 | 2024-10-17 | 2024-10-20 | 2024-10-22 | 2024-10-26 | 2024-10-26 | 2024-10-29 | 2024-10-31 | 2024-11-02 | 2024-11-02 | 2024-11-06 | 2024-11-08 | 2024-11-09 | 2024-11-10 | 2024-11-16 | 2024-11-21 | 2024-11-28 | 2024-11-28 | 2024-11-28 | 2024-12-03 | 2024-12-03 | 2024-12-05 | 2024-12-10 | 2024-12-18 | 2024-11-10 | 2024-11-28 | 2024-11-30 | 2024-12-22 | 2024-12-19 | 2024-12-25 | 2024-12-27 | 2025-01-02 | 2025-01-08
V_213 | 2024-06-27 | 2024-07-04 | 2024-07-06 | 2024-07-12 | 2024-07-17 | 2024-07-20 | 2024-07-21 | 2024-07-25 | [18 empty] | 2024-10-26 | 2024-10-31 | 2024-11-05 | 2024-11-12 | 2024-11-16 | 2024-11-21 | 2024-11-28 | 2024-11-28 | 2024-12-03 | 2024-12-05 | 2024-12-05 | 2024-12-05 | 2024-12-11 | 2024-12-12 | 2024-12-17 | 2024-12-25 | 2024-09-18 | 2024-09-20 | 2024-09-27 | 2024-10-04 | 2024-10-09 | 2024-10-10 | 2024-10-16 | 2024-10-16 | 2024-10-17 | 2024-10-20 | 2024-10-22 | 2024-10-26 | 2024-10-26 | 2024-10-29 | 2024-10-31 | 2024-11-02 | 2024-11-02 | 2024-11-06 | 2024-11-08 | 2024-11-09 | 2024-11-10 | 2024-11-16 | 2024-11-21 | 2024-11-28 | 2024-11-28 | 2024-11-28 | 2024-12-03 | 2024-12-03 | 2024-12-05 | 2024-12-10 | 2024-12-18 | 2024-11-10 | 2024-11-28 | 2024-11-30 | 2024-12-22 | 2024-12-19 | 2024-12-25 | 2024-12-27 | 2025-01-02 | 2025-01-08
V_214 | 2024-06-27 | 2024-07-04 | 2024-07-06 | 2024-07-12 | 2024-07-17 | 2024-07-20 | 2024-07-21 | 2024-07-25 | [18 empty] | 2024-10-26 | 2024-10-31 | 2024-11-05 | 2024-11-12 | 2024-11-16 | 2024-11-21 | 2024-11-28 | 2024-11-28 | 2024-12-03 | 2024-12-05 | 2024-12-05 | 2024-12-05 | 2024-12-11 | 2024-12-12 | 2024-12-17 | 2024-12-25 | 2024-09-18 | 2024-09-20 | 2024-09-27 | 2024-10-04 | 2024-10-09 | 2024-10-10 | 2024-10-16 | 2024-10-16 | 2024-10-17 | 2024-10-20 | 2024-10-22 | 2024-10-26 | 2024-10-26 | 2024-10-29 | 2024-10-31 | 2024-11-02 | 2024-11-02 | 2024-11-06 | 2024-11-08 | 2024-11-09 | 2024-11-10 | 2024-11-16 | 2024-11-21 | 2024-11-28 | 2024-11-28 | 2024-11-28 | 2024-12-03 | 2024-12-03 | 2024-12-05 | 2024-12-10 | 2024-12-18 | 2024-11-10 | 2024-11-28 | 2024-11-30 | 2024-12-22 | 2024-12-19 | 2024-12-25 | 2024-12-27 | 2025-01-02 | 2025-01-08
V_215 | 2024-06-27 | 2024-07-04 | 2024-07-06 | 2024-07-12 | 2024-07-17 | 2024-07-20 | 2024-07-21 | 2024-07-25 | [18 empty] | 2024-10-26 | 2024-10-31 | 2024-11-05 | 2024-11-12 | 2024-11-16 | 2024-11-21 | 2024-11-28 | 2024-11-28 | 2024-12-03 | 2024-12-05 | 2024-12-05 | 2024-12-05 | 2024-12-11 | 2024-12-12 | 2024-12-17 | 2024-12-25 | 2024-09-18 | 2024-09-20 | 2024-09-27 | 2024-10-04 | 2024-10-09 | 2024-10-10 | 2024-10-16 | 2024-10-16 | 2024-10-17 | 2024-10-20 | 2024-10-22 | 2024-10-26 | 2024-10-26 | 2024-10-29 | 2024-10-31 | 2024-11-02 | 2024-11-02 | 2024-11-06 | 2024-11-08 | 2024-11-09 | 2024-11-10 | 2024-11-16 | 2024-11-21 | 2024-11-28 | 2024-11-28 | 2024-11-28 | 2024-12-03 | 2024-12-03 | 2024-12-05 | 2024-12-10 | 2024-12-18 | 2024-11-10 | 2024-11-28 | 2024-11-30 | 2024-12-22 | 2024-12-19 | 2024-12-25 | 2024-12-27 | 2025-01-02 | 2025-01-08
V_216 | 2024-06-27 | 2024-07-04 | 2024-07-06 | 2024-07-12 | 2024-07-17 | 2024-07-20 | 2024-07-21 | 2024-07-25 | [18 empty] | 2024-10-26 | 2024-10-31 | 2024-11-05 | 2024-11-12 | 2024-11-16 | 2024-11-21 | 2024-11-28 | 2024-11-28 | 2024-12-03 | 2024-12-05 | 2024-12-05 | 2024-12-05 | 2024-12-11 | 2024-12-12 | 2024-12-17 | 2024-12-25 | 2024-09-18 | 2024-09-20 | 2024-09-27 | 2024-10-04 | 2024-10-09 | 2024-10-10 | 2024-10-16 | 2024-10-16 | 2024-10-17 | 2024-10-20 | 2024-10-22 | 2024-10-26 | 2024-10-26 | 2024-10-29 | 2024-10-31 | 2024-11-02 | 2024-11-02 | 2024-11-06 | 2024-11-08 | 2024-11-09 | 2024-11-10 | 2024-11-16 | 2024-11-21 | 2024-11-28 | 2024-11-28 | 2024-11-28 | 2024-12-03 | 2024-12-03 | 2024-12-05 | 2024-12-10 | 2024-12-18 | 2024-11-10 | 2024-11-28 | 2024-11-30 | 2024-12-22 | 2024-12-19 | 2024-12-25 | 2024-12-27 | 2025-01-02 | 2025-01-08
V_217 | 2024-07-04 | 2024-07-11 | 2024-07-13 | 2024-07-19 | 2024-07-24 | 2024-07-27 | 2024-07-28 | 2024-08-01 | 2024-08-06 | 2024-08-09 | 2024-08-13 | 2024-08-13 | 2024-09-18 | 2024-09-26 | 2024-10-03 | 2024-10-03 | 2024-10-10 | 2024-10-17 | 2024-10-17 | 2024-10-20 | 2024-10-20 | 2024-10-22 | 2024-10-27 | 2024-10-27 | 2024-11-03 | 2024-11-03 | 2024-11-03 | 2024-11-08 | 2024-11-13 | 2024-11-20 | 2024-11-24 | 2024-11-29 | 2024-12-06 | 2024-12-06 | 2024-12-11 | 2024-12-13 | 2024-12-13 | 2024-12-13 | 2024-12-19 | 2024-12-20 | 2024-12-25 | 2025-01-02 | 2024-09-26 | 2024-09-28 | 2024-10-05 | 2024-10-12 | 2024-10-17 | 2024-10-18 | 2024-10-24 | 2024-10-24 | 2024-10-25 | 2024-10-29 | 2024-10-30 | 2024-11-03 | 2024-11-03 | 2024-11-06 | 2024-11-08 | 2024-11-10 | 2024-11-10 | 2024-11-14 | 2024-11-16 | 2024-11-17 | 2024-11-19 | 2024-11-24 | 2024-11-29 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-11 | 2024-12-11 | 2024-12-13 | 2024-12-18 | 2024-12-26 | 2024-11-19 | 2024-12-06 | 2024-12-08 | 2024-12-31 | 2024-12-27 | 2025-01-02 | 2025-01-04 | 2025-01-10 | 2025-01-16
V_218 | 2024-07-04 | 2024-07-11 | 2024-07-13 | 2024-07-19 | 2024-07-24 | 2024-07-27 | 2024-07-28 | 2024-08-01 | 2024-08-06 | 2024-08-09 | 2024-08-13 | 2024-08-13 | 2024-09-18 | 2024-09-26 | 2024-10-03 | 2024-10-03 | 2024-10-10 | 2024-10-17 | 2024-10-17 | 2024-10-20 | 2024-10-20 | 2024-10-22 | 2024-10-27 | 2024-10-27 | 2024-11-03 | 2024-11-03 | 2024-11-03 | 2024-11-08 | 2024-11-13 | 2024-11-20 | 2024-11-24 | 2024-11-29 | 2024-12-06 | 2024-12-06 | 2024-12-11 | 2024-12-13 | 2024-12-13 | 2024-12-13 | 2024-12-19 | 2024-12-20 | 2024-12-25 | 2025-01-02 | 2024-09-26 | 2024-09-28 | 2024-10-05 | 2024-10-12 | 2024-10-17 | 2024-10-18 | 2024-10-24 | 2024-10-24 | 2024-10-25 | 2024-10-29 | 2024-10-30 | 2024-11-03 | 2024-11-03 | 2024-11-06 | 2024-11-08 | 2024-11-10 | 2024-11-10 | 2024-11-14 | 2024-11-16 | 2024-11-17 | 2024-11-19 | 2024-11-24 | 2024-11-29 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-11 | 2024-12-11 | 2024-12-13 | 2024-12-18 | 2024-12-26 | 2024-11-19 | 2024-12-06 | 2024-12-08 | 2024-12-31 | 2024-12-27 | 2025-01-02 | 2025-01-04 | 2025-01-10 | 2025-01-16
V_219 | 2024-07-04 | 2024-07-11 | 2024-07-13 | 2024-07-19 | 2024-07-24 | 2024-07-27 | 2024-07-28 | 2024-08-01 | 2024-08-06 | 2024-08-09 | 2024-08-13 | 2024-08-13 | 2024-09-18 | 2024-09-26 | 2024-10-03 | 2024-10-03 | 2024-10-10 | 2024-10-17 | 2024-10-17 | 2024-10-20 | 2024-10-20 | 2024-10-22 | 2024-10-27 | 2024-10-27 | 2024-11-03 | 2024-11-03 | 2024-11-03 | 2024-11-08 | 2024-11-13 | 2024-11-20 | 2024-11-24 | 2024-11-29 | 2024-12-06 | 2024-12-06 | 2024-12-11 | 2024-12-13 | 2024-12-13 | 2024-12-13 | 2024-12-19 | 2024-12-20 | 2024-12-25 | 2025-01-02 | 2024-09-26 | 2024-09-28 | 2024-10-05 | 2024-10-12 | 2024-10-17 | 2024-10-18 | 2024-10-24 | 2024-10-24 | 2024-10-25 | 2024-10-29 | 2024-10-30 | 2024-11-03 | 2024-11-03 | 2024-11-06 | 2024-11-08 | 2024-11-10 | 2024-11-10 | 2024-11-14 | 2024-11-16 | 2024-11-17 | 2024-11-19 | 2024-11-24 | 2024-11-29 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-11 | 2024-12-11 | 2024-12-13 | 2024-12-18 | 2024-12-26 | 2024-11-19 | 2024-12-06 | 2024-12-08 | 2024-12-31 | 2024-12-27 | 2025-01-02 | 2025-01-04 | 2025-01-10 | 2025-01-16
V_220 | 2024-07-04 | 2024-07-11 | 2024-07-13 | 2024-07-19 | 2024-07-24 | 2024-07-27 | 2024-07-28 | 2024-08-01 | 2024-08-06 | 2024-08-09 | 2024-08-13 | 2024-08-13 | 2024-09-18 | 2024-09-26 | 2024-10-03 | 2024-10-03 | 2024-10-10 | 2024-10-17 | 2024-10-17 | 2024-10-20 | 2024-10-20 | 2024-10-22 | 2024-10-27 | 2024-10-27 | 2024-11-03 | 2024-11-03 | 2024-11-03 | 2024-11-08 | 2024-11-13 | 2024-11-20 | 2024-11-24 | 2024-11-29 | 2024-12-06 | 2024-12-06 | 2024-12-11 | 2024-12-13 | 2024-12-13 | 2024-12-13 | 2024-12-19 | 2024-12-20 | 2024-12-25 | 2025-01-02 | 2024-09-26 | 2024-09-28 | 2024-10-05 | 2024-10-12 | 2024-10-17 | 2024-10-18 | 2024-10-24 | 2024-10-24 | 2024-10-25 | 2024-10-29 | 2024-10-30 | 2024-11-03 | 2024-11-03 | 2024-11-06 | 2024-11-08 | 2024-11-10 | 2024-11-10 | 2024-11-14 | 2024-11-16 | 2024-11-17 | 2024-11-19 | 2024-11-24 | 2024-11-29 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-11 | 2024-12-11 | 2024-12-13 | 2024-12-18 | 2024-12-26 | 2024-11-19 | 2024-12-06 | 2024-12-08 | 2024-12-31 | 2024-12-27 | 2025-01-02 | 2025-01-04 | 2025-01-10 | 2025-01-16
V_221 | 2024-07-04 | 2024-07-11 | 2024-07-13 | 2024-07-19 | 2024-07-24 | 2024-07-27 | 2024-07-28 | 2024-08-01 | 2024-08-06 | 2024-08-09 | 2024-08-13 | 2024-08-13 | 2024-09-18 | 2024-09-26 | 2024-10-03 | 2024-10-03 | 2024-10-10 | 2024-10-17 | 2024-10-17 | 2024-10-20 | 2024-10-20 | 2024-10-22 | 2024-10-27 | 2024-10-27 | 2024-11-03 | 2024-11-03 | 2024-11-03 | 2024-11-08 | 2024-11-13 | 2024-11-20 | 2024-11-24 | 2024-11-29 | 2024-12-06 | 2024-12-06 | 2024-12-11 | 2024-12-13 | 2024-12-13 | 2024-12-13 | 2024-12-19 | 2024-12-20 | 2024-12-25 | 2025-01-02 | 2024-09-26 | 2024-09-28 | 2024-10-05 | 2024-10-12 | 2024-10-17 | 2024-10-18 | 2024-10-24 | 2024-10-24 | 2024-10-25 | 2024-10-29 | 2024-10-30 | 2024-11-03 | 2024-11-03 | 2024-11-06 | 2024-11-08 | 2024-11-10 | 2024-11-10 | 2024-11-14 | 2024-11-16 | 2024-11-17 | 2024-11-19 | 2024-11-24 | 2024-11-29 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-11 | 2024-12-11 | 2024-12-13 | 2024-12-18 | 2024-12-26 | 2024-11-19 | 2024-12-06 | 2024-12-08 | 2024-12-31 | 2024-12-27 | 2025-01-02 | 2025-01-04 | 2025-01-10 | 2025-01-16
V_222 | 2024-07-04 | 2024-07-11 | 2024-07-13 | 2024-07-19 | 2024-07-24 | 2024-07-27 | 2024-07-28 | 2024-08-01 | 2024-08-06 | 2024-08-09 | 2024-08-13 | 2024-08-13 | 2024-09-18 | 2024-09-26 | 2024-10-03 | 2024-10-03 | 2024-10-10 | 2024-10-17 | 2024-10-17 | 2024-10-20 | 2024-10-20 | 2024-10-22 | 2024-10-27 | 2024-10-27 | 2024-11-03 | 2024-11-03 | 2024-11-03 | 2024-11-08 | 2024-11-13 | 2024-11-20 | 2024-11-24 | 2024-11-29 | 2024-12-06 | 2024-12-06 | 2024-12-11 | 2024-12-13 | 2024-12-13 | 2024-12-13 | 2024-12-19 | 2024-12-20 | 2024-12-25 | 2025-01-02 | 2024-09-26 | 2024-09-28 | 2024-10-05 | 2024-10-12 | 2024-10-17 | 2024-10-18 | 2024-10-24 | 2024-10-24 | 2024-10-25 | 2024-10-29 | 2024-10-30 | 2024-11-03 | 2024-11-03 | 2024-11-06 | 2024-11-08 | 2024-11-10 | 2024-11-10 | 2024-11-14 | 2024-11-16 | 2024-11-17 | 2024-11-19 | 2024-11-24 | 2024-11-29 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-11 | 2024-12-11 | 2024-12-13 | 2024-12-18 | 2024-12-26 | 2024-11-19 | 2024-12-06 | 2024-12-08 | 2024-12-31 | 2024-12-27 | 2025-01-02 | 2025-01-04 | 2025-01-10 | 2025-01-16
V_223 | 2024-07-04 | 2024-07-11 | 2024-07-13 | 2024-07-19 | 2024-07-24 | 2024-07-27 | 2024-07-28 | 2024-08-01 | 2024-08-06 | 2024-08-09 | 2024-08-13 | 2024-08-13 | 2024-09-18 | 2024-09-26 | 2024-10-03 | 2024-10-03 | 2024-10-10 | 2024-10-17 | 2024-10-17 | 2024-10-20 | 2024-10-20 | 2024-10-22 | 2024-10-27 | 2024-10-27 | 2024-11-03 | 2024-11-03 | 2024-11-03 | 2024-11-08 | 2024-11-13 | 2024-11-20 | 2024-11-24 | 2024-11-29 | 2024-12-06 | 2024-12-06 | 2024-12-11 | 2024-12-13 | 2024-12-13 | 2024-12-13 | 2024-12-19 | 2024-12-20 | 2024-12-25 | 2025-01-02 | 2024-09-26 | 2024-09-28 | 2024-10-05 | 2024-10-12 | 2024-10-17 | 2024-10-18 | 2024-10-24 | 2024-10-24 | 2024-10-25 | 2024-10-29 | 2024-10-30 | 2024-11-03 | 2024-11-03 | 2024-11-06 | 2024-11-08 | 2024-11-10 | 2024-11-10 | 2024-11-14 | 2024-11-16 | 2024-11-17 | 2024-11-19 | 2024-11-24 | 2024-11-29 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-11 | 2024-12-11 | 2024-12-13 | 2024-12-18 | 2024-12-26 | 2024-11-19 | 2024-12-06 | 2024-12-08 | 2024-12-31 | 2024-12-27 | 2025-01-02 | 2025-01-04 | 2025-01-10 | 2025-01-16
V_224 | 2024-07-04 | 2024-07-11 | 2024-07-13 | 2024-07-19 | 2024-07-24 | 2024-07-27 | 2024-07-28 | 2024-08-01 | 2024-08-06 | 2024-08-09 | 2024-08-13 | 2024-08-13 | 2024-09-18 | 2024-09-26 | 2024-10-03 | 2024-10-03 | 2024-10-10 | 2024-10-17 | 2024-10-17 | 2024-10-20 | 2024-10-20 | 2024-10-22 | 2024-10-27 | 2024-10-27 | 2024-11-03 | 2024-11-03 | 2024-11-03 | 2024-11-08 | 2024-11-13 | 2024-11-20 | 2024-11-24 | 2024-11-29 | 2024-12-06 | 2024-12-06 | 2024-12-11 | 2024-12-13 | 2024-12-13 | 2024-12-13 | 2024-12-19 | 2024-12-20 | 2024-12-25 | 2025-01-02 | 2024-09-26 | 2024-09-28 | 2024-10-05 | 2024-10-12 | 2024-10-17 | 2024-10-18 | 2024-10-24 | 2024-10-24 | 2024-10-25 | 2024-10-29 | 2024-10-30 | 2024-11-03 | 2024-11-03 | 2024-11-06 | 2024-11-08 | 2024-11-10 | 2024-11-10 | 2024-11-14 | 2024-11-16 | 2024-11-17 | 2024-11-19 | 2024-11-24 | 2024-11-29 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-11 | 2024-12-11 | 2024-12-13 | 2024-12-18 | 2024-12-26 | 2024-11-19 | 2024-12-06 | 2024-12-08 | 2024-12-31 | 2024-12-27 | 2025-01-02 | 2025-01-04 | 2025-01-10 | 2025-01-16
V_225 | 2024-07-11 | 2024-07-18 | 2024-07-20 | 2024-07-26 | 2024-07-31 | 2024-08-03 | 2024-08-04 | 2024-08-08 | 2024-08-13 | 2024-08-16 | 2024-08-20 | 2024-08-20 | 2024-09-26 | 2024-10-04 | 2024-10-11 | 2024-10-11 | 2024-10-18 | 2024-10-25 | 2024-10-25 | 2024-10-29 | 2024-10-29 | 2024-10-30 | 2024-11-05 | 2024-11-05 | 2024-11-12 | 2024-11-12 | 2024-11-12 | 2024-11-16 | 2024-11-21 | 2024-11-28 | 2024-12-03 | 2024-12-07 | 2024-12-14 | 2024-12-14 | 2024-12-19 | 2024-12-21 | 2024-12-21 | 2024-12-21 | 2024-12-27 | 2024-12-28 | 2025-01-02 | 2025-01-10 | 2024-10-04 | 2024-10-06 | 2024-10-13 | 2024-10-20 | 2024-10-25 | 2024-10-26 | 2024-11-01 | 2024-11-01 | 2024-11-02 | 2024-11-06 | 2024-11-07 | 2024-11-12 | 2024-11-12 | 2024-11-14 | 2024-11-16 | 2024-11-19 | 2024-11-19 | 2024-11-22 | 2024-11-24 | 2024-11-26 | 2024-11-27 | 2024-12-03 | 2024-12-07 | 2024-12-14 | 2024-12-14 | 2024-12-14 | 2024-12-19 | 2024-12-19 | 2024-12-21 | 2024-12-26 | 2025-01-03 | 2024-11-27 | 2024-12-14 | 2024-12-17 | 2025-01-08 | 2025-01-04 | 2025-01-10 | 2025-01-12 | 2025-01-18 | 2025-01-24
V_226 | 2024-07-26 | 2024-08-02 | 2024-08-04 | 2024-08-10 | 2024-08-15 | 2024-08-18 | 2024-08-19 | 2024-08-23 | 2024-08-28 | 2024-08-31 | 2024-09-04 | 2024-09-04 | 2024-10-11 | 2024-10-19 | 2024-10-26 | 2024-10-26 | 2024-11-02 | 2024-11-09 | 2024-11-09 | 2024-11-13 | 2024-11-13 | 2024-11-14 | 2024-11-20 | 2024-11-20 | 2024-11-27 | 2024-11-27 | 2024-11-27 | 2024-12-01 | 2024-12-06 | 2024-12-13 | 2024-12-18 | 2024-12-22 | 2024-12-29 | 2024-12-29 | 2025-01-03 | 2025-01-05 | 2025-01-05 | 2025-01-05 | 2025-01-11 | 2025-01-12 | 2025-01-17 | 2025-01-25 | 2024-10-19 | 2024-10-21 | 2024-10-28 | 2024-11-04 | 2024-11-09 | 2024-11-10 | 2024-11-16 | 2024-11-16 | 2024-11-17 | 2024-11-21 | 2024-11-22 | 2024-11-27 | 2024-11-27 | 2024-11-29 | 2024-12-01 | 2024-12-04 | 2024-12-04 | 2024-12-07 | 2024-12-09 | 2024-12-11 | 2024-12-12 | 2024-12-18 | 2024-12-22 | 2024-12-29 | 2024-12-29 | 2024-12-29 | 2025-01-03 | 2025-01-03 | 2025-01-05 | 2025-01-10 | 2025-01-18 | 2024-12-12 | 2024-12-29 | 2025-01-01 | 2025-01-23 | 2025-01-19 | 2025-01-25 | 2025-01-27 | 2025-02-02 | 2025-02-08
V_227 | 2024-07-26 | 2024-08-02 | 2024-08-04 | 2024-08-10 | 2024-08-15 | 2024-08-18 | 2024-08-19 | 2024-08-23 | 2024-08-28 | 2024-08-31 | 2024-09-04 | 2024-09-04 | 2024-10-11 | 2024-10-19 | 2024-10-26 | 2024-10-26 | 2024-11-02 | 2024-11-09 | 2024-11-09 | 2024-11-13 | 2024-11-13 | 2024-11-14 | 2024-11-20 | 2024-11-20 | 2024-11-27 | 2024-11-27 | 2024-11-27 | 2024-12-01 | 2024-12-06 | 2024-12-13 | 2024-12-18 | 2024-12-22 | 2024-12-29 | 2024-12-29 | 2025-01-03 | 2025-01-05 | 2025-01-05 | 2025-01-05 | 2025-01-11 | 2025-01-12 | 2025-01-17 | 2025-01-25 | 2024-10-19 | 2024-10-21 | 2024-10-28 | 2024-11-04 | 2024-11-09 | 2024-11-10 | 2024-11-16 | 2024-11-16 | 2024-11-17 | 2024-11-21 | 2024-11-22 | 2024-11-27 | 2024-11-27 | 2024-11-29 | 2024-12-01 | 2024-12-04 | 2024-12-04 | 2024-12-07 | 2024-12-09 | 2024-12-11 | 2024-12-12 | 2024-12-18 | 2024-12-22 | 2024-12-29 | 2024-12-29 | 2024-12-29 | 2025-01-03 | 2025-01-03 | 2025-01-05 | 2025-01-10 | 2025-01-18 | 2024-12-12 | 2024-12-29 | 2025-01-01 | 2025-01-23 | 2025-01-19 | 2025-01-25 | 2025-01-27 | 2025-02-02 | 2025-02-08
V_228 | 2024-07-26 | 2024-08-02 | 2024-08-04 | 2024-08-10 | 2024-08-15 | 2024-08-18 | 2024-08-19 | 2024-08-23 | 2024-08-28 | 2024-08-31 | 2024-09-04 | 2024-09-04 | 2024-10-11 | 2024-10-19 | 2024-10-26 | 2024-10-26 | 2024-11-02 | 2024-11-09 | 2024-11-09 | 2024-11-13 | 2024-11-13 | 2024-11-14 | 2024-11-20 | 2024-11-20 | 2024-11-27 | 2024-11-27 | 2024-11-27 | 2024-12-01 | 2024-12-06 | 2024-12-13 | 2024-12-18 | 2024-12-22 | 2024-12-29 | 2024-12-29 | 2025-01-03 | 2025-01-05 | 2025-01-05 | 2025-01-05 | 2025-01-11 | 2025-01-12 | 2025-01-17 | 2025-01-25 | 2024-10-19 | 2024-10-21 | 2024-10-28 | 2024-11-04 | 2024-11-09 | 2024-11-10 | 2024-11-16 | 2024-11-16 | 2024-11-17 | 2024-11-21 | 2024-11-22 | 2024-11-27 | 2024-11-27 | 2024-11-29 | 2024-12-01 | 2024-12-04 | 2024-12-04 | 2024-12-07 | 2024-12-09 | 2024-12-11 | 2024-12-12 | 2024-12-18 | 2024-12-22 | 2024-12-29 | 2024-12-29 | 2024-12-29 | 2025-01-03 | 2025-01-03 | 2025-01-05 | 2025-01-10 | 2025-01-18 | 2024-12-12 | 2024-12-29 | 2025-01-01 | 2025-01-23 | 2025-01-19 | 2025-01-25 | 2025-01-27 | 2025-02-02 | 2025-02-08
V_229 | 2024-07-26 | 2024-08-02 | 2024-08-04 | 2024-08-10 | 2024-08-15 | 2024-08-18 | 2024-08-19 | 2024-08-23 | 2024-08-28 | 2024-08-31 | 2024-09-04 | 2024-09-04 | 2024-10-11 | 2024-10-19 | 2024-10-26 | 2024-10-26 | 2024-11-02 | 2024-11-09 | 2024-11-09 | 2024-11-13 | 2024-11-13 | 2024-11-14 | 2024-11-20 | 2024-11-20 | 2024-11-27 | 2024-11-27 | 2024-11-27 | 2024-12-01 | 2024-12-06 | 2024-12-13 | 2024-12-18 | 2024-12-22 | 2024-12-29 | 2024-12-29 | 2025-01-03 | 2025-01-05 | 2025-01-05 | 2025-01-05 | 2025-01-11 | 2025-01-12 | 2025-01-17 | 2025-01-25 | 2024-10-19 | 2024-10-21 | 2024-10-28 | 2024-11-04 | 2024-11-09 | 2024-11-10 | 2024-11-16 | 2024-11-16 | 2024-11-17 | 2024-11-21 | 2024-11-22 | 2024-11-27 | 2024-11-27 | 2024-11-29 | 2024-12-01 | 2024-12-04 | 2024-12-04 | 2024-12-07 | 2024-12-09 | 2024-12-11 | 2024-12-12 | 2024-12-18 | 2024-12-22 | 2024-12-29 | 2024-12-29 | 2024-12-29 | 2025-01-03 | 2025-01-03 | 2025-01-05 | 2025-01-10 | 2025-01-18 | 2024-12-12 | 2024-12-29 | 2025-01-01 | 2025-01-23 | 2025-01-19 | 2025-01-25 | 2025-01-27 | 2025-02-02 | 2025-02-08
V_230 | 2024-07-26 | 2024-08-02 | 2024-08-04 | 2024-08-10 | 2024-08-15 | 2024-08-18 | 2024-08-19 | 2024-08-23 | 2024-08-28 | 2024-08-31 | 2024-09-04 | 2024-09-04 | 2024-10-11 | 2024-10-19 | 2024-10-26 | 2024-10-26 | 2024-11-02 | 2024-11-09 | 2024-11-09 | 2024-11-13 | 2024-11-13 | 2024-11-14 | 2024-11-20 | 2024-11-20 | 2024-11-27 | 2024-11-27 | 2024-11-27 | 2024-12-01 | 2024-12-06 | 2024-12-13 | 2024-12-18 | 2024-12-22 | 2024-12-29 | 2024-12-29 | 2025-01-03 | 2025-01-05 | 2025-01-05 | 2025-01-05 | 2025-01-11 | 2025-01-12 | 2025-01-17 | 2025-01-25 | 2024-10-19 | 2024-10-21 | 2024-10-28 | 2024-11-04 | 2024-11-09 | 2024-11-10 | 2024-11-16 | 2024-11-16 | 2024-11-17 | 2024-11-21 | 2024-11-22 | 2024-11-27 | 2024-11-27 | 2024-11-29 | 2024-12-01 | 2024-12-04 | 2024-12-04 | 2024-12-07 | 2024-12-09 | 2024-12-11 | 2024-12-12 | 2024-12-18 | 2024-12-22 | 2024-12-29 | 2024-12-29 | 2024-12-29 | 2025-01-03 | 2025-01-03 | 2025-01-05 | 2025-01-10 | 2025-01-18 | 2024-12-12 | 2024-12-29 | 2025-01-01 | 2025-01-23 | 2025-01-19 | 2025-01-25 | 2025-01-27 | 2025-02-02 | 2025-02-08
V_231 | 2024-07-26 | 2024-08-02 | 2024-08-04 | 2024-08-10 | 2024-08-15 | 2024-08-18 | 2024-08-19 | 2024-08-23 | 2024-08-28 | 2024-08-31 | 2024-09-04 | 2024-09-04 | 2024-10-11 | 2024-10-19 | 2024-10-26 | 2024-10-26 | 2024-11-02 | 2024-11-09 | 2024-11-09 | 2024-11-13 | 2024-11-13 | 2024-11-14 | 2024-11-20 | 2024-11-20 | 2024-11-27 | 2024-11-27 | 2024-11-27 | 2024-12-01 | 2024-12-06 | 2024-12-13 | 2024-12-18 | 2024-12-22 | 2024-12-29 | 2024-12-29 | 2025-01-03 | 2025-01-05 | 2025-01-05 | 2025-01-05 | 2025-01-11 | 2025-01-12 | 2025-01-17 | 2025-01-25 | 2024-10-19 | 2024-10-21 | 2024-10-28 | 2024-11-04 | 2024-11-09 | 2024-11-10 | 2024-11-16 | 2024-11-16 | 2024-11-17 | 2024-11-21 | 2024-11-22 | 2024-11-27 | 2024-11-27 | 2024-11-29 | 2024-12-01 | 2024-12-04 | 2024-12-04 | 2024-12-07 | 2024-12-09 | 2024-12-11 | 2024-12-12 | 2024-12-18 | 2024-12-22 | 2024-12-29 | 2024-12-29 | 2024-12-29 | 2025-01-03 | 2025-01-03 | 2025-01-05 | 2025-01-10 | 2025-01-18 | 2024-12-12 | 2024-12-29 | 2025-01-01 | 2025-01-23 | 2025-01-19 | 2025-01-25 | 2025-01-27 | 2025-02-02 | 2025-02-08
V_232 | 2024-07-26 | 2024-08-02 | 2024-08-04 | 2024-08-10 | 2024-08-15 | 2024-08-18 | 2024-08-19 | 2024-08-23 | 2024-08-28 | 2024-08-31 | 2024-09-04 | 2024-09-04 | 2024-10-11 | 2024-10-19 | 2024-10-26 | 2024-10-26 | 2024-11-02 | 2024-11-09 | 2024-11-09 | 2024-11-13 | 2024-11-13 | 2024-11-14 | 2024-11-20 | 2024-11-20 | 2024-11-27 | 2024-11-27 | 2024-11-27 | 2024-12-01 | 2024-12-06 | 2024-12-13 | 2024-12-18 | 2024-12-22 | 2024-12-29 | 2024-12-29 | 2025-01-03 | 2025-01-05 | 2025-01-05 | 2025-01-05 | 2025-01-11 | 2025-01-12 | 2025-01-17 | 2025-01-25 | 2024-10-19 | 2024-10-21 | 2024-10-28 | 2024-11-04 | 2024-11-09 | 2024-11-10 | 2024-11-16 | 2024-11-16 | 2024-11-17 | 2024-11-21 | 2024-11-22 | 2024-11-27 | 2024-11-27 | 2024-11-29 | 2024-12-01 | 2024-12-04 | 2024-12-04 | 2024-12-07 | 2024-12-09 | 2024-12-11 | 2024-12-12 | 2024-12-18 | 2024-12-22 | 2024-12-29 | 2024-12-29 | 2024-12-29 | 2025-01-03 | 2025-01-03 | 2025-01-05 | 2025-01-10 | 2025-01-18 | 2024-12-12 | 2024-12-29 | 2025-01-01 | 2025-01-23 | 2025-01-19 | 2025-01-25 | 2025-01-27 | 2025-02-02 | 2025-02-08
V_233 | 2024-08-02 | 2024-08-09 | 2024-08-11 | 2024-08-17 | 2024-08-22 | 2024-08-25 | 2024-08-26 | 2024-08-30 | 2024-09-04 | 2024-09-07 | 2024-09-11 | 2024-09-11 | 2024-10-19 | 2024-10-27 | 2024-11-03 | 2024-11-03 | 2024-11-10 | 2024-11-17 | 2024-11-17 | 2024-11-21 | 2024-11-21 | 2024-11-22 | 2024-11-28 | 2024-11-28 | 2024-12-05 | 2024-12-05 | 2024-12-05 | 2024-12-09 | 2024-12-14 | 2024-12-21 | 2024-12-26 | 2024-12-30 | 2025-01-06 | 2025-01-06 | 2025-01-11 | 2025-01-13 | 2025-01-13 | 2025-01-13 | 2025-01-19 | 2025-01-20 | 2025-01-25 | 2025-02-02 | 2024-10-27 | 2024-10-30 | 2024-11-06 | 2024-11-13 | 2024-11-17 | 2024-11-18 | 2024-11-24 | 2024-11-24 | 2024-11-25 | 2024-11-29 | 2024-11-30 | 2024-12-05 | 2024-12-05 | 2024-12-07 | 2024-12-09 | 2024-12-12 | 2024-12-12 | 2024-12-15 | 2024-12-18 | 2024-12-19 | 2024-12-20 | 2024-12-26 | 2024-12-30 | 2025-01-06 | 2025-01-06 | 2025-01-06 | 2025-01-11 | 2025-01-11 | 2025-01-13 | 2025-01-18 | 2025-01-26 | 2024-12-20 | 2025-01-06 | 2025-01-09 | 2025-01-31 | 2025-01-27 | 2025-02-02 | 2025-02-05 | 2025-02-10 | 2025-02-16
V_234 | 2024-08-02 | 2024-08-09 | 2024-08-11 | 2024-08-17 | 2024-08-22 | 2024-08-25 | 2024-08-26 | 2024-08-30 | 2024-09-04 | 2024-09-07 | 2024-09-11 | 2024-09-11 | 2024-10-19 | 2024-10-27 | 2024-11-03 | 2024-11-03 | 2024-11-10 | 2024-11-17 | 2024-11-17 | 2024-11-21 | 2024-11-21 | 2024-11-22 | 2024-11-28 | 2024-11-28 | 2024-12-05 | 2024-12-05 | 2024-12-05 | 2024-12-09 | 2024-12-14 | 2024-12-21 | 2024-12-26 | 2024-12-30 | 2025-01-06 | 2025-01-06 | 2025-01-11 | 2025-01-13 | 2025-01-13 | 2025-01-13 | 2025-01-19 | 2025-01-20 | 2025-01-25 | 2025-02-02 | 2024-10-27 | 2024-10-30 | 2024-11-06 | 2024-11-13 | 2024-11-17 | 2024-11-18 | 2024-11-24 | 2024-11-24 | 2024-11-25 | 2024-11-29 | 2024-11-30 | 2024-12-05 | 2024-12-05 | 2024-12-07 | 2024-12-09 | 2024-12-12 | 2024-12-12 | 2024-12-15 | 2024-12-18 | 2024-12-19 | 2024-12-20 | 2024-12-26 | 2024-12-30 | 2025-01-06 | 2025-01-06 | 2025-01-06 | 2025-01-11 | 2025-01-11 | 2025-01-13 | 2025-01-18 | 2025-01-26 | 2024-12-20 | 2025-01-06 | 2025-01-09 | 2025-01-31 | 2025-01-27 | 2025-02-02 | 2025-02-05 | 2025-02-10 | 2025-02-16
V_235 | 2024-08-02 | 2024-08-09 | 2024-08-11 | 2024-08-17 | 2024-08-22 | 2024-08-25 | 2024-08-26 | 2024-08-30 | 2024-09-04 | 2024-09-07 | 2024-09-11 | 2024-09-11 | 2024-10-19 | 2024-10-27 | 2024-11-03 | 2024-11-03 | 2024-11-10 | 2024-11-17 | 2024-11-17 | 2024-11-21 | 2024-11-21 | 2024-11-22 | 2024-11-28 | 2024-11-28 | 2024-12-05 | 2024-12-05 | 2024-12-05 | 2024-12-09 | 2024-12-14 | 2024-12-21 | 2024-12-26 | 2024-12-30 | 2025-01-06 | 2025-01-06 | 2025-01-11 | 2025-01-13 | 2025-01-13 | 2025-01-13 | 2025-01-19 | 2025-01-20 | 2025-01-25 | 2025-02-02 | 2024-10-27 | 2024-10-30 | 2024-11-06 | 2024-11-13 | 2024-11-17 | 2024-11-18 | 2024-11-24 | 2024-11-24 | 2024-11-25 | 2024-11-29 | 2024-11-30 | 2024-12-05 | 2024-12-05 | 2024-12-07 | 2024-12-09 | 2024-12-12 | 2024-12-12 | 2024-12-15 | 2024-12-18 | 2024-12-19 | 2024-12-20 | 2024-12-26 | 2024-12-30 | 2025-01-06 | 2025-01-06 | 2025-01-06 | 2025-01-11 | 2025-01-11 | 2025-01-13 | 2025-01-18 | 2025-01-26 | 2024-12-20 | 2025-01-06 | 2025-01-09 | 2025-01-31 | 2025-01-27 | 2025-02-02 | 2025-02-05 | 2025-02-10 | 2025-02-16
V_236 | 2024-08-02 | 2024-08-09 | 2024-08-11 | 2024-08-17 | 2024-08-22 | 2024-08-25 | 2024-08-26 | 2024-08-30 | 2024-09-04 | 2024-09-07 | 2024-09-11 | 2024-09-11 | 2024-10-19 | 2024-10-27 | 2024-11-03 | 2024-11-03 | 2024-11-10 | 2024-11-17 | 2024-11-17 | 2024-11-21 | 2024-11-21 | 2024-11-22 | 2024-11-28 | 2024-11-28 | 2024-12-05 | 2024-12-05 | 2024-12-05 | 2024-12-09 | 2024-12-14 | 2024-12-21 | 2024-12-26 | 2024-12-30 | 2025-01-06 | 2025-01-06 | 2025-01-11 | 2025-01-13 | 2025-01-13 | 2025-01-13 | 2025-01-19 | 2025-01-20 | 2025-01-25 | 2025-02-02 | 2024-10-27 | 2024-10-30 | 2024-11-06 | 2024-11-13 | 2024-11-17 | 2024-11-18 | 2024-11-24 | 2024-11-24 | 2024-11-25 | 2024-11-29 | 2024-11-30 | 2024-12-05 | 2024-12-05 | 2024-12-07 | 2024-12-09 | 2024-12-12 | 2024-12-12 | 2024-12-15 | 2024-12-18 | 2024-12-19 | 2024-12-20 | 2024-12-26 | 2024-12-30 | 2025-01-06 | 2025-01-06 | 2025-01-06 | 2025-01-11 | 2025-01-11 | 2025-01-13 | 2025-01-18 | 2025-01-26 | 2024-12-20 | 2025-01-06 | 2025-01-09 | 2025-01-31 | 2025-01-27 | 2025-02-02 | 2025-02-05 | 2025-02-10 | 2025-02-16
V_237 | 2024-08-02 | 2024-08-09 | 2024-08-11 | 2024-08-17 | 2024-08-22 | 2024-08-25 | 2024-08-26 | 2024-08-30 | 2024-09-04 | 2024-09-07 | 2024-09-11 | 2024-09-11 | 2024-10-19 | 2024-10-27 | 2024-11-03 | 2024-11-03 | 2024-11-10 | 2024-11-17 | 2024-11-17 | 2024-11-21 | 2024-11-21 | 2024-11-22 | 2024-11-28 | 2024-11-28 | 2024-12-05 | 2024-12-05 | 2024-12-05 | 2024-12-09 | 2024-12-14 | 2024-12-21 | 2024-12-26 | 2024-12-30 | 2025-01-06 | 2025-01-06 | 2025-01-11 | 2025-01-13 | 2025-01-13 | 2025-01-13 | 2025-01-19 | 2025-01-20 | 2025-01-25 | 2025-02-02 | 2024-10-27 | 2024-10-30 | 2024-11-06 | 2024-11-13 | 2024-11-17 | 2024-11-18 | 2024-11-24 | 2024-11-24 | 2024-11-25 | 2024-11-29 | 2024-11-30 | 2024-12-05 | 2024-12-05 | 2024-12-07 | 2024-12-09 | 2024-12-12 | 2024-12-12 | 2024-12-15 | 2024-12-18 | 2024-12-19 | 2024-12-20 | 2024-12-26 | 2024-12-30 | 2025-01-06 | 2025-01-06 | 2025-01-06 | 2025-01-11 | 2025-01-11 | 2025-01-13 | 2025-01-18 | 2025-01-26 | 2024-12-20 | 2025-01-06 | 2025-01-09 | 2025-01-31 | 2025-01-27 | 2025-02-02 | 2025-02-05 | 2025-02-10 | 2025-02-16
V_238 | 2024-08-02 | 2024-08-09 | 2024-08-11 | 2024-08-17 | 2024-08-22 | 2024-08-25 | 2024-08-26 | 2024-08-30 | 2024-09-04 | 2024-09-07 | 2024-09-11 | 2024-09-11 | 2024-10-19 | 2024-10-27 | 2024-11-03 | 2024-11-03 | 2024-11-10 | 2024-11-17 | 2024-11-17 | 2024-11-21 | 2024-11-21 | 2024-11-22 | 2024-11-28 | 2024-11-28 | 2024-12-05 | 2024-12-05 | 2024-12-05 | 2024-12-09 | 2024-12-14 | 2024-12-21 | 2024-12-26 | 2024-12-30 | 2025-01-06 | 2025-01-06 | 2025-01-11 | 2025-01-13 | 2025-01-13 | 2025-01-13 | 2025-01-19 | 2025-01-20 | 2025-01-25 | 2025-02-02 | 2024-10-27 | 2024-10-30 | 2024-11-06 | 2024-11-13 | 2024-11-17 | 2024-11-18 | 2024-11-24 | 2024-11-24 | 2024-11-25 | 2024-11-29 | 2024-11-30 | 2024-12-05 | 2024-12-05 | 2024-12-07 | 2024-12-09 | 2024-12-12 | 2024-12-12 | 2024-12-15 | 2024-12-18 | 2024-12-19 | 2024-12-20 | 2024-12-26 | 2024-12-30 | 2025-01-06 | 2025-01-06 | 2025-01-06 | 2025-01-11 | 2025-01-11 | 2025-01-13 | 2025-01-18 | 2025-01-26 | 2024-12-20 | 2025-01-06 | 2025-01-09 | 2025-01-31 | 2025-01-27 | 2025-02-02 | 2025-02-05 | 2025-02-10 | 2025-02-16
V_239 | 2024-08-02 | 2024-08-09 | 2024-08-11 | 2024-08-17 | 2024-08-22 | 2024-08-25 | 2024-08-26 | 2024-08-30 | 2024-09-04 | 2024-09-07 | 2024-09-11 | 2024-09-11 | 2024-10-19 | 2024-10-27 | 2024-11-03 | 2024-11-03 | 2024-11-10 | 2024-11-17 | 2024-11-17 | 2024-11-21 | 2024-11-21 | 2024-11-22 | 2024-11-28 | 2024-11-28 | 2024-12-05 | 2024-12-05 | 2024-12-05 | 2024-12-09 | 2024-12-14 | 2024-12-21 | 2024-12-26 | 2024-12-30 | 2025-01-06 | 2025-01-06 | 2025-01-11 | 2025-01-13 | 2025-01-13 | 2025-01-13 | 2025-01-19 | 2025-01-20 | 2025-01-25 | 2025-02-02 | 2024-10-27 | 2024-10-30 | 2024-11-06 | 2024-11-13 | 2024-11-17 | 2024-11-18 | 2024-11-24 | 2024-11-24 | 2024-11-25 | 2024-11-29 | 2024-11-30 | 2024-12-05 | 2024-12-05 | 2024-12-07 | 2024-12-09 | 2024-12-12 | 2024-12-12 | 2024-12-15 | 2024-12-18 | 2024-12-19 | 2024-12-20 | 2024-12-26 | 2024-12-30 | 2025-01-06 | 2025-01-06 | 2025-01-06 | 2025-01-11 | 2025-01-11 | 2025-01-13 | 2025-01-18 | 2025-01-26 | 2024-12-20 | 2025-01-06 | 2025-01-09 | 2025-01-31 | 2025-01-27 | 2025-02-02 | 2025-02-05 | 2025-02-10 | 2025-02-16
V_240 | 2024-08-02 | 2024-08-09 | 2024-08-11 | 2024-08-17 | 2024-08-22 | 2024-08-25 | 2024-08-26 | 2024-08-30 | 2024-09-04 | 2024-09-07 | 2024-09-11 | 2024-09-11 | 2024-10-19 | 2024-10-27 | 2024-11-03 | 2024-11-03 | 2024-11-10 | 2024-11-17 | 2024-11-17 | 2024-11-21 | 2024-11-21 | 2024-11-22 | 2024-11-28 | 2024-11-28 | 2024-12-05 | 2024-12-05 | 2024-12-05 | 2024-12-09 | 2024-12-14 | 2024-12-21 | 2024-12-26 | 2024-12-30 | 2025-01-06 | 2025-01-06 | 2025-01-11 | 2025-01-13 | 2025-01-13 | 2025-01-13 | 2025-01-19 | 2025-01-20 | 2025-01-25 | 2025-02-02 | 2024-10-27 | 2024-10-30 | 2024-11-06 | 2024-11-13 | 2024-11-17 | 2024-11-18 | 2024-11-24 | 2024-11-24 | 2024-11-25 | 2024-11-29 | 2024-11-30 | 2024-12-05 | 2024-12-05 | 2024-12-07 | 2024-12-09 | 2024-12-12 | 2024-12-12 | 2024-12-15 | 2024-12-18 | 2024-12-19 | 2024-12-20 | 2024-12-26 | 2024-12-30 | 2025-01-06 | 2025-01-06 | 2025-01-06 | 2025-01-11 | 2025-01-11 | 2025-01-13 | 2025-01-18 | 2025-01-26 | 2024-12-20 | 2025-01-06 | 2025-01-09 | 2025-01-31 | 2025-01-27 | 2025-02-02 | 2025-02-05 | 2025-02-10 | 2025-02-16
V_241 | 2024-08-09 | 2024-08-16 | 2024-08-18 | 2024-08-24 | 2024-08-29 | 2024-09-01 | 2024-09-02 | 2024-09-06 | 2024-09-11 | 2024-09-14 | 2024-09-18 | 2024-09-18 | 2024-10-27 | 2024-11-04 | 2024-11-11 | 2024-11-11 | 2024-11-18 | 2024-11-25 | 2024-11-25 | 2024-11-29 | 2024-11-29 | 2024-11-30 | 2024-12-06 | 2024-12-06 | 2024-12-13 | 2024-12-13 | 2024-12-13 | 2024-12-18 | 2024-12-22 | 2024-12-29 | 2025-01-03 | 2025-01-08 | 2025-01-15 | 2025-01-15 | 2025-01-19 | 2025-01-22 | 2025-01-22 | 2025-01-22 | 2025-01-27 | 2025-01-29 | 2025-02-02 | 2025-02-10 | 2024-11-04 | 2024-11-07 | 2024-11-14 | 2024-11-21 | 2024-11-25 | 2024-11-27 | 2024-12-02 | 2024-12-02 | 2024-12-04 | 2024-12-07 | 2024-12-08 | 2024-12-13 | 2024-12-13 | 2024-12-15 | 2024-12-18 | 2024-12-20 | 2024-12-20 | 2024-12-23 | 2024-12-26 | 2024-12-27 | 2024-12-28 | 2025-01-03 | 2025-01-08 | 2025-01-15 | 2025-01-15 | 2025-01-15 | 2025-01-19 | 2025-01-19 | 2025-01-22 | 2025-01-26 | 2025-02-03 | 2024-12-28 | 2025-01-15 | 2025-01-17 | 2025-02-08 | 2025-02-05 | 2025-02-10 | 2025-02-13 | 2025-02-19 | 2025-02-24
V_242 | 2024-08-09 | 2024-08-16 | 2024-08-18 | 2024-08-24 | 2024-08-29 | 2024-09-01 | 2024-09-02 | 2024-09-06 | 2024-09-11 | 2024-09-14 | 2024-09-18 | 2024-09-18 | 2024-10-27 | 2024-11-04 | 2024-11-11 | 2024-11-11 | 2024-11-18 | 2024-11-25 | 2024-11-25 | 2024-11-29 | 2024-11-29 | 2024-11-30 | 2024-12-06 | 2024-12-06 | 2024-12-13 | 2024-12-13 | 2024-12-13 | 2024-12-18 | 2024-12-22 | 2024-12-29 | 2025-01-03 | 2025-01-08 | 2025-01-15 | 2025-01-15 | 2025-01-19 | 2025-01-22 | 2025-01-22 | 2025-01-22 | 2025-01-27 | 2025-01-29 | 2025-02-02 | 2025-02-10 | 2024-11-04 | 2024-11-07 | 2024-11-14 | 2024-11-21 | 2024-11-25 | 2024-11-27 | 2024-12-02 | 2024-12-02 | 2024-12-04 | 2024-12-07 | 2024-12-08 | 2024-12-13 | 2024-12-13 | 2024-12-15 | 2024-12-18 | 2024-12-20 | 2024-12-20 | 2024-12-23 | 2024-12-26 | 2024-12-27 | 2024-12-28 | 2025-01-03 | 2025-01-08 | 2025-01-15 | 2025-01-15 | 2025-01-15 | 2025-01-19 | 2025-01-19 | 2025-01-22 | 2025-01-26 | 2025-02-03 | 2024-12-28 | 2025-01-15 | 2025-01-17 | 2025-02-08 | 2025-02-05 | 2025-02-10 | 2025-02-13 | 2025-02-19 | 2025-02-24
V_243 | 2024-08-09 | 2024-08-16 | 2024-08-18 | 2024-08-24 | 2024-08-29 | 2024-09-01 | 2024-09-02 | 2024-09-06 | 2024-09-11 | 2024-09-14 | 2024-09-18 | 2024-09-18 | 2024-10-27 | 2024-11-04 | 2024-11-11 | 2024-11-11 | 2024-11-18 | 2024-11-25 | 2024-11-25 | 2024-11-29 | 2024-11-29 | 2024-11-30 | 2024-12-06 | 2024-12-06 | 2024-12-13 | 2024-12-13 | 2024-12-13 | 2024-12-18 | 2024-12-22 | 2024-12-29 | 2025-01-03 | 2025-01-08 | 2025-01-15 | 2025-01-15 | 2025-01-19 | 2025-01-22 | 2025-01-22 | 2025-01-22 | 2025-01-27 | 2025-01-29 | 2025-02-02 | 2025-02-10 | 2024-11-04 | 2024-11-07 | 2024-11-14 | 2024-11-21 | 2024-11-25 | 2024-11-27 | 2024-12-02 | 2024-12-02 | 2024-12-04 | 2024-12-07 | 2024-12-08 | 2024-12-13 | 2024-12-13 | 2024-12-15 | 2024-12-18 | 2024-12-20 | 2024-12-20 | 2024-12-23 | 2024-12-26 | 2024-12-27 | 2024-12-28 | 2025-01-03 | 2025-01-08 | 2025-01-15 | 2025-01-15 | 2025-01-15 | 2025-01-19 | 2025-01-19 | 2025-01-22 | 2025-01-26 | 2025-02-03 | 2024-12-28 | 2025-01-15 | 2025-01-17 | 2025-02-08 | 2025-02-05 | 2025-02-10 | 2025-02-13 | 2025-02-19 | 2025-02-24
V_244 | 2024-08-09 | 2024-08-16 | 2024-08-18 | 2024-08-24 | 2024-08-29 | 2024-09-01 | 2024-09-02 | 2024-09-06 | 2024-09-11 | 2024-09-14 | 2024-09-18 | 2024-09-18 | 2024-10-27 | 2024-11-04 | 2024-11-11 | 2024-11-11 | 2024-11-18 | 2024-11-25 | 2024-11-25 | 2024-11-29 | 2024-11-29 | 2024-11-30 | 2024-12-06 | 2024-12-06 | 2024-12-13 | 2024-12-13 | 2024-12-13 | 2024-12-18 | 2024-12-22 | 2024-12-29 | 2025-01-03 | 2025-01-08 | 2025-01-15 | 2025-01-15 | 2025-01-19 | 2025-01-22 | 2025-01-22 | 2025-01-22 | 2025-01-27 | 2025-01-29 | 2025-02-02 | 2025-02-10 | 2024-11-04 | 2024-11-07 | 2024-11-14 | 2024-11-21 | 2024-11-25 | 2024-11-27 | 2024-12-02 | 2024-12-02 | 2024-12-04 | 2024-12-07 | 2024-12-08 | 2024-12-13 | 2024-12-13 | 2024-12-15 | 2024-12-18 | 2024-12-20 | 2024-12-20 | 2024-12-23 | 2024-12-26 | 2024-12-27 | 2024-12-28 | 2025-01-03 | 2025-01-08 | 2025-01-15 | 2025-01-15 | 2025-01-15 | 2025-01-19 | 2025-01-19 | 2025-01-22 | 2025-01-26 | 2025-02-03 | 2024-12-28 | 2025-01-15 | 2025-01-17 | 2025-02-08 | 2025-02-05 | 2025-02-10 | 2025-02-13 | 2025-02-19 | 2025-02-24
V_245 | 2024-08-09 | 2024-08-16 | 2024-08-18 | 2024-08-24 | 2024-08-29 | 2024-09-01 | 2024-09-02 | 2024-09-06 | 2024-09-11 | 2024-09-14 | 2024-09-18 | 2024-09-18 | 2024-10-27 | 2024-11-04 | 2024-11-11 | 2024-11-11 | 2024-11-18 | 2024-11-25 | 2024-11-25 | 2024-11-29 | 2024-11-29 | 2024-11-30 | 2024-12-06 | 2024-12-06 | 2024-12-13 | 2024-12-13 | 2024-12-13 | 2024-12-18 | 2024-12-22 | 2024-12-29 | 2025-01-03 | 2025-01-08 | 2025-01-15 | 2025-01-15 | 2025-01-19 | 2025-01-22 | 2025-01-22 | 2025-01-22 | 2025-01-27 | 2025-01-29 | 2025-02-02 | 2025-02-10 | 2024-11-04 | 2024-11-07 | 2024-11-14 | 2024-11-21 | 2024-11-25 | 2024-11-27 | 2024-12-02 | 2024-12-02 | 2024-12-04 | 2024-12-07 | 2024-12-08 | 2024-12-13 | 2024-12-13 | 2024-12-15 | 2024-12-18 | 2024-12-20 | 2024-12-20 | 2024-12-23 | 2024-12-26 | 2024-12-27 | 2024-12-28 | 2025-01-03 | 2025-01-08 | 2025-01-15 | 2025-01-15 | 2025-01-15 | 2025-01-19 | 2025-01-19 | 2025-01-22 | 2025-01-26 | 2025-02-03 | 2024-12-28 | 2025-01-15 | 2025-01-17 | 2025-02-08 | 2025-02-05 | 2025-02-10 | 2025-02-13 | 2025-02-19 | 2025-02-24
V_246 | 2024-08-09 | 2024-08-16 | 2024-08-18 | 2024-08-24 | 2024-08-29 | 2024-09-01 | 2024-09-02 | 2024-09-06 | 2024-09-11 | 2024-09-14 | 2024-09-18 | 2024-09-18 | 2024-10-27 | 2024-11-04 | 2024-11-11 | 2024-11-11 | 2024-11-18 | 2024-11-25 | 2024-11-25 | 2024-11-29 | 2024-11-29 | 2024-11-30 | 2024-12-06 | 2024-12-06 | 2024-12-13 | 2024-12-13 | 2024-12-13 | 2024-12-18 | 2024-12-22 | 2024-12-29 | 2025-01-03 | 2025-01-08 | 2025-01-15 | 2025-01-15 | 2025-01-19 | 2025-01-22 | 2025-01-22 | 2025-01-22 | 2025-01-27 | 2025-01-29 | 2025-02-02 | 2025-02-10 | 2024-11-04 | 2024-11-07 | 2024-11-14 | 2024-11-21 | 2024-11-25 | 2024-11-27 | 2024-12-02 | 2024-12-02 | 2024-12-04 | 2024-12-07 | 2024-12-08 | 2024-12-13 | 2024-12-13 | 2024-12-15 | 2024-12-18 | 2024-12-20 | 2024-12-20 | 2024-12-23 | 2024-12-26 | 2024-12-27 | 2024-12-28 | 2025-01-03 | 2025-01-08 | 2025-01-15 | 2025-01-15 | 2025-01-15 | 2025-01-19 | 2025-01-19 | 2025-01-22 | 2025-01-26 | 2025-02-03 | 2024-12-28 | 2025-01-15 | 2025-01-17 | 2025-02-08 | 2025-02-05 | 2025-02-10 | 2025-02-13 | 2025-02-19 | 2025-02-24
V_247 | 2024-08-09 | 2024-08-16 | 2024-08-18 | 2024-08-24 | 2024-08-29 | 2024-09-01 | 2024-09-02 | 2024-09-06 | 2024-09-11 | 2024-09-14 | 2024-09-18 | 2024-09-18 | 2024-10-27 | 2024-11-04 | 2024-11-11 | 2024-11-11 | 2024-11-18 | 2024-11-25 | 2024-11-25 | 2024-11-29 | 2024-11-29 | 2024-11-30 | 2024-12-06 | 2024-12-06 | 2024-12-13 | 2024-12-13 | 2024-12-13 | 2024-12-18 | 2024-12-22 | 2024-12-29 | 2025-01-03 | 2025-01-08 | 2025-01-15 | 2025-01-15 | 2025-01-19 | 2025-01-22 | 2025-01-22 | 2025-01-22 | 2025-01-27 | 2025-01-29 | 2025-02-02 | 2025-02-10 | 2024-11-04 | 2024-11-07 | 2024-11-14 | 2024-11-21 | 2024-11-25 | 2024-11-27 | 2024-12-02 | 2024-12-02 | 2024-12-04 | 2024-12-07 | 2024-12-08 | 2024-12-13 | 2024-12-13 | 2024-12-15 | 2024-12-18 | 2024-12-20 | 2024-12-20 | 2024-12-23 | 2024-12-26 | 2024-12-27 | 2024-12-28 | 2025-01-03 | 2025-01-08 | 2025-01-15 | 2025-01-15 | 2025-01-15 | 2025-01-19 | 2025-01-19 | 2025-01-22 | 2025-01-26 | 2025-02-03 | 2024-12-28 | 2025-01-15 | 2025-01-17 | 2025-02-08 | 2025-02-05 | 2025-02-10 | 2025-02-13 | 2025-02-19 | 2025-02-24
V_248 | 2024-08-09 | 2024-08-16 | 2024-08-18 | 2024-08-24 | 2024-08-29 | 2024-09-01 | 2024-09-02 | 2024-09-06 | 2024-09-11 | 2024-09-14 | 2024-09-18 | 2024-09-18 | 2024-10-27 | 2024-11-04 | 2024-11-11 | 2024-11-11 | 2024-11-18 | 2024-11-25 | 2024-11-25 | 2024-11-29 | 2024-11-29 | 2024-11-30 | 2024-12-06 | 2024-12-06 | 2024-12-13 | 2024-12-13 | 2024-12-13 | 2024-12-18 | 2024-12-22 | 2024-12-29 | 2025-01-03 | 2025-01-08 | 2025-01-15 | 2025-01-15 | 2025-01-19 | 2025-01-22 | 2025-01-22 | 2025-01-22 | 2025-01-27 | 2025-01-29 | 2025-02-02 | 2025-02-10 | 2024-11-04 | 2024-11-07 | 2024-11-14 | 2024-11-21 | 2024-11-25 | 2024-11-27 | 2024-12-02 | 2024-12-02 | 2024-12-04 | 2024-12-07 | 2024-12-08 | 2024-12-13 | 2024-12-13 | 2024-12-15 | 2024-12-18 | 2024-12-20 | 2024-12-20 | 2024-12-23 | 2024-12-26 | 2024-12-27 | 2024-12-28 | 2025-01-03 | 2025-01-08 | 2025-01-15 | 2025-01-15 | 2025-01-15 | 2025-01-19 | 2025-01-19 | 2025-01-22 | 2025-01-26 | 2025-02-03 | 2024-12-28 | 2025-01-15 | 2025-01-17 | 2025-02-08 | 2025-02-05 | 2025-02-10 | 2025-02-13 | 2025-02-19 | 2025-02-24
V_249 | 2024-08-16 | 2024-08-23 | 2024-08-25 | 2024-08-31 | 2024-09-05 | 2024-09-08 | 2024-09-09 | 2024-09-13 | 2024-09-18 | 2024-09-21 | 2024-09-25 | 2024-09-25 | 2024-11-04 | 2024-11-13 | 2024-11-20 | 2024-11-20 | 2024-11-27 | 2024-12-04 | 2024-12-04 | 2024-12-07 | 2024-12-07 | 2024-12-08 | 2024-12-14 | 2024-12-14 | 2024-12-21 | 2024-12-21 | 2024-12-21 | 2024-12-26 | 2024-12-30 | 2025-01-06 | 2025-01-11 | 2025-01-16 | 2025-01-23 | 2025-01-23 | 2025-01-27 | 2025-01-30 | 2025-01-30 | 2025-01-30 | 2025-02-05 | 2025-02-06 | 2025-02-10 | 2025-02-19 | 2024-11-13 | 2024-11-15 | 2024-11-22 | 2024-11-29 | 2024-12-04 | 2024-12-05 | 2024-12-11 | 2024-12-11 | 2024-12-12 | 2024-12-15 | 2024-12-16 | 2024-12-21 | 2024-12-21 | 2024-12-23 | 2024-12-26 | 2024-12-28 | 2024-12-28 | 2025-01-01 | 2025-01-03 | 2025-01-04 | 2025-01-05 | 2025-01-11 | 2025-01-16 | 2025-01-23 | 2025-01-23 | 2025-01-23 | 2025-01-27 | 2025-01-27 | 2025-01-30 | 2025-02-03 | 2025-02-12 | 2025-01-05 | 2025-01-23 | 2025-01-25 | 2025-02-16 | 2025-02-13 | 2025-02-19 | 2025-02-21 | 2025-02-27 | 2025-03-05
V_250 | 2024-08-16 | 2024-08-23 | 2024-08-25 | 2024-08-31 | 2024-09-05 | 2024-09-08 | 2024-09-09 | 2024-09-13 | 2024-09-18 | 2024-09-21 | 2024-09-25 | 2024-09-25 | 2024-11-04 | 2024-11-13 | 2024-11-20 | 2024-11-20 | 2024-11-27 | 2024-12-04 | 2024-12-04 | 2024-12-07 | 2024-12-07 | 2024-12-08 | 2024-12-14 | 2024-12-14 | 2024-12-21 | 2024-12-21 | 2024-12-21 | 2024-12-26 | 2024-12-30 | 2025-01-06 | 2025-01-11 | 2025-01-16 | 2025-01-23 | 2025-01-23 | 2025-01-27 | 2025-01-30 | 2025-01-30 | 2025-01-30 | 2025-02-05 | 2025-02-06 | 2025-02-10 | 2025-02-19 | 2024-11-13 | 2024-11-15 | 2024-11-22 | 2024-11-29 | 2024-12-04 | 2024-12-05 | 2024-12-11 | 2024-12-11 | 2024-12-12 | 2024-12-15 | 2024-12-16 | 2024-12-21 | 2024-12-21 | 2024-12-23 | 2024-12-26 | 2024-12-28 | 2024-12-28 | 2025-01-01 | 2025-01-03 | 2025-01-04 | 2025-01-05 | 2025-01-11 | 2025-01-16 | 2025-01-23 | 2025-01-23 | 2025-01-23 | 2025-01-27 | 2025-01-27 | 2025-01-30 | 2025-02-03 | 2025-02-12 | 2025-01-05 | 2025-01-23 | 2025-01-25 | 2025-02-16 | 2025-02-13 | 2025-02-19 | 2025-02-21 | 2025-02-27 | 2025-03-05
V_251 | 2024-08-16 | 2024-08-23 | 2024-08-25 | 2024-08-31 | 2024-09-05 | 2024-09-08 | 2024-09-09 | 2024-09-13 | 2024-09-18 | 2024-09-21 | 2024-09-25 | 2024-09-25 | 2024-11-04 | 2024-11-13 | 2024-11-20 | 2024-11-20 | 2024-11-27 | 2024-12-04 | 2024-12-04 | 2024-12-07 | 2024-12-07 | 2024-12-08 | 2024-12-14 | 2024-12-14 | 2024-12-21 | 2024-12-21 | 2024-12-21 | 2024-12-26 | 2024-12-30 | 2025-01-06 | 2025-01-11 | 2025-01-16 | 2025-01-23 | 2025-01-23 | 2025-01-27 | 2025-01-30 | 2025-01-30 | 2025-01-30 | 2025-02-05 | 2025-02-06 | 2025-02-10 | 2025-02-19 | 2024-11-13 | 2024-11-15 | 2024-11-22 | 2024-11-29 | 2024-12-04 | 2024-12-05 | 2024-12-11 | 2024-12-11 | 2024-12-12 | 2024-12-15 | 2024-12-16 | 2024-12-21 | 2024-12-21 | 2024-12-23 | 2024-12-26 | 2024-12-28 | 2024-12-28 | 2025-01-01 | 2025-01-03 | 2025-01-04 | 2025-01-05 | 2025-01-11 | 2025-01-16 | 2025-01-23 | 2025-01-23 | 2025-01-23 | 2025-01-27 | 2025-01-27 | 2025-01-30 | 2025-02-03 | 2025-02-12 | 2025-01-05 | 2025-01-23 | 2025-01-25 | 2025-02-16 | 2025-02-13 | 2025-02-19 | 2025-02-21 | 2025-02-27 | 2025-03-05
V_252 | 2024-08-16 | 2024-08-23 | 2024-08-25 | 2024-08-31 | 2024-09-05 | 2024-09-08 | 2024-09-09 | 2024-09-13 | 2024-09-18 | 2024-09-21 | 2024-09-25 | 2024-09-25 | 2024-11-04 | 2024-11-13 | 2024-11-20 | 2024-11-20 | 2024-11-27 | 2024-12-04 | 2024-12-04 | 2024-12-07 | 2024-12-07 | 2024-12-08 | 2024-12-14 | 2024-12-14 | 2024-12-21 | 2024-12-21 | 2024-12-21 | 2024-12-26 | 2024-12-30 | 2025-01-06 | 2025-01-11 | 2025-01-16 | 2025-01-23 | 2025-01-23 | 2025-01-27 | 2025-01-30 | 2025-01-30 | 2025-01-30 | 2025-02-05 | 2025-02-06 | 2025-02-10 | 2025-02-19 | 2024-11-13 | 2024-11-15 | 2024-11-22 | 2024-11-29 | 2024-12-04 | 2024-12-05 | 2024-12-11 | 2024-12-11 | 2024-12-12 | 2024-12-15 | 2024-12-16 | 2024-12-21 | 2024-12-21 | 2024-12-23 | 2024-12-26 | 2024-12-28 | 2024-12-28 | 2025-01-01 | 2025-01-03 | 2025-01-04 | 2025-01-05 | 2025-01-11 | 2025-01-16 | 2025-01-23 | 2025-01-23 | 2025-01-23 | 2025-01-27 | 2025-01-27 | 2025-01-30 | 2025-02-03 | 2025-02-12 | 2025-01-05 | 2025-01-23 | 2025-01-25 | 2025-02-16 | 2025-02-13 | 2025-02-19 | 2025-02-21 | 2025-02-27 | 2025-03-05
V_253 | 2024-08-16 | 2024-08-23 | 2024-08-25 | 2024-08-31 | 2024-09-05 | 2024-09-08 | 2024-09-09 | 2024-09-13 | 2024-09-18 | 2024-09-21 | 2024-09-25 | 2024-09-25 | 2024-11-04 | 2024-11-13 | 2024-11-20 | 2024-11-20 | 2024-11-27 | 2024-12-04 | 2024-12-04 | 2024-12-07 | 2024-12-07 | 2024-12-08 | 2024-12-14 | 2024-12-14 | 2024-12-21 | 2024-12-21 | 2024-12-21 | 2024-12-26 | 2024-12-30 | 2025-01-06 | 2025-01-11 | 2025-01-16 | 2025-01-23 | 2025-01-23 | 2025-01-27 | 2025-01-30 | 2025-01-30 | 2025-01-30 | 2025-02-05 | 2025-02-06 | 2025-02-10 | 2025-02-19 | 2024-11-13 | 2024-11-15 | 2024-11-22 | 2024-11-29 | 2024-12-04 | 2024-12-05 | 2024-12-11 | 2024-12-11 | 2024-12-12 | 2024-12-15 | 2024-12-16 | 2024-12-21 | 2024-12-21 | 2024-12-23 | 2024-12-26 | 2024-12-28 | 2024-12-28 | 2025-01-01 | 2025-01-03 | 2025-01-04 | 2025-01-05 | 2025-01-11 | 2025-01-16 | 2025-01-23 | 2025-01-23 | 2025-01-23 | 2025-01-27 | 2025-01-27 | 2025-01-30 | 2025-02-03 | 2025-02-12 | 2025-01-05 | 2025-01-23 | 2025-01-25 | 2025-02-16 | 2025-02-13 | 2025-02-19 | 2025-02-21 | 2025-02-27 | 2025-03-05
V_254 | 2024-08-16 | 2024-08-23 | 2024-08-25 | 2024-08-31 | 2024-09-05 | 2024-09-08 | 2024-09-09 | 2024-09-13 | 2024-09-18 | 2024-09-21 | 2024-09-25 | 2024-09-25 | 2024-11-04 | 2024-11-13 | 2024-11-20 | 2024-11-20 | 2024-11-27 | 2024-12-04 | 2024-12-04 | 2024-12-07 | 2024-12-07 | 2024-12-08 | 2024-12-14 | 2024-12-14 | 2024-12-21 | 2024-12-21 | 2024-12-21 | 2024-12-26 | 2024-12-30 | 2025-01-06 | 2025-01-11 | 2025-01-16 | 2025-01-23 | 2025-01-23 | 2025-01-27 | 2025-01-30 | 2025-01-30 | 2025-01-30 | 2025-02-05 | 2025-02-06 | 2025-02-10 | 2025-02-19 | 2024-11-13 | 2024-11-15 | 2024-11-22 | 2024-11-29 | 2024-12-04 | 2024-12-05 | 2024-12-11 | 2024-12-11 | 2024-12-12 | 2024-12-15 | 2024-12-16 | 2024-12-21 | 2024-12-21 | 2024-12-23 | 2024-12-26 | 2024-12-28 | 2024-12-28 | 2025-01-01 | 2025-01-03 | 2025-01-04 | 2025-01-05 | 2025-01-11 | 2025-01-16 | 2025-01-23 | 2025-01-23 | 2025-01-23 | 2025-01-27 | 2025-01-27 | 2025-01-30 | 2025-02-03 | 2025-02-12 | 2025-01-05 | 2025-01-23 | 2025-01-25 | 2025-02-16 | 2025-02-13 | 2025-02-19 | 2025-02-21 | 2025-02-27 | 2025-03-05
V_255 | 2024-08-16 | 2024-08-23 | 2024-08-25 | 2024-08-31 | 2024-09-05 | 2024-09-08 | 2024-09-09 | 2024-09-13 | 2024-09-18 | 2024-09-21 | 2024-09-25 | 2024-09-25 | 2024-11-04 | 2024-11-13 | 2024-11-20 | 2024-11-20 | 2024-11-27 | 2024-12-04 | 2024-12-04 | 2024-12-07 | 2024-12-07 | 2024-12-08 | 2024-12-14 | 2024-12-14 | 2024-12-21 | 2024-12-21 | 2024-12-21 | 2024-12-26 | 2024-12-30 | 2025-01-06 | 2025-01-11 | 2025-01-16 | 2025-01-23 | 2025-01-23 | 2025-01-27 | 2025-01-30 | 2025-01-30 | 2025-01-30 | 2025-02-05 | 2025-02-06 | 2025-02-10 | 2025-02-19 | 2024-11-13 | 2024-11-15 | 2024-11-22 | 2024-11-29 | 2024-12-04 | 2024-12-05 | 2024-12-11 | 2024-12-11 | 2024-12-12 | 2024-12-15 | 2024-12-16 | 2024-12-21 | 2024-12-21 | 2024-12-23 | 2024-12-26 | 2024-12-28 | 2024-12-28 | 2025-01-01 | 2025-01-03 | 2025-01-04 | 2025-01-05 | 2025-01-11 | 2025-01-16 | 2025-01-23 | 2025-01-23 | 2025-01-23 | 2025-01-27 | 2025-01-27 | 2025-01-30 | 2025-02-03 | 2025-02-12 | 2025-01-05 | 2025-01-23 | 2025-01-25 | 2025-02-16 | 2025-02-13 | 2025-02-19 | 2025-02-21 | 2025-02-27 | 2025-03-05
V_256 | 2024-08-16 | 2024-08-23 | 2024-08-25 | 2024-08-31 | 2024-09-05 | 2024-09-08 | 2024-09-09 | 2024-09-13 | 2024-09-18 | 2024-09-21 | 2024-09-25 | 2024-09-25 | 2024-11-04 | 2024-11-13 | 2024-11-20 | 2024-11-20 | 2024-11-27 | 2024-12-04 | 2024-12-04 | 2024-12-07 | 2024-12-07 | 2024-12-08 | 2024-12-14 | 2024-12-14 | 2024-12-21 | 2024-12-21 | 2024-12-21 | 2024-12-26 | 2024-12-30 | 2025-01-06 | 2025-01-11 | 2025-01-16 | 2025-01-23 | 2025-01-23 | 2025-01-27 | 2025-01-30 | 2025-01-30 | 2025-01-30 | 2025-02-05 | 2025-02-06 | 2025-02-10 | 2025-02-19 | 2024-11-13 | 2024-11-15 | 2024-11-22 | 2024-11-29 | 2024-12-04 | 2024-12-05 | 2024-12-11 | 2024-12-11 | 2024-12-12 | 2024-12-15 | 2024-12-16 | 2024-12-21 | 2024-12-21 | 2024-12-23 | 2024-12-26 | 2024-12-28 | 2024-12-28 | 2025-01-01 | 2025-01-03 | 2025-01-04 | 2025-01-05 | 2025-01-11 | 2025-01-16 | 2025-01-23 | 2025-01-23 | 2025-01-23 | 2025-01-27 | 2025-01-27 | 2025-01-30 | 2025-02-03 | 2025-02-12 | 2025-01-05 | 2025-01-23 | 2025-01-25 | 2025-02-16 | 2025-02-13 | 2025-02-19 | 2025-02-21 | 2025-02-27 | 2025-03-05
V_257 | 2024-08-23 | 2024-08-30 | 2024-09-01 | 2024-09-07 | 2024-09-12 | 2024-09-15 | 2024-09-16 | 2024-09-20 | 2024-09-25 | 2024-09-28 | 2024-10-02 | 2024-10-02 | 2024-11-13 | 2024-11-21 | 2024-11-28 | 2024-11-28 | 2024-12-05 | 2024-12-12 | 2024-12-12 | 2024-12-15 | 2024-12-15 | 2024-12-16 | 2024-12-22 | 2024-12-22 | 2024-12-29 | 2024-12-29 | 2024-12-29 | 2025-01-03 | 2025-01-08 | 2025-01-15 | 2025-01-19 | 2025-01-24 | 2025-01-31 | 2025-01-31 | 2025-02-05 | 2025-02-07 | 2025-02-07 | 2025-02-07 | 2025-02-13 | 2025-02-14 | 2025-02-19 | 2025-02-27 | 2024-11-21 | 2024-11-23 | 2024-11-30 | 2024-12-07 | 2024-12-12 | 2024-12-13 | 2024-12-19 | 2024-12-19 | 2024-12-20 | 2024-12-23 | 2024-12-25 | 2024-12-29 | 2024-12-29 | 2025-01-01 | 2025-01-03 | 2025-01-05 | 2025-01-05 | 2025-01-09 | 2025-01-11 | 2025-01-12 | 2025-01-13 | 2025-01-19 | 2025-01-24 | 2025-01-31 | 2025-01-31 | 2025-01-31 | 2025-02-05 | 2025-02-05 | 2025-02-07 | 2025-02-12 | 2025-02-20 | 2025-01-13 | 2025-01-31 | 2025-02-02 | 2025-02-24 | 2025-02-21 | 2025-02-27 | 2025-03-01 | 2025-03-07 | 2025-03-13
V_258 | 2024-08-23 | 2024-08-30 | 2024-09-01 | 2024-09-07 | 2024-09-12 | 2024-09-15 | 2024-09-16 | 2024-09-20 | 2024-09-25 | 2024-09-28 | 2024-10-02 | 2024-10-02 | 2024-11-13 | 2024-11-21 | 2024-11-28 | 2024-11-28 | 2024-12-05 | 2024-12-12 | 2024-12-12 | 2024-12-15 | 2024-12-15 | 2024-12-16 | 2024-12-22 | 2024-12-22 | 2024-12-29 | 2024-12-29 | 2024-12-29 | 2025-01-03 | 2025-01-08 | 2025-01-15 | 2025-01-19 | 2025-01-24 | 2025-01-31 | 2025-01-31 | 2025-02-05 | 2025-02-07 | 2025-02-07 | 2025-02-07 | 2025-02-13 | 2025-02-14 | 2025-02-19 | 2025-02-27 | 2024-11-21 | 2024-11-23 | 2024-11-30 | 2024-12-07 | 2024-12-12 | 2024-12-13 | 2024-12-19 | 2024-12-19 | 2024-12-20 | 2024-12-23 | 2024-12-25 | 2024-12-29 | 2024-12-29 | 2025-01-01 | 2025-01-03 | 2025-01-05 | 2025-01-05 | 2025-01-09 | 2025-01-11 | 2025-01-12 | 2025-01-13 | 2025-01-19 | 2025-01-24 | 2025-01-31 | 2025-01-31 | 2025-01-31 | 2025-02-05 | 2025-02-05 | 2025-02-07 | 2025-02-12 | 2025-02-20 | 2025-01-13 | 2025-01-31 | 2025-02-02 | 2025-02-24 | 2025-02-21 | 2025-02-27 | 2025-03-01 | 2025-03-07 | 2025-03-13
V_259 | 2024-08-23 | 2024-08-30 | 2024-09-01 | 2024-09-07 | 2024-09-12 | 2024-09-15 | 2024-09-16 | 2024-09-20 | 2024-09-25 | 2024-09-28 | 2024-10-02 | 2024-10-02 | 2024-11-13 | 2024-11-21 | 2024-11-28 | 2024-11-28 | 2024-12-05 | 2024-12-12 | 2024-12-12 | 2024-12-15 | 2024-12-15 | 2024-12-16 | 2024-12-22 | 2024-12-22 | 2024-12-29 | 2024-12-29 | 2024-12-29 | 2025-01-03 | 2025-01-08 | 2025-01-15 | 2025-01-19 | 2025-01-24 | 2025-01-31 | 2025-01-31 | 2025-02-05 | 2025-02-07 | 2025-02-07 | 2025-02-07 | 2025-02-13 | 2025-02-14 | 2025-02-19 | 2025-02-27 | 2024-11-21 | 2024-11-23 | 2024-11-30 | 2024-12-07 | 2024-12-12 | 2024-12-13 | 2024-12-19 | 2024-12-19 | 2024-12-20 | 2024-12-23 | 2024-12-25 | 2024-12-29 | 2024-12-29 | 2025-01-01 | 2025-01-03 | 2025-01-05 | 2025-01-05 | 2025-01-09 | 2025-01-11 | 2025-01-12 | 2025-01-13 | 2025-01-19 | 2025-01-24 | 2025-01-31 | 2025-01-31 | 2025-01-31 | 2025-02-05 | 2025-02-05 | 2025-02-07 | 2025-02-12 | 2025-02-20 | 2025-01-13 | 2025-01-31 | 2025-02-02 | 2025-02-24 | 2025-02-21 | 2025-02-27 | 2025-03-01 | 2025-03-07 | 2025-03-13
V_260 | 2024-08-23 | 2024-08-30 | 2024-09-01 | 2024-09-07 | 2024-09-12 | 2024-09-15 | 2024-09-16 | 2024-09-20 | 2024-09-25 | 2024-09-28 | 2024-10-02 | 2024-10-02 | 2024-11-13 | 2024-11-21 | 2024-11-28 | 2024-11-28 | 2024-12-05 | 2024-12-12 | 2024-12-12 | 2024-12-15 | 2024-12-15 | 2024-12-16 | 2024-12-22 | 2024-12-22 | 2024-12-29 | 2024-12-29 | 2024-12-29 | 2025-01-03 | 2025-01-08 | 2025-01-15 | 2025-01-19 | 2025-01-24 | 2025-01-31 | 2025-01-31 | 2025-02-05 | 2025-02-07 | 2025-02-07 | 2025-02-07 | 2025-02-13 | 2025-02-14 | 2025-02-19 | 2025-02-27 | 2024-11-21 | 2024-11-23 | 2024-11-30 | 2024-12-07 | 2024-12-12 | 2024-12-13 | 2024-12-19 | 2024-12-19 | 2024-12-20 | 2024-12-23 | 2024-12-25 | 2024-12-29 | 2024-12-29 | 2025-01-01 | 2025-01-03 | 2025-01-05 | 2025-01-05 | 2025-01-09 | 2025-01-11 | 2025-01-12 | 2025-01-13 | 2025-01-19 | 2025-01-24 | 2025-01-31 | 2025-01-31 | 2025-01-31 | 2025-02-05 | 2025-02-05 | 2025-02-07 | 2025-02-12 | 2025-02-20 | 2025-01-13 | 2025-01-31 | 2025-02-02 | 2025-02-24 | 2025-02-21 | 2025-02-27 | 2025-03-01 | 2025-03-07 | 2025-03-13
V_261 | 2024-08-23 | 2024-08-30 | 2024-09-01 | 2024-09-07 | 2024-09-12 | 2024-09-15 | 2024-09-16 | 2024-09-20 | 2024-09-25 | 2024-09-28 | 2024-10-02 | 2024-10-02 | 2024-11-13 | 2024-11-21 | 2024-11-28 | 2024-11-28 | 2024-12-05 | 2024-12-12 | 2024-12-12 | 2024-12-15 | 2024-12-15 | 2024-12-16 | 2024-12-22 | 2024-12-22 | 2024-12-29 | 2024-12-29 | 2024-12-29 | 2025-01-03 | 2025-01-08 | 2025-01-15 | 2025-01-19 | 2025-01-24 | 2025-01-31 | 2025-01-31 | 2025-02-05 | 2025-02-07 | 2025-02-07 | 2025-02-07 | 2025-02-13 | 2025-02-14 | 2025-02-19 | 2025-02-27 | 2024-11-21 | 2024-11-23 | 2024-11-30 | 2024-12-07 | 2024-12-12 | 2024-12-13 | 2024-12-19 | 2024-12-19 | 2024-12-20 | 2024-12-23 | 2024-12-25 | 2024-12-29 | 2024-12-29 | 2025-01-01 | 2025-01-03 | 2025-01-05 | 2025-01-05 | 2025-01-09 | 2025-01-11 | 2025-01-12 | 2025-01-13 | 2025-01-19 | 2025-01-24 | 2025-01-31 | 2025-01-31 | 2025-01-31 | 2025-02-05 | 2025-02-05 | 2025-02-07 | 2025-02-12 | 2025-02-20 | 2025-01-13 | 2025-01-31 | 2025-02-02 | 2025-02-24 | 2025-02-21 | 2025-02-27 | 2025-03-01 | 2025-03-07 | 2025-03-13
V_262 | 2024-08-23 | 2024-08-30 | 2024-09-01 | 2024-09-07 | 2024-09-12 | 2024-09-15 | 2024-09-16 | 2024-09-20 | 2024-09-25 | 2024-09-28 | 2024-10-02 | 2024-10-02 | 2024-11-13 | 2024-11-21 | 2024-11-28 | 2024-11-28 | 2024-12-05 | 2024-12-12 | 2024-12-12 | 2024-12-15 | 2024-12-15 | 2024-12-16 | 2024-12-22 | 2024-12-22 | 2024-12-29 | 2024-12-29 | 2024-12-29 | 2025-01-03 | 2025-01-08 | 2025-01-15 | 2025-01-19 | 2025-01-24 | 2025-01-31 | 2025-01-31 | 2025-02-05 | 2025-02-07 | 2025-02-07 | 2025-02-07 | 2025-02-13 | 2025-02-14 | 2025-02-19 | 2025-02-27 | 2024-11-21 | 2024-11-23 | 2024-11-30 | 2024-12-07 | 2024-12-12 | 2024-12-13 | 2024-12-19 | 2024-12-19 | 2024-12-20 | 2024-12-23 | 2024-12-25 | 2024-12-29 | 2024-12-29 | 2025-01-01 | 2025-01-03 | 2025-01-05 | 2025-01-05 | 2025-01-09 | 2025-01-11 | 2025-01-12 | 2025-01-13 | 2025-01-19 | 2025-01-24 | 2025-01-31 | 2025-01-31 | 2025-01-31 | 2025-02-05 | 2025-02-05 | 2025-02-07 | 2025-02-12 | 2025-02-20 | 2025-01-13 | 2025-01-31 | 2025-02-02 | 2025-02-24 | 2025-02-21 | 2025-02-27 | 2025-03-01 | 2025-03-07 | 2025-03-13
V_263 | 2024-08-23 | 2024-08-30 | 2024-09-01 | 2024-09-07 | 2024-09-12 | 2024-09-15 | 2024-09-16 | 2024-09-20 | 2024-09-25 | 2024-09-28 | 2024-10-02 | 2024-10-02 | 2024-11-13 | 2024-11-21 | 2024-11-28 | 2024-11-28 | 2024-12-05 | 2024-12-12 | 2024-12-12 | 2024-12-15 | 2024-12-15 | 2024-12-16 | 2024-12-22 | 2024-12-22 | 2024-12-29 | 2024-12-29 | 2024-12-29 | 2025-01-03 | 2025-01-08 | 2025-01-15 | 2025-01-19 | 2025-01-24 | 2025-01-31 | 2025-01-31 | 2025-02-05 | 2025-02-07 | 2025-02-07 | 2025-02-07 | 2025-02-13 | 2025-02-14 | 2025-02-19 | 2025-02-27 | 2024-11-21 | 2024-11-23 | 2024-11-30 | 2024-12-07 | 2024-12-12 | 2024-12-13 | 2024-12-19 | 2024-12-19 | 2024-12-20 | 2024-12-23 | 2024-12-25 | 2024-12-29 | 2024-12-29 | 2025-01-01 | 2025-01-03 | 2025-01-05 | 2025-01-05 | 2025-01-09 | 2025-01-11 | 2025-01-12 | 2025-01-13 | 2025-01-19 | 2025-01-24 | 2025-01-31 | 2025-01-31 | 2025-01-31 | 2025-02-05 | 2025-02-05 | 2025-02-07 | 2025-02-12 | 2025-02-20 | 2025-01-13 | 2025-01-31 | 2025-02-02 | 2025-02-24 | 2025-02-21 | 2025-02-27 | 2025-03-01 | 2025-03-07 | 2025-03-13
V_264 | 2024-08-23 | 2024-08-30 | 2024-09-01 | 2024-09-07 | 2024-09-12 | 2024-09-15 | 2024-09-16 | 2024-09-20 | 2024-09-25 | 2024-09-28 | 2024-10-02 | 2024-10-02 | 2024-11-13 | 2024-11-21 | 2024-11-28 | 2024-11-28 | 2024-12-05 | 2024-12-12 | 2024-12-12 | 2024-12-15 | 2024-12-15 | 2024-12-16 | 2024-12-22 | 2024-12-22 | 2024-12-29 | 2024-12-29 | 2024-12-29 | 2025-01-03 | 2025-01-08 | 2025-01-15 | 2025-01-19 | 2025-01-24 | 2025-01-31 | 2025-01-31 | 2025-02-05 | 2025-02-07 | 2025-02-07 | 2025-02-07 | 2025-02-13 | 2025-02-14 | 2025-02-19 | 2025-02-27 | 2024-11-21 | 2024-11-23 | 2024-11-30 | 2024-12-07 | 2024-12-12 | 2024-12-13 | 2024-12-19 | 2024-12-19 | 2024-12-20 | 2024-12-23 | 2024-12-25 | 2024-12-29 | 2024-12-29 | 2025-01-01 | 2025-01-03 | 2025-01-05 | 2025-01-05 | 2025-01-09 | 2025-01-11 | 2025-01-12 | 2025-01-13 | 2025-01-19 | 2025-01-24 | 2025-01-31 | 2025-01-31 | 2025-01-31 | 2025-02-05 | 2025-02-05 | 2025-02-07 | 2025-02-12 | 2025-02-20 | 2025-01-13 | 2025-01-31 | 2025-02-02 | 2025-02-24 | 2025-02-21 | 2025-02-27 | 2025-03-01 | 2025-03-07 | 2025-03-13
V_265 | 2024-08-30 | 2024-09-06 | 2024-09-08 | 2024-09-14 | 2024-09-19 | 2024-09-22 | 2024-09-23 | 2024-09-27 | 2024-10-02 | 2024-10-05 | 2024-10-09 | 2024-10-09 | 2024-11-21 | 2024-11-29 | 2024-12-06 | 2024-12-06 | 2024-12-13 | 2024-12-20 | 2024-12-20 | 2024-12-23 | 2024-12-23 | 2024-12-25 | 2024-12-30 | 2024-12-30 | 2025-01-06 | 2025-01-06 | 2025-01-06 | 2025-01-11 | 2025-01-16 | 2025-01-23 | 2025-01-27 | 2025-02-01 | 2025-02-08 | 2025-02-08 | 2025-02-13 | 2025-02-15 | 2025-02-15 | 2025-02-15 | 2025-02-21 | 2025-02-22 | 2025-02-27 | 2025-03-07 | 2024-11-29 | 2024-12-01 | 2024-12-08 | 2024-12-15 | 2024-12-20 | 2024-12-21 | 2024-12-27 | 2024-12-27 | 2024-12-28 | 2025-01-01 | 2025-01-02 | 2025-01-06 | 2025-01-06 | 2025-01-09 | 2025-01-11 | 2025-01-13 | 2025-01-13 | 2025-01-17 | 2025-01-19 | 2025-01-20 | 2025-01-22 | 2025-01-27 | 2025-02-01 | 2025-02-08 | 2025-02-08 | 2025-02-08 | 2025-02-13 | 2025-02-13 | 2025-02-15 | 2025-02-20 | 2025-02-28 | 2025-01-22 | 2025-02-08 | 2025-02-10 | 2025-03-05 | 2025-03-01 | 2025-03-07 | 2025-03-09 | 2025-03-15 | 2025-03-21
V_266 | 2024-08-30 | 2024-09-06 | 2024-09-08 | 2024-09-14 | 2024-09-19 | 2024-09-22 | 2024-09-23 | 2024-09-27 | 2024-10-02 | 2024-10-05 | 2024-10-09 | 2024-10-09 | 2024-11-21 | 2024-11-29 | 2024-12-06 | 2024-12-06 | 2024-12-13 | 2024-12-20 | 2024-12-20 | 2024-12-23 | 2024-12-23 | 2024-12-25 | 2024-12-30 | 2024-12-30 | 2025-01-06 | 2025-01-06 | 2025-01-06 | 2025-01-11 | 2025-01-16 | 2025-01-23 | 2025-01-27 | 2025-02-01 | 2025-02-08 | 2025-02-08 | 2025-02-13 | 2025-02-15 | 2025-02-15 | 2025-02-15 | 2025-02-21 | 2025-02-22 | 2025-02-27 | 2025-03-07 | 2024-11-29 | 2024-12-01 | 2024-12-08 | 2024-12-15 | 2024-12-20 | 2024-12-21 | 2024-12-27 | 2024-12-27 | 2024-12-28 | 2025-01-01 | 2025-01-02 | 2025-01-06 | 2025-01-06 | 2025-01-09 | 2025-01-11 | 2025-01-13 | 2025-01-13 | 2025-01-17 | 2025-01-19 | 2025-01-20 | 2025-01-22 | 2025-01-27 | 2025-02-01 | 2025-02-08 | 2025-02-08 | 2025-02-08 | 2025-02-13 | 2025-02-13 | 2025-02-15 | 2025-02-20 | 2025-02-28 | 2025-01-22 | 2025-02-08 | 2025-02-10 | 2025-03-05 | 2025-03-01 | 2025-03-07 | 2025-03-09 | 2025-03-15 | 2025-03-21
V_267 | 2024-08-30 | 2024-09-06 | 2024-09-08 | 2024-09-14 | 2024-09-19 | 2024-09-22 | 2024-09-23 | 2024-09-27 | 2024-10-02 | 2024-10-05 | 2024-10-09 | 2024-10-09 | 2024-11-21 | 2024-11-29 | 2024-12-06 | 2024-12-06 | 2024-12-13 | 2024-12-20 | 2024-12-20 | 2024-12-23 | 2024-12-23 | 2024-12-25 | 2024-12-30 | 2024-12-30 | 2025-01-06 | 2025-01-06 | 2025-01-06 | 2025-01-11 | 2025-01-16 | 2025-01-23 | 2025-01-27 | 2025-02-01 | 2025-02-08 | 2025-02-08 | 2025-02-13 | 2025-02-15 | 2025-02-15 | 2025-02-15 | 2025-02-21 | 2025-02-22 | 2025-02-27 | 2025-03-07 | 2024-11-29 | 2024-12-01 | 2024-12-08 | 2024-12-15 | 2024-12-20 | 2024-12-21 | 2024-12-27 | 2024-12-27 | 2024-12-28 | 2025-01-01 | 2025-01-02 | 2025-01-06 | 2025-01-06 | 2025-01-09 | 2025-01-11 | 2025-01-13 | 2025-01-13 | 2025-01-17 | 2025-01-19 | 2025-01-20 | 2025-01-22 | 2025-01-27 | 2025-02-01 | 2025-02-08 | 2025-02-08 | 2025-02-08 | 2025-02-13 | 2025-02-13 | 2025-02-15 | 2025-02-20 | 2025-02-28 | 2025-01-22 | 2025-02-08 | 2025-02-10 | 2025-03-05 | 2025-03-01 | 2025-03-07 | 2025-03-09 | 2025-03-15 | 2025-03-21
V_268 | 2024-08-30 | 2024-09-06 | 2024-09-08 | 2024-09-14 | 2024-09-19 | 2024-09-22 | 2024-09-23 | 2024-09-27 | 2024-10-02 | 2024-10-05 | 2024-10-09 | 2024-10-09 | 2024-11-21 | 2024-11-29 | 2024-12-06 | 2024-12-06 | 2024-12-13 | 2024-12-20 | 2024-12-20 | 2024-12-23 | 2024-12-23 | 2024-12-25 | 2024-12-30 | 2024-12-30 | 2025-01-06 | 2025-01-06 | 2025-01-06 | 2025-01-11 | 2025-01-16 | 2025-01-23 | 2025-01-27 | 2025-02-01 | 2025-02-08 | 2025-02-08 | 2025-02-13 | 2025-02-15 | 2025-02-15 | 2025-02-15 | 2025-02-21 | 2025-02-22 | 2025-02-27 | 2025-03-07 | 2024-11-29 | 2024-12-01 | 2024-12-08 | 2024-12-15 | 2024-12-20 | 2024-12-21 | 2024-12-27 | 2024-12-27 | 2024-12-28 | 2025-01-01 | 2025-01-02 | 2025-01-06 | 2025-01-06 | 2025-01-09 | 2025-01-11 | 2025-01-13 | 2025-01-13 | 2025-01-17 | 2025-01-19 | 2025-01-20 | 2025-01-22 | 2025-01-27 | 2025-02-01 | 2025-02-08 | 2025-02-08 | 2025-02-08 | 2025-02-13 | 2025-02-13 | 2025-02-15 | 2025-02-20 | 2025-02-28 | 2025-01-22 | 2025-02-08 | 2025-02-10 | 2025-03-05 | 2025-03-01 | 2025-03-07 | 2025-03-09 | 2025-03-15 | 2025-03-21
V_269 | 2024-08-30 | 2024-09-06 | 2024-09-08 | 2024-09-14 | 2024-09-19 | 2024-09-22 | 2024-09-23 | 2024-09-27 | 2024-10-02 | 2024-10-05 | 2024-10-09 | 2024-10-09 | 2024-11-21 | 2024-11-29 | 2024-12-06 | 2024-12-06 | 2024-12-13 | 2024-12-20 | 2024-12-20 | 2024-12-23 | 2024-12-23 | 2024-12-25 | 2024-12-30 | 2024-12-30 | 2025-01-06 | 2025-01-06 | 2025-01-06 | 2025-01-11 | 2025-01-16 | 2025-01-23 | 2025-01-27 | 2025-02-01 | 2025-02-08 | 2025-02-08 | 2025-02-13 | 2025-02-15 | 2025-02-15 | 2025-02-15 | 2025-02-21 | 2025-02-22 | 2025-02-27 | 2025-03-07 | 2024-11-29 | 2024-12-01 | 2024-12-08 | 2024-12-15 | 2024-12-20 | 2024-12-21 | 2024-12-27 | 2024-12-27 | 2024-12-28 | 2025-01-01 | 2025-01-02 | 2025-01-06 | 2025-01-06 | 2025-01-09 | 2025-01-11 | 2025-01-13 | 2025-01-13 | 2025-01-17 | 2025-01-19 | 2025-01-20 | 2025-01-22 | 2025-01-27 | 2025-02-01 | 2025-02-08 | 2025-02-08 | 2025-02-08 | 2025-02-13 | 2025-02-13 | 2025-02-15 | 2025-02-20 | 2025-02-28 | 2025-01-22 | 2025-02-08 | 2025-02-10 | 2025-03-05 | 2025-03-01 | 2025-03-07 | 2025-03-09 | 2025-03-15 | 2025-03-21
V_270 | 2024-08-30 | 2024-09-06 | 2024-09-08 | 2024-09-14 | 2024-09-19 | 2024-09-22 | 2024-09-23 | 2024-09-27 | 2024-10-02 | 2024-10-05 | 2024-10-09 | 2024-10-09 | 2024-11-21 | 2024-11-29 | 2024-12-06 | 2024-12-06 | 2024-12-13 | 2024-12-20 | 2024-12-20 | 2024-12-23 | 2024-12-23 | 2024-12-25 | 2024-12-30 | 2024-12-30 | 2025-01-06 | 2025-01-06 | 2025-01-06 | 2025-01-11 | 2025-01-16 | 2025-01-23 | 2025-01-27 | 2025-02-01 | 2025-02-08 | 2025-02-08 | 2025-02-13 | 2025-02-15 | 2025-02-15 | 2025-02-15 | 2025-02-21 | 2025-02-22 | 2025-02-27 | 2025-03-07 | 2024-11-29 | 2024-12-01 | 2024-12-08 | 2024-12-15 | 2024-12-20 | 2024-12-21 | 2024-12-27 | 2024-12-27 | 2024-12-28 | 2025-01-01 | 2025-01-02 | 2025-01-06 | 2025-01-06 | 2025-01-09 | 2025-01-11 | 2025-01-13 | 2025-01-13 | 2025-01-17 | 2025-01-19 | 2025-01-20 | 2025-01-22 | 2025-01-27 | 2025-02-01 | 2025-02-08 | 2025-02-08 | 2025-02-08 | 2025-02-13 | 2025-02-13 | 2025-02-15 | 2025-02-20 | 2025-02-28 | 2025-01-22 | 2025-02-08 | 2025-02-10 | 2025-03-05 | 2025-03-01 | 2025-03-07 | 2025-03-09 | 2025-03-15 | 2025-03-21
V_271 | 2024-08-30 | 2024-09-06 | 2024-09-08 | 2024-09-14 | 2024-09-19 | 2024-09-22 | 2024-09-23 | 2024-09-27 | 2024-10-02 | 2024-10-05 | 2024-10-09 | 2024-10-09 | 2024-11-21 | 2024-11-29 | 2024-12-06 | 2024-12-06 | 2024-12-13 | 2024-12-20 | 2024-12-20 | 2024-12-23 | 2024-12-23 | 2024-12-25 | 2024-12-30 | 2024-12-30 | 2025-01-06 | 2025-01-06 | 2025-01-06 | 2025-01-11 | 2025-01-16 | 2025-01-23 | 2025-01-27 | 2025-02-01 | 2025-02-08 | 2025-02-08 | 2025-02-13 | 2025-02-15 | 2025-02-15 | 2025-02-15 | 2025-02-21 | 2025-02-22 | 2025-02-27 | 2025-03-07 | 2024-11-29 | 2024-12-01 | 2024-12-08 | 2024-12-15 | 2024-12-20 | 2024-12-21 | 2024-12-27 | 2024-12-27 | 2024-12-28 | 2025-01-01 | 2025-01-02 | 2025-01-06 | 2025-01-06 | 2025-01-09 | 2025-01-11 | 2025-01-13 | 2025-01-13 | 2025-01-17 | 2025-01-19 | 2025-01-20 | 2025-01-22 | 2025-01-27 | 2025-02-01 | 2025-02-08 | 2025-02-08 | 2025-02-08 | 2025-02-13 | 2025-02-13 | 2025-02-15 | 2025-02-20 | 2025-02-28 | 2025-01-22 | 2025-02-08 | 2025-02-10 | 2025-03-05 | 2025-03-01 | 2025-03-07 | 2025-03-09 | 2025-03-15 | 2025-03-21
V_272 | 2024-08-30 | 2024-09-06 | 2024-09-08 | 2024-09-14 | 2024-09-19 | 2024-09-22 | 2024-09-23 | 2024-09-27 | 2024-10-02 | 2024-10-05 | 2024-10-09 | 2024-10-09 | 2024-11-21 | 2024-11-29 | 2024-12-06 | 2024-12-06 | 2024-12-13 | 2024-12-20 | 2024-12-20 | 2024-12-23 | 2024-12-23 | 2024-12-25 | 2024-12-30 | 2024-12-30 | 2025-01-06 | 2025-01-06 | 2025-01-06 | 2025-01-11 | 2025-01-16 | 2025-01-23 | 2025-01-27 | 2025-02-01 | 2025-02-08 | 2025-02-08 | 2025-02-13 | 2025-02-15 | 2025-02-15 | 2025-02-15 | 2025-02-21 | 2025-02-22 | 2025-02-27 | 2025-03-07 | 2024-11-29 | 2024-12-01 | 2024-12-08 | 2024-12-15 | 2024-12-20 | 2024-12-21 | 2024-12-27 | 2024-12-27 | 2024-12-28 | 2025-01-01 | 2025-01-02 | 2025-01-06 | 2025-01-06 | 2025-01-09 | 2025-01-11 | 2025-01-13 | 2025-01-13 | 2025-01-17 | 2025-01-19 | 2025-01-20 | 2025-01-22 | 2025-01-27 | 2025-02-01 | 2025-02-08 | 2025-02-08 | 2025-02-08 | 2025-02-13 | 2025-02-13 | 2025-02-15 | 2025-02-20 | 2025-02-28 | 2025-01-22 | 2025-02-08 | 2025-02-10 | 2025-03-05 | 2025-03-01 | 2025-03-07 | 2025-03-09 | 2025-03-15 | 2025-03-21
V_273 | 2024-09-06 | 2024-09-13 | 2024-09-15 | 2024-09-21 | 2024-09-26 | 2024-09-29 | 2024-09-30 | 2024-10-04 | 2024-10-09 | 2024-10-12 | 2024-10-16 | 2024-10-16 | 2024-11-29 | 2024-12-07 | 2024-12-14 | 2024-12-14 | 2024-12-21 | 2024-12-28 | 2024-12-28 | 2025-01-01 | 2025-01-01 | 2025-01-02 | 2025-01-08 | 2025-01-08 | 2025-01-15 | 2025-01-15 | 2025-01-15 | 2025-01-19 | 2025-01-24 | 2025-01-31 | 2025-02-05 | 2025-02-09 | 2025-02-16 | 2025-02-16 | 2025-02-21 | 2025-02-23 | 2025-02-23 | 2025-02-23 | 2025-03-01 | 2025-03-02 | 2025-03-07 | 2025-03-15 | 2024-12-07 | 2024-12-09 | 2024-12-16 | 2024-12-23 | 2024-12-28 | 2024-12-29 | 2025-01-04 | 2025-01-04 | 2025-01-05 | 2025-01-09 | 2025-01-10 | 2025-01-15 | 2025-01-15 | 2025-01-17 | 2025-01-19 | 2025-01-22 | 2025-01-22 | 2025-01-25 | 2025-01-27 | 2025-01-29 | 2025-01-30 | 2025-02-05 | 2025-02-09 | 2025-02-16 | 2025-02-16 | 2025-02-16 | 2025-02-21 | 2025-02-21 | 2025-02-23 | 2025-02-28 | 2025-03-08 | 2025-01-30 | 2025-02-16 | 2025-02-19 | 2025-03-13 | 2025-03-09 | 2025-03-15 | 2025-03-17 | 2025-03-23 | 2025-03-29
V_274 | 2024-09-06 | 2024-09-13 | 2024-09-15 | 2024-09-21 | 2024-09-26 | 2024-09-29 | 2024-09-30 | 2024-10-04 | 2024-10-09 | 2024-10-12 | 2024-10-16 | 2024-10-16 | 2024-11-29 | 2024-12-07 | 2024-12-14 | 2024-12-14 | 2024-12-21 | 2024-12-28 | 2024-12-28 | 2025-01-01 | 2025-01-01 | 2025-01-02 | 2025-01-08 | 2025-01-08 | 2025-01-15 | 2025-01-15 | 2025-01-15 | 2025-01-19 | 2025-01-24 | 2025-01-31 | 2025-02-05 | 2025-02-09 | 2025-02-16 | 2025-02-16 | 2025-02-21 | 2025-02-23 | 2025-02-23 | 2025-02-23 | 2025-03-01 | 2025-03-02 | 2025-03-07 | 2025-03-15 | 2024-12-07 | 2024-12-09 | 2024-12-16 | 2024-12-23 | 2024-12-28 | 2024-12-29 | 2025-01-04 | 2025-01-04 | 2025-01-05 | 2025-01-09 | 2025-01-10 | 2025-01-15 | 2025-01-15 | 2025-01-17 | 2025-01-19 | 2025-01-22 | 2025-01-22 | 2025-01-25 | 2025-01-27 | 2025-01-29 | 2025-01-30 | 2025-02-05 | 2025-02-09 | 2025-02-16 | 2025-02-16 | 2025-02-16 | 2025-02-21 | 2025-02-21 | 2025-02-23 | 2025-02-28 | 2025-03-08 | 2025-01-30 | 2025-02-16 | 2025-02-19 | 2025-03-13 | 2025-03-09 | 2025-03-15 | 2025-03-17 | 2025-03-23 | 2025-03-29
V_275 | 2024-09-06 | 2024-09-13 | 2024-09-15 | 2024-09-21 | 2024-09-26 | 2024-09-29 | 2024-09-30 | 2024-10-04 | 2024-10-09 | 2024-10-12 | 2024-10-16 | 2024-10-16 | 2024-11-29 | 2024-12-07 | 2024-12-14 | 2024-12-14 | 2024-12-21 | 2024-12-28 | 2024-12-28 | 2025-01-01 | 2025-01-01 | 2025-01-02 | 2025-01-08 | 2025-01-08 | 2025-01-15 | 2025-01-15 | 2025-01-15 | 2025-01-19 | 2025-01-24 | 2025-01-31 | 2025-02-05 | 2025-02-09 | 2025-02-16 | 2025-02-16 | 2025-02-21 | 2025-02-23 | 2025-02-23 | 2025-02-23 | 2025-03-01 | 2025-03-02 | 2025-03-07 | 2025-03-15 | 2024-12-07 | 2024-12-09 | 2024-12-16 | 2024-12-23 | 2024-12-28 | 2024-12-29 | 2025-01-04 | 2025-01-04 | 2025-01-05 | 2025-01-09 | 2025-01-10 | 2025-01-15 | 2025-01-15 | 2025-01-17 | 2025-01-19 | 2025-01-22 | 2025-01-22 | 2025-01-25 | 2025-01-27 | 2025-01-29 | 2025-01-30 | 2025-02-05 | 2025-02-09 | 2025-02-16 | 2025-02-16 | 2025-02-16 | 2025-02-21 | 2025-02-21 | 2025-02-23 | 2025-02-28 | 2025-03-08 | 2025-01-30 | 2025-02-16 | 2025-02-19 | 2025-03-13 | 2025-03-09 | 2025-03-15 | 2025-03-17 | 2025-03-23 | 2025-03-29
V_276 | 2024-09-06 | 2024-09-13 | 2024-09-15 | 2024-09-21 | 2024-09-26 | 2024-09-29 | 2024-09-30 | 2024-10-04 | 2024-10-09 | 2024-10-12 | 2024-10-16 | 2024-10-16 | 2024-11-29 | 2024-12-07 | 2024-12-14 | 2024-12-14 | 2024-12-21 | 2024-12-28 | 2024-12-28 | 2025-01-01 | 2025-01-01 | 2025-01-02 | 2025-01-08 | 2025-01-08 | 2025-01-15 | 2025-01-15 | 2025-01-15 | 2025-01-19 | 2025-01-24 | 2025-01-31 | 2025-02-05 | 2025-02-09 | 2025-02-16 | 2025-02-16 | 2025-02-21 | 2025-02-23 | 2025-02-23 | 2025-02-23 | 2025-03-01 | 2025-03-02 | 2025-03-07 | 2025-03-15 | 2024-12-07 | 2024-12-09 | 2024-12-16 | 2024-12-23 | 2024-12-28 | 2024-12-29 | 2025-01-04 | 2025-01-04 | 2025-01-05 | 2025-01-09 | 2025-01-10 | 2025-01-15 | 2025-01-15 | 2025-01-17 | 2025-01-19 | 2025-01-22 | 2025-01-22 | 2025-01-25 | 2025-01-27 | 2025-01-29 | 2025-01-30 | 2025-02-05 | 2025-02-09 | 2025-02-16 | 2025-02-16 | 2025-02-16 | 2025-02-21 | 2025-02-21 | 2025-02-23 | 2025-02-28 | 2025-03-08 | 2025-01-30 | 2025-02-16 | 2025-02-19 | 2025-03-13 | 2025-03-09 | 2025-03-15 | 2025-03-17 | 2025-03-23 | 2025-03-29
V_277 | 2024-09-06 | 2024-09-13 | 2024-09-15 | 2024-09-21 | 2024-09-26 | 2024-09-29 | 2024-09-30 | 2024-10-04 | 2024-10-09 | 2024-10-12 | 2024-10-16 | 2024-10-16 | 2024-11-29 | 2024-12-07 | 2024-12-14 | 2024-12-14 | 2024-12-21 | 2024-12-28 | 2024-12-28 | 2025-01-01 | 2025-01-01 | 2025-01-02 | 2025-01-08 | 2025-01-08 | 2025-01-15 | 2025-01-15 | 2025-01-15 | 2025-01-19 | 2025-01-24 | 2025-01-31 | 2025-02-05 | 2025-02-09 | 2025-02-16 | 2025-02-16 | 2025-02-21 | 2025-02-23 | 2025-02-23 | 2025-02-23 | 2025-03-01 | 2025-03-02 | 2025-03-07 | 2025-03-15 | 2024-12-07 | 2024-12-09 | 2024-12-16 | 2024-12-23 | 2024-12-28 | 2024-12-29 | 2025-01-04 | 2025-01-04 | 2025-01-05 | 2025-01-09 | 2025-01-10 | 2025-01-15 | 2025-01-15 | 2025-01-17 | 2025-01-19 | 2025-01-22 | 2025-01-22 | 2025-01-25 | 2025-01-27 | 2025-01-29 | 2025-01-30 | 2025-02-05 | 2025-02-09 | 2025-02-16 | 2025-02-16 | 2025-02-16 | 2025-02-21 | 2025-02-21 | 2025-02-23 | 2025-02-28 | 2025-03-08 | 2025-01-30 | 2025-02-16 | 2025-02-19 | 2025-03-13 | 2025-03-09 | 2025-03-15 | 2025-03-17 | 2025-03-23 | 2025-03-29
V_278 | 2024-09-06 | 2024-09-13 | 2024-09-15 | 2024-09-21 | 2024-09-26 | 2024-09-29 | 2024-09-30 | 2024-10-04 | 2024-10-09 | 2024-10-12 | 2024-10-16 | 2024-10-16 | 2024-11-29 | 2024-12-07 | 2024-12-14 | 2024-12-14 | 2024-12-21 | 2024-12-28 | 2024-12-28 | 2025-01-01 | 2025-01-01 | 2025-01-02 | 2025-01-08 | 2025-01-08 | 2025-01-15 | 2025-01-15 | 2025-01-15 | 2025-01-19 | 2025-01-24 | 2025-01-31 | 2025-02-05 | 2025-02-09 | 2025-02-16 | 2025-02-16 | 2025-02-21 | 2025-02-23 | 2025-02-23 | 2025-02-23 | 2025-03-01 | 2025-03-02 | 2025-03-07 | 2025-03-15 | 2024-12-07 | 2024-12-09 | 2024-12-16 | 2024-12-23 | 2024-12-28 | 2024-12-29 | 2025-01-04 | 2025-01-04 | 2025-01-05 | 2025-01-09 | 2025-01-10 | 2025-01-15 | 2025-01-15 | 2025-01-17 | 2025-01-19 | 2025-01-22 | 2025-01-22 | 2025-01-25 | 2025-01-27 | 2025-01-29 | 2025-01-30 | 2025-02-05 | 2025-02-09 | 2025-02-16 | 2025-02-16 | 2025-02-16 | 2025-02-21 | 2025-02-21 | 2025-02-23 | 2025-02-28 | 2025-03-08 | 2025-01-30 | 2025-02-16 | 2025-02-19 | 2025-03-13 | 2025-03-09 | 2025-03-15 | 2025-03-17 | 2025-03-23 | 2025-03-29
V_279 | 2024-09-06 | 2024-09-13 | 2024-09-15 | 2024-09-21 | 2024-09-26 | 2024-09-29 | 2024-09-30 | 2024-10-04 | 2024-10-09 | 2024-10-12 | 2024-10-16 | 2024-10-16 | 2024-11-29 | 2024-12-07 | 2024-12-14 | 2024-12-14 | 2024-12-21 | 2024-12-28 | 2024-12-28 | 2025-01-01 | 2025-01-01 | 2025-01-02 | 2025-01-08 | 2025-01-08 | 2025-01-15 | 2025-01-15 | 2025-01-15 | 2025-01-19 | 2025-01-24 | 2025-01-31 | 2025-02-05 | 2025-02-09 | 2025-02-16 | 2025-02-16 | 2025-02-21 | 2025-02-23 | 2025-02-23 | 2025-02-23 | 2025-03-01 | 2025-03-02 | 2025-03-07 | 2025-03-15 | 2024-12-07 | 2024-12-09 | 2024-12-16 | 2024-12-23 | 2024-12-28 | 2024-12-29 | 2025-01-04 | 2025-01-04 | 2025-01-05 | 2025-01-09 | 2025-01-10 | 2025-01-15 | 2025-01-15 | 2025-01-17 | 2025-01-19 | 2025-01-22 | 2025-01-22 | 2025-01-25 | 2025-01-27 | 2025-01-29 | 2025-01-30 | 2025-02-05 | 2025-02-09 | 2025-02-16 | 2025-02-16 | 2025-02-16 | 2025-02-21 | 2025-02-21 | 2025-02-23 | 2025-02-28 | 2025-03-08 | 2025-01-30 | 2025-02-16 | 2025-02-19 | 2025-03-13 | 2025-03-09 | 2025-03-15 | 2025-03-17 | 2025-03-23 | 2025-03-29
V_280 | 2024-09-06 | 2024-09-13 | 2024-09-15 | 2024-09-21 | 2024-09-26 | 2024-09-29 | 2024-09-30 | 2024-10-04 | 2024-10-09 | 2024-10-12 | 2024-10-16 | 2024-10-16 | 2024-11-29 | 2024-12-07 | 2024-12-14 | 2024-12-14 | 2024-12-21 | 2024-12-28 | 2024-12-28 | 2025-01-01 | 2025-01-01 | 2025-01-02 | 2025-01-08 | 2025-01-08 | 2025-01-15 | 2025-01-15 | 2025-01-15 | 2025-01-19 | 2025-01-24 | 2025-01-31 | 2025-02-05 | 2025-02-09 | 2025-02-16 | 2025-02-16 | 2025-02-21 | 2025-02-23 | 2025-02-23 | 2025-02-23 | 2025-03-01 | 2025-03-02 | 2025-03-07 | 2025-03-15 | 2024-12-07 | 2024-12-09 | 2024-12-16 | 2024-12-23 | 2024-12-28 | 2024-12-29 | 2025-01-04 | 2025-01-04 | 2025-01-05 | 2025-01-09 | 2025-01-10 | 2025-01-15 | 2025-01-15 | 2025-01-17 | 2025-01-19 | 2025-01-22 | 2025-01-22 | 2025-01-25 | 2025-01-27 | 2025-01-29 | 2025-01-30 | 2025-02-05 | 2025-02-09 | 2025-02-16 | 2025-02-16 | 2025-02-16 | 2025-02-21 | 2025-02-21 | 2025-02-23 | 2025-02-28 | 2025-03-08 | 2025-01-30 | 2025-02-16 | 2025-02-19 | 2025-03-13 | 2025-03-09 | 2025-03-15 | 2025-03-17 | 2025-03-23 | 2025-03-29
V_281 | 2024-09-13 | 2024-09-20 | 2024-09-22 | 2024-09-28 | 2024-10-03 | 2024-10-06 | 2024-10-07 | 2024-10-11 | 2024-10-16 | 2024-10-19 | 2024-10-23 | 2024-10-23 | 2024-12-07 | 2024-12-15 | 2024-12-22 | 2024-12-22 | 2024-12-29 | 2025-01-05 | 2025-01-05 | 2025-01-09 | 2025-01-09 | 2025-01-10 | 2025-01-16 | 2025-01-16 | 2025-01-23 | 2025-01-23 | 2025-01-23 | 2025-01-27 | 2025-02-01 | 2025-02-08 | 2025-02-13 | 2025-02-17 | 2025-02-24 | 2025-02-24 | 2025-03-01 | 2025-03-03 | 2025-03-03 | 2025-03-03 | 2025-03-09 | 2025-03-10 | 2025-03-15 | 2025-03-23 | 2024-12-15 | 2024-12-18 | 2024-12-25 | 2025-01-01 | 2025-01-05 | 2025-01-06 | 2025-01-12 | 2025-01-12 | 2025-01-13 | 2025-01-17 | 2025-01-18 | 2025-01-23 | 2025-01-23 | 2025-01-25 | 2025-01-27 | 2025-01-30 | 2025-01-30 | 2025-02-02 | 2025-02-05 | 2025-02-06 | 2025-02-07 | 2025-02-13 | 2025-02-17 | 2025-02-24 | 2025-02-24 | 2025-02-24 | 2025-03-01 | 2025-03-01 | 2025-03-03 | 2025-03-08 | 2025-03-16 | 2025-02-07 | 2025-02-24 | 2025-02-27 | 2025-03-21 | 2025-03-17 | 2025-03-23 | 2025-03-26 | 2025-03-31 | 2025-04-06
V_282 | 2024-09-13 | 2024-09-20 | 2024-09-22 | 2024-09-28 | 2024-10-03 | 2024-10-06 | 2024-10-07 | 2024-10-11 | 2024-10-16 | 2024-10-19 | 2024-10-23 | 2024-10-23 | 2024-12-07 | 2024-12-15 | 2024-12-22 | 2024-12-22 | 2024-12-29 | 2025-01-05 | 2025-01-05 | 2025-01-09 | 2025-01-09 | 2025-01-10 | 2025-01-16 | 2025-01-16 | 2025-01-23 | 2025-01-23 | 2025-01-23 | 2025-01-27 | 2025-02-01 | 2025-02-08 | 2025-02-13 | 2025-02-17 | 2025-02-24 | 2025-02-24 | 2025-03-01 | 2025-03-03 | 2025-03-03 | 2025-03-03 | 2025-03-09 | 2025-03-10 | 2025-03-15 | 2025-03-23 | 2024-12-15 | 2024-12-18 | 2024-12-25 | 2025-01-01 | 2025-01-05 | 2025-01-06 | 2025-01-12 | 2025-01-12 | 2025-01-13 | 2025-01-17 | 2025-01-18 | 2025-01-23 | 2025-01-23 | 2025-01-25 | 2025-01-27 | 2025-01-30 | 2025-01-30 | 2025-02-02 | 2025-02-05 | 2025-02-06 | 2025-02-07 | 2025-02-13 | 2025-02-17 | 2025-02-24 | 2025-02-24 | 2025-02-24 | 2025-03-01 | 2025-03-01 | 2025-03-03 | 2025-03-08 | 2025-03-16 | 2025-02-07 | 2025-02-24 | 2025-02-27 | 2025-03-21 | 2025-03-17 | 2025-03-23 | 2025-03-26 | 2025-03-31 | 2025-04-06
V_283 | 2024-09-13 | 2024-09-20 | 2024-09-22 | 2024-09-28 | 2024-10-03 | 2024-10-06 | 2024-10-07 | 2024-10-11 | 2024-10-16 | 2024-10-19 | 2024-10-23 | 2024-10-23 | 2024-12-07 | 2024-12-15 | 2024-12-22 | 2024-12-22 | 2024-12-29 | 2025-01-05 | 2025-01-05 | 2025-01-09 | 2025-01-09 | 2025-01-10 | 2025-01-16 | 2025-01-16 | 2025-01-23 | 2025-01-23 | 2025-01-23 | 2025-01-27 | 2025-02-01 | 2025-02-08 | 2025-02-13 | 2025-02-17 | 2025-02-24 | 2025-02-24 | 2025-03-01 | 2025-03-03 | 2025-03-03 | 2025-03-03 | 2025-03-09 | 2025-03-10 | 2025-03-15 | 2025-03-23 | 2024-12-15 | 2024-12-18 | 2024-12-25 | 2025-01-01 | 2025-01-05 | 2025-01-06 | 2025-01-12 | 2025-01-12 | 2025-01-13 | 2025-01-17 | 2025-01-18 | 2025-01-23 | 2025-01-23 | 2025-01-25 | 2025-01-27 | 2025-01-30 | 2025-01-30 | 2025-02-02 | 2025-02-05 | 2025-02-06 | 2025-02-07 | 2025-02-13 | 2025-02-17 | 2025-02-24 | 2025-02-24 | 2025-02-24 | 2025-03-01 | 2025-03-01 | 2025-03-03 | 2025-03-08 | 2025-03-16 | 2025-02-07 | 2025-02-24 | 2025-02-27 | 2025-03-21 | 2025-03-17 | 2025-03-23 | 2025-03-26 | 2025-03-31 | 2025-04-06
V_284 | 2024-09-13 | 2024-09-20 | 2024-09-22 | 2024-09-28 | 2024-10-03 | 2024-10-06 | 2024-10-07 | 2024-10-11 | 2024-10-16 | 2024-10-19 | 2024-10-23 | 2024-10-23 | 2024-12-07 | 2024-12-15 | 2024-12-22 | 2024-12-22 | 2024-12-29 | 2025-01-05 | 2025-01-05 | 2025-01-09 | 2025-01-09 | 2025-01-10 | 2025-01-16 | 2025-01-16 | 2025-01-23 | 2025-01-23 | 2025-01-23 | 2025-01-27 | 2025-02-01 | 2025-02-08 | 2025-02-13 | 2025-02-17 | 2025-02-24 | 2025-02-24 | 2025-03-01 | 2025-03-03 | 2025-03-03 | 2025-03-03 | 2025-03-09 | 2025-03-10 | 2025-03-15 | 2025-03-23 | 2024-12-15 | 2024-12-18 | 2024-12-25 | 2025-01-01 | 2025-01-05 | 2025-01-06 | 2025-01-12 | 2025-01-12 | 2025-01-13 | 2025-01-17 | 2025-01-18 | 2025-01-23 | 2025-01-23 | 2025-01-25 | 2025-01-27 | 2025-01-30 | 2025-01-30 | 2025-02-02 | 2025-02-05 | 2025-02-06 | 2025-02-07 | 2025-02-13 | 2025-02-17 | 2025-02-24 | 2025-02-24 | 2025-02-24 | 2025-03-01 | 2025-03-01 | 2025-03-03 | 2025-03-08 | 2025-03-16 | 2025-02-07 | 2025-02-24 | 2025-02-27 | 2025-03-21 | 2025-03-17 | 2025-03-23 | 2025-03-26 | 2025-03-31 | 2025-04-06
V_285 | 2024-09-13 | 2024-09-20 | 2024-09-22 | 2024-09-28 | 2024-10-03 | 2024-10-06 | 2024-10-07 | 2024-10-11 | 2024-10-16 | 2024-10-19 | 2024-10-23 | 2024-10-23 | 2024-12-07 | 2024-12-15 | 2024-12-22 | 2024-12-22 | 2024-12-29 | 2025-01-05 | 2025-01-05 | 2025-01-09 | 2025-01-09 | 2025-01-10 | 2025-01-16 | 2025-01-16 | 2025-01-23 | 2025-01-23 | 2025-01-23 | 2025-01-27 | 2025-02-01 | 2025-02-08 | 2025-02-13 | 2025-02-17 | 2025-02-24 | 2025-02-24 | 2025-03-01 | 2025-03-03 | 2025-03-03 | 2025-03-03 | 2025-03-09 | 2025-03-10 | 2025-03-15 | 2025-03-23 | 2024-12-15 | 2024-12-18 | 2024-12-25 | 2025-01-01 | 2025-01-05 | 2025-01-06 | 2025-01-12 | 2025-01-12 | 2025-01-13 | 2025-01-17 | 2025-01-18 | 2025-01-23 | 2025-01-23 | 2025-01-25 | 2025-01-27 | 2025-01-30 | 2025-01-30 | 2025-02-02 | 2025-02-05 | 2025-02-06 | 2025-02-07 | 2025-02-13 | 2025-02-17 | 2025-02-24 | 2025-02-24 | 2025-02-24 | 2025-03-01 | 2025-03-01 | 2025-03-03 | 2025-03-08 | 2025-03-16 | 2025-02-07 | 2025-02-24 | 2025-02-27 | 2025-03-21 | 2025-03-17 | 2025-03-23 | 2025-03-26 | 2025-03-31 | 2025-04-06
V_286 | 2024-09-13 | 2024-09-20 | 2024-09-22 | 2024-09-28 | 2024-10-03 | 2024-10-06 | 2024-10-07 | 2024-10-11 | 2024-10-16 | 2024-10-19 | 2024-10-23 | 2024-10-23 | 2024-12-07 | 2024-12-15 | 2024-12-22 | 2024-12-22 | 2024-12-29 | 2025-01-05 | 2025-01-05 | 2025-01-09 | 2025-01-09 | 2025-01-10 | 2025-01-16 | 2025-01-16 | 2025-01-23 | 2025-01-23 | 2025-01-23 | 2025-01-27 | 2025-02-01 | 2025-02-08 | 2025-02-13 | 2025-02-17 | 2025-02-24 | 2025-02-24 | 2025-03-01 | 2025-03-03 | 2025-03-03 | 2025-03-03 | 2025-03-09 | 2025-03-10 | 2025-03-15 | 2025-03-23 | 2024-12-15 | 2024-12-18 | 2024-12-25 | 2025-01-01 | 2025-01-05 | 2025-01-06 | 2025-01-12 | 2025-01-12 | 2025-01-13 | 2025-01-17 | 2025-01-18 | 2025-01-23 | 2025-01-23 | 2025-01-25 | 2025-01-27 | 2025-01-30 | 2025-01-30 | 2025-02-02 | 2025-02-05 | 2025-02-06 | 2025-02-07 | 2025-02-13 | 2025-02-17 | 2025-02-24 | 2025-02-24 | 2025-02-24 | 2025-03-01 | 2025-03-01 | 2025-03-03 | 2025-03-08 | 2025-03-16 | 2025-02-07 | 2025-02-24 | 2025-02-27 | 2025-03-21 | 2025-03-17 | 2025-03-23 | 2025-03-26 | 2025-03-31 | 2025-04-06
V_287 | 2024-09-13 | 2024-09-20 | 2024-09-22 | 2024-09-28 | 2024-10-03 | 2024-10-06 | 2024-10-07 | 2024-10-11 | 2024-10-16 | 2024-10-19 | 2024-10-23 | 2024-10-23 | 2024-12-07 | 2024-12-15 | 2024-12-22 | 2024-12-22 | 2024-12-29 | 2025-01-05 | 2025-01-05 | 2025-01-09 | 2025-01-09 | 2025-01-10 | 2025-01-16 | 2025-01-16 | 2025-01-23 | 2025-01-23 | 2025-01-23 | 2025-01-27 | 2025-02-01 | 2025-02-08 | 2025-02-13 | 2025-02-17 | 2025-02-24 | 2025-02-24 | 2025-03-01 | 2025-03-03 | 2025-03-03 | 2025-03-03 | 2025-03-09 | 2025-03-10 | 2025-03-15 | 2025-03-23 | 2024-12-15 | 2024-12-18 | 2024-12-25 | 2025-01-01 | 2025-01-05 | 2025-01-06 | 2025-01-12 | 2025-01-12 | 2025-01-13 | 2025-01-17 | 2025-01-18 | 2025-01-23 | 2025-01-23 | 2025-01-25 | 2025-01-27 | 2025-01-30 | 2025-01-30 | 2025-02-02 | 2025-02-05 | 2025-02-06 | 2025-02-07 | 2025-02-13 | 2025-02-17 | 2025-02-24 | 2025-02-24 | 2025-02-24 | 2025-03-01 | 2025-03-01 | 2025-03-03 | 2025-03-08 | 2025-03-16 | 2025-02-07 | 2025-02-24 | 2025-02-27 | 2025-03-21 | 2025-03-17 | 2025-03-23 | 2025-03-26 | 2025-03-31 | 2025-04-06
V_288 | 2024-09-13 | 2024-09-20 | 2024-09-22 | 2024-09-28 | 2024-10-03 | 2024-10-06 | 2024-10-07 | 2024-10-11 | 2024-10-16 | 2024-10-19 | 2024-10-23 | 2024-10-23 | 2024-12-07 | 2024-12-15 | 2024-12-22 | 2024-12-22 | 2024-12-29 | 2025-01-05 | 2025-01-05 | 2025-01-09 | 2025-01-09 | 2025-01-10 | 2025-01-16 | 2025-01-16 | 2025-01-23 | 2025-01-23 | 2025-01-23 | 2025-01-27 | 2025-02-01 | 2025-02-08 | 2025-02-13 | 2025-02-17 | 2025-02-24 | 2025-02-24 | 2025-03-01 | 2025-03-03 | 2025-03-03 | 2025-03-03 | 2025-03-09 | 2025-03-10 | 2025-03-15 | 2025-03-23 | 2024-12-15 | 2024-12-18 | 2024-12-25 | 2025-01-01 | 2025-01-05 | 2025-01-06 | 2025-01-12 | 2025-01-12 | 2025-01-13 | 2025-01-17 | 2025-01-18 | 2025-01-23 | 2025-01-23 | 2025-01-25 | 2025-01-27 | 2025-01-30 | 2025-01-30 | 2025-02-02 | 2025-02-05 | 2025-02-06 | 2025-02-07 | 2025-02-13 | 2025-02-17 | 2025-02-24 | 2025-02-24 | 2025-02-24 | 2025-03-01 | 2025-03-01 | 2025-03-03 | 2025-03-08 | 2025-03-16 | 2025-02-07 | 2025-02-24 | 2025-02-27 | 2025-03-21 | 2025-03-17 | 2025-03-23 | 2025-03-26 | 2025-03-31 | 2025-04-06
V_289 | 2024-09-20 | 2024-09-27 | 2024-09-29 | 2024-10-05 | 2024-10-10 | 2024-10-13 | 2024-10-14 | 2024-10-18 | 2024-10-23 | 2024-10-26 | 2024-10-30 | 2024-10-30 | 2024-12-15 | 2024-12-23 | 2024-12-30 | 2024-12-30 | 2025-01-06 | 2025-01-13 | 2025-01-13 | 2025-01-17 | 2025-01-17 | 2025-01-18 | 2025-01-24 | 2025-01-24 | 2025-01-31 | 2025-01-31 | 2025-01-31 | 2025-02-05 | 2025-02-09 | 2025-02-16 | 2025-02-21 | 2025-02-26 | 2025-03-05 | 2025-03-05 | 2025-03-09 | 2025-03-12 | 2025-03-12 | 2025-03-12 | 2025-03-17 | 2025-03-19 | 2025-03-23 | 2025-03-31 | 2024-12-23 | 2024-12-26 | 2025-01-02 | 2025-01-09 | 2025-01-13 | 2025-01-15 | 2025-01-20 | 2025-01-20 | 2025-01-22 | 2025-01-25 | 2025-01-26 | 2025-01-31 | 2025-01-31 | 2025-02-02 | 2025-02-05 | 2025-02-07 | 2025-02-07 | 2025-02-10 | 2025-02-13 | 2025-02-14 | 2025-02-15 | 2025-02-21 | 2025-02-26 | 2025-03-05 | 2025-03-05 | 2025-03-05 | 2025-03-09 | 2025-03-09 | 2025-03-12 | 2025-03-16 | 2025-03-24 | 2025-02-15 | 2025-03-05 | 2025-03-07 | 2025-03-29 | 2025-03-26 | 2025-03-31 | 2025-04-03 | 2025-04-09 | 2025-04-14
V_290 | 2024-09-20 | 2024-09-27 | 2024-09-29 | 2024-10-05 | 2024-10-10 | 2024-10-13 | 2024-10-14 | 2024-10-18 | 2024-10-23 | 2024-10-26 | 2024-10-30 | 2024-10-30 | 2024-12-15 | 2024-12-23 | 2024-12-30 | 2024-12-30 | 2025-01-06 | 2025-01-13 | 2025-01-13 | 2025-01-17 | 2025-01-17 | 2025-01-18 | 2025-01-24 | 2025-01-24 | 2025-01-31 | 2025-01-31 | 2025-01-31 | 2025-02-05 | 2025-02-09 | 2025-02-16 | 2025-02-21 | 2025-02-26 | 2025-03-05 | 2025-03-05 | 2025-03-09 | 2025-03-12 | 2025-03-12 | 2025-03-12 | 2025-03-17 | 2025-03-19 | 2025-03-23 | 2025-03-31 | 2024-12-23 | 2024-12-26 | 2025-01-02 | 2025-01-09 | 2025-01-13 | 2025-01-15 | 2025-01-20 | 2025-01-20 | 2025-01-22 | 2025-01-25 | 2025-01-26 | 2025-01-31 | 2025-01-31 | 2025-02-02 | 2025-02-05 | 2025-02-07 | 2025-02-07 | 2025-02-10 | 2025-02-13 | 2025-02-14 | 2025-02-15 | 2025-02-21 | 2025-02-26 | 2025-03-05 | 2025-03-05 | 2025-03-05 | 2025-03-09 | 2025-03-09 | 2025-03-12 | 2025-03-16 | 2025-03-24 | 2025-02-15 | 2025-03-05 | 2025-03-07 | 2025-03-29 | 2025-03-26 | 2025-03-31 | 2025-04-03 | 2025-04-09 | 2025-04-14
V_291 | 2024-09-20 | 2024-09-27 | 2024-09-29 | 2024-10-05 | 2024-10-10 | 2024-10-13 | 2024-10-14 | 2024-10-18 | 2024-10-23 | 2024-10-26 | 2024-10-30 | 2024-10-30 | 2024-12-15 | 2024-12-23 | 2024-12-30 | 2024-12-30 | 2025-01-06 | 2025-01-13 | 2025-01-13 | 2025-01-17 | 2025-01-17 | 2025-01-18 | 2025-01-24 | 2025-01-24 | 2025-01-31 | 2025-01-31 | 2025-01-31 | 2025-02-05 | 2025-02-09 | 2025-02-16 | 2025-02-21 | 2025-02-26 | 2025-03-05 | 2025-03-05 | 2025-03-09 | 2025-03-12 | 2025-03-12 | 2025-03-12 | 2025-03-17 | 2025-03-19 | 2025-03-23 | 2025-03-31 | 2024-12-23 | 2024-12-26 | 2025-01-02 | 2025-01-09 | 2025-01-13 | 2025-01-15 | 2025-01-20 | 2025-01-20 | 2025-01-22 | 2025-01-25 | 2025-01-26 | 2025-01-31 | 2025-01-31 | 2025-02-02 | 2025-02-05 | 2025-02-07 | 2025-02-07 | 2025-02-10 | 2025-02-13 | 2025-02-14 | 2025-02-15 | 2025-02-21 | 2025-02-26 | 2025-03-05 | 2025-03-05 | 2025-03-05 | 2025-03-09 | 2025-03-09 | 2025-03-12 | 2025-03-16 | 2025-03-24 | 2025-02-15 | 2025-03-05 | 2025-03-07 | 2025-03-29 | 2025-03-26 | 2025-03-31 | 2025-04-03 | 2025-04-09 | 2025-04-14
V_292 | 2024-09-20 | 2024-09-27 | 2024-09-29 | 2024-10-05 | 2024-10-10 | 2024-10-13 | 2024-10-14 | 2024-10-18 | 2024-10-23 | 2024-10-26 | 2024-10-30 | 2024-10-30 | 2024-12-15 | 2024-12-23 | 2024-12-30 | 2024-12-30 | 2025-01-06 | 2025-01-13 | 2025-01-13 | 2025-01-17 | 2025-01-17 | 2025-01-18 | 2025-01-24 | 2025-01-24 | 2025-01-31 | 2025-01-31 | 2025-01-31 | 2025-02-05 | 2025-02-09 | 2025-02-16 | 2025-02-21 | 2025-02-26 | 2025-03-05 | 2025-03-05 | 2025-03-09 | 2025-03-12 | 2025-03-12 | 2025-03-12 | 2025-03-17 | 2025-03-19 | 2025-03-23 | 2025-03-31 | 2024-12-23 | 2024-12-26 | 2025-01-02 | 2025-01-09 | 2025-01-13 | 2025-01-15 | 2025-01-20 | 2025-01-20 | 2025-01-22 | 2025-01-25 | 2025-01-26 | 2025-01-31 | 2025-01-31 | 2025-02-02 | 2025-02-05 | 2025-02-07 | 2025-02-07 | 2025-02-10 | 2025-02-13 | 2025-02-14 | 2025-02-15 | 2025-02-21 | 2025-02-26 | 2025-03-05 | 2025-03-05 | 2025-03-05 | 2025-03-09 | 2025-03-09 | 2025-03-12 | 2025-03-16 | 2025-03-24 | 2025-02-15 | 2025-03-05 | 2025-03-07 | 2025-03-29 | 2025-03-26 | 2025-03-31 | 2025-04-03 | 2025-04-09 | 2025-04-14
V_293 | 2024-09-20 | 2024-09-27 | 2024-09-29 | 2024-10-05 | 2024-10-10 | 2024-10-13 | 2024-10-14 | 2024-10-18 | 2024-10-23 | 2024-10-26 | 2024-10-30 | 2024-10-30 | 2024-12-15 | 2024-12-23 | 2024-12-30 | 2024-12-30 | 2025-01-06 | 2025-01-13 | 2025-01-13 | 2025-01-17 | 2025-01-17 | 2025-01-18 | 2025-01-24 | 2025-01-24 | 2025-01-31 | 2025-01-31 | 2025-01-31 | 2025-02-05 | 2025-02-09 | 2025-02-16 | 2025-02-21 | 2025-02-26 | 2025-03-05 | 2025-03-05 | 2025-03-09 | 2025-03-12 | 2025-03-12 | 2025-03-12 | 2025-03-17 | 2025-03-19 | 2025-03-23 | 2025-03-31 | 2024-12-23 | 2024-12-26 | 2025-01-02 | 2025-01-09 | 2025-01-13 | 2025-01-15 | 2025-01-20 | 2025-01-20 | 2025-01-22 | 2025-01-25 | 2025-01-26 | 2025-01-31 | 2025-01-31 | 2025-02-02 | 2025-02-05 | 2025-02-07 | 2025-02-07 | 2025-02-10 | 2025-02-13 | 2025-02-14 | 2025-02-15 | 2025-02-21 | 2025-02-26 | 2025-03-05 | 2025-03-05 | 2025-03-05 | 2025-03-09 | 2025-03-09 | 2025-03-12 | 2025-03-16 | 2025-03-24 | 2025-02-15 | 2025-03-05 | 2025-03-07 | 2025-03-29 | 2025-03-26 | 2025-03-31 | 2025-04-03 | 2025-04-09 | 2025-04-14
V_294 | 2024-09-20 | 2024-09-27 | 2024-09-29 | 2024-10-05 | 2024-10-10 | 2024-10-13 | 2024-10-14 | 2024-10-18 | 2024-10-23 | 2024-10-26 | 2024-10-30 | 2024-10-30 | 2024-12-15 | 2024-12-23 | 2024-12-30 | 2024-12-30 | 2025-01-06 | 2025-01-13 | 2025-01-13 | 2025-01-17 | 2025-01-17 | 2025-01-18 | 2025-01-24 | 2025-01-24 | 2025-01-31 | 2025-01-31 | 2025-01-31 | 2025-02-05 | 2025-02-09 | 2025-02-16 | 2025-02-21 | 2025-02-26 | 2025-03-05 | 2025-03-05 | 2025-03-09 | 2025-03-12 | 2025-03-12 | 2025-03-12 | 2025-03-17 | 2025-03-19 | 2025-03-23 | 2025-03-31 | 2024-12-23 | 2024-12-26 | 2025-01-02 | 2025-01-09 | 2025-01-13 | 2025-01-15 | 2025-01-20 | 2025-01-20 | 2025-01-22 | 2025-01-25 | 2025-01-26 | 2025-01-31 | 2025-01-31 | 2025-02-02 | 2025-02-05 | 2025-02-07 | 2025-02-07 | 2025-02-10 | 2025-02-13 | 2025-02-14 | 2025-02-15 | 2025-02-21 | 2025-02-26 | 2025-03-05 | 2025-03-05 | 2025-03-05 | 2025-03-09 | 2025-03-09 | 2025-03-12 | 2025-03-16 | 2025-03-24 | 2025-02-15 | 2025-03-05 | 2025-03-07 | 2025-03-29 | 2025-03-26 | 2025-03-31 | 2025-04-03 | 2025-04-09 | 2025-04-14
V_295 | 2024-09-20 | 2024-09-27 | 2024-09-29 | 2024-10-05 | 2024-10-10 | 2024-10-13 | 2024-10-14 | 2024-10-18 | 2024-10-23 | 2024-10-26 | 2024-10-30 | 2024-10-30 | 2024-12-15 | 2024-12-23 | 2024-12-30 | 2024-12-30 | 2025-01-06 | 2025-01-13 | 2025-01-13 | 2025-01-17 | 2025-01-17 | 2025-01-18 | 2025-01-24 | 2025-01-24 | 2025-01-31 | 2025-01-31 | 2025-01-31 | 2025-02-05 | 2025-02-09 | 2025-02-16 | 2025-02-21 | 2025-02-26 | 2025-03-05 | 2025-03-05 | 2025-03-09 | 2025-03-12 | 2025-03-12 | 2025-03-12 | 2025-03-17 | 2025-03-19 | 2025-03-23 | 2025-03-31 | 2024-12-23 | 2024-12-26 | 2025-01-02 | 2025-01-09 | 2025-01-13 | 2025-01-15 | 2025-01-20 | 2025-01-20 | 2025-01-22 | 2025-01-25 | 2025-01-26 | 2025-01-31 | 2025-01-31 | 2025-02-02 | 2025-02-05 | 2025-02-07 | 2025-02-07 | 2025-02-10 | 2025-02-13 | 2025-02-14 | 2025-02-15 | 2025-02-21 | 2025-02-26 | 2025-03-05 | 2025-03-05 | 2025-03-05 | 2025-03-09 | 2025-03-09 | 2025-03-12 | 2025-03-16 | 2025-03-24 | 2025-02-15 | 2025-03-05 | 2025-03-07 | 2025-03-29 | 2025-03-26 | 2025-03-31 | 2025-04-03 | 2025-04-09 | 2025-04-14
V_296 | 2024-09-20 | 2024-09-27 | 2024-09-29 | 2024-10-05 | 2024-10-10 | 2024-10-13 | 2024-10-14 | 2024-10-18 | 2024-10-23 | 2024-10-26 | 2024-10-30 | 2024-10-30 | 2024-12-15 | 2024-12-23 | 2024-12-30 | 2024-12-30 | 2025-01-06 | 2025-01-13 | 2025-01-13 | 2025-01-17 | 2025-01-17 | 2025-01-18 | 2025-01-24 | 2025-01-24 | 2025-01-31 | 2025-01-31 | 2025-01-31 | 2025-02-05 | 2025-02-09 | 2025-02-16 | 2025-02-21 | 2025-02-26 | 2025-03-05 | 2025-03-05 | 2025-03-09 | 2025-03-12 | 2025-03-12 | 2025-03-12 | 2025-03-17 | 2025-03-19 | 2025-03-23 | 2025-03-31 | 2024-12-23 | 2024-12-26 | 2025-01-02 | 2025-01-09 | 2025-01-13 | 2025-01-15 | 2025-01-20 | 2025-01-20 | 2025-01-22 | 2025-01-25 | 2025-01-26 | 2025-01-31 | 2025-01-31 | 2025-02-02 | 2025-02-05 | 2025-02-07 | 2025-02-07 | 2025-02-10 | 2025-02-13 | 2025-02-14 | 2025-02-15 | 2025-02-21 | 2025-02-26 | 2025-03-05 | 2025-03-05 | 2025-03-05 | 2025-03-09 | 2025-03-09 | 2025-03-12 | 2025-03-16 | 2025-03-24 | 2025-02-15 | 2025-03-05 | 2025-03-07 | 2025-03-29 | 2025-03-26 | 2025-03-31 | 2025-04-03 | 2025-04-09 | 2025-04-14
V_297 | 2024-09-27 | 2024-10-04 | 2024-10-06 | 2024-10-12 | 2024-10-17 | 2024-10-20 | 2024-10-21 | 2024-10-25 | 2024-10-30 | 2024-11-02 | 2024-11-06 | 2024-11-06 | 2024-12-23 | 2025-01-01 | 2025-01-08 | 2025-01-08 | 2025-01-15 | 2025-01-22 | 2025-01-22 | 2025-01-25 | 2025-01-25 | 2025-01-26 | 2025-02-01 | 2025-02-01 | 2025-02-08 | 2025-02-08 | 2025-02-08 | 2025-02-13 | 2025-02-17 | 2025-02-24 | 2025-03-01 | 2025-03-06 | 2025-03-13 | 2025-03-13 | 2025-03-17 | 2025-03-20 | 2025-03-20 | 2025-03-20 | 2025-03-26 | 2025-03-27 | 2025-03-31 | 2025-04-09 | 2025-01-01 | 2025-01-03 | 2025-01-10 | 2025-01-17 | 2025-01-22 | 2025-01-23 | 2025-01-29 | 2025-01-29 | 2025-01-30 | 2025-02-02 | 2025-02-03 | 2025-02-08 | 2025-02-08 | 2025-02-10 | 2025-02-13 | 2025-02-15 | 2025-02-15 | 2025-02-19 | 2025-02-21 | 2025-02-22 | 2025-02-23 | 2025-03-01 | 2025-03-06 | 2025-03-13 | 2025-03-13 | 2025-03-13 | 2025-03-17 | 2025-03-17 | 2025-03-20 | 2025-03-24 | 2025-04-02 | 2025-02-23 | 2025-03-13 | 2025-03-15 | 2025-04-06 | 2025-04-03 | 2025-04-09 | 2025-04-11 | 2025-04-17 | 2025-04-23
V_298 | 2024-09-27 | 2024-10-04 | 2024-10-06 | 2024-10-12 | 2024-10-17 | 2024-10-20 | 2024-10-21 | 2024-10-25 | 2024-10-30 | 2024-11-02 | 2024-11-06 | 2024-11-06 | 2024-12-23 | 2025-01-01 | 2025-01-08 | 2025-01-08 | 2025-01-15 | 2025-01-22 | 2025-01-22 | 2025-01-25 | 2025-01-25 | 2025-01-26 | 2025-02-01 | 2025-02-01 | 2025-02-08 | 2025-02-08 | 2025-02-08 | 2025-02-13 | 2025-02-17 | 2025-02-24 | 2025-03-01 | 2025-03-06 | 2025-03-13 | 2025-03-13 | 2025-03-17 | 2025-03-20 | 2025-03-20 | 2025-03-20 | 2025-03-26 | 2025-03-27 | 2025-03-31 | 2025-04-09 | 2025-01-01 | 2025-01-03 | 2025-01-10 | 2025-01-17 | 2025-01-22 | 2025-01-23 | 2025-01-29 | 2025-01-29 | 2025-01-30 | 2025-02-02 | 2025-02-03 | 2025-02-08 | 2025-02-08 | 2025-02-10 | 2025-02-13 | 2025-02-15 | 2025-02-15 | 2025-02-19 | 2025-02-21 | 2025-02-22 | 2025-02-23 | 2025-03-01 | 2025-03-06 | 2025-03-13 | 2025-03-13 | 2025-03-13 | 2025-03-17 | 2025-03-17 | 2025-03-20 | 2025-03-24 | 2025-04-02 | 2025-02-23 | 2025-03-13 | 2025-03-15 | 2025-04-06 | 2025-04-03 | 2025-04-09 | 2025-04-11 | 2025-04-17 | 2025-04-23
V_299 | 2024-09-27 | 2024-10-04 | 2024-10-06 | 2024-10-12 | 2024-10-17 | 2024-10-20 | 2024-10-21 | 2024-10-25 | 2024-10-30 | 2024-11-02 | 2024-11-06 | 2024-11-06 | 2024-12-23 | 2025-01-01 | 2025-01-08 | 2025-01-08 | 2025-01-15 | 2025-01-22 | 2025-01-22 | 2025-01-25 | 2025-01-25 | 2025-01-26 | 2025-02-01 | 2025-02-01 | 2025-02-08 | 2025-02-08 | 2025-02-08 | 2025-02-13 | 2025-02-17 | 2025-02-24 | 2025-03-01 | 2025-03-06 | 2025-03-13 | 2025-03-13 | 2025-03-17 | 2025-03-20 | 2025-03-20 | 2025-03-20 | 2025-03-26 | 2025-03-27 | 2025-03-31 | 2025-04-09 | 2025-01-01 | 2025-01-03 | 2025-01-10 | 2025-01-17 | 2025-01-22 | 2025-01-23 | 2025-01-29 | 2025-01-29 | 2025-01-30 | 2025-02-02 | 2025-02-03 | 2025-02-08 | 2025-02-08 | 2025-02-10 | 2025-02-13 | 2025-02-15 | 2025-02-15 | 2025-02-19 | 2025-02-21 | 2025-02-22 | 2025-02-23 | 2025-03-01 | 2025-03-06 | 2025-03-13 | 2025-03-13 | 2025-03-13 | 2025-03-17 | 2025-03-17 | 2025-03-20 | 2025-03-24 | 2025-04-02 | 2025-02-23 | 2025-03-13 | 2025-03-15 | 2025-04-06 | 2025-04-03 | 2025-04-09 | 2025-04-11 | 2025-04-17 | 2025-04-23
V_300 | 2024-09-27 | 2024-10-04 | 2024-10-06 | 2024-10-12 | 2024-10-17 | 2024-10-20 | 2024-10-21 | 2024-10-25 | 2024-10-30 | 2024-11-02 | 2024-11-06 | 2024-11-06 | 2024-12-23 | 2025-01-01 | 2025-01-08 | 2025-01-08 | 2025-01-15 | 2025-01-22 | 2025-01-22 | 2025-01-25 | 2025-01-25 | 2025-01-26 | 2025-02-01 | 2025-02-01 | 2025-02-08 | 2025-02-08 | 2025-02-08 | 2025-02-13 | 2025-02-17 | 2025-02-24 | 2025-03-01 | 2025-03-06 | 2025-03-13 | 2025-03-13 | 2025-03-17 | 2025-03-20 | 2025-03-20 | 2025-03-20 | 2025-03-26 | 2025-03-27 | 2025-03-31 | 2025-04-09 | 2025-01-01 | 2025-01-03 | 2025-01-10 | 2025-01-17 | 2025-01-22 | 2025-01-23 | 2025-01-29 | 2025-01-29 | 2025-01-30 | 2025-02-02 | 2025-02-03 | 2025-02-08 | 2025-02-08 | 2025-02-10 | 2025-02-13 | 2025-02-15 | 2025-02-15 | 2025-02-19 | 2025-02-21 | 2025-02-22 | 2025-02-23 | 2025-03-01 | 2025-03-06 | 2025-03-13 | 2025-03-13 | 2025-03-13 | 2025-03-17 | 2025-03-17 | 2025-03-20 | 2025-03-24 | 2025-04-02 | 2025-02-23 | 2025-03-13 | 2025-03-15 | 2025-04-06 | 2025-04-03 | 2025-04-09 | 2025-04-11 | 2025-04-17 | 2025-04-23
V_301 | 2024-09-27 | 2024-10-04 | 2024-10-06 | 2024-10-12 | 2024-10-17 | 2024-10-20 | 2024-10-21 | 2024-10-25 | 2024-10-30 | 2024-11-02 | 2024-11-06 | 2024-11-06 | 2024-12-23 | 2025-01-01 | 2025-01-08 | 2025-01-08 | 2025-01-15 | 2025-01-22 | 2025-01-22 | 2025-01-25 | 2025-01-25 | 2025-01-26 | 2025-02-01 | 2025-02-01 | 2025-02-08 | 2025-02-08 | 2025-02-08 | 2025-02-13 | 2025-02-17 | 2025-02-24 | 2025-03-01 | 2025-03-06 | 2025-03-13 | 2025-03-13 | 2025-03-17 | 2025-03-20 | 2025-03-20 | 2025-03-20 | 2025-03-26 | 2025-03-27 | 2025-03-31 | 2025-04-09 | 2025-01-01 | 2025-01-03 | 2025-01-10 | 2025-01-17 | 2025-01-22 | 2025-01-23 | 2025-01-29 | 2025-01-29 | 2025-01-30 | 2025-02-02 | 2025-02-03 | 2025-02-08 | 2025-02-08 | 2025-02-10 | 2025-02-13 | 2025-02-15 | 2025-02-15 | 2025-02-19 | 2025-02-21 | 2025-02-22 | 2025-02-23 | 2025-03-01 | 2025-03-06 | 2025-03-13 | 2025-03-13 | 2025-03-13 | 2025-03-17 | 2025-03-17 | 2025-03-20 | 2025-03-24 | 2025-04-02 | 2025-02-23 | 2025-03-13 | 2025-03-15 | 2025-04-06 | 2025-04-03 | 2025-04-09 | 2025-04-11 | 2025-04-17 | 2025-04-23
V_302 | 2024-09-27 | 2024-10-04 | 2024-10-06 | 2024-10-12 | 2024-10-17 | 2024-10-20 | 2024-10-21 | 2024-10-25 | 2024-10-30 | 2024-11-02 | 2024-11-06 | 2024-11-06 | 2024-12-23 | 2025-01-01 | 2025-01-08 | 2025-01-08 | 2025-01-15 | 2025-01-22 | 2025-01-22 | 2025-01-25 | 2025-01-25 | 2025-01-26 | 2025-02-01 | 2025-02-01 | 2025-02-08 | 2025-02-08 | 2025-02-08 | 2025-02-13 | 2025-02-17 | 2025-02-24 | 2025-03-01 | 2025-03-06 | 2025-03-13 | 2025-03-13 | 2025-03-17 | 2025-03-20 | 2025-03-20 | 2025-03-20 | 2025-03-26 | 2025-03-27 | 2025-03-31 | 2025-04-09 | 2025-01-01 | 2025-01-03 | 2025-01-10 | 2025-01-17 | 2025-01-22 | 2025-01-23 | 2025-01-29 | 2025-01-29 | 2025-01-30 | 2025-02-02 | 2025-02-03 | 2025-02-08 | 2025-02-08 | 2025-02-10 | 2025-02-13 | 2025-02-15 | 2025-02-15 | 2025-02-19 | 2025-02-21 | 2025-02-22 | 2025-02-23 | 2025-03-01 | 2025-03-06 | 2025-03-13 | 2025-03-13 | 2025-03-13 | 2025-03-17 | 2025-03-17 | 2025-03-20 | 2025-03-24 | 2025-04-02 | 2025-02-23 | 2025-03-13 | 2025-03-15 | 2025-04-06 | 2025-04-03 | 2025-04-09 | 2025-04-11 | 2025-04-17 | 2025-04-23
V_303 | 2024-09-27 | 2024-10-04 | 2024-10-06 | 2024-10-12 | 2024-10-17 | 2024-10-20 | 2024-10-21 | 2024-10-25 | 2024-10-30 | 2024-11-02 | 2024-11-06 | 2024-11-06 | 2024-12-23 | 2025-01-01 | 2025-01-08 | 2025-01-08 | 2025-01-15 | 2025-01-22 | 2025-01-22 | 2025-01-25 | 2025-01-25 | 2025-01-26 | 2025-02-01 | 2025-02-01 | 2025-02-08 | 2025-02-08 | 2025-02-08 | 2025-02-13 | 2025-02-17 | 2025-02-24 | 2025-03-01 | 2025-03-06 | 2025-03-13 | 2025-03-13 | 2025-03-17 | 2025-03-20 | 2025-03-20 | 2025-03-20 | 2025-03-26 | 2025-03-27 | 2025-03-31 | 2025-04-09 | 2025-01-01 | 2025-01-03 | 2025-01-10 | 2025-01-17 | 2025-01-22 | 2025-01-23 | 2025-01-29 | 2025-01-29 | 2025-01-30 | 2025-02-02 | 2025-02-03 | 2025-02-08 | 2025-02-08 | 2025-02-10 | 2025-02-13 | 2025-02-15 | 2025-02-15 | 2025-02-19 | 2025-02-21 | 2025-02-22 | 2025-02-23 | 2025-03-01 | 2025-03-06 | 2025-03-13 | 2025-03-13 | 2025-03-13 | 2025-03-17 | 2025-03-17 | 2025-03-20 | 2025-03-24 | 2025-04-02 | 2025-02-23 | 2025-03-13 | 2025-03-15 | 2025-04-06 | 2025-04-03 | 2025-04-09 | 2025-04-11 | 2025-04-17 | 2025-04-23
V_304 | 2024-09-27 | 2024-10-04 | 2024-10-06 | 2024-10-12 | 2024-10-17 | 2024-10-20 | 2024-10-21 | 2024-10-25 | 2024-10-30 | 2024-11-02 | 2024-11-06 | 2024-11-06 | 2024-12-23 | 2025-01-01 | 2025-01-08 | 2025-01-08 | 2025-01-15 | 2025-01-22 | 2025-01-22 | 2025-01-25 | 2025-01-25 | 2025-01-26 | 2025-02-01 | 2025-02-01 | 2025-02-08 | 2025-02-08 | 2025-02-08 | 2025-02-13 | 2025-02-17 | 2025-02-24 | 2025-03-01 | 2025-03-06 | 2025-03-13 | 2025-03-13 | 2025-03-17 | 2025-03-20 | 2025-03-20 | 2025-03-20 | 2025-03-26 | 2025-03-27 | 2025-03-31 | 2025-04-09 | 2025-01-01 | 2025-01-03 | 2025-01-10 | 2025-01-17 | 2025-01-22 | 2025-01-23 | 2025-01-29 | 2025-01-29 | 2025-01-30 | 2025-02-02 | 2025-02-03 | 2025-02-08 | 2025-02-08 | 2025-02-10 | 2025-02-13 | 2025-02-15 | 2025-02-15 | 2025-02-19 | 2025-02-21 | 2025-02-22 | 2025-02-23 | 2025-03-01 | 2025-03-06 | 2025-03-13 | 2025-03-13 | 2025-03-13 | 2025-03-17 | 2025-03-17 | 2025-03-20 | 2025-03-24 | 2025-04-02 | 2025-02-23 | 2025-03-13 | 2025-03-15 | 2025-04-06 | 2025-04-03 | 2025-04-09 | 2025-04-11 | 2025-04-17 | 2025-04-23
V_305 | 2024-10-04 | 2024-10-11 | 2024-10-13 | 2024-10-19 | 2024-10-24 | 2024-10-27 | 2024-10-28 | 2024-11-01 | 2024-11-06 | 2024-11-09 | 2024-11-13 | 2024-11-13 | 2025-01-01 | 2025-01-09 | 2025-01-16 | 2025-01-16 | 2025-01-23 | 2025-01-30 | 2025-01-30 | 2025-02-02 | 2025-02-02 | 2025-02-03 | 2025-02-09 | 2025-02-09 | 2025-02-16 | 2025-02-16 | 2025-02-16 | 2025-02-21 | 2025-02-26 | 2025-03-05 | 2025-03-09 | 2025-03-14 | 2025-03-21 | 2025-03-21 | 2025-03-26 | 2025-03-28 | 2025-03-28 | 2025-03-28 | 2025-04-03 | 2025-04-04 | 2025-04-09 | 2025-04-17 | 2025-01-09 | 2025-01-11 | 2025-01-18 | 2025-01-25 | 2025-01-30 | 2025-01-31 | 2025-02-06 | 2025-02-06 | 2025-02-07 | 2025-02-10 | 2025-02-12 | 2025-02-16 | 2025-02-16 | 2025-02-19 | 2025-02-21 | 2025-02-23 | 2025-02-23 | 2025-02-27 | 2025-03-01 | 2025-03-02 | 2025-03-03 | 2025-03-09 | 2025-03-14 | 2025-03-21 | 2025-03-21 | 2025-03-21 | 2025-03-26 | 2025-03-26 | 2025-03-28 | 2025-04-02 | 2025-04-10 | 2025-03-03 | 2025-03-21 | 2025-03-23 | 2025-04-14 | 2025-04-11 | 2025-04-17 | 2025-04-19 | 2025-04-25 | 2025-05-01
V_306 | 2024-10-04 | 2024-10-11 | 2024-10-13 | 2024-10-19 | 2024-10-24 | 2024-10-27 | 2024-10-28 | 2024-11-01 | 2024-11-06 | 2024-11-09 | 2024-11-13 | 2024-11-13 | 2025-01-01 | 2025-01-09 | 2025-01-16 | 2025-01-16 | 2025-01-23 | 2025-01-30 | 2025-01-30 | 2025-02-02 | 2025-02-02 | 2025-02-03 | 2025-02-09 | 2025-02-09 | 2025-02-16 | 2025-02-16 | 2025-02-16 | 2025-02-21 | 2025-02-26 | 2025-03-05 | 2025-03-09 | 2025-03-14 | 2025-03-21 | 2025-03-21 | 2025-03-26 | 2025-03-28 | 2025-03-28 | 2025-03-28 | 2025-04-03 | 2025-04-04 | 2025-04-09 | 2025-04-17 | 2025-01-09 | 2025-01-11 | 2025-01-18 | 2025-01-25 | 2025-01-30 | 2025-01-31 | 2025-02-06 | 2025-02-06 | 2025-02-07 | 2025-02-10 | 2025-02-12 | 2025-02-16 | 2025-02-16 | 2025-02-19 | 2025-02-21 | 2025-02-23 | 2025-02-23 | 2025-02-27 | 2025-03-01 | 2025-03-02 | 2025-03-03 | 2025-03-09 | 2025-03-14 | 2025-03-21 | 2025-03-21 | 2025-03-21 | 2025-03-26 | 2025-03-26 | 2025-03-28 | 2025-04-02 | 2025-04-10 | 2025-03-03 | 2025-03-21 | 2025-03-23 | 2025-04-14 | 2025-04-11 | 2025-04-17 | 2025-04-19 | 2025-04-25 | 2025-05-01
V_307 | 2024-10-04 | 2024-10-11 | 2024-10-13 | 2024-10-19 | 2024-10-24 | 2024-10-27 | 2024-10-28 | 2024-11-01 | 2024-11-06 | 2024-11-09 | 2024-11-13 | 2024-11-13 | 2025-01-01 | 2025-01-09 | 2025-01-16 | 2025-01-16 | 2025-01-23 | 2025-01-30 | 2025-01-30 | 2025-02-02 | 2025-02-02 | 2025-02-03 | 2025-02-09 | 2025-02-09 | 2025-02-16 | 2025-02-16 | 2025-02-16 | 2025-02-21 | 2025-02-26 | 2025-03-05 | 2025-03-09 | 2025-03-14 | 2025-03-21 | 2025-03-21 | 2025-03-26 | 2025-03-28 | 2025-03-28 | 2025-03-28 | 2025-04-03 | 2025-04-04 | 2025-04-09 | 2025-04-17 | 2025-01-09 | 2025-01-11 | 2025-01-18 | 2025-01-25 | 2025-01-30 | 2025-01-31 | 2025-02-06 | 2025-02-06 | 2025-02-07 | 2025-02-10 | 2025-02-12 | 2025-02-16 | 2025-02-16 | 2025-02-19 | 2025-02-21 | 2025-02-23 | 2025-02-23 | 2025-02-27 | 2025-03-01 | 2025-03-02 | 2025-03-03 | 2025-03-09 | 2025-03-14 | 2025-03-21 | 2025-03-21 | 2025-03-21 | 2025-03-26 | 2025-03-26 | 2025-03-28 | 2025-04-02 | 2025-04-10 | 2025-03-03 | 2025-03-21 | 2025-03-23 | 2025-04-14 | 2025-04-11 | 2025-04-17 | 2025-04-19 | 2025-04-25 | 2025-05-01
V_308 | 2024-10-04 | 2024-10-11 | 2024-10-13 | 2024-10-19 | 2024-10-24 | 2024-10-27 | 2024-10-28 | 2024-11-01 | 2024-11-06 | 2024-11-09 | 2024-11-13 | 2024-11-13 | 2025-01-01 | 2025-01-09 | 2025-01-16 | 2025-01-16 | 2025-01-23 | 2025-01-30 | 2025-01-30 | 2025-02-02 | 2025-02-02 | 2025-02-03 | 2025-02-09 | 2025-02-09 | 2025-02-16 | 2025-02-16 | 2025-02-16 | 2025-02-21 | 2025-02-26 | 2025-03-05 | 2025-03-09 | 2025-03-14 | 2025-03-21 | 2025-03-21 | 2025-03-26 | 2025-03-28 | 2025-03-28 | 2025-03-28 | 2025-04-03 | 2025-04-04 | 2025-04-09 | 2025-04-17 | 2025-01-09 | 2025-01-11 | 2025-01-18 | 2025-01-25 | 2025-01-30 | 2025-01-31 | 2025-02-06 | 2025-02-06 | 2025-02-07 | 2025-02-10 | 2025-02-12 | 2025-02-16 | 2025-02-16 | 2025-02-19 | 2025-02-21 | 2025-02-23 | 2025-02-23 | 2025-02-27 | 2025-03-01 | 2025-03-02 | 2025-03-03 | 2025-03-09 | 2025-03-14 | 2025-03-21 | 2025-03-21 | 2025-03-21 | 2025-03-26 | 2025-03-26 | 2025-03-28 | 2025-04-02 | 2025-04-10 | 2025-03-03 | 2025-03-21 | 2025-03-23 | 2025-04-14 | 2025-04-11 | 2025-04-17 | 2025-04-19 | 2025-04-25 | 2025-05-01
V_309 | 2024-10-04 | 2024-10-11 | 2024-10-13 | 2024-10-19 | 2024-10-24 | 2024-10-27 | 2024-10-28 | 2024-11-01 | 2024-11-06 | 2024-11-09 | 2024-11-13 | 2024-11-13 | 2025-01-01 | 2025-01-09 | 2025-01-16 | 2025-01-16 | 2025-01-23 | 2025-01-30 | 2025-01-30 | 2025-02-02 | 2025-02-02 | 2025-02-03 | 2025-02-09 | 2025-02-09 | 2025-02-16 | 2025-02-16 | 2025-02-16 | 2025-02-21 | 2025-02-26 | 2025-03-05 | 2025-03-09 | 2025-03-14 | 2025-03-21 | 2025-03-21 | 2025-03-26 | 2025-03-28 | 2025-03-28 | 2025-03-28 | 2025-04-03 | 2025-04-04 | 2025-04-09 | 2025-04-17 | 2025-01-09 | 2025-01-11 | 2025-01-18 | 2025-01-25 | 2025-01-30 | 2025-01-31 | 2025-02-06 | 2025-02-06 | 2025-02-07 | 2025-02-10 | 2025-02-12 | 2025-02-16 | 2025-02-16 | 2025-02-19 | 2025-02-21 | 2025-02-23 | 2025-02-23 | 2025-02-27 | 2025-03-01 | 2025-03-02 | 2025-03-03 | 2025-03-09 | 2025-03-14 | 2025-03-21 | 2025-03-21 | 2025-03-21 | 2025-03-26 | 2025-03-26 | 2025-03-28 | 2025-04-02 | 2025-04-10 | 2025-03-03 | 2025-03-21 | 2025-03-23 | 2025-04-14 | 2025-04-11 | 2025-04-17 | 2025-04-19 | 2025-04-25 | 2025-05-01
V_310 | 2024-10-04 | 2024-10-11 | 2024-10-13 | 2024-10-19 | 2024-10-24 | 2024-10-27 | 2024-10-28 | 2024-11-01 | 2024-11-06 | 2024-11-09 | 2024-11-13 | 2024-11-13 | 2025-01-01 | 2025-01-09 | 2025-01-16 | 2025-01-16 | 2025-01-23 | 2025-01-30 | 2025-01-30 | 2025-02-02 | 2025-02-02 | 2025-02-03 | 2025-02-09 | 2025-02-09 | 2025-02-16 | 2025-02-16 | 2025-02-16 | 2025-02-21 | 2025-02-26 | 2025-03-05 | 2025-03-09 | 2025-03-14 | 2025-03-21 | 2025-03-21 | 2025-03-26 | 2025-03-28 | 2025-03-28 | 2025-03-28 | 2025-04-03 | 2025-04-04 | 2025-04-09 | 2025-04-17 | 2025-01-09 | 2025-01-11 | 2025-01-18 | 2025-01-25 | 2025-01-30 | 2025-01-31 | 2025-02-06 | 2025-02-06 | 2025-02-07 | 2025-02-10 | 2025-02-12 | 2025-02-16 | 2025-02-16 | 2025-02-19 | 2025-02-21 | 2025-02-23 | 2025-02-23 | 2025-02-27 | 2025-03-01 | 2025-03-02 | 2025-03-03 | 2025-03-09 | 2025-03-14 | 2025-03-21 | 2025-03-21 | 2025-03-21 | 2025-03-26 | 2025-03-26 | 2025-03-28 | 2025-04-02 | 2025-04-10 | 2025-03-03 | 2025-03-21 | 2025-03-23 | 2025-04-14 | 2025-04-11 | 2025-04-17 | 2025-04-19 | 2025-04-25 | 2025-05-01
V_311 | 2024-10-04 | 2024-10-11 | 2024-10-13 | 2024-10-19 | 2024-10-24 | 2024-10-27 | 2024-10-28 | 2024-11-01 | 2024-11-06 | 2024-11-09 | 2024-11-13 | 2024-11-13 | 2025-01-01 | 2025-01-09 | 2025-01-16 | 2025-01-16 | 2025-01-23 | 2025-01-30 | 2025-01-30 | 2025-02-02 | 2025-02-02 | 2025-02-03 | 2025-02-09 | 2025-02-09 | 2025-02-16 | 2025-02-16 | 2025-02-16 | 2025-02-21 | 2025-02-26 | 2025-03-05 | 2025-03-09 | 2025-03-14 | 2025-03-21 | 2025-03-21 | 2025-03-26 | 2025-03-28 | 2025-03-28 | 2025-03-28 | 2025-04-03 | 2025-04-04 | 2025-04-09 | 2025-04-17 | 2025-01-09 | 2025-01-11 | 2025-01-18 | 2025-01-25 | 2025-01-30 | 2025-01-31 | 2025-02-06 | 2025-02-06 | 2025-02-07 | 2025-02-10 | 2025-02-12 | 2025-02-16 | 2025-02-16 | 2025-02-19 | 2025-02-21 | 2025-02-23 | 2025-02-23 | 2025-02-27 | 2025-03-01 | 2025-03-02 | 2025-03-03 | 2025-03-09 | 2025-03-14 | 2025-03-21 | 2025-03-21 | 2025-03-21 | 2025-03-26 | 2025-03-26 | 2025-03-28 | 2025-04-02 | 2025-04-10 | 2025-03-03 | 2025-03-21 | 2025-03-23 | 2025-04-14 | 2025-04-11 | 2025-04-17 | 2025-04-19 | 2025-04-25 | 2025-05-01
V_312 | 2024-10-04 | 2024-10-11 | 2024-10-13 | 2024-10-19 | 2024-10-24 | 2024-10-27 | 2024-10-28 | 2024-11-01 | 2024-11-06 | [59 empty] | 2025-03-26 | 2025-03-26 | 2025-03-28 | 2025-04-02 | 2025-04-10 | 2025-03-03 | 2025-03-21 | 2025-03-23 | 2025-04-14 | 2025-04-11 | 2025-04-17 | 2025-04-19 | 2025-04-25 | 2025-05-01
V_313 | 2024-10-11 | 2024-10-18 | 2024-10-20 | 2024-10-26 | 2024-10-31 | 2024-11-03 | 2024-11-04 | 2024-11-08 | 2024-11-13 | [59 empty] | 2025-04-03 | 2025-04-03 | 2025-04-05 | 2025-04-10 | 2025-04-18 | 2025-03-12 | 2025-03-29 | 2025-03-31 | 2025-04-23 | 2025-04-19 | 2025-04-25 | 2025-04-27 | 2025-05-03 | 2025-05-09
V_314 | 2024-10-11 | 2024-10-18 | 2024-10-20 | 2024-10-26 | 2024-10-31 | 2024-11-03 | 2024-11-04 | 2024-11-08 | 2024-11-13 | [59 empty] | 2025-04-03 | 2025-04-03 | 2025-04-05 | 2025-04-10 | 2025-04-18 | 2025-03-12 | 2025-03-29 | 2025-03-31 | 2025-04-23 | 2025-04-19 | 2025-04-25 | 2025-04-27 | 2025-05-03 | 2025-05-09
V_315 | 2024-10-11 | 2024-10-18 | 2024-10-20 | 2024-10-26 | 2024-10-31 | 2024-11-03 | 2024-11-04 | 2024-11-08 | 2024-11-13 | [59 empty] | 2025-04-03 | 2025-04-03 | 2025-04-05 | 2025-04-10 | 2025-04-18 | 2025-03-12 | 2025-03-29 | 2025-03-31 | 2025-04-23 | 2025-04-19 | 2025-04-25 | 2025-04-27 | 2025-05-03 | 2025-05-09
V_316 | 2024-10-11 | 2024-10-18 | 2024-10-20 | 2024-10-26 | 2024-10-31 | 2024-11-03 | 2024-11-04 | 2024-11-08 | 2024-11-13 | [59 empty] | 2025-04-03 | 2025-04-03 | 2025-04-05 | 2025-04-10 | 2025-04-18 | 2025-03-12 | 2025-03-29 | 2025-03-31 | 2025-04-23 | 2025-04-19 | 2025-04-25 | 2025-04-27 | 2025-05-03 | 2025-05-09
V_317 | 2024-10-11 | 2024-10-18 | 2024-10-20 | 2024-10-26 | 2024-10-31 | 2024-11-03 | 2024-11-04 | 2024-11-08 | 2024-11-13 | [59 empty] | 2025-04-03 | 2025-04-03 | 2025-04-05 | 2025-04-10 | 2025-04-18 | 2025-03-12 | 2025-03-29 | 2025-03-31 | 2025-04-23 | 2025-04-19 | 2025-04-25 | 2025-04-27 | 2025-05-03 | 2025-05-09
V_318 | 2024-10-11 | 2024-10-18 | 2024-10-20 | 2024-10-26 | 2024-10-31 | 2024-11-03 | 2024-11-04 | 2024-11-08 | 2024-11-13 | [59 empty] | 2025-04-03 | 2025-04-03 | 2025-04-05 | 2025-04-10 | 2025-04-18 | 2025-03-12 | 2025-03-29 | 2025-03-31 | 2025-04-23 | 2025-04-19 | 2025-04-25 | 2025-04-27 | 2025-05-03 | 2025-05-09
V_319 | 2024-10-11 | 2024-10-18 | 2024-10-20 | 2024-10-26 | 2024-10-31 | 2024-11-03 | 2024-11-04 | 2024-11-08 | 2024-11-13 | [59 empty] | 2025-04-03 | 2025-04-03 | 2025-04-05 | 2025-04-10 | 2025-04-18 | 2025-03-12 | 2025-03-29 | 2025-03-31 | 2025-04-23 | 2025-04-19 | 2025-04-25 | 2025-04-27 | 2025-05-03 | 2025-05-09
V_320 | 2024-10-11 | 2024-10-18 | 2024-10-20 | 2024-10-26 | 2024-10-31 | 2024-11-03 | 2024-11-04 | 2024-11-08 | 2024-11-13 | [59 empty] | 2025-04-03 | 2025-04-03 | 2025-04-05 | 2025-04-10 | 2025-04-18 | 2025-03-12 | 2025-03-29 | 2025-03-31 | 2025-04-23 | 2025-04-19 | 2025-04-25 | 2025-04-27 | 2025-05-03 | 2025-05-09
V_321 | 2024-10-18 | 2024-10-25 | 2024-10-27 | 2024-11-02 | 2024-11-07 | 2024-11-10 | 2024-11-11 | 2024-11-15 | 2024-11-20 | [59 empty] | 2025-04-11 | 2025-04-11 | 2025-04-13 | 2025-04-18 | 2025-04-26 | 2025-03-20 | 2025-04-06 | 2025-04-09 | 2025-05-01 | 2025-04-26 | 2025-05-02 | 2025-05-05 | 2025-05-11 | 2025-05-17
V_322 | 2024-10-18 | 2024-10-25 | 2024-10-27 | 2024-11-02 | 2024-11-07 | 2024-11-10 | 2024-11-11 | 2024-11-15 | 2024-11-20 | [59 empty] | 2025-04-11 | 2025-04-11 | 2025-04-13 | 2025-04-18 | 2025-04-26 | 2025-03-20 | 2025-04-06 | 2025-04-09 | 2025-05-01 | 2025-04-26 | 2025-05-02 | 2025-05-05 | 2025-05-11 | 2025-05-17
V_323 | 2024-10-18 | 2024-10-25 | 2024-10-27 | 2024-11-02 | 2024-11-07 | 2024-11-10 | 2024-11-11 | 2024-11-15 | 2024-11-20 | [59 empty] | 2025-04-11 | 2025-04-11 | 2025-04-13 | 2025-04-18 | 2025-04-26 | 2025-03-20 | 2025-04-06 | 2025-04-09 | 2025-05-01 | 2025-04-26 | 2025-05-02 | 2025-05-05 | 2025-05-11 | 2025-05-17
V_324 | 2024-10-18 | 2024-10-25 | 2024-10-27 | 2024-11-02 | 2024-11-07 | 2024-11-10 | 2024-11-11 | 2024-11-15 | 2024-11-20 | [59 empty] | 2025-04-11 | 2025-04-11 | 2025-04-13 | 2025-04-18 | 2025-04-26 | 2025-03-20 | 2025-04-06 | 2025-04-09 | 2025-05-01 | 2025-04-26 | 2025-05-02 | 2025-05-05 | 2025-05-11 | 2025-05-17
V_325 | 2024-10-18 | 2024-10-25 | 2024-10-27 | 2024-11-02 | 2024-11-07 | 2024-11-10 | 2024-11-11 | 2024-11-15 | 2024-11-20 | [59 empty] | 2025-04-11 | 2025-04-11 | 2025-04-13 | 2025-04-18 | 2025-04-26 | 2025-03-20 | 2025-04-06 | 2025-04-09 | 2025-05-01 | 2025-04-26 | 2025-05-02 | 2025-05-05 | 2025-05-11 | 2025-05-17
V_326 | 2024-10-18 | 2024-10-25 | 2024-10-27 | 2024-11-02 | 2024-11-07 | 2024-11-10 | 2024-11-11 | 2024-11-15 | 2024-11-20 | [59 empty] | 2025-04-11 | 2025-04-11 | 2025-04-13 | 2025-04-18 | 2025-04-26 | 2025-03-20 | 2025-04-06 | 2025-04-09 | 2025-05-01 | 2025-04-26 | 2025-05-02 | 2025-05-05 | 2025-05-11 | 2025-05-17
V_327 | 2024-10-18 | 2024-10-25 | 2024-10-27 | 2024-11-02 | 2024-11-07 | 2024-11-10 | 2024-11-11 | 2024-11-15 | 2024-11-20 | [59 empty] | 2025-04-11 | 2025-04-11 | 2025-04-13 | 2025-04-18 | 2025-04-26 | 2025-03-20 | 2025-04-06 | 2025-04-09 | 2025-05-01 | 2025-04-26 | 2025-05-02 | 2025-05-05 | 2025-05-11 | 2025-05-17
V_328 | 2024-10-18 | 2024-10-25 | 2024-10-27 | 2024-11-02 | 2024-11-07 | 2024-11-10 | 2024-11-11 | 2024-11-15 | 2024-11-20 | [59 empty] | 2025-04-11 | 2025-04-11 | 2025-04-13 | 2025-04-18 | 2025-04-26 | 2025-03-20 | 2025-04-06 | 2025-04-09 | 2025-05-01 | 2025-04-26 | 2025-05-02 | 2025-05-05 | 2025-05-11 | 2025-05-17
V_329 | 2024-10-25 | 2024-11-01 | 2024-11-03 | 2024-11-09 | 2024-11-14 | 2024-11-17 | 2024-11-18 | 2024-11-22 | 2024-11-27 | [59 empty] | 2025-04-19 | 2025-04-19 | 2025-04-21 | 2025-04-26 | 2025-05-04 | 2025-03-28 | 2025-04-14 | 2025-04-17 | 2025-05-09 | 2025-05-03 | 2025-05-09 | 2025-05-14 | 2025-05-19 | 2025-05-25
V_330 | 2024-10-25 | 2024-11-01 | 2024-11-03 | 2024-11-09 | 2024-11-14 | 2024-11-17 | 2024-11-18 | 2024-11-22 | 2024-11-27 | [59 empty] | 2025-04-19 | 2025-04-19 | 2025-04-21 | 2025-04-26 | 2025-05-04 | 2025-03-28 | 2025-04-14 | 2025-04-17 | 2025-05-09 | 2025-05-03 | 2025-05-09 | 2025-05-14 | 2025-05-19 | 2025-05-25
V_331 | 2024-10-25 | 2024-11-01 | 2024-11-03 | 2024-11-09 | 2024-11-14 | 2024-11-17 | 2024-11-18 | 2024-11-22 | 2024-11-27 | [59 empty] | 2025-04-19 | 2025-04-19 | 2025-04-21 | 2025-04-26 | 2025-05-04 | 2025-03-28 | 2025-04-14 | 2025-04-17 | 2025-05-09 | 2025-05-03 | 2025-05-09 | 2025-05-14 | 2025-05-19 | 2025-05-25
V_332 | 2024-10-25 | 2024-11-01 | 2024-11-03 | 2024-11-09 | 2024-11-14 | 2024-11-17 | 2024-11-18 | 2024-11-22 | 2024-11-27 | [59 empty] | 2025-04-19 | 2025-04-19 | 2025-04-21 | 2025-04-26 | 2025-05-04 | 2025-03-28 | 2025-04-14 | 2025-04-17 | 2025-05-09 | 2025-05-03 | 2025-05-09 | 2025-05-14 | 2025-05-19 | 2025-05-25
V_333 | 2024-10-25 | 2024-11-01 | 2024-11-03 | 2024-11-09 | 2024-11-14 | 2024-11-17 | 2024-11-18 | 2024-11-22 | 2024-11-27 | [59 empty] | 2025-04-19 | 2025-04-19 | 2025-04-21 | 2025-04-26 | 2025-05-04 | 2025-03-28 | 2025-04-14 | 2025-04-17 | 2025-05-09 | 2025-05-03 | 2025-05-09 | 2025-05-14 | 2025-05-19 | 2025-05-25
V_334 | 2024-10-25 | 2024-11-01 | 2024-11-03 | 2024-11-09 | 2024-11-14 | 2024-11-17 | 2024-11-18 | 2024-11-22 | 2024-11-27 | [59 empty] | 2025-04-19 | 2025-04-19 | 2025-04-21 | 2025-04-26 | 2025-05-04 | 2025-03-28 | 2025-04-14 | 2025-04-17 | 2025-05-09 | 2025-05-03 | 2025-05-09 | 2025-05-14 | 2025-05-19 | 2025-05-25
V_335 | 2024-10-25 | 2024-11-01 | 2024-11-03 | 2024-11-09 | 2024-11-14 | 2024-11-17 | 2024-11-18 | 2024-11-22 | 2024-11-27 | [59 empty] | 2025-04-19 | 2025-04-19 | 2025-04-21 | 2025-04-26 | 2025-05-04 | 2025-03-28 | 2025-04-14 | 2025-04-17 | 2025-05-09 | 2025-05-03 | 2025-05-09 | 2025-05-14 | 2025-05-19 | 2025-05-25
V_336 | 2024-10-25 | 2024-11-01 | 2024-11-03 | 2024-11-09 | 2024-11-14 | 2024-11-17 | 2024-11-18 | 2024-11-22 | 2024-11-27 | [59 empty] | 2025-04-19 | 2025-04-19 | 2025-04-21 | 2025-04-26 | 2025-05-04 | 2025-03-28 | 2025-04-14 | 2025-04-17 | 2025-05-09 | 2025-05-03 | 2025-05-09 | 2025-05-14 | 2025-05-19 | 2025-05-25
V_337 | 2024-11-01 | 2024-11-08 | 2024-11-10 | 2024-11-16 | 2024-11-21 | 2024-11-24 | 2024-11-25 | 2024-11-29 | 2024-12-04 | [59 empty] | 2025-04-27 | 2025-04-27 | 2025-04-30 | 2025-05-04 | 2025-05-12 | 2025-04-05 | 2025-04-23 | 2025-04-25 | 2025-05-17 | 2025-05-11 | 2025-05-17 | 2025-05-22 | 2025-05-28 | 2025-06-02
V_338 | 2024-11-01 | 2024-11-08 | 2024-11-10 | 2024-11-16 | 2024-11-21 | 2024-11-24 | 2024-11-25 | 2024-11-29 | 2024-12-04 | [59 empty] | 2025-04-27 | 2025-04-27 | 2025-04-30 | 2025-05-04 | 2025-05-12 | 2025-04-05 | 2025-04-23 | 2025-04-25 | 2025-05-17 | 2025-05-11 | 2025-05-17 | 2025-05-22 | 2025-05-28 | 2025-06-02
V_339 | 2024-11-01 | 2024-11-08 | 2024-11-10 | 2024-11-16 | 2024-11-21 | 2024-11-24 | 2024-11-25 | 2024-11-29 | 2024-12-04 | [59 empty] | 2025-04-27 | 2025-04-27 | 2025-04-30 | 2025-05-04 | 2025-05-12 | 2025-04-05 | 2025-04-23 | 2025-04-25 | 2025-05-17 | 2025-05-11 | 2025-05-17 | 2025-05-22 | 2025-05-28 | 2025-06-02
V_340 | 2024-11-01 | 2024-11-08 | 2024-11-10 | 2024-11-16 | 2024-11-21 | 2024-11-24 | 2024-11-25 | 2024-11-29 | 2024-12-04 | [59 empty] | 2025-04-27 | 2025-04-27 | 2025-04-30 | 2025-05-04 | 2025-05-12 | 2025-04-05 | 2025-04-23 | 2025-04-25 | 2025-05-17 | 2025-05-11 | 2025-05-17 | 2025-05-22 | 2025-05-28 | 2025-06-02
V_341 | 2024-11-01 | 2024-11-08 | 2024-11-10 | 2024-11-16 | 2024-11-21 | 2024-11-24 | 2024-11-25 | 2024-11-29 | 2024-12-04 | [59 empty] | 2025-04-27 | 2025-04-27 | 2025-04-30 | 2025-05-04 | 2025-05-12 | 2025-04-05 | 2025-04-23 | 2025-04-25 | 2025-05-17 | 2025-05-11 | 2025-05-17 | 2025-05-22 | 2025-05-28 | 2025-06-02
V_342 | 2024-11-01 | 2024-11-08 | 2024-11-10 | 2024-11-16 | 2024-11-21 | 2024-11-24 | 2024-11-25 | 2024-11-29 | 2024-12-04 | [59 empty] | 2025-04-27 | 2025-04-27 | 2025-04-30 | 2025-05-04 | 2025-05-12 | 2025-04-05 | 2025-04-23 | 2025-04-25 | 2025-05-17 | 2025-05-11 | 2025-05-17 | 2025-05-22 | 2025-05-28 | 2025-06-02
V_343 | 2024-11-01 | 2024-11-08 | 2024-11-10 | 2024-11-16 | 2024-11-21 | 2024-11-24 | 2024-11-25 | 2024-11-29 | 2024-12-04 | [59 empty] | 2025-04-27 | 2025-04-27 | 2025-04-30 | 2025-05-04 | 2025-05-12 | 2025-04-05 | 2025-04-23 | 2025-04-25 | 2025-05-17 | 2025-05-11 | 2025-05-17 | 2025-05-22 | 2025-05-28 | 2025-06-02
V_344 | 2024-11-01 | 2024-11-08 | 2024-11-10 | 2024-11-16 | 2024-11-21 | 2024-11-24 | 2024-11-25 | 2024-11-29 | 2024-12-04 | [59 empty] | 2025-04-27 | 2025-04-27 | 2025-04-30 | 2025-05-04 | 2025-05-12 | 2025-04-05 | 2025-04-23 | 2025-04-25 | 2025-05-17 | 2025-05-11 | 2025-05-17 | 2025-05-22 | 2025-05-28 | 2025-06-02
V_345 | 2024-11-08 | 2024-11-15 | 2024-11-17 | 2024-11-23 | 2024-11-28 | 2024-12-01 | 2024-12-02 | 2024-12-06 | 2024-12-11 | [59 empty] | 2025-05-05 | 2025-05-05 | 2025-05-08 | 2025-05-12 | 2025-05-21 | 2025-04-13 | 2025-05-01 | 2025-05-03 | 2025-05-25 | 2025-05-19 | 2025-05-25 | 2025-05-30 | 2025-06-05 | 2025-06-11
V_346 | 2024-11-08 | 2024-11-15 | 2024-11-17 | 2024-11-23 | 2024-11-28 | 2024-12-01 | 2024-12-02 | 2024-12-06 | 2024-12-11 | [59 empty] | 2025-05-05 | 2025-05-05 | 2025-05-08 | 2025-05-12 | 2025-05-21 | 2025-04-13 | 2025-05-01 | 2025-05-03 | 2025-05-25 | 2025-05-19 | 2025-05-25 | 2025-05-30 | 2025-06-05 | 2025-06-11
V_347 | 2024-11-08 | 2024-11-15 | 2024-11-17 | 2024-11-23 | 2024-11-28 | 2024-12-01 | 2024-12-02 | 2024-12-06 | 2024-12-11 | [59 empty] | 2025-05-05 | 2025-05-05 | 2025-05-08 | 2025-05-12 | 2025-05-21 | 2025-04-13 | 2025-05-01 | 2025-05-03 | 2025-05-25 | 2025-05-19 | 2025-05-25 | 2025-05-30 | 2025-06-05 | 2025-06-11
V_348 | 2024-11-08 | 2024-11-15 | 2024-11-17 | 2024-11-23 | 2024-11-28 | 2024-12-01 | 2024-12-02 | 2024-12-06 | 2024-12-11 | [59 empty] | 2025-05-05 | 2025-05-05 | 2025-05-08 | 2025-05-12 | 2025-05-21 | 2025-04-13 | 2025-05-01 | 2025-05-03 | 2025-05-25 | 2025-05-19 | 2025-05-25 | 2025-05-30 | 2025-06-05 | 2025-06-11
V_349 | 2024-11-08 | 2024-11-15 | 2024-11-17 | 2024-11-23 | 2024-11-28 | 2024-12-01 | 2024-12-02 | 2024-12-06 | 2024-12-11 | [59 empty] | 2025-05-05 | 2025-05-05 | 2025-05-08 | 2025-05-12 | 2025-05-21 | 2025-04-13 | 2025-05-01 | 2025-05-03 | 2025-05-25 | 2025-05-19 | 2025-05-25 | 2025-05-30 | 2025-06-05 | 2025-06-11
V_350 | 2024-11-08 | 2024-11-15 | 2024-11-17 | 2024-11-23 | 2024-11-28 | 2024-12-01 | 2024-12-02 | 2024-12-06 | 2024-12-11 | [59 empty] | 2025-05-05 | 2025-05-05 | 2025-05-08 | 2025-05-12 | 2025-05-21 | 2025-04-13 | 2025-05-01 | 2025-05-03 | 2025-05-25 | 2025-05-19 | 2025-05-25 | 2025-05-30 | 2025-06-05 | 2025-06-11
V_351 | 2024-11-08 | 2024-11-15 | 2024-11-17 | 2024-11-23 | 2024-11-28 | 2024-12-01 | 2024-12-02 | 2024-12-06 | 2024-12-11 | [59 empty] | 2025-05-05 | 2025-05-05 | 2025-05-08 | 2025-05-12 | 2025-05-21 | 2025-04-13 | 2025-05-01 | 2025-05-03 | 2025-05-25 | 2025-05-19 | 2025-05-25 | 2025-05-30 | 2025-06-05 | 2025-06-11
V_352 | 2024-11-08 | 2024-11-15 | 2024-11-17 | 2024-11-23 | 2024-11-28 | 2024-12-01 | 2024-12-02 | 2024-12-06 | 2024-12-11 | 2024-12-14 | 2024-12-18 | 2024-12-18 | 2025-02-10 | 2025-02-19 | 2025-02-26 | 2025-02-26 | 2025-03-05 | 2025-03-12 | 2025-03-12 | 2025-03-15 | 2025-03-15 | 2025-03-16 | 2025-03-22 | 2025-03-22 | 2025-03-29 | 2025-03-29 | 2025-03-29 | 2025-04-03 | 2025-04-07 | 2025-04-14 | 2025-04-19 | 2025-04-24 | 2025-05-01 | 2025-05-01 | 2025-05-05 | 2025-05-08 | 2025-05-08 | 2025-05-08 | 2025-05-12 | 2025-05-14 | 2025-05-18 | 2025-05-25 | 2025-02-19 | 2025-02-21 | 2025-02-28 | 2025-03-07 | 2025-03-12 | 2025-03-13 | 2025-03-19 | 2025-03-19 | 2025-03-20 | 2025-03-23 | 2025-03-24 | 2025-03-29 | 2025-03-29 | 2025-03-31 | 2025-04-03 | 2025-04-05 | 2025-04-05 | 2025-04-09 | 2025-04-11 | 2025-04-12 | 2025-04-13 | 2025-04-19 | 2025-04-24 | 2025-05-01 | 2025-05-01 | 2025-05-01 | 2025-05-05 | 2025-05-05 | 2025-05-08 | 2025-05-12 | 2025-05-21 | 2025-04-13 | 2025-05-01 | 2025-05-03 | 2025-05-25 | 2025-05-19 | 2025-05-25 | 2025-05-30 | 2025-06-05 | 2025-06-11
V_353 | 2024-11-15 | 2024-11-22 | 2024-11-24 | 2024-11-30 | 2024-12-05 | 2024-12-08 | 2024-12-09 | 2024-12-13 | 2024-12-18 | 2024-12-21 | 2024-12-25 | 2024-12-25 | 2025-02-19 | 2025-02-27 | 2025-03-06 | 2025-03-06 | 2025-03-13 | 2025-03-20 | 2025-03-20 | 2025-03-23 | 2025-03-23 | 2025-03-24 | 2025-03-30 | 2025-03-30 | 2025-04-06 | 2025-04-06 | 2025-04-06 | 2025-04-11 | 2025-04-16 | 2025-04-23 | 2025-04-27 | 2025-05-02 | 2025-05-09 | 2025-05-09 | 2025-05-14 | 2025-05-16 | 2025-05-16 | 2025-05-16 | 2025-05-21 | 2025-05-22 | 2025-05-26 | 2025-06-02 | 2025-02-27 | 2025-03-01 | 2025-03-08 | 2025-03-15 | 2025-03-20 | 2025-03-21 | 2025-03-27 | 2025-03-27 | 2025-03-28 | 2025-03-31 | 2025-04-02 | 2025-04-06 | 2025-04-06 | 2025-04-09 | 2025-04-11 | 2025-04-13 | 2025-04-13 | 2025-04-17 | 2025-04-19 | 2025-04-20 | 2025-04-21 | 2025-04-27 | 2025-05-02 | 2025-05-09 | 2025-05-09 | 2025-05-09 | 2025-05-14 | 2025-05-14 | 2025-05-16 | 2025-05-21 | 2025-05-29 | 2025-04-21 | 2025-05-09 | 2025-05-11 | 2025-06-02 | 2025-05-28 | 2025-06-02 | 2025-06-07 | 2025-06-13 | 2025-06-19
V_354 | 2024-11-15 | 2024-11-22 | 2024-11-24 | 2024-11-30 | 2024-12-05 | 2024-12-08 | 2024-12-09 | 2024-12-13 | 2024-12-18 | 2024-12-21 | 2024-12-25 | 2024-12-25 | 2025-02-19 | 2025-02-27 | 2025-03-06 | 2025-03-06 | 2025-03-13 | 2025-03-20 | 2025-03-20 | 2025-03-23 | 2025-03-23 | 2025-03-24 | 2025-03-30 | 2025-03-30 | 2025-04-06 | 2025-04-06 | 2025-04-06 | 2025-04-11 | 2025-04-16 | 2025-04-23 | 2025-04-27 | 2025-05-02 | 2025-05-09 | 2025-05-09 | 2025-05-14 | 2025-05-16 | 2025-05-16 | 2025-05-16 | 2025-05-21 | 2025-05-22 | 2025-05-26 | 2025-06-02 | 2025-02-27 | 2025-03-01 | 2025-03-08 | 2025-03-15 | 2025-03-20 | 2025-03-21 | 2025-03-27 | 2025-03-27 | 2025-03-28 | 2025-03-31 | 2025-04-02 | 2025-04-06 | 2025-04-06 | 2025-04-09 | 2025-04-11 | 2025-04-13 | 2025-04-13 | 2025-04-17 | 2025-04-19 | 2025-04-20 | 2025-04-21 | 2025-04-27 | 2025-05-02 | 2025-05-09 | 2025-05-09 | 2025-05-09 | 2025-05-14 | 2025-05-14 | 2025-05-16 | 2025-05-21 | 2025-05-29 | 2025-04-21 | 2025-05-09 | 2025-05-11 | 2025-06-02 | 2025-05-28 | 2025-06-02 | 2025-06-07 | 2025-06-13 | 2025-06-19
V_355 | 2024-11-15 | 2024-11-22 | 2024-11-24 | 2024-11-30 | 2024-12-05 | 2024-12-08 | 2024-12-09 | 2024-12-13 | 2024-12-18 | 2024-12-21 | 2024-12-25 | 2024-12-25 | 2025-02-19 | 2025-02-27 | 2025-03-06 | 2025-03-06 | 2025-03-13 | 2025-03-20 | 2025-03-20 | 2025-03-23 | 2025-03-23 | 2025-03-24 | 2025-03-30 | 2025-03-30 | 2025-04-06 | 2025-04-06 | 2025-04-06 | 2025-04-11 | 2025-04-16 | 2025-04-23 | 2025-04-27 | 2025-05-02 | 2025-05-09 | 2025-05-09 | 2025-05-14 | 2025-05-16 | 2025-05-16 | 2025-05-16 | 2025-05-21 | 2025-05-22 | 2025-05-26 | 2025-06-02 | 2025-02-27 | 2025-03-01 | 2025-03-08 | 2025-03-15 | 2025-03-20 | 2025-03-21 | 2025-03-27 | 2025-03-27 | 2025-03-28 | 2025-03-31 | 2025-04-02 | 2025-04-06 | 2025-04-06 | 2025-04-09 | 2025-04-11 | 2025-04-13 | 2025-04-13 | 2025-04-17 | 2025-04-19 | 2025-04-20 | 2025-04-21 | 2025-04-27 | 2025-05-02 | 2025-05-09 | 2025-05-09 | 2025-05-09 | 2025-05-14 | 2025-05-14 | 2025-05-16 | 2025-05-21 | 2025-05-29 | 2025-04-21 | 2025-05-09 | 2025-05-11 | 2025-06-02 | 2025-05-28 | 2025-06-02 | 2025-06-07 | 2025-06-13 | 2025-06-19
V_356 | 2024-11-15 | 2024-11-22 | 2024-11-24 | 2024-11-30 | 2024-12-05 | 2024-12-08 | 2024-12-09 | 2024-12-13 | 2024-12-18 | 2024-12-21 | 2024-12-25 | 2024-12-25 | 2025-02-19 | 2025-02-27 | 2025-03-06 | 2025-03-06 | 2025-03-13 | 2025-03-20 | 2025-03-20 | 2025-03-23 | 2025-03-23 | 2025-03-24 | 2025-03-30 | 2025-03-30 | 2025-04-06 | 2025-04-06 | 2025-04-06 | 2025-04-11 | 2025-04-16 | 2025-04-23 | 2025-04-27 | 2025-05-02 | 2025-05-09 | 2025-05-09 | 2025-05-14 | 2025-05-16 | 2025-05-16 | 2025-05-16 | 2025-05-21 | 2025-05-22 | 2025-05-26 | 2025-06-02 | 2025-02-27 | 2025-03-01 | 2025-03-08 | 2025-03-15 | 2025-03-20 | 2025-03-21 | 2025-03-27 | 2025-03-27 | 2025-03-28 | 2025-03-31 | 2025-04-02 | 2025-04-06 | 2025-04-06 | 2025-04-09 | 2025-04-11 | 2025-04-13 | 2025-04-13 | 2025-04-17 | 2025-04-19 | 2025-04-20 | 2025-04-21 | 2025-04-27 | 2025-05-02 | 2025-05-09 | 2025-05-09 | 2025-05-09 | 2025-05-14 | 2025-05-14 | 2025-05-16 | 2025-05-21 | 2025-05-29 | 2025-04-21 | 2025-05-09 | 2025-05-11 | 2025-06-02 | 2025-05-28 | 2025-06-02 | 2025-06-07 | 2025-06-13 | 2025-06-19
V_357 | 2024-11-15 | 2024-11-22 | 2024-11-24 | 2024-11-30 | 2024-12-05 | 2024-12-08 | 2024-12-09 | 2024-12-13 | 2024-12-18 | 2024-12-21 | 2024-12-25 | 2024-12-25 | 2025-02-19 | 2025-02-27 | 2025-03-06 | 2025-03-06 | 2025-03-13 | 2025-03-20 | 2025-03-20 | 2025-03-23 | 2025-03-23 | 2025-03-24 | 2025-03-30 | 2025-03-30 | 2025-04-06 | 2025-04-06 | 2025-04-06 | 2025-04-11 | 2025-04-16 | 2025-04-23 | 2025-04-27 | 2025-05-02 | 2025-05-09 | 2025-05-09 | 2025-05-14 | 2025-05-16 | 2025-05-16 | 2025-05-16 | 2025-05-21 | 2025-05-22 | 2025-05-26 | 2025-06-02 | 2025-02-27 | 2025-03-01 | 2025-03-08 | 2025-03-15 | 2025-03-20 | 2025-03-21 | 2025-03-27 | 2025-03-27 | 2025-03-28 | 2025-03-31 | 2025-04-02 | 2025-04-06 | 2025-04-06 | 2025-04-09 | 2025-04-11 | 2025-04-13 | 2025-04-13 | 2025-04-17 | 2025-04-19 | 2025-04-20 | 2025-04-21 | 2025-04-27 | 2025-05-02 | 2025-05-09 | 2025-05-09 | 2025-05-09 | 2025-05-14 | 2025-05-14 | 2025-05-16 | 2025-05-21 | 2025-05-29 | 2025-04-21 | 2025-05-09 | 2025-05-11 | 2025-06-02 | 2025-05-28 | 2025-06-02 | 2025-06-07 | 2025-06-13 | 2025-06-19
V_358 | 2024-11-15 | 2024-11-22 | 2024-11-24 | 2024-11-30 | 2024-12-05 | 2024-12-08 | 2024-12-09 | 2024-12-13 | 2024-12-18 | 2024-12-21 | 2024-12-25 | 2024-12-25 | 2025-02-19 | 2025-02-27 | 2025-03-06 | 2025-03-06 | 2025-03-13 | 2025-03-20 | 2025-03-20 | 2025-03-23 | 2025-03-23 | 2025-03-24 | 2025-03-30 | 2025-03-30 | 2025-04-06 | 2025-04-06 | 2025-04-06 | 2025-04-11 | 2025-04-16 | 2025-04-23 | 2025-04-27 | 2025-05-02 | 2025-05-09 | 2025-05-09 | 2025-05-14 | 2025-05-16 | 2025-05-16 | 2025-05-16 | 2025-05-21 | 2025-05-22 | 2025-05-26 | 2025-06-02 | 2025-02-27 | 2025-03-01 | 2025-03-08 | 2025-03-15 | 2025-03-20 | 2025-03-21 | 2025-03-27 | 2025-03-27 | 2025-03-28 | 2025-03-31 | 2025-04-02 | 2025-04-06 | 2025-04-06 | 2025-04-09 | 2025-04-11 | 2025-04-13 | 2025-04-13 | 2025-04-17 | 2025-04-19 | 2025-04-20 | 2025-04-21 | 2025-04-27 | 2025-05-02 | 2025-05-09 | 2025-05-09 | 2025-05-09 | 2025-05-14 | 2025-05-14 | 2025-05-16 | 2025-05-21 | 2025-05-29 | 2025-04-21 | 2025-05-09 | 2025-05-11 | 2025-06-02 | 2025-05-28 | 2025-06-02 | 2025-06-07 | 2025-06-13 | 2025-06-19
V_359 | 2024-11-15 | 2024-11-22 | 2024-11-24 | 2024-11-30 | 2024-12-05 | 2024-12-08 | 2024-12-09 | 2024-12-13 | 2024-12-18 | 2024-12-21 | 2024-12-25 | 2024-12-25 | 2025-02-19 | 2025-02-27 | 2025-03-06 | 2025-03-06 | 2025-03-13 | 2025-03-20 | 2025-03-20 | 2025-03-23 | 2025-03-23 | 2025-03-24 | 2025-03-30 | 2025-03-30 | 2025-04-06 | 2025-04-06 | 2025-04-06 | 2025-04-11 | 2025-04-16 | 2025-04-23 | 2025-04-27 | 2025-05-02 | 2025-05-09 | 2025-05-09 | 2025-05-14 | 2025-05-16 | 2025-05-16 | 2025-05-16 | 2025-05-21 | 2025-05-22 | 2025-05-26 | 2025-06-02 | 2025-02-27 | 2025-03-01 | 2025-03-08 | 2025-03-15 | 2025-03-20 | 2025-03-21 | 2025-03-27 | 2025-03-27 | 2025-03-28 | 2025-03-31 | 2025-04-02 | 2025-04-06 | 2025-04-06 | 2025-04-09 | 2025-04-11 | 2025-04-13 | 2025-04-13 | 2025-04-17 | 2025-04-19 | 2025-04-20 | 2025-04-21 | 2025-04-27 | 2025-05-02 | 2025-05-09 | 2025-05-09 | 2025-05-09 | 2025-05-14 | 2025-05-14 | 2025-05-16 | 2025-05-21 | 2025-05-29 | 2025-04-21 | 2025-05-09 | 2025-05-11 | 2025-06-02 | 2025-05-28 | 2025-06-02 | 2025-06-07 | 2025-06-13 | 2025-06-19
V_360 | 2024-11-15 | 2024-11-22 | 2024-11-24 | 2024-11-30 | 2024-12-05 | 2024-12-08 | 2024-12-09 | 2024-12-13 | 2024-12-18 | 2024-12-21 | 2024-12-25 | 2024-12-25 | 2025-02-19 | 2025-02-27 | 2025-03-06 | 2025-03-06 | 2025-03-13 | 2025-03-20 | 2025-03-20 | 2025-03-23 | 2025-03-23 | 2025-03-24 | 2025-03-30 | 2025-03-30 | 2025-04-06 | 2025-04-06 | 2025-04-06 | 2025-04-11 | 2025-04-16 | 2025-04-23 | 2025-04-27 | 2025-05-02 | 2025-05-09 | 2025-05-09 | 2025-05-14 | 2025-05-16 | 2025-05-16 | 2025-05-16 | 2025-05-21 | 2025-05-22 | 2025-05-26 | 2025-06-02 | 2025-02-27 | 2025-03-01 | 2025-03-08 | 2025-03-15 | 2025-03-20 | 2025-03-21 | 2025-03-27 | 2025-03-27 | 2025-03-28 | 2025-03-31 | 2025-04-02 | 2025-04-06 | 2025-04-06 | 2025-04-09 | 2025-04-11 | 2025-04-13 | 2025-04-13 | 2025-04-17 | 2025-04-19 | 2025-04-20 | 2025-04-21 | 2025-04-27 | 2025-05-02 | 2025-05-09 | 2025-05-09 | 2025-05-09 | 2025-05-14 | 2025-05-14 | 2025-05-16 | 2025-05-21 | 2025-05-29 | 2025-04-21 | 2025-05-09 | 2025-05-11 | 2025-06-02 | 2025-05-28 | 2025-06-02 | 2025-06-07 | 2025-06-13 | 2025-06-19
V_361 | 2024-11-22 | 2024-11-29 | 2024-12-01 | 2024-12-07 | 2024-12-12 | 2024-12-15 | 2024-12-16 | 2024-12-20 | 2024-12-25 | 2024-12-28 | 2025-01-01 | 2025-01-01 | 2025-02-27 | 2025-03-07 | 2025-03-14 | 2025-03-14 | 2025-03-21 | 2025-03-28 | 2025-03-28 | 2025-03-31 | 2025-03-31 | 2025-04-02 | 2025-04-07 | 2025-04-07 | 2025-04-14 | 2025-04-14 | 2025-04-14 | 2025-04-19 | 2025-04-24 | 2025-05-01 | 2025-05-05 | 2025-05-10 | 2025-05-17 | 2025-05-17 | 2025-05-22 | 2025-05-24 | 2025-05-24 | 2025-05-24 | 2025-05-29 | 2025-05-30 | 2025-06-04 | 2025-06-11 | 2025-03-07 | 2025-03-09 | 2025-03-16 | 2025-03-23 | 2025-03-28 | 2025-03-29 | 2025-04-04 | 2025-04-04 | 2025-04-05 | 2025-04-09 | 2025-04-10 | 2025-04-14 | 2025-04-14 | 2025-04-17 | 2025-04-19 | 2025-04-21 | 2025-04-21 | 2025-04-25 | 2025-04-27 | 2025-04-28 | 2025-04-30 | 2025-05-05 | 2025-05-10 | 2025-05-17 | 2025-05-17 | 2025-05-17 | 2025-05-22 | 2025-05-22 | 2025-05-24 | 2025-05-29 | 2025-06-06 | 2025-04-30 | 2025-05-17 | 2025-05-19 | 2025-06-11 | 2025-06-05 | 2025-06-11 | 2025-06-15 | 2025-06-21 | 2025-06-27
V_362 | 2024-11-22 | 2024-11-29 | 2024-12-01 | 2024-12-07 | 2024-12-12 | 2024-12-15 | 2024-12-16 | 2024-12-20 | 2024-12-25 | 2024-12-28 | 2025-01-01 | 2025-01-01 | 2025-02-27 | 2025-03-07 | 2025-03-14 | 2025-03-14 | 2025-03-21 | 2025-03-28 | 2025-03-28 | 2025-03-31 | 2025-03-31 | 2025-04-02 | 2025-04-07 | 2025-04-07 | 2025-04-14 | 2025-04-14 | 2025-04-14 | 2025-04-19 | 2025-04-24 | 2025-05-01 | 2025-05-05 | 2025-05-10 | 2025-05-17 | 2025-05-17 | 2025-05-22 | 2025-05-24 | 2025-05-24 | 2025-05-24 | 2025-05-29 | 2025-05-30 | 2025-06-04 | 2025-06-11 | 2025-03-07 | 2025-03-09 | 2025-03-16 | 2025-03-23 | 2025-03-28 | 2025-03-29 | 2025-04-04 | 2025-04-04 | 2025-04-05 | 2025-04-09 | 2025-04-10 | 2025-04-14 | 2025-04-14 | 2025-04-17 | 2025-04-19 | 2025-04-21 | 2025-04-21 | 2025-04-25 | 2025-04-27 | 2025-04-28 | 2025-04-30 | 2025-05-05 | 2025-05-10 | 2025-05-17 | 2025-05-17 | 2025-05-17 | 2025-05-22 | 2025-05-22 | 2025-05-24 | 2025-05-29 | 2025-06-06 | 2025-04-30 | 2025-05-17 | 2025-05-19 | 2025-06-11 | 2025-06-05 | 2025-06-11 | 2025-06-15 | 2025-06-21 | 2025-06-27
V_363 | 2024-11-22 | 2024-11-29 | 2024-12-01 | 2024-12-07 | 2024-12-12 | 2024-12-15 | 2024-12-16 | 2024-12-20 | 2024-12-25 | 2024-12-28 | 2025-01-01 | 2025-01-01 | 2025-02-27 | 2025-03-07 | 2025-03-14 | 2025-03-14 | 2025-03-21 | 2025-03-28 | 2025-03-28 | 2025-03-31 | 2025-03-31 | 2025-04-02 | 2025-04-07 | 2025-04-07 | 2025-04-14 | 2025-04-14 | 2025-04-14 | 2025-04-19 | 2025-04-24 | 2025-05-01 | 2025-05-05 | 2025-05-10 | 2025-05-17 | 2025-05-17 | 2025-05-22 | 2025-05-24 | 2025-05-24 | 2025-05-24 | 2025-05-29 | 2025-05-30 | 2025-06-04 | 2025-06-11 | 2025-03-07 | 2025-03-09 | 2025-03-16 | 2025-03-23 | 2025-03-28 | 2025-03-29 | 2025-04-04 | 2025-04-04 | 2025-04-05 | 2025-04-09 | 2025-04-10 | 2025-04-14 | 2025-04-14 | 2025-04-17 | 2025-04-19 | 2025-04-21 | 2025-04-21 | 2025-04-25 | 2025-04-27 | 2025-04-28 | 2025-04-30 | 2025-05-05 | 2025-05-10 | 2025-05-17 | 2025-05-17 | 2025-05-17 | 2025-05-22 | 2025-05-22 | 2025-05-24 | 2025-05-29 | 2025-06-06 | 2025-04-30 | 2025-05-17 | 2025-05-19 | 2025-06-11 | 2025-06-05 | 2025-06-11 | 2025-06-15 | 2025-06-21 | 2025-06-27
V_364 | 2024-11-22 | 2024-11-29 | 2024-12-01 | 2024-12-07 | 2024-12-12 | 2024-12-15 | 2024-12-16 | 2024-12-20 | 2024-12-25 | 2024-12-28 | 2025-01-01 | 2025-01-01 | 2025-02-27 | 2025-03-07 | 2025-03-14 | 2025-03-14 | 2025-03-21 | 2025-03-28 | 2025-03-28 | 2025-03-31 | 2025-03-31 | 2025-04-02 | 2025-04-07 | 2025-04-07 | 2025-04-14 | 2025-04-14 | 2025-04-14 | 2025-04-19 | 2025-04-24 | 2025-05-01 | 2025-05-05 | 2025-05-10 | 2025-05-17 | 2025-05-17 | 2025-05-22 | 2025-05-24 | 2025-05-24 | 2025-05-24 | 2025-05-29 | 2025-05-30 | 2025-06-04 | 2025-06-11 | 2025-03-07 | 2025-03-09 | 2025-03-16 | 2025-03-23 | 2025-03-28 | 2025-03-29 | 2025-04-04 | 2025-04-04 | 2025-04-05 | 2025-04-09 | 2025-04-10 | 2025-04-14 | 2025-04-14 | 2025-04-17 | 2025-04-19 | 2025-04-21 | 2025-04-21 | 2025-04-25 | 2025-04-27 | 2025-04-28 | 2025-04-30 | 2025-05-05 | 2025-05-10 | 2025-05-17 | 2025-05-17 | 2025-05-17 | 2025-05-22 | 2025-05-22 | 2025-05-24 | 2025-05-29 | 2025-06-06 | 2025-04-30 | 2025-05-17 | 2025-05-19 | 2025-06-11 | 2025-06-05 | 2025-06-11 | 2025-06-15 | 2025-06-21 | 2025-06-27
V_365 | 2024-11-22 | 2024-11-29 | 2024-12-01 | 2024-12-07 | 2024-12-12 | 2024-12-15 | 2024-12-16 | 2024-12-20 | 2024-12-25 | 2024-12-28 | 2025-01-01 | 2025-01-01 | 2025-02-27 | 2025-03-07 | 2025-03-14 | 2025-03-14 | 2025-03-21 | 2025-03-28 | 2025-03-28 | 2025-03-31 | 2025-03-31 | 2025-04-02 | 2025-04-07 | 2025-04-07 | 2025-04-14 | 2025-04-14 | 2025-04-14 | 2025-04-19 | 2025-04-24 | 2025-05-01 | 2025-05-05 | 2025-05-10 | 2025-05-17 | 2025-05-17 | 2025-05-22 | 2025-05-24 | 2025-05-24 | 2025-05-24 | 2025-05-29 | 2025-05-30 | 2025-06-04 | 2025-06-11 | 2025-03-07 | 2025-03-09 | 2025-03-16 | 2025-03-23 | 2025-03-28 | 2025-03-29 | 2025-04-04 | 2025-04-04 | 2025-04-05 | 2025-04-09 | 2025-04-10 | 2025-04-14 | 2025-04-14 | 2025-04-17 | 2025-04-19 | 2025-04-21 | 2025-04-21 | 2025-04-25 | 2025-04-27 | 2025-04-28 | 2025-04-30 | 2025-05-05 | 2025-05-10 | 2025-05-17 | 2025-05-17 | 2025-05-17 | 2025-05-22 | 2025-05-22 | 2025-05-24 | 2025-05-29 | 2025-06-06 | 2025-04-30 | 2025-05-17 | 2025-05-19 | 2025-06-11 | 2025-06-05 | 2025-06-11 | 2025-06-15 | 2025-06-21 | 2025-06-27
V_366 | 2024-11-22 | 2024-11-29 | 2024-12-01 | 2024-12-07 | 2024-12-12 | 2024-12-15 | 2024-12-16 | 2024-12-20 | 2024-12-25 | 2024-12-28 | 2025-01-01 | 2025-01-01 | 2025-02-27 | 2025-03-07 | 2025-03-14 | 2025-03-14 | 2025-03-21 | 2025-03-28 | 2025-03-28 | 2025-03-31 | 2025-03-31 | 2025-04-02 | 2025-04-07 | 2025-04-07 | 2025-04-14 | 2025-04-14 | 2025-04-14 | 2025-04-19 | 2025-04-24 | 2025-05-01 | 2025-05-05 | 2025-05-10 | 2025-05-17 | 2025-05-17 | 2025-05-22 | 2025-05-24 | 2025-05-24 | 2025-05-24 | 2025-05-29 | 2025-05-30 | 2025-06-04 | 2025-06-11 | 2025-03-07 | 2025-03-09 | 2025-03-16 | 2025-03-23 | 2025-03-28 | 2025-03-29 | 2025-04-04 | 2025-04-04 | 2025-04-05 | 2025-04-09 | 2025-04-10 | 2025-04-14 | 2025-04-14 | 2025-04-17 | 2025-04-19 | 2025-04-21 | 2025-04-21 | 2025-04-25 | 2025-04-27 | 2025-04-28 | 2025-04-30 | 2025-05-05 | 2025-05-10 | 2025-05-17 | 2025-05-17 | 2025-05-17 | 2025-05-22 | 2025-05-22 | 2025-05-24 | 2025-05-29 | 2025-06-06 | 2025-04-30 | 2025-05-17 | 2025-05-19 | 2025-06-11 | 2025-06-05 | 2025-06-11 | 2025-06-15 | 2025-06-21 | 2025-06-27
V_367 | 2024-11-22 | 2024-11-29 | 2024-12-01 | 2024-12-07 | 2024-12-12 | 2024-12-15 | 2024-12-16 | 2024-12-20 | 2024-12-25 | 2024-12-28 | 2025-01-01 | 2025-01-01 | 2025-02-27 | 2025-03-07 | 2025-03-14 | 2025-03-14 | 2025-03-21 | 2025-03-28 | 2025-03-28 | 2025-03-31 | 2025-03-31 | 2025-04-02 | 2025-04-07 | 2025-04-07 | 2025-04-14 | 2025-04-14 | 2025-04-14 | 2025-04-19 | 2025-04-24 | 2025-05-01 | 2025-05-05 | 2025-05-10 | 2025-05-17 | 2025-05-17 | 2025-05-22 | 2025-05-24 | 2025-05-24 | 2025-05-24 | 2025-05-29 | 2025-05-30 | 2025-06-04 | 2025-06-11 | 2025-03-07 | 2025-03-09 | 2025-03-16 | 2025-03-23 | 2025-03-28 | 2025-03-29 | 2025-04-04 | 2025-04-04 | 2025-04-05 | 2025-04-09 | 2025-04-10 | 2025-04-14 | 2025-04-14 | 2025-04-17 | 2025-04-19 | 2025-04-21 | 2025-04-21 | 2025-04-25 | 2025-04-27 | 2025-04-28 | 2025-04-30 | 2025-05-05 | 2025-05-10 | 2025-05-17 | 2025-05-17 | 2025-05-17 | 2025-05-22 | 2025-05-22 | 2025-05-24 | 2025-05-29 | 2025-06-06 | 2025-04-30 | 2025-05-17 | 2025-05-19 | 2025-06-11 | 2025-06-05 | 2025-06-11 | 2025-06-15 | 2025-06-21 | 2025-06-27
V_368 | 2024-11-22 | 2024-11-29 | 2024-12-01 | 2024-12-07 | 2024-12-12 | 2024-12-15 | 2024-12-16 | 2024-12-20 | 2024-12-25 | 2024-12-28 | 2025-01-01 | 2025-01-01 | 2025-02-27 | 2025-03-07 | 2025-03-14 | 2025-03-14 | 2025-03-21 | 2025-03-28 | 2025-03-28 | 2025-03-31 | 2025-03-31 | 2025-04-02 | 2025-04-07 | 2025-04-07 | 2025-04-14 | 2025-04-14 | 2025-04-14 | 2025-04-19 | 2025-04-24 | 2025-05-01 | 2025-05-05 | 2025-05-10 | 2025-05-17 | 2025-05-17 | 2025-05-22 | 2025-05-24 | 2025-05-24 | 2025-05-24 | 2025-05-29 | 2025-05-30 | 2025-06-04 | 2025-06-11 | 2025-03-07 | 2025-03-09 | 2025-03-16 | 2025-03-23 | 2025-03-28 | 2025-03-29 | 2025-04-04 | 2025-04-04 | 2025-04-05 | 2025-04-09 | 2025-04-10 | 2025-04-14 | 2025-04-14 | 2025-04-17 | 2025-04-19 | 2025-04-21 | 2025-04-21 | 2025-04-25 | 2025-04-27 | 2025-04-28 | 2025-04-30 | 2025-05-05 | 2025-05-10 | 2025-05-17 | 2025-05-17 | 2025-05-17 | 2025-05-22 | 2025-05-22 | 2025-05-24 | 2025-05-29 | 2025-06-06 | 2025-04-30 | 2025-05-17 | 2025-05-19 | 2025-06-11 | 2025-06-05 | 2025-06-11 | 2025-06-15 | 2025-06-21 | 2025-06-27
V_369 | 2024-11-29 | 2024-12-06 | 2024-12-08 | 2024-12-14 | 2024-12-19 | 2024-12-22 | 2024-12-23 | 2024-12-27 | 2025-01-01 | 2025-01-04 | 2025-01-08 | 2025-01-08 | 2025-03-07 | 2025-03-15 | 2025-03-22 | 2025-03-22 | 2025-03-29 | 2025-04-05 | 2025-04-05 | 2025-04-09 | 2025-04-09 | 2025-04-10 | 2025-04-16 | 2025-04-16 | 2025-04-23 | 2025-04-23 | 2025-04-23 | 2025-04-27 | 2025-05-02 | 2025-05-09 | 2025-05-14 | 2025-05-18 | 2025-05-25 | 2025-05-25 | 2025-05-30 | 2025-06-01 | 2025-06-01 | 2025-06-01 | 2025-06-06 | 2025-06-07 | 2025-06-12 | 2025-06-19 | 2025-03-15 | 2025-03-17 | 2025-03-24 | 2025-03-31 | 2025-04-05 | 2025-04-06 | 2025-04-12 | 2025-04-12 | 2025-04-13 | 2025-04-17 | 2025-04-18 | 2025-04-23 | 2025-04-23 | 2025-04-25 | 2025-04-27 | 2025-04-30 | 2025-04-30 | 2025-05-03 | 2025-05-05 | 2025-05-07 | 2025-05-08 | 2025-05-14 | 2025-05-18 | 2025-05-25 | 2025-05-25 | 2025-05-25 | 2025-05-30 | 2025-05-30 | 2025-06-01 | 2025-06-06 | 2025-06-14 | 2025-05-08 | 2025-05-25 | 2025-05-28 | 2025-06-19 | 2025-06-13 | 2025-06-19 | 2025-06-23 | 2025-06-29 | 2025-07-05
V_370 | 2024-11-29 | 2024-12-06 | 2024-12-08 | 2024-12-14 | 2024-12-19 | 2024-12-22 | 2024-12-23 | 2024-12-27 | 2025-01-01 | 2025-01-04 | 2025-01-08 | 2025-01-08 | 2025-03-07 | 2025-03-15 | 2025-03-22 | 2025-03-22 | 2025-03-29 | 2025-04-05 | 2025-04-05 | 2025-04-09 | 2025-04-09 | 2025-04-10 | 2025-04-16 | 2025-04-16 | 2025-04-23 | 2025-04-23 | 2025-04-23 | 2025-04-27 | 2025-05-02 | 2025-05-09 | 2025-05-14 | 2025-05-18 | 2025-05-25 | 2025-05-25 | 2025-05-30 | 2025-06-01 | 2025-06-01 | 2025-06-01 | 2025-06-06 | 2025-06-07 | 2025-06-12 | 2025-06-19 | 2025-03-15 | 2025-03-17 | 2025-03-24 | 2025-03-31 | 2025-04-05 | 2025-04-06 | 2025-04-12 | 2025-04-12 | 2025-04-13 | 2025-04-17 | 2025-04-18 | 2025-04-23 | 2025-04-23 | 2025-04-25 | 2025-04-27 | 2025-04-30 | 2025-04-30 | 2025-05-03 | 2025-05-05 | 2025-05-07 | 2025-05-08 | 2025-05-14 | 2025-05-18 | 2025-05-25 | 2025-05-25 | 2025-05-25 | 2025-05-30 | 2025-05-30 | 2025-06-01 | 2025-06-06 | 2025-06-14 | 2025-05-08 | 2025-05-25 | 2025-05-28 | 2025-06-19 | 2025-06-13 | 2025-06-19 | 2025-06-23 | 2025-06-29 | 2025-07-05
V_371 | 2024-11-29 | 2024-12-06 | 2024-12-08 | 2024-12-14 | 2024-12-19 | 2024-12-22 | 2024-12-23 | 2024-12-27 | 2025-01-01 | 2025-01-04 | 2025-01-08 | 2025-01-08 | 2025-03-07 | 2025-03-15 | 2025-03-22 | 2025-03-22 | 2025-03-29 | 2025-04-05 | 2025-04-05 | 2025-04-09 | 2025-04-09 | 2025-04-10 | 2025-04-16 | 2025-04-16 | 2025-04-23 | 2025-04-23 | 2025-04-23 | 2025-04-27 | 2025-05-02 | 2025-05-09 | 2025-05-14 | 2025-05-18 | 2025-05-25 | 2025-05-25 | 2025-05-30 | 2025-06-01 | 2025-06-01 | 2025-06-01 | 2025-06-06 | 2025-06-07 | 2025-06-12 | 2025-06-19 | 2025-03-15 | 2025-03-17 | 2025-03-24 | 2025-03-31 | 2025-04-05 | 2025-04-06 | 2025-04-12 | 2025-04-12 | 2025-04-13 | 2025-04-17 | 2025-04-18 | 2025-04-23 | 2025-04-23 | 2025-04-25 | 2025-04-27 | 2025-04-30 | 2025-04-30 | 2025-05-03 | 2025-05-05 | 2025-05-07 | 2025-05-08 | 2025-05-14 | 2025-05-18 | 2025-05-25 | 2025-05-25 | 2025-05-25 | 2025-05-30 | 2025-05-30 | 2025-06-01 | 2025-06-06 | 2025-06-14 | 2025-05-08 | 2025-05-25 | 2025-05-28 | 2025-06-19 | 2025-06-13 | 2025-06-19 | 2025-06-23 | 2025-06-29 | 2025-07-05
V_372 | 2024-11-29 | 2024-12-06 | 2024-12-08 | 2024-12-14 | 2024-12-19 | 2024-12-22 | 2024-12-23 | 2024-12-27 | 2025-01-01 | 2025-01-04 | 2025-01-08 | 2025-01-08 | 2025-03-07 | 2025-03-15 | 2025-03-22 | 2025-03-22 | 2025-03-29 | 2025-04-05 | 2025-04-05 | 2025-04-09 | 2025-04-09 | 2025-04-10 | 2025-04-16 | 2025-04-16 | 2025-04-23 | 2025-04-23 | 2025-04-23 | 2025-04-27 | 2025-05-02 | 2025-05-09 | 2025-05-14 | 2025-05-18 | 2025-05-25 | 2025-05-25 | 2025-05-30 | 2025-06-01 | 2025-06-01 | 2025-06-01 | 2025-06-06 | 2025-06-07 | 2025-06-12 | 2025-06-19 | 2025-03-15 | 2025-03-17 | 2025-03-24 | 2025-03-31 | 2025-04-05 | 2025-04-06 | 2025-04-12 | 2025-04-12 | 2025-04-13 | 2025-04-17 | 2025-04-18 | 2025-04-23 | 2025-04-23 | 2025-04-25 | 2025-04-27 | 2025-04-30 | 2025-04-30 | 2025-05-03 | 2025-05-05 | 2025-05-07 | 2025-05-08 | 2025-05-14 | 2025-05-18 | 2025-05-25 | 2025-05-25 | 2025-05-25 | 2025-05-30 | 2025-05-30 | 2025-06-01 | 2025-06-06 | 2025-06-14 | 2025-05-08 | 2025-05-25 | 2025-05-28 | 2025-06-19 | 2025-06-13 | 2025-06-19 | 2025-06-23 | 2025-06-29 | 2025-07-05
V_373 | 2024-11-29 | 2024-12-06 | 2024-12-08 | 2024-12-14 | 2024-12-19 | 2024-12-22 | 2024-12-23 | 2024-12-27 | 2025-01-01 | 2025-01-04 | 2025-01-08 | 2025-01-08 | 2025-03-07 | 2025-03-15 | 2025-03-22 | 2025-03-22 | 2025-03-29 | 2025-04-05 | 2025-04-05 | 2025-04-09 | 2025-04-09 | 2025-04-10 | 2025-04-16 | 2025-04-16 | 2025-04-23 | 2025-04-23 | 2025-04-23 | 2025-04-27 | 2025-05-02 | 2025-05-09 | 2025-05-14 | 2025-05-18 | 2025-05-25 | 2025-05-25 | 2025-05-30 | 2025-06-01 | 2025-06-01 | 2025-06-01 | 2025-06-06 | 2025-06-07 | 2025-06-12 | 2025-06-19 | 2025-03-15 | 2025-03-17 | 2025-03-24 | 2025-03-31 | 2025-04-05 | 2025-04-06 | 2025-04-12 | 2025-04-12 | 2025-04-13 | 2025-04-17 | 2025-04-18 | 2025-04-23 | 2025-04-23 | 2025-04-25 | 2025-04-27 | 2025-04-30 | 2025-04-30 | 2025-05-03 | 2025-05-05 | 2025-05-07 | 2025-05-08 | 2025-05-14 | 2025-05-18 | 2025-05-25 | 2025-05-25 | 2025-05-25 | 2025-05-30 | 2025-05-30 | 2025-06-01 | 2025-06-06 | 2025-06-14 | 2025-05-08 | 2025-05-25 | 2025-05-28 | 2025-06-19 | 2025-06-13 | 2025-06-19 | 2025-06-23 | 2025-06-29 | 2025-07-05
V_374 | 2024-11-29 | 2024-12-06 | 2024-12-08 | 2024-12-14 | 2024-12-19 | 2024-12-22 | 2024-12-23 | 2024-12-27 | 2025-01-01 | 2025-01-04 | 2025-01-08 | 2025-01-08 | 2025-03-07 | 2025-03-15 | 2025-03-22 | 2025-03-22 | 2025-03-29 | 2025-04-05 | 2025-04-05 | 2025-04-09 | 2025-04-09 | 2025-04-10 | 2025-04-16 | 2025-04-16 | 2025-04-23 | 2025-04-23 | 2025-04-23 | 2025-04-27 | 2025-05-02 | 2025-05-09 | 2025-05-14 | 2025-05-18 | 2025-05-25 | 2025-05-25 | 2025-05-30 | 2025-06-01 | 2025-06-01 | 2025-06-01 | 2025-06-06 | 2025-06-07 | 2025-06-12 | 2025-06-19 | 2025-03-15 | 2025-03-17 | 2025-03-24 | 2025-03-31 | 2025-04-05 | 2025-04-06 | 2025-04-12 | 2025-04-12 | 2025-04-13 | 2025-04-17 | 2025-04-18 | 2025-04-23 | 2025-04-23 | 2025-04-25 | 2025-04-27 | 2025-04-30 | 2025-04-30 | 2025-05-03 | 2025-05-05 | 2025-05-07 | 2025-05-08 | 2025-05-14 | 2025-05-18 | 2025-05-25 | 2025-05-25 | 2025-05-25 | 2025-05-30 | 2025-05-30 | 2025-06-01 | 2025-06-06 | 2025-06-14 | 2025-05-08 | 2025-05-25 | 2025-05-28 | 2025-06-19 | 2025-06-13 | 2025-06-19 | 2025-06-23 | 2025-06-29 | 2025-07-05
V_375 | 2024-11-29 | 2024-12-06 | 2024-12-08 | 2024-12-14 | 2024-12-19 | 2024-12-22 | 2024-12-23 | 2024-12-27 | 2025-01-01 | 2025-01-04 | 2025-01-08 | 2025-01-08 | 2025-03-07 | 2025-03-15 | 2025-03-22 | 2025-03-22 | 2025-03-29 | 2025-04-05 | 2025-04-05 | 2025-04-09 | 2025-04-09 | 2025-04-10 | 2025-04-16 | 2025-04-16 | 2025-04-23 | 2025-04-23 | 2025-04-23 | 2025-04-27 | 2025-05-02 | 2025-05-09 | 2025-05-14 | 2025-05-18 | 2025-05-25 | 2025-05-25 | 2025-05-30 | 2025-06-01 | 2025-06-01 | 2025-06-01 | 2025-06-06 | 2025-06-07 | 2025-06-12 | 2025-06-19 | 2025-03-15 | 2025-03-17 | 2025-03-24 | 2025-03-31 | 2025-04-05 | 2025-04-06 | 2025-04-12 | 2025-04-12 | 2025-04-13 | 2025-04-17 | 2025-04-18 | 2025-04-23 | 2025-04-23 | 2025-04-25 | 2025-04-27 | 2025-04-30 | 2025-04-30 | 2025-05-03 | 2025-05-05 | 2025-05-07 | 2025-05-08 | 2025-05-14 | 2025-05-18 | 2025-05-25 | 2025-05-25 | 2025-05-25 | 2025-05-30 | 2025-05-30 | 2025-06-01 | 2025-06-06 | 2025-06-14 | 2025-05-08 | 2025-05-25 | 2025-05-28 | 2025-06-19 | 2025-06-13 | 2025-06-19 | 2025-06-23 | 2025-06-29 | 2025-07-05
V_376 | 2024-11-29 | 2024-12-06 | 2024-12-08 | 2024-12-14 | 2024-12-19 | 2024-12-22 | 2024-12-23 | 2024-12-27 | 2025-01-01 | 2025-01-04 | 2025-01-08 | 2025-01-08 | 2025-03-07 | 2025-03-15 | 2025-03-22 | 2025-03-22 | 2025-03-29 | 2025-04-05 | 2025-04-05 | 2025-04-09 | 2025-04-09 | 2025-04-10 | 2025-04-16 | 2025-04-16 | 2025-04-23 | 2025-04-23 | 2025-04-23 | 2025-04-27 | 2025-05-02 | 2025-05-09 | 2025-05-14 | 2025-05-18 | 2025-05-25 | 2025-05-25 | 2025-05-30 | 2025-06-01 | 2025-06-01 | 2025-06-01 | 2025-06-06 | 2025-06-07 | 2025-06-12 | 2025-06-19 | 2025-03-15 | 2025-03-17 | 2025-03-24 | 2025-03-31 | 2025-04-05 | 2025-04-06 | 2025-04-12 | 2025-04-12 | 2025-04-13 | 2025-04-17 | 2025-04-18 | 2025-04-23 | 2025-04-23 | 2025-04-25 | 2025-04-27 | 2025-04-30 | 2025-04-30 | 2025-05-03 | 2025-05-05 | 2025-05-07 | 2025-05-08 | 2025-05-14 | 2025-05-18 | 2025-05-25 | 2025-05-25 | 2025-05-25 | 2025-05-30 | 2025-05-30 | 2025-06-01 | 2025-06-06 | 2025-06-14 | 2025-05-08 | 2025-05-25 | 2025-05-28 | 2025-06-19 | 2025-06-13 | 2025-06-19 | 2025-06-23 | 2025-06-29 | 2025-07-05
V_377 | 2024-12-06 | 2024-12-13 | 2024-12-15 | 2024-12-21 | 2024-12-26 | 2024-12-29 | 2024-12-30 | 2025-01-03 | 2025-01-08 | 2025-01-11 | 2025-01-15 | 2025-01-15 | 2025-03-15 | 2025-03-23 | 2025-03-30 | 2025-03-30 | 2025-04-06 | 2025-04-13 | 2025-04-13 | 2025-04-17 | 2025-04-17 | 2025-04-18 | 2025-04-24 | 2025-04-24 | 2025-05-01 | 2025-05-01 | 2025-05-01 | 2025-05-05 | 2025-05-10 | 2025-05-17 | 2025-05-22 | 2025-05-26 | 2025-06-02 | 2025-06-02 | 2025-06-07 | 2025-06-09 | 2025-06-09 | 2025-06-09 | 2025-06-14 | 2025-06-15 | 2025-06-20 | 2025-06-27 | 2025-03-23 | 2025-03-26 | 2025-04-02 | 2025-04-09 | 2025-04-13 | 2025-04-14 | 2025-04-20 | 2025-04-20 | 2025-04-21 | 2025-04-25 | 2025-04-26 | 2025-05-01 | 2025-05-01 | 2025-05-03 | 2025-05-05 | 2025-05-08 | 2025-05-08 | 2025-05-11 | 2025-05-14 | 2025-05-15 | 2025-05-16 | 2025-05-22 | 2025-05-26 | 2025-06-02 | 2025-06-02 | 2025-06-02 | 2025-06-07 | 2025-06-07 | 2025-06-09 | 2025-06-14 | 2025-06-22 | 2025-05-16 | 2025-06-02 | 2025-06-05 | 2025-06-27 | 2025-06-21 | 2025-06-27 | 2025-07-02 | 2025-07-07 | 2025-07-13
V_378 | 2024-12-06 | 2024-12-13 | 2024-12-15 | 2024-12-21 | 2024-12-26 | 2024-12-29 | 2024-12-30 | 2025-01-03 | 2025-01-08 | 2025-01-11 | 2025-01-15 | 2025-01-15 | 2025-03-15 | 2025-03-23 | 2025-03-30 | 2025-03-30 | 2025-04-06 | 2025-04-13 | 2025-04-13 | 2025-04-17 | 2025-04-17 | 2025-04-18 | 2025-04-24 | 2025-04-24 | 2025-05-01 | 2025-05-01 | 2025-05-01 | 2025-05-05 | 2025-05-10 | 2025-05-17 | 2025-05-22 | 2025-05-26 | 2025-06-02 | 2025-06-02 | 2025-06-07 | 2025-06-09 | 2025-06-09 | 2025-06-09 | 2025-06-14 | 2025-06-15 | 2025-06-20 | 2025-06-27 | 2025-03-23 | 2025-03-26 | 2025-04-02 | 2025-04-09 | 2025-04-13 | 2025-04-14 | 2025-04-20 | 2025-04-20 | 2025-04-21 | 2025-04-25 | 2025-04-26 | 2025-05-01 | 2025-05-01 | 2025-05-03 | 2025-05-05 | 2025-05-08 | 2025-05-08 | 2025-05-11 | 2025-05-14 | 2025-05-15 | 2025-05-16 | 2025-05-22 | 2025-05-26 | 2025-06-02 | 2025-06-02 | 2025-06-02 | 2025-06-07 | 2025-06-07 | 2025-06-09 | 2025-06-14 | 2025-06-22 | 2025-05-16 | 2025-06-02 | 2025-06-05 | 2025-06-27 | 2025-06-21 | 2025-06-27 | 2025-07-02 | 2025-07-07 | 2025-07-13
V_379 | 2024-12-06 | 2024-12-13 | 2024-12-15 | 2024-12-21 | 2024-12-26 | 2024-12-29 | 2024-12-30 | 2025-01-03 | 2025-01-08 | 2025-01-11 | 2025-01-15 | 2025-01-15 | 2025-03-15 | 2025-03-23 | 2025-03-30 | 2025-03-30 | 2025-04-06 | 2025-04-13 | 2025-04-13 | 2025-04-17 | 2025-04-17 | 2025-04-18 | 2025-04-24 | 2025-04-24 | 2025-05-01 | 2025-05-01 | 2025-05-01 | 2025-05-05 | 2025-05-10 | 2025-05-17 | 2025-05-22 | 2025-05-26 | 2025-06-02 | 2025-06-02 | 2025-06-07 | 2025-06-09 | 2025-06-09 | 2025-06-09 | 2025-06-14 | 2025-06-15 | 2025-06-20 | 2025-06-27 | 2025-03-23 | 2025-03-26 | 2025-04-02 | 2025-04-09 | 2025-04-13 | 2025-04-14 | 2025-04-20 | 2025-04-20 | 2025-04-21 | 2025-04-25 | 2025-04-26 | 2025-05-01 | 2025-05-01 | 2025-05-03 | 2025-05-05 | 2025-05-08 | 2025-05-08 | 2025-05-11 | 2025-05-14 | 2025-05-15 | 2025-05-16 | 2025-05-22 | 2025-05-26 | 2025-06-02 | 2025-06-02 | 2025-06-02 | 2025-06-07 | 2025-06-07 | 2025-06-09 | 2025-06-14 | 2025-06-22 | 2025-05-16 | 2025-06-02 | 2025-06-05 | 2025-06-27 | 2025-06-21 | 2025-06-27 | 2025-07-02 | 2025-07-07 | 2025-07-13
V_380 | 2024-12-06 | 2024-12-13 | [9 empty] | 2025-01-15 | 2025-03-15 | 2025-03-23 | 2025-03-30 | 2025-03-30 | 2025-04-06 | 2025-04-13 | 2025-04-13 | 2025-04-17 | 2025-04-17 | 2025-04-18 | 2025-04-24 | 2025-04-24 | 2025-05-01 | 2025-05-01 | 2025-05-01 | 2025-05-05 | 2025-05-10 | 2025-05-17 | 2025-05-22 | 2025-05-26 | 2025-06-02 | 2025-06-02 | 2025-06-07 | 2025-06-09 | 2025-06-09 | 2025-06-09 | 2025-06-14 | 2025-06-15 | 2025-06-20 | 2025-06-27 | 2025-03-23 | 2025-03-26 | 2025-04-02 | 2025-04-09 | 2025-04-13 | 2025-04-14 | 2025-04-20 | 2025-04-20 | 2025-04-21 | 2025-04-25 | 2025-04-26 | 2025-05-01 | 2025-05-01 | 2025-05-03 | 2025-05-05 | 2025-05-08 | 2025-05-08 | 2025-05-11 | 2025-05-14 | 2025-05-15 | 2025-05-16 | 2025-05-22 | 2025-05-26 | 2025-06-02 | 2025-06-02 | 2025-06-02 | 2025-06-07 | 2025-06-07 | 2025-06-09 | 2025-06-14 | 2025-06-22 | 2025-05-16 | 2025-06-02 | 2025-06-05 | 2025-06-27 | 2025-06-21 | 2025-06-27 | 2025-07-02 | 2025-07-07 | 2025-07-13
V_381 | 2024-12-06 | 2024-12-13 | [9 empty] | 2025-01-15 | 2025-03-15 | 2025-03-23 | 2025-03-30 | 2025-03-30 | 2025-04-06 | 2025-04-13 | 2025-04-13 | 2025-04-17 | 2025-04-17 | 2025-04-18 | 2025-04-24 | 2025-04-24 | 2025-05-01 | 2025-05-01 | 2025-05-01 | 2025-05-05 | 2025-05-10 | 2025-05-17 | 2025-05-22 | 2025-05-26 | 2025-06-02 | 2025-06-02 | 2025-06-07 | 2025-06-09 | 2025-06-09 | 2025-06-09 | 2025-06-14 | 2025-06-15 | 2025-06-20 | 2025-06-27 | 2025-03-23 | 2025-03-26 | 2025-04-02 | 2025-04-09 | 2025-04-13 | 2025-04-14 | 2025-04-20 | 2025-04-20 | 2025-04-21 | 2025-04-25 | 2025-04-26 | 2025-05-01 | 2025-05-01 | 2025-05-03 | 2025-05-05 | 2025-05-08 | 2025-05-08 | 2025-05-11 | 2025-05-14 | 2025-05-15 | 2025-05-16 | 2025-05-22 | 2025-05-26 | 2025-06-02 | 2025-06-02 | 2025-06-02 | 2025-06-07 | 2025-06-07 | 2025-06-09 | 2025-06-14 | 2025-06-22 | 2025-05-16 | 2025-06-02 | 2025-06-05 | 2025-06-27 | 2025-06-21 | 2025-06-27 | 2025-07-02 | 2025-07-07 | 2025-07-13
V_382 | 2024-12-06 | 2024-12-13 | [9 empty] | 2025-01-15 | 2025-03-15 | 2025-03-23 | 2025-03-30 | 2025-03-30 | 2025-04-06 | 2025-04-13 | 2025-04-13 | 2025-04-17 | 2025-04-17 | 2025-04-18 | 2025-04-24 | 2025-04-24 | 2025-05-01 | 2025-05-01 | 2025-05-01 | 2025-05-05 | 2025-05-10 | 2025-05-17 | 2025-05-22 | 2025-05-26 | 2025-06-02 | 2025-06-02 | 2025-06-07 | 2025-06-09 | 2025-06-09 | 2025-06-09 | 2025-06-14 | 2025-06-15 | 2025-06-20 | 2025-06-27 | 2025-03-23 | 2025-03-26 | 2025-04-02 | 2025-04-09 | 2025-04-13 | 2025-04-14 | 2025-04-20 | 2025-04-20 | 2025-04-21 | 2025-04-25 | 2025-04-26 | 2025-05-01 | 2025-05-01 | 2025-05-03 | 2025-05-05 | 2025-05-08 | 2025-05-08 | 2025-05-11 | 2025-05-14 | 2025-05-15 | 2025-05-16 | 2025-05-22 | 2025-05-26 | 2025-06-02 | 2025-06-02 | 2025-06-02 | 2025-06-07 | 2025-06-07 | 2025-06-09 | 2025-06-14 | 2025-06-22 | 2025-05-16 | 2025-06-02 | 2025-06-05 | 2025-06-27 | 2025-06-21 | 2025-06-27 | 2025-07-02 | 2025-07-07 | 2025-07-13
V_383 | 2024-12-06 | 2024-12-13 | [9 empty] | 2025-01-15 | 2025-03-15 | 2025-03-23 | 2025-03-30 | 2025-03-30 | 2025-04-06 | 2025-04-13 | 2025-04-13 | 2025-04-17 | 2025-04-17 | 2025-04-18 | 2025-04-24 | 2025-04-24 | 2025-05-01 | 2025-05-01 | 2025-05-01 | 2025-05-05 | 2025-05-10 | 2025-05-17 | 2025-05-22 | 2025-05-26 | 2025-06-02 | 2025-06-02 | 2025-06-07 | 2025-06-09 | 2025-06-09 | 2025-06-09 | 2025-06-14 | 2025-06-15 | 2025-06-20 | 2025-06-27 | 2025-03-23 | 2025-03-26 | 2025-04-02 | 2025-04-09 | 2025-04-13 | 2025-04-14 | 2025-04-20 | 2025-04-20 | 2025-04-21 | 2025-04-25 | 2025-04-26 | 2025-05-01 | 2025-05-01 | 2025-05-03 | 2025-05-05 | 2025-05-08 | 2025-05-08 | 2025-05-11 | 2025-05-14 | 2025-05-15 | 2025-05-16 | 2025-05-22 | 2025-05-26 | 2025-06-02 | 2025-06-02 | 2025-06-02 | 2025-06-07 | 2025-06-07 | 2025-06-09 | 2025-06-14 | 2025-06-22 | 2025-05-16 | 2025-06-02 | 2025-06-05 | 2025-06-27 | 2025-06-21 | 2025-06-27 | 2025-07-02 | 2025-07-07 | 2025-07-13
V_384 | 2024-12-06 | 2024-12-13 | [9 empty] | 2025-01-15 | 2025-03-15 | 2025-03-23 | 2025-03-30 | 2025-03-30 | 2025-04-06 | 2025-04-13 | 2025-04-13 | 2025-04-17 | 2025-04-17 | 2025-04-18 | 2025-04-24 | 2025-04-24 | 2025-05-01 | 2025-05-01 | 2025-05-01 | 2025-05-05 | 2025-05-10 | 2025-05-17 | 2025-05-22 | 2025-05-26 | 2025-06-02 | 2025-06-02 | 2025-06-07 | 2025-06-09 | 2025-06-09 | 2025-06-09 | 2025-06-14 | 2025-06-15 | 2025-06-20 | 2025-06-27 | 2025-03-23 | 2025-03-26 | 2025-04-02 | 2025-04-09 | 2025-04-13 | 2025-04-14 | 2025-04-20 | 2025-04-20 | 2025-04-21 | 2025-04-25 | 2025-04-26 | 2025-05-01 | 2025-05-01 | 2025-05-03 | 2025-05-05 | 2025-05-08 | 2025-05-08 | 2025-05-11 | 2025-05-14 | 2025-05-15 | 2025-05-16 | 2025-05-22 | 2025-05-26 | 2025-06-02 | 2025-06-02 | 2025-06-02 | 2025-06-07 | 2025-06-07 | 2025-06-09 | 2025-06-14 | 2025-06-22 | 2025-05-16 | 2025-06-02 | 2025-06-05 | 2025-06-27 | 2025-06-21 | 2025-06-27 | 2025-07-02 | 2025-07-07 | 2025-07-13
V_385 | 2024-12-13 | 2024-12-20 | [9 empty] | 2025-01-22 | 2025-03-23 | 2025-03-31 | 2025-04-07 | 2025-04-07 | 2025-04-14 | 2025-04-21 | 2025-04-21 | 2025-04-25 | 2025-04-25 | 2025-04-26 | 2025-05-02 | 2025-05-02 | 2025-05-09 | 2025-05-09 | 2025-05-09 | 2025-05-14 | 2025-05-18 | 2025-05-25 | 2025-05-30 | 2025-06-04 | 2025-06-11 | 2025-06-11 | 2025-06-15 | 2025-06-18 | 2025-06-18 | 2025-06-18 | 2025-06-22 | 2025-06-23 | 2025-06-28 | 2025-07-05 | 2025-03-31 | 2025-04-03 | 2025-04-10 | 2025-04-17 | 2025-04-21 | 2025-04-23 | 2025-04-28 | 2025-04-28 | 2025-04-30 | 2025-05-03 | 2025-05-04 | 2025-05-09 | 2025-05-09 | 2025-05-11 | 2025-05-14 | 2025-05-16 | 2025-05-16 | 2025-05-19 | 2025-05-22 | 2025-05-23 | 2025-05-24 | 2025-05-30 | 2025-06-04 | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-15 | 2025-06-15 | 2025-06-18 | 2025-06-22 | 2025-06-30 | 2025-05-24 | 2025-06-11 | 2025-06-13 | 2025-07-05 | 2025-06-29 | 2025-07-05 | 2025-07-10 | 2025-07-16 | 2025-07-21
V_386 | 2024-12-13 | 2024-12-20 | [9 empty] | 2025-01-22 | 2025-03-23 | 2025-03-31 | 2025-04-07 | 2025-04-07 | 2025-04-14 | 2025-04-21 | 2025-04-21 | 2025-04-25 | 2025-04-25 | 2025-04-26 | 2025-05-02 | 2025-05-02 | 2025-05-09 | 2025-05-09 | 2025-05-09 | 2025-05-14 | 2025-05-18 | 2025-05-25 | 2025-05-30 | 2025-06-04 | 2025-06-11 | 2025-06-11 | 2025-06-15 | 2025-06-18 | 2025-06-18 | 2025-06-18 | 2025-06-22 | 2025-06-23 | 2025-06-28 | 2025-07-05 | 2025-03-31 | 2025-04-03 | 2025-04-10 | 2025-04-17 | 2025-04-21 | 2025-04-23 | 2025-04-28 | 2025-04-28 | 2025-04-30 | 2025-05-03 | 2025-05-04 | 2025-05-09 | 2025-05-09 | 2025-05-11 | 2025-05-14 | 2025-05-16 | 2025-05-16 | 2025-05-19 | 2025-05-22 | 2025-05-23 | 2025-05-24 | 2025-05-30 | 2025-06-04 | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-15 | 2025-06-15 | 2025-06-18 | 2025-06-22 | 2025-06-30 | 2025-05-24 | 2025-06-11 | 2025-06-13 | 2025-07-05 | 2025-06-29 | 2025-07-05 | 2025-07-10 | 2025-07-16 | 2025-07-21
V_387 | 2024-12-13 | 2024-12-20 | [9 empty] | 2025-01-22 | 2025-03-23 | 2025-03-31 | 2025-04-07 | 2025-04-07 | 2025-04-14 | 2025-04-21 | 2025-04-21 | 2025-04-25 | 2025-04-25 | 2025-04-26 | 2025-05-02 | 2025-05-02 | 2025-05-09 | 2025-05-09 | 2025-05-09 | 2025-05-14 | 2025-05-18 | 2025-05-25 | 2025-05-30 | 2025-06-04 | 2025-06-11 | 2025-06-11 | 2025-06-15 | 2025-06-18 | 2025-06-18 | 2025-06-18 | 2025-06-22 | 2025-06-23 | 2025-06-28 | 2025-07-05 | 2025-03-31 | 2025-04-03 | 2025-04-10 | 2025-04-17 | 2025-04-21 | 2025-04-23 | 2025-04-28 | 2025-04-28 | 2025-04-30 | 2025-05-03 | 2025-05-04 | 2025-05-09 | 2025-05-09 | 2025-05-11 | 2025-05-14 | 2025-05-16 | 2025-05-16 | 2025-05-19 | 2025-05-22 | 2025-05-23 | 2025-05-24 | 2025-05-30 | 2025-06-04 | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-15 | 2025-06-15 | 2025-06-18 | 2025-06-22 | 2025-06-30 | 2025-05-24 | 2025-06-11 | 2025-06-13 | 2025-07-05 | 2025-06-29 | 2025-07-05 | 2025-07-10 | 2025-07-16 | 2025-07-21
V_388 | 2024-12-13 | 2024-12-20 | [9 empty] | 2025-01-22 | 2025-03-23 | 2025-03-31 | 2025-04-07 | 2025-04-07 | 2025-04-14 | 2025-04-21 | 2025-04-21 | 2025-04-25 | 2025-04-25 | 2025-04-26 | 2025-05-02 | 2025-05-02 | 2025-05-09 | 2025-05-09 | 2025-05-09 | 2025-05-14 | 2025-05-18 | 2025-05-25 | 2025-05-30 | 2025-06-04 | 2025-06-11 | 2025-06-11 | 2025-06-15 | 2025-06-18 | 2025-06-18 | 2025-06-18 | 2025-06-22 | 2025-06-23 | 2025-06-28 | 2025-07-05 | 2025-03-31 | 2025-04-03 | 2025-04-10 | 2025-04-17 | 2025-04-21 | 2025-04-23 | 2025-04-28 | 2025-04-28 | 2025-04-30 | 2025-05-03 | 2025-05-04 | 2025-05-09 | 2025-05-09 | 2025-05-11 | 2025-05-14 | 2025-05-16 | 2025-05-16 | 2025-05-19 | 2025-05-22 | 2025-05-23 | 2025-05-24 | 2025-05-30 | 2025-06-04 | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-15 | 2025-06-15 | 2025-06-18 | 2025-06-22 | 2025-06-30 | 2025-05-24 | 2025-06-11 | 2025-06-13 | 2025-07-05 | 2025-06-29 | 2025-07-05 | 2025-07-10 | 2025-07-16 | 2025-07-21
V_389 | 2024-12-13 | 2024-12-20 | [9 empty] | 2025-01-22 | 2025-03-23 | 2025-03-31 | 2025-04-07 | 2025-04-07 | 2025-04-14 | 2025-04-21 | 2025-04-21 | 2025-04-25 | 2025-04-25 | 2025-04-26 | 2025-05-02 | 2025-05-02 | 2025-05-09 | 2025-05-09 | 2025-05-09 | 2025-05-14 | 2025-05-18 | 2025-05-25 | 2025-05-30 | 2025-06-04 | 2025-06-11 | 2025-06-11 | 2025-06-15 | 2025-06-18 | 2025-06-18 | 2025-06-18 | 2025-06-22 | 2025-06-23 | 2025-06-28 | 2025-07-05 | 2025-03-31 | 2025-04-03 | 2025-04-10 | 2025-04-17 | 2025-04-21 | 2025-04-23 | 2025-04-28 | 2025-04-28 | 2025-04-30 | 2025-05-03 | 2025-05-04 | 2025-05-09 | 2025-05-09 | 2025-05-11 | 2025-05-14 | 2025-05-16 | 2025-05-16 | 2025-05-19 | 2025-05-22 | 2025-05-23 | 2025-05-24 | 2025-05-30 | 2025-06-04 | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-15 | 2025-06-15 | 2025-06-18 | 2025-06-22 | 2025-06-30 | 2025-05-24 | 2025-06-11 | 2025-06-13 | 2025-07-05 | 2025-06-29 | 2025-07-05 | 2025-07-10 | 2025-07-16 | 2025-07-21
V_390 | 2024-12-13 | 2024-12-20 | 2024-12-22 | 2024-12-28 | 2025-01-02 | 2025-01-05 | 2025-01-06 | 2025-01-10 | 2025-01-15 | 2025-01-18 | 2025-01-22 | 2025-01-22 | 2025-03-23 | 2025-03-31 | 2025-04-07 | 2025-04-07 | 2025-04-14 | 2025-04-21 | 2025-04-21 | 2025-04-25 | 2025-04-25 | 2025-04-26 | 2025-05-02 | 2025-05-02 | 2025-05-09 | 2025-05-09 | 2025-05-09 | 2025-05-14 | 2025-05-18 | 2025-05-25 | 2025-05-30 | 2025-06-04 | 2025-06-11 | 2025-06-11 | 2025-06-15 | 2025-06-18 | 2025-06-18 | 2025-06-18 | 2025-06-22 | 2025-06-23 | 2025-06-28 | 2025-07-05 | 2025-03-31 | 2025-04-03 | 2025-04-10 | 2025-04-17 | 2025-04-21 | 2025-04-23 | 2025-04-28 | 2025-04-28 | 2025-04-30 | 2025-05-03 | 2025-05-04 | 2025-05-09 | 2025-05-09 | 2025-05-11 | 2025-05-14 | 2025-05-16 | 2025-05-16 | 2025-05-19 | 2025-05-22 | 2025-05-23 | 2025-05-24 | 2025-05-30 | 2025-06-04 | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-15 | 2025-06-15 | 2025-06-18 | 2025-06-22 | 2025-06-30 | 2025-05-24 | 2025-06-11 | 2025-06-13 | 2025-07-05 | 2025-06-29 | 2025-07-05 | 2025-07-10 | 2025-07-16 | 2025-07-21
V_391 | 2024-12-13 | 2024-12-20 | 2024-12-22 | 2024-12-28 | 2025-01-02 | 2025-01-05 | 2025-01-06 | 2025-01-10 | 2025-01-15 | 2025-01-18 | 2025-01-22 | 2025-01-22 | 2025-03-23 | 2025-03-31 | 2025-04-07 | 2025-04-07 | 2025-04-14 | 2025-04-21 | 2025-04-21 | 2025-04-25 | 2025-04-25 | 2025-04-26 | 2025-05-02 | 2025-05-02 | 2025-05-09 | 2025-05-09 | 2025-05-09 | 2025-05-14 | 2025-05-18 | 2025-05-25 | 2025-05-30 | 2025-06-04 | 2025-06-11 | 2025-06-11 | 2025-06-15 | 2025-06-18 | 2025-06-18 | 2025-06-18 | 2025-06-22 | 2025-06-23 | 2025-06-28 | 2025-07-05 | 2025-03-31 | 2025-04-03 | 2025-04-10 | 2025-04-17 | 2025-04-21 | 2025-04-23 | 2025-04-28 | 2025-04-28 | 2025-04-30 | 2025-05-03 | 2025-05-04 | 2025-05-09 | 2025-05-09 | 2025-05-11 | 2025-05-14 | 2025-05-16 | 2025-05-16 | 2025-05-19 | 2025-05-22 | 2025-05-23 | 2025-05-24 | 2025-05-30 | 2025-06-04 | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-15 | 2025-06-15 | 2025-06-18 | 2025-06-22 | 2025-06-30 | 2025-05-24 | 2025-06-11 | 2025-06-13 | 2025-07-05 | 2025-06-29 | 2025-07-05 | 2025-07-10 | 2025-07-16 | 2025-07-21
V_392 | 2024-12-13 | 2024-12-20 | 2024-12-22 | 2024-12-28 | 2025-01-02 | 2025-01-05 | 2025-01-06 | 2025-01-10 | 2025-01-15 | 2025-01-18 | 2025-01-22 | 2025-01-22 | 2025-03-23 | 2025-03-31 | 2025-04-07 | 2025-04-07 | 2025-04-14 | 2025-04-21 | 2025-04-21 | 2025-04-25 | 2025-04-25 | 2025-04-26 | 2025-05-02 | 2025-05-02 | 2025-05-09 | 2025-05-09 | 2025-05-09 | 2025-05-14 | 2025-05-18 | 2025-05-25 | 2025-05-30 | 2025-06-04 | 2025-06-11 | 2025-06-11 | 2025-06-15 | 2025-06-18 | 2025-06-18 | 2025-06-18 | 2025-06-22 | 2025-06-23 | 2025-06-28 | 2025-07-05 | 2025-03-31 | 2025-04-03 | 2025-04-10 | 2025-04-17 | 2025-04-21 | 2025-04-23 | 2025-04-28 | 2025-04-28 | 2025-04-30 | 2025-05-03 | 2025-05-04 | 2025-05-09 | 2025-05-09 | 2025-05-11 | 2025-05-14 | 2025-05-16 | 2025-05-16 | 2025-05-19 | 2025-05-22 | 2025-05-23 | 2025-05-24 | 2025-05-30 | 2025-06-04 | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-15 | 2025-06-15 | 2025-06-18 | 2025-06-22 | 2025-06-30 | 2025-05-24 | 2025-06-11 | 2025-06-13 | 2025-07-05 | 2025-06-29 | 2025-07-05 | 2025-07-10 | 2025-07-16 | 2025-07-21
V_393 | 2024-12-20 | 2024-12-27 | 2024-12-29 | 2025-01-04 | 2025-01-09 | 2025-01-12 | 2025-01-13 | 2025-01-17 | 2025-01-22 | 2025-01-25 | 2025-01-29 | 2025-01-29 | 2025-03-31 | 2025-04-09 | 2025-04-16 | 2025-04-16 | 2025-04-23 | 2025-04-30 | 2025-04-30 | 2025-05-03 | 2025-05-03 | 2025-05-04 | 2025-05-10 | 2025-05-10 | 2025-05-17 | 2025-05-17 | 2025-05-17 | 2025-05-22 | 2025-05-26 | 2025-06-02 | 2025-06-07 | 2025-06-12 | 2025-06-19 | 2025-06-19 | 2025-06-23 | 2025-06-26 | 2025-06-26 | 2025-06-26 | 2025-06-30 | 2025-07-02 | 2025-07-06 | 2025-07-13 | 2025-04-09 | 2025-04-11 | 2025-04-18 | 2025-04-25 | 2025-04-30 | 2025-05-01 | 2025-05-07 | 2025-05-07 | 2025-05-08 | 2025-05-11 | 2025-05-12 | 2025-05-17 | 2025-05-17 | 2025-05-19 | 2025-05-22 | 2025-05-24 | 2025-05-24 | 2025-05-28 | 2025-05-30 | 2025-05-31 | 2025-06-01 | 2025-06-07 | 2025-06-12 | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-23 | 2025-06-23 | 2025-06-26 | 2025-06-30 | 2025-07-09 | 2025-06-01 | 2025-06-19 | 2025-06-21 | 2025-07-13 | 2025-07-07 | 2025-07-13 | 2025-07-18 | 2025-07-24 | 2025-07-30
V_394 | 2024-12-20 | 2024-12-27 | 2024-12-29 | 2025-01-04 | 2025-01-09 | 2025-01-12 | 2025-01-13 | 2025-01-17 | 2025-01-22 | 2025-01-25 | 2025-01-29 | 2025-01-29 | 2025-03-31 | 2025-04-09 | 2025-04-16 | 2025-04-16 | 2025-04-23 | 2025-04-30 | 2025-04-30 | 2025-05-03 | 2025-05-03 | 2025-05-04 | 2025-05-10 | 2025-05-10 | 2025-05-17 | 2025-05-17 | 2025-05-17 | 2025-05-22 | 2025-05-26 | 2025-06-02 | 2025-06-07 | 2025-06-12 | 2025-06-19 | 2025-06-19 | 2025-06-23 | 2025-06-26 | 2025-06-26 | 2025-06-26 | 2025-06-30 | 2025-07-02 | 2025-07-06 | 2025-07-13 | 2025-04-09 | 2025-04-11 | 2025-04-18 | 2025-04-25 | 2025-04-30 | 2025-05-01 | 2025-05-07 | 2025-05-07 | 2025-05-08 | 2025-05-11 | 2025-05-12 | 2025-05-17 | 2025-05-17 | 2025-05-19 | 2025-05-22 | 2025-05-24 | 2025-05-24 | 2025-05-28 | 2025-05-30 | 2025-05-31 | 2025-06-01 | 2025-06-07 | 2025-06-12 | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-23 | 2025-06-23 | 2025-06-26 | 2025-06-30 | 2025-07-09 | 2025-06-01 | 2025-06-19 | 2025-06-21 | 2025-07-13 | 2025-07-07 | 2025-07-13 | 2025-07-18 | 2025-07-24 | 2025-07-30
V_395 | 2024-12-20 | 2024-12-27 | 2024-12-29 | 2025-01-04 | 2025-01-09 | 2025-01-12 | 2025-01-13 | 2025-01-17 | 2025-01-22 | 2025-01-25 | 2025-01-29 | 2025-01-29 | 2025-03-31 | 2025-04-09 | 2025-04-16 | 2025-04-16 | 2025-04-23 | 2025-04-30 | 2025-04-30 | 2025-05-03 | 2025-05-03 | 2025-05-04 | 2025-05-10 | 2025-05-10 | 2025-05-17 | 2025-05-17 | 2025-05-17 | 2025-05-22 | 2025-05-26 | 2025-06-02 | 2025-06-07 | 2025-06-12 | 2025-06-19 | 2025-06-19 | 2025-06-23 | 2025-06-26 | 2025-06-26 | 2025-06-26 | 2025-06-30 | 2025-07-02 | 2025-07-06 | 2025-07-13 | 2025-04-09 | 2025-04-11 | 2025-04-18 | 2025-04-25 | 2025-04-30 | 2025-05-01 | 2025-05-07 | 2025-05-07 | 2025-05-08 | 2025-05-11 | 2025-05-12 | 2025-05-17 | 2025-05-17 | 2025-05-19 | 2025-05-22 | 2025-05-24 | 2025-05-24 | 2025-05-28 | 2025-05-30 | 2025-05-31 | 2025-06-01 | 2025-06-07 | 2025-06-12 | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-23 | 2025-06-23 | 2025-06-26 | 2025-06-30 | 2025-07-09 | 2025-06-01 | 2025-06-19 | 2025-06-21 | 2025-07-13 | 2025-07-07 | 2025-07-13 | 2025-07-18 | 2025-07-24 | 2025-07-30
V_396 | 2024-12-20 | 2024-12-27 | 2024-12-29 | 2025-01-04 | 2025-01-09 | 2025-01-12 | 2025-01-13 | 2025-01-17 | 2025-01-22 | 2025-01-25 | 2025-01-29 | 2025-01-29 | 2025-03-31 | 2025-04-09 | 2025-04-16 | 2025-04-16 | 2025-04-23 | 2025-04-30 | 2025-04-30 | 2025-05-03 | 2025-05-03 | 2025-05-04 | 2025-05-10 | 2025-05-10 | 2025-05-17 | 2025-05-17 | 2025-05-17 | 2025-05-22 | 2025-05-26 | 2025-06-02 | 2025-06-07 | 2025-06-12 | 2025-06-19 | 2025-06-19 | 2025-06-23 | 2025-06-26 | 2025-06-26 | 2025-06-26 | 2025-06-30 | 2025-07-02 | 2025-07-06 | 2025-07-13 | 2025-04-09 | 2025-04-11 | 2025-04-18 | 2025-04-25 | 2025-04-30 | 2025-05-01 | 2025-05-07 | 2025-05-07 | 2025-05-08 | 2025-05-11 | 2025-05-12 | 2025-05-17 | 2025-05-17 | 2025-05-19 | 2025-05-22 | 2025-05-24 | 2025-05-24 | 2025-05-28 | 2025-05-30 | 2025-05-31 | 2025-06-01 | 2025-06-07 | 2025-06-12 | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-23 | 2025-06-23 | 2025-06-26 | 2025-06-30 | 2025-07-09 | 2025-06-01 | 2025-06-19 | 2025-06-21 | 2025-07-13 | 2025-07-07 | 2025-07-13 | 2025-07-18 | 2025-07-24 | 2025-07-30
V_397 | 2024-12-20 | 2024-12-27 | 2024-12-29 | 2025-01-04 | 2025-01-09 | 2025-01-12 | 2025-01-13 | 2025-01-17 | 2025-01-22 | 2025-01-25 | 2025-01-29 | 2025-01-29 | 2025-03-31 | 2025-04-09 | 2025-04-16 | 2025-04-16 | 2025-04-23 | 2025-04-30 | 2025-04-30 | 2025-05-03 | 2025-05-03 | 2025-05-04 | 2025-05-10 | 2025-05-10 | 2025-05-17 | 2025-05-17 | 2025-05-17 | 2025-05-22 | 2025-05-26 | 2025-06-02 | 2025-06-07 | 2025-06-12 | 2025-06-19 | 2025-06-19 | 2025-06-23 | 2025-06-26 | 2025-06-26 | 2025-06-26 | 2025-06-30 | 2025-07-02 | 2025-07-06 | 2025-07-13 | 2025-04-09 | 2025-04-11 | 2025-04-18 | 2025-04-25 | 2025-04-30 | 2025-05-01 | 2025-05-07 | 2025-05-07 | 2025-05-08 | 2025-05-11 | 2025-05-12 | 2025-05-17 | 2025-05-17 | 2025-05-19 | 2025-05-22 | 2025-05-24 | 2025-05-24 | 2025-05-28 | 2025-05-30 | 2025-05-31 | 2025-06-01 | 2025-06-07 | 2025-06-12 | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-23 | 2025-06-23 | 2025-06-26 | 2025-06-30 | 2025-07-09 | 2025-06-01 | 2025-06-19 | 2025-06-21 | 2025-07-13 | 2025-07-07 | 2025-07-13 | 2025-07-18 | 2025-07-24 | 2025-07-30
V_398 | 2024-12-20 | 2024-12-27 | 2024-12-29 | 2025-01-04 | 2025-01-09 | 2025-01-12 | 2025-01-13 | 2025-01-17 | 2025-01-22 | 2025-01-25 | 2025-01-29 | 2025-01-29 | 2025-03-31 | 2025-04-09 | 2025-04-16 | 2025-04-16 | 2025-04-23 | 2025-04-30 | 2025-04-30 | 2025-05-03 | 2025-05-03 | 2025-05-04 | 2025-05-10 | 2025-05-10 | 2025-05-17 | 2025-05-17 | 2025-05-17 | 2025-05-22 | 2025-05-26 | 2025-06-02 | 2025-06-07 | 2025-06-12 | 2025-06-19 | 2025-06-19 | 2025-06-23 | 2025-06-26 | 2025-06-26 | 2025-06-26 | 2025-06-30 | 2025-07-02 | 2025-07-06 | 2025-07-13 | 2025-04-09 | 2025-04-11 | 2025-04-18 | 2025-04-25 | 2025-04-30 | 2025-05-01 | 2025-05-07 | 2025-05-07 | 2025-05-08 | 2025-05-11 | 2025-05-12 | 2025-05-17 | 2025-05-17 | 2025-05-19 | 2025-05-22 | 2025-05-24 | 2025-05-24 | 2025-05-28 | 2025-05-30 | 2025-05-31 | 2025-06-01 | 2025-06-07 | 2025-06-12 | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-23 | 2025-06-23 | 2025-06-26 | 2025-06-30 | 2025-07-09 | 2025-06-01 | 2025-06-19 | 2025-06-21 | 2025-07-13 | 2025-07-07 | 2025-07-13 | 2025-07-18 | 2025-07-24 | 2025-07-30
V_399 | 2024-12-20 | 2024-12-27 | 2024-12-29 | 2025-01-04 | 2025-01-09 | 2025-01-12 | 2025-01-13 | 2025-01-17 | 2025-01-22 | 2025-01-25 | 2025-01-29 | 2025-01-29 | 2025-03-31 | 2025-04-09 | 2025-04-16 | 2025-04-16 | 2025-04-23 | 2025-04-30 | 2025-04-30 | 2025-05-03 | 2025-05-03 | 2025-05-04 | 2025-05-10 | 2025-05-10 | 2025-05-17 | 2025-05-17 | 2025-05-17 | 2025-05-22 | 2025-05-26 | 2025-06-02 | 2025-06-07 | 2025-06-12 | 2025-06-19 | 2025-06-19 | 2025-06-23 | 2025-06-26 | 2025-06-26 | 2025-06-26 | 2025-06-30 | 2025-07-02 | 2025-07-06 | 2025-07-13 | 2025-04-09 | 2025-04-11 | 2025-04-18 | 2025-04-25 | 2025-04-30 | 2025-05-01 | 2025-05-07 | 2025-05-07 | 2025-05-08 | 2025-05-11 | 2025-05-12 | 2025-05-17 | 2025-05-17 | 2025-05-19 | 2025-05-22 | 2025-05-24 | 2025-05-24 | 2025-05-28 | 2025-05-30 | 2025-05-31 | 2025-06-01 | 2025-06-07 | 2025-06-12 | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-23 | 2025-06-23 | 2025-06-26 | 2025-06-30 | 2025-07-09 | 2025-06-01 | 2025-06-19 | 2025-06-21 | 2025-07-13 | 2025-07-07 | 2025-07-13 | 2025-07-18 | 2025-07-24 | 2025-07-30
V_400 | 2024-12-20 | 2024-12-27 | 2024-12-29 | 2025-01-04 | 2025-01-09 | 2025-01-12 | 2025-01-13 | 2025-01-17 | 2025-01-22 | 2025-01-25 | 2025-01-29 | 2025-01-29 | 2025-03-31 | 2025-04-09 | 2025-04-16 | 2025-04-16 | 2025-04-23 | 2025-04-30 | 2025-04-30 | 2025-05-03 | 2025-05-03 | 2025-05-04 | 2025-05-10 | 2025-05-10 | 2025-05-17 | 2025-05-17 | 2025-05-17 | 2025-05-22 | 2025-05-26 | 2025-06-02 | 2025-06-07 | 2025-06-12 | 2025-06-19 | 2025-06-19 | 2025-06-23 | 2025-06-26 | 2025-06-26 | 2025-06-26 | 2025-06-30 | 2025-07-02 | 2025-07-06 | 2025-07-13 | 2025-04-09 | 2025-04-11 | 2025-04-18 | 2025-04-25 | 2025-04-30 | 2025-05-01 | 2025-05-07 | 2025-05-07 | 2025-05-08 | 2025-05-11 | 2025-05-12 | 2025-05-17 | 2025-05-17 | 2025-05-19 | 2025-05-22 | 2025-05-24 | 2025-05-24 | 2025-05-28 | 2025-05-30 | 2025-05-31 | 2025-06-01 | 2025-06-07 | 2025-06-12 | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-23 | 2025-06-23 | 2025-06-26 | 2025-06-30 | 2025-07-09 | 2025-06-01 | 2025-06-19 | 2025-06-21 | 2025-07-13 | 2025-07-07 | 2025-07-13 | 2025-07-18 | 2025-07-24 | 2025-07-30
V_401 | 2024-12-27 | 2025-01-03 | 2025-01-05 | 2025-01-11 | 2025-01-16 | 2025-01-19 | 2025-01-20 | 2025-01-24 | 2025-01-29 | 2025-02-01 | 2025-02-05 | 2025-02-05 | 2025-04-09 | 2025-04-17 | 2025-04-24 | 2025-04-24 | 2025-05-01 | 2025-05-08 | 2025-05-08 | 2025-05-11 | 2025-05-11 | 2025-05-12 | 2025-05-18 | 2025-05-18 | 2025-05-25 | 2025-05-25 | 2025-05-25 | 2025-05-30 | 2025-06-04 | 2025-06-11 | 2025-06-15 | 2025-06-20 | 2025-06-27 | 2025-06-27 | 2025-07-02 | 2025-07-04 | 2025-07-04 | 2025-07-04 | 2025-07-09 | 2025-07-10 | 2025-07-14 | 2025-07-21 | 2025-04-17 | 2025-04-19 | 2025-04-26 | 2025-05-03 | 2025-05-08 | 2025-05-09 | 2025-05-15 | 2025-05-15 | 2025-05-16 | 2025-05-19 | 2025-05-21 | 2025-05-25 | 2025-05-25 | 2025-05-28 | 2025-05-30 | 2025-06-01 | 2025-06-01 | 2025-06-05 | 2025-06-07 | 2025-06-08 | 2025-06-09 | 2025-06-15 | 2025-06-20 | 2025-06-27 | 2025-06-27 | 2025-06-27 | 2025-07-02 | 2025-07-02 | 2025-07-04 | 2025-07-09 | 2025-07-17 | 2025-06-09 | 2025-06-27 | 2025-06-29 | 2025-07-21 | 2025-07-16 | 2025-07-21 | 2025-07-26 | 2025-08-01 | 2025-08-07
V_402 | 2024-12-27 | 2025-01-03 | 2025-01-05 | 2025-01-11 | 2025-01-16 | 2025-01-19 | 2025-01-20 | 2025-01-24 | 2025-01-29 | 2025-02-01 | 2025-02-05 | 2025-02-05 | 2025-04-09 | 2025-04-17 | 2025-04-24 | 2025-04-24 | 2025-05-01 | 2025-05-08 | 2025-05-08 | 2025-05-11 | 2025-05-11 | 2025-05-12 | 2025-05-18 | 2025-05-18 | 2025-05-25 | 2025-05-25 | 2025-05-25 | 2025-05-30 | 2025-06-04 | 2025-06-11 | 2025-06-15 | 2025-06-20 | 2025-06-27 | 2025-06-27 | 2025-07-02 | 2025-07-04 | 2025-07-04 | 2025-07-04 | 2025-07-09 | 2025-07-10 | 2025-07-14 | 2025-07-21 | 2025-04-17 | 2025-04-19 | 2025-04-26 | 2025-05-03 | 2025-05-08 | 2025-05-09 | 2025-05-15 | 2025-05-15 | 2025-05-16 | 2025-05-19 | 2025-05-21 | 2025-05-25 | 2025-05-25 | 2025-05-28 | 2025-05-30 | 2025-06-01 | 2025-06-01 | 2025-06-05 | 2025-06-07 | 2025-06-08 | 2025-06-09 | 2025-06-15 | 2025-06-20 | 2025-06-27 | 2025-06-27 | 2025-06-27 | 2025-07-02 | 2025-07-02 | 2025-07-04 | 2025-07-09 | 2025-07-17 | 2025-06-09 | 2025-06-27 | 2025-06-29 | 2025-07-21 | 2025-07-16 | 2025-07-21 | 2025-07-26 | 2025-08-01 | 2025-08-07
V_403 | 2024-12-27 | 2025-01-03 | 2025-01-05 | 2025-01-11 | 2025-01-16 | 2025-01-19 | 2025-01-20 | 2025-01-24 | 2025-01-29 | 2025-02-01 | 2025-02-05 | 2025-02-05 | 2025-04-09 | 2025-04-17 | 2025-04-24 | 2025-04-24 | 2025-05-01 | 2025-05-08 | 2025-05-08 | 2025-05-11 | 2025-05-11 | 2025-05-12 | 2025-05-18 | 2025-05-18 | 2025-05-25 | 2025-05-25 | 2025-05-25 | 2025-05-30 | 2025-06-04 | 2025-06-11 | 2025-06-15 | 2025-06-20 | 2025-06-27 | 2025-06-27 | 2025-07-02 | 2025-07-04 | 2025-07-04 | 2025-07-04 | 2025-07-09 | 2025-07-10 | 2025-07-14 | 2025-07-21 | 2025-04-17 | 2025-04-19 | 2025-04-26 | 2025-05-03 | 2025-05-08 | 2025-05-09 | 2025-05-15 | 2025-05-15 | 2025-05-16 | 2025-05-19 | 2025-05-21 | 2025-05-25 | 2025-05-25 | 2025-05-28 | 2025-05-30 | 2025-06-01 | 2025-06-01 | 2025-06-05 | 2025-06-07 | 2025-06-08 | 2025-06-09 | 2025-06-15 | 2025-06-20 | 2025-06-27 | 2025-06-27 | 2025-06-27 | 2025-07-02 | 2025-07-02 | 2025-07-04 | 2025-07-09 | 2025-07-17 | 2025-06-09 | 2025-06-27 | 2025-06-29 | 2025-07-21 | 2025-07-16 | 2025-07-21 | 2025-07-26 | 2025-08-01 | 2025-08-07
V_404 | 2024-12-27 | 2025-01-03 | 2025-01-05 | 2025-01-11 | 2025-01-16 | 2025-01-19 | 2025-01-20 | 2025-01-24 | 2025-01-29 | 2025-02-01 | 2025-02-05 | 2025-02-05 | 2025-04-09 | 2025-04-17 | 2025-04-24 | 2025-04-24 | 2025-05-01 | 2025-05-08 | 2025-05-08 | 2025-05-11 | 2025-05-11 | 2025-05-12 | 2025-05-18 | 2025-05-18 | 2025-05-25 | 2025-05-25 | 2025-05-25 | 2025-05-30 | 2025-06-04 | 2025-06-11 | 2025-06-15 | 2025-06-20 | 2025-06-27 | 2025-06-27 | 2025-07-02 | 2025-07-04 | 2025-07-04 | 2025-07-04 | 2025-07-09 | 2025-07-10 | 2025-07-14 | 2025-07-21 | 2025-04-17 | 2025-04-19 | 2025-04-26 | 2025-05-03 | 2025-05-08 | 2025-05-09 | 2025-05-15 | 2025-05-15 | 2025-05-16 | 2025-05-19 | 2025-05-21 | 2025-05-25 | 2025-05-25 | 2025-05-28 | 2025-05-30 | 2025-06-01 | 2025-06-01 | 2025-06-05 | 2025-06-07 | 2025-06-08 | 2025-06-09 | 2025-06-15 | 2025-06-20 | 2025-06-27 | 2025-06-27 | 2025-06-27 | 2025-07-02 | 2025-07-02 | 2025-07-04 | 2025-07-09 | 2025-07-17 | 2025-06-09 | 2025-06-27 | 2025-06-29 | 2025-07-21 | 2025-07-16 | 2025-07-21 | 2025-07-26 | 2025-08-01 | 2025-08-07
V_405 | 2024-12-27 | 2025-01-03 | 2025-01-05 | 2025-01-11 | 2025-01-16 | 2025-01-19 | 2025-01-20 | 2025-01-24 | 2025-01-29 | 2025-02-01 | 2025-02-05 | 2025-02-05 | 2025-04-09 | 2025-04-17 | 2025-04-24 | 2025-04-24 | 2025-05-01 | 2025-05-08 | 2025-05-08 | 2025-05-11 | 2025-05-11 | 2025-05-12 | 2025-05-18 | 2025-05-18 | 2025-05-25 | 2025-05-25 | 2025-05-25 | 2025-05-30 | 2025-06-04 | 2025-06-11 | 2025-06-15 | 2025-06-20 | 2025-06-27 | 2025-06-27 | 2025-07-02 | 2025-07-04 | 2025-07-04 | 2025-07-04 | 2025-07-09 | 2025-07-10 | 2025-07-14 | 2025-07-21 | 2025-04-17 | 2025-04-19 | 2025-04-26 | 2025-05-03 | 2025-05-08 | 2025-05-09 | 2025-05-15 | 2025-05-15 | 2025-05-16 | 2025-05-19 | 2025-05-21 | 2025-05-25 | 2025-05-25 | 2025-05-28 | 2025-05-30 | 2025-06-01 | 2025-06-01 | 2025-06-05 | 2025-06-07 | 2025-06-08 | 2025-06-09 | 2025-06-15 | 2025-06-20 | 2025-06-27 | 2025-06-27 | 2025-06-27 | 2025-07-02 | 2025-07-02 | 2025-07-04 | 2025-07-09 | 2025-07-17 | 2025-06-09 | 2025-06-27 | 2025-06-29 | 2025-07-21 | 2025-07-16 | 2025-07-21 | 2025-07-26 | 2025-08-01 | 2025-08-07
V_406 | 2024-12-27 | 2025-01-03 | 2025-01-05 | 2025-01-11 | 2025-01-16 | 2025-01-19 | 2025-01-20 | 2025-01-24 | 2025-01-29 | 2025-02-01 | 2025-02-05 | 2025-02-05 | 2025-04-09 | 2025-04-17 | 2025-04-24 | 2025-04-24 | 2025-05-01 | 2025-05-08 | 2025-05-08 | 2025-05-11 | 2025-05-11 | 2025-05-12 | 2025-05-18 | 2025-05-18 | 2025-05-25 | 2025-05-25 | 2025-05-25 | 2025-05-30 | 2025-06-04 | 2025-06-11 | 2025-06-15 | 2025-06-20 | 2025-06-27 | 2025-06-27 | 2025-07-02 | 2025-07-04 | 2025-07-04 | 2025-07-04 | 2025-07-09 | 2025-07-10 | 2025-07-14 | 2025-07-21 | 2025-04-17 | 2025-04-19 | 2025-04-26 | 2025-05-03 | 2025-05-08 | 2025-05-09 | 2025-05-15 | 2025-05-15 | 2025-05-16 | 2025-05-19 | 2025-05-21 | 2025-05-25 | 2025-05-25 | 2025-05-28 | 2025-05-30 | 2025-06-01 | 2025-06-01 | 2025-06-05 | 2025-06-07 | 2025-06-08 | 2025-06-09 | 2025-06-15 | 2025-06-20 | 2025-06-27 | 2025-06-27 | 2025-06-27 | 2025-07-02 | 2025-07-02 | 2025-07-04 | 2025-07-09 | 2025-07-17 | 2025-06-09 | 2025-06-27 | 2025-06-29 | 2025-07-21 | 2025-07-16 | 2025-07-21 | 2025-07-26 | 2025-08-01 | 2025-08-07
V_407 | 2024-12-27 | 2025-01-03 | 2025-01-05 | 2025-01-11 | 2025-01-16 | 2025-01-19 | 2025-01-20 | 2025-01-24 | 2025-01-29 | 2025-02-01 | 2025-02-05 | 2025-02-05 | 2025-04-09 | 2025-04-17 | 2025-04-24 | 2025-04-24 | 2025-05-01 | 2025-05-08 | 2025-05-08 | 2025-05-11 | 2025-05-11 | 2025-05-12 | 2025-05-18 | 2025-05-18 | 2025-05-25 | 2025-05-25 | 2025-05-25 | 2025-05-30 | 2025-06-04 | 2025-06-11 | 2025-06-15 | 2025-06-20 | 2025-06-27 | 2025-06-27 | 2025-07-02 | 2025-07-04 | 2025-07-04 | 2025-07-04 | 2025-07-09 | 2025-07-10 | 2025-07-14 | 2025-07-21 | 2025-04-17 | 2025-04-19 | 2025-04-26 | 2025-05-03 | 2025-05-08 | 2025-05-09 | 2025-05-15 | 2025-05-15 | 2025-05-16 | 2025-05-19 | 2025-05-21 | 2025-05-25 | 2025-05-25 | 2025-05-28 | 2025-05-30 | 2025-06-01 | 2025-06-01 | 2025-06-05 | 2025-06-07 | 2025-06-08 | 2025-06-09 | 2025-06-15 | 2025-06-20 | 2025-06-27 | 2025-06-27 | 2025-06-27 | 2025-07-02 | 2025-07-02 | 2025-07-04 | 2025-07-09 | 2025-07-17 | 2025-06-09 | 2025-06-27 | 2025-06-29 | 2025-07-21 | 2025-07-16 | 2025-07-21 | 2025-07-26 | 2025-08-01 | 2025-08-07
V_408 | 2024-12-27 | 2025-01-03 | 2025-01-05 | 2025-01-11 | 2025-01-16 | 2025-01-19 | 2025-01-20 | 2025-01-24 | 2025-01-29 | 2025-02-01 | 2025-02-05 | 2025-02-05 | 2025-04-09 | 2025-04-17 | 2025-04-24 | 2025-04-24 | 2025-05-01 | 2025-05-08 | 2025-05-08 | 2025-05-11 | 2025-05-11 | 2025-05-12 | 2025-05-18 | 2025-05-18 | 2025-05-25 | 2025-05-25 | 2025-05-25 | 2025-05-30 | 2025-06-04 | 2025-06-11 | 2025-06-15 | 2025-06-20 | 2025-06-27 | 2025-06-27 | 2025-07-02 | 2025-07-04 | 2025-07-04 | 2025-07-04 | 2025-07-09 | 2025-07-10 | 2025-07-14 | 2025-07-21 | 2025-04-17 | 2025-04-19 | 2025-04-26 | 2025-05-03 | 2025-05-08 | 2025-05-09 | 2025-05-15 | 2025-05-15 | 2025-05-16 | 2025-05-19 | 2025-05-21 | 2025-05-25 | 2025-05-25 | 2025-05-28 | 2025-05-30 | 2025-06-01 | 2025-06-01 | 2025-06-05 | 2025-06-07 | 2025-06-08 | 2025-06-09 | 2025-06-15 | 2025-06-20 | 2025-06-27 | 2025-06-27 | 2025-06-27 | 2025-07-02 | 2025-07-02 | 2025-07-04 | 2025-07-09 | 2025-07-17 | 2025-06-09 | 2025-06-27 | 2025-06-29 | 2025-07-21 | 2025-07-16 | 2025-07-21 | 2025-07-26 | 2025-08-01 | 2025-08-07
V_409 | 2025-01-03 | 2025-01-10 | 2025-01-12 | 2025-01-18 | 2025-01-23 | 2025-01-26 | 2025-01-27 | 2025-01-31 | 2025-02-05 | 2025-02-08 | 2025-02-12 | 2025-02-12 | 2025-04-17 | 2025-04-25 | 2025-05-02 | 2025-05-02 | 2025-05-09 | 2025-05-16 | 2025-05-16 | 2025-05-19 | 2025-05-19 | 2025-05-21 | 2025-05-26 | 2025-05-26 | 2025-06-02 | 2025-06-02 | 2025-06-02 | 2025-06-07 | 2025-06-12 | 2025-06-19 | 2025-06-23 | 2025-06-28 | 2025-07-05 | 2025-07-05 | 2025-07-10 | 2025-07-12 | 2025-07-12 | 2025-07-12 | 2025-07-17 | 2025-07-18 | 2025-07-23 | 2025-07-30 | 2025-04-25 | 2025-04-27 | 2025-05-04 | 2025-05-11 | 2025-05-16 | 2025-05-17 | 2025-05-23 | 2025-05-23 | 2025-05-24 | 2025-05-28 | 2025-05-29 | 2025-06-02 | 2025-06-02 | 2025-06-05 | 2025-06-07 | 2025-06-09 | 2025-06-09 | 2025-06-13 | 2025-06-15 | 2025-06-16 | 2025-06-18 | 2025-06-23 | 2025-06-28 | 2025-07-05 | 2025-07-05 | 2025-07-05 | 2025-07-10 | 2025-07-10 | 2025-07-12 | 2025-07-17 | 2025-07-25 | 2025-06-18 | 2025-07-05 | 2025-07-07 | 2025-07-30 | 2025-07-24 | 2025-07-30 | 2025-08-03 | 2025-08-09 | 2025-08-15
V_410 | 2025-01-03 | 2025-01-10 | 2025-01-12 | 2025-01-18 | 2025-01-23 | 2025-01-26 | 2025-01-27 | 2025-01-31 | 2025-02-05 | 2025-02-08 | 2025-02-12 | 2025-02-12 | 2025-04-17 | 2025-04-25 | 2025-05-02 | 2025-05-02 | 2025-05-09 | 2025-05-16 | 2025-05-16 | 2025-05-19 | 2025-05-19 | 2025-05-21 | 2025-05-26 | 2025-05-26 | 2025-06-02 | 2025-06-02 | 2025-06-02 | 2025-06-07 | 2025-06-12 | 2025-06-19 | 2025-06-23 | 2025-06-28 | 2025-07-05 | 2025-07-05 | 2025-07-10 | 2025-07-12 | 2025-07-12 | 2025-07-12 | 2025-07-17 | 2025-07-18 | 2025-07-23 | 2025-07-30 | 2025-04-25 | 2025-04-27 | 2025-05-04 | 2025-05-11 | 2025-05-16 | 2025-05-17 | 2025-05-23 | 2025-05-23 | 2025-05-24 | 2025-05-28 | 2025-05-29 | 2025-06-02 | 2025-06-02 | 2025-06-05 | 2025-06-07 | 2025-06-09 | 2025-06-09 | 2025-06-13 | 2025-06-15 | 2025-06-16 | 2025-06-18 | 2025-06-23 | 2025-06-28 | 2025-07-05 | 2025-07-05 | 2025-07-05 | 2025-07-10 | 2025-07-10 | 2025-07-12 | 2025-07-17 | 2025-07-25 | 2025-06-18 | 2025-07-05 | 2025-07-07 | 2025-07-30 | 2025-07-24 | 2025-07-30 | 2025-08-03 | 2025-08-09 | 2025-08-15
V_411 | 2025-01-03 | 2025-01-10 | 2025-01-12 | 2025-01-18 | 2025-01-23 | 2025-01-26 | 2025-01-27 | 2025-01-31 | 2025-02-05 | 2025-02-08 | 2025-02-12 | 2025-02-12 | 2025-04-17 | 2025-04-25 | 2025-05-02 | 2025-05-02 | 2025-05-09 | 2025-05-16 | 2025-05-16 | 2025-05-19 | 2025-05-19 | 2025-05-21 | 2025-05-26 | 2025-05-26 | 2025-06-02 | 2025-06-02 | 2025-06-02 | 2025-06-07 | 2025-06-12 | 2025-06-19 | 2025-06-23 | 2025-06-28 | 2025-07-05 | 2025-07-05 | 2025-07-10 | 2025-07-12 | 2025-07-12 | 2025-07-12 | 2025-07-17 | 2025-07-18 | 2025-07-23 | 2025-07-30 | 2025-04-25 | 2025-04-27 | 2025-05-04 | 2025-05-11 | 2025-05-16 | 2025-05-17 | 2025-05-23 | 2025-05-23 | 2025-05-24 | 2025-05-28 | 2025-05-29 | 2025-06-02 | 2025-06-02 | 2025-06-05 | 2025-06-07 | 2025-06-09 | 2025-06-09 | 2025-06-13 | 2025-06-15 | 2025-06-16 | 2025-06-18 | 2025-06-23 | 2025-06-28 | 2025-07-05 | 2025-07-05 | 2025-07-05 | 2025-07-10 | 2025-07-10 | 2025-07-12 | 2025-07-17 | 2025-07-25 | 2025-06-18 | 2025-07-05 | 2025-07-07 | 2025-07-30 | 2025-07-24 | 2025-07-30 | 2025-08-03 | 2025-08-09 | 2025-08-15
V_412 | 2025-01-03 | 2025-01-10 | 2025-01-12 | 2025-01-18 | 2025-01-23 | 2025-01-26 | 2025-01-27 | 2025-01-31 | 2025-02-05 | 2025-02-08 | 2025-02-12 | 2025-02-12 | 2025-04-17 | 2025-04-25 | 2025-05-02 | 2025-05-02 | 2025-05-09 | 2025-05-16 | 2025-05-16 | 2025-05-19 | 2025-05-19 | 2025-05-21 | 2025-05-26 | 2025-05-26 | 2025-06-02 | 2025-06-02 | 2025-06-02 | 2025-06-07 | 2025-06-12 | 2025-06-19 | 2025-06-23 | 2025-06-28 | 2025-07-05 | 2025-07-05 | 2025-07-10 | 2025-07-12 | 2025-07-12 | 2025-07-12 | 2025-07-17 | 2025-07-18 | 2025-07-23 | 2025-07-30 | 2025-04-25 | 2025-04-27 | 2025-05-04 | 2025-05-11 | 2025-05-16 | 2025-05-17 | 2025-05-23 | 2025-05-23 | 2025-05-24 | 2025-05-28 | 2025-05-29 | 2025-06-02 | 2025-06-02 | 2025-06-05 | 2025-06-07 | 2025-06-09 | 2025-06-09 | 2025-06-13 | 2025-06-15 | 2025-06-16 | 2025-06-18 | 2025-06-23 | 2025-06-28 | 2025-07-05 | 2025-07-05 | 2025-07-05 | 2025-07-10 | 2025-07-10 | 2025-07-12 | 2025-07-17 | 2025-07-25 | 2025-06-18 | 2025-07-05 | 2025-07-07 | 2025-07-30 | 2025-07-24 | 2025-07-30 | 2025-08-03 | 2025-08-09 | 2025-08-15
V_413 | 2025-01-03 | 2025-01-10 | 2025-01-12 | 2025-01-18 | 2025-01-23 | 2025-01-26 | 2025-01-27 | 2025-01-31 | 2025-02-05 | 2025-02-08 | 2025-02-12 | 2025-02-12 | 2025-04-17 | 2025-04-25 | 2025-05-02 | 2025-05-02 | 2025-05-09 | 2025-05-16 | 2025-05-16 | 2025-05-19 | 2025-05-19 | 2025-05-21 | 2025-05-26 | 2025-05-26 | 2025-06-02 | 2025-06-02 | 2025-06-02 | 2025-06-07 | 2025-06-12 | 2025-06-19 | 2025-06-23 | 2025-06-28 | 2025-07-05 | 2025-07-05 | 2025-07-10 | 2025-07-12 | 2025-07-12 | 2025-07-12 | 2025-07-17 | 2025-07-18 | 2025-07-23 | 2025-07-30 | 2025-04-25 | 2025-04-27 | 2025-05-04 | 2025-05-11 | 2025-05-16 | 2025-05-17 | 2025-05-23 | 2025-05-23 | 2025-05-24 | 2025-05-28 | 2025-05-29 | 2025-06-02 | 2025-06-02 | 2025-06-05 | 2025-06-07 | 2025-06-09 | 2025-06-09 | 2025-06-13 | 2025-06-15 | 2025-06-16 | 2025-06-18 | 2025-06-23 | 2025-06-28 | 2025-07-05 | 2025-07-05 | 2025-07-05 | 2025-07-10 | 2025-07-10 | 2025-07-12 | 2025-07-17 | 2025-07-25 | 2025-06-18 | 2025-07-05 | 2025-07-07 | 2025-07-30 | 2025-07-24 | 2025-07-30 | 2025-08-03 | 2025-08-09 | 2025-08-15
V_414 | 2025-01-03 | 2025-01-10 | 2025-01-12 | 2025-01-18 | 2025-01-23 | 2025-01-26 | 2025-01-27 | 2025-01-31 | 2025-02-05 | 2025-02-08 | 2025-02-12 | 2025-02-12 | 2025-04-17 | 2025-04-25 | 2025-05-02 | 2025-05-02 | 2025-05-09 | 2025-05-16 | 2025-05-16 | 2025-05-19 | 2025-05-19 | 2025-05-21 | 2025-05-26 | 2025-05-26 | 2025-06-02 | 2025-06-02 | 2025-06-02 | 2025-06-07 | 2025-06-12 | 2025-06-19 | 2025-06-23 | 2025-06-28 | 2025-07-05 | 2025-07-05 | 2025-07-10 | 2025-07-12 | 2025-07-12 | 2025-07-12 | 2025-07-17 | 2025-07-18 | 2025-07-23 | 2025-07-30 | 2025-04-25 | 2025-04-27 | 2025-05-04 | 2025-05-11 | 2025-05-16 | 2025-05-17 | 2025-05-23 | 2025-05-23 | 2025-05-24 | 2025-05-28 | 2025-05-29 | 2025-06-02 | 2025-06-02 | 2025-06-05 | 2025-06-07 | 2025-06-09 | 2025-06-09 | 2025-06-13 | 2025-06-15 | 2025-06-16 | 2025-06-18 | 2025-06-23 | 2025-06-28 | 2025-07-05 | 2025-07-05 | 2025-07-05 | 2025-07-10 | 2025-07-10 | 2025-07-12 | 2025-07-17 | 2025-07-25 | 2025-06-18 | 2025-07-05 | 2025-07-07 | 2025-07-30 | 2025-07-24 | 2025-07-30 | 2025-08-03 | 2025-08-09 | 2025-08-15
V_415 | 2025-01-03 | 2025-01-10 | 2025-01-12 | 2025-01-18 | 2025-01-23 | 2025-01-26 | 2025-01-27 | 2025-01-31 | 2025-02-05 | 2025-02-08 | 2025-02-12 | 2025-02-12 | 2025-04-17 | 2025-04-25 | 2025-05-02 | 2025-05-02 | 2025-05-09 | 2025-05-16 | 2025-05-16 | 2025-05-19 | 2025-05-19 | 2025-05-21 | 2025-05-26 | 2025-05-26 | 2025-06-02 | 2025-06-02 | 2025-06-02 | 2025-06-07 | 2025-06-12 | 2025-06-19 | 2025-06-23 | 2025-06-28 | 2025-07-05 | 2025-07-05 | 2025-07-10 | 2025-07-12 | 2025-07-12 | 2025-07-12 | 2025-07-17 | 2025-07-18 | 2025-07-23 | 2025-07-30 | 2025-04-25 | 2025-04-27 | 2025-05-04 | 2025-05-11 | 2025-05-16 | 2025-05-17 | 2025-05-23 | 2025-05-23 | 2025-05-24 | 2025-05-28 | 2025-05-29 | 2025-06-02 | 2025-06-02 | 2025-06-05 | 2025-06-07 | 2025-06-09 | 2025-06-09 | 2025-06-13 | 2025-06-15 | 2025-06-16 | 2025-06-18 | 2025-06-23 | 2025-06-28 | 2025-07-05 | 2025-07-05 | 2025-07-05 | 2025-07-10 | 2025-07-10 | 2025-07-12 | 2025-07-17 | 2025-07-25 | 2025-06-18 | 2025-07-05 | 2025-07-07 | 2025-07-30 | 2025-07-24 | 2025-07-30 | 2025-08-03 | 2025-08-09 | 2025-08-15
V_416 | 2025-01-03 | 2025-01-10 | 2025-01-12 | 2025-01-18 | 2025-01-23 | 2025-01-26 | 2025-01-27 | 2025-01-31 | 2025-02-05 | 2025-02-08 | 2025-02-12 | 2025-02-12 | 2025-04-17 | 2025-04-25 | 2025-05-02 | 2025-05-02 | 2025-05-09 | 2025-05-16 | 2025-05-16 | 2025-05-19 | 2025-05-19 | 2025-05-21 | 2025-05-26 | 2025-05-26 | 2025-06-02 | 2025-06-02 | 2025-06-02 | 2025-06-07 | 2025-06-12 | 2025-06-19 | 2025-06-23 | 2025-06-28 | 2025-07-05 | 2025-07-05 | 2025-07-10 | 2025-07-12 | 2025-07-12 | 2025-07-12 | 2025-07-17 | 2025-07-18 | 2025-07-23 | 2025-07-30 | 2025-04-25 | 2025-04-27 | 2025-05-04 | 2025-05-11 | 2025-05-16 | 2025-05-17 | 2025-05-23 | 2025-05-23 | 2025-05-24 | 2025-05-28 | 2025-05-29 | 2025-06-02 | 2025-06-02 | 2025-06-05 | 2025-06-07 | 2025-06-09 | 2025-06-09 | 2025-06-13 | 2025-06-15 | 2025-06-16 | 2025-06-18 | 2025-06-23 | 2025-06-28 | 2025-07-05 | 2025-07-05 | 2025-07-05 | 2025-07-10 | 2025-07-10 | 2025-07-12 | 2025-07-17 | 2025-07-25 | 2025-06-18 | 2025-07-05 | 2025-07-07 | 2025-07-30 | 2025-07-24 | 2025-07-30 | 2025-08-03 | 2025-08-09 | 2025-08-15
V_417 | 2025-01-10 | 2025-01-17 | 2025-01-19 | 2025-01-25 | 2025-01-30 | 2025-02-02 | 2025-02-03 | 2025-02-07 | 2025-02-12 | 2025-02-15 | 2025-02-19 | 2025-02-19 | 2025-04-25 | 2025-05-03 | 2025-05-10 | 2025-05-10 | 2025-05-17 | 2025-05-24 | 2025-05-24 | 2025-05-28 | 2025-05-28 | 2025-05-29 | 2025-06-04 | 2025-06-04 | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-15 | 2025-06-20 | 2025-06-27 | 2025-07-02 | 2025-07-06 | 2025-07-13 | 2025-07-13 | 2025-07-18 | 2025-07-20 | 2025-07-20 | 2025-07-20 | 2025-07-25 | 2025-07-26 | 2025-07-31 | 2025-08-07 | 2025-05-03 | 2025-05-05 | 2025-05-12 | 2025-05-19 | 2025-05-24 | 2025-05-25 | 2025-05-31 | 2025-05-31 | 2025-06-01 | 2025-06-05 | 2025-06-06 | 2025-06-11 | 2025-06-11 | 2025-06-13 | 2025-06-15 | 2025-06-18 | 2025-06-18 | 2025-06-21 | 2025-06-23 | 2025-06-25 | 2025-06-26 | 2025-07-02 | 2025-07-06 | 2025-07-13 | 2025-07-13 | 2025-07-13 | 2025-07-18 | 2025-07-18 | 2025-07-20 | 2025-07-25 | 2025-08-02 | 2025-06-26 | 2025-07-13 | 2025-07-16 | 2025-08-07 | 2025-08-01 | 2025-08-07 | 2025-08-11 | 2025-08-16 | 2025-08-22
V_418 | 2025-01-10 | 2025-01-17 | 2025-01-19 | 2025-01-25 | 2025-01-30 | 2025-02-02 | 2025-02-03 | 2025-02-07 | 2025-02-12 | 2025-02-15 | 2025-02-19 | 2025-02-19 | 2025-04-25 | 2025-05-03 | 2025-05-10 | 2025-05-10 | 2025-05-17 | 2025-05-24 | 2025-05-24 | 2025-05-28 | 2025-05-28 | 2025-05-29 | 2025-06-04 | 2025-06-04 | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-15 | 2025-06-20 | 2025-06-27 | 2025-07-02 | 2025-07-06 | 2025-07-13 | 2025-07-13 | 2025-07-18 | 2025-07-20 | 2025-07-20 | 2025-07-20 | 2025-07-25 | 2025-07-26 | 2025-07-31 | 2025-08-07 | 2025-05-03 | 2025-05-05 | 2025-05-12 | 2025-05-19 | 2025-05-24 | 2025-05-25 | 2025-05-31 | 2025-05-31 | 2025-06-01 | 2025-06-05 | 2025-06-06 | 2025-06-11 | 2025-06-11 | 2025-06-13 | 2025-06-15 | 2025-06-18 | 2025-06-18 | 2025-06-21 | 2025-06-23 | 2025-06-25 | 2025-06-26 | 2025-07-02 | 2025-07-06 | 2025-07-13 | 2025-07-13 | 2025-07-13 | 2025-07-18 | 2025-07-18 | 2025-07-20 | 2025-07-25 | 2025-08-02 | 2025-06-26 | 2025-07-13 | 2025-07-16 | 2025-08-07 | 2025-08-01 | 2025-08-07 | 2025-08-11 | 2025-08-16 | 2025-08-22
V_419 | 2025-01-10 | 2025-01-17 | 2025-01-19 | 2025-01-25 | [75 empty] | 2025-08-11 | 2025-08-16 | 2025-08-22
V_420 | 2025-01-10 | 2025-01-17 | 2025-01-19 | 2025-01-25 | [75 empty] | 2025-08-11 | 2025-08-16 | 2025-08-22
V_421 | 2025-01-10 | 2025-01-17 | 2025-01-19 | 2025-01-25 | [75 empty] | 2025-08-11 | 2025-08-16 | 2025-08-22
V_422 | 2025-01-10 | 2025-01-17 | 2025-01-19 | 2025-01-25 | [75 empty] | 2025-08-11 | 2025-08-16 | 2025-08-22
V_423 | 2025-01-10 | 2025-01-17 | 2025-01-19 | 2025-01-25 | [75 empty] | 2025-08-11 | 2025-08-16 | 2025-08-22
V_424 | 2025-01-10 | 2025-01-17 | 2025-01-19 | 2025-01-25 | [75 empty] | 2025-08-11 | 2025-08-16 | 2025-08-22
V_425 | 2025-01-17 | 2025-01-24 | 2025-01-26 | 2025-02-01 | [75 empty] | 2025-08-20 | 2025-08-24 | 2025-08-30
V_426 | 2025-01-17 | 2025-01-24 | 2025-01-26 | 2025-02-01 | [75 empty] | 2025-08-20 | 2025-08-24 | 2025-08-30
V_427 | 2025-01-17 | 2025-01-24 | 2025-01-26 | 2025-02-01 | [75 empty] | 2025-08-20 | 2025-08-24 | 2025-08-30
V_428 | 2025-01-17 | 2025-01-24 | 2025-01-26 | 2025-02-01 | 2025-02-06 | 2025-02-09 | 2025-02-10 | 2025-02-14 | 2025-02-19 | 2025-02-22 | 2025-02-26 | 2025-02-26 | 2025-05-03 | 2025-05-11 | 2025-05-18 | 2025-05-18 | 2025-05-25 | 2025-06-01 | 2025-06-01 | 2025-06-05 | 2025-06-05 | 2025-06-06 | 2025-06-12 | 2025-06-12 | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-23 | 2025-06-28 | 2025-07-05 | 2025-07-10 | 2025-07-14 | 2025-07-21 | 2025-07-21 | 2025-07-26 | 2025-07-28 | 2025-07-28 | 2025-07-28 | 2025-08-02 | 2025-08-03 | 2025-08-08 | 2025-08-15 | 2025-05-11 | 2025-05-14 | 2025-05-21 | 2025-05-28 | 2025-06-01 | 2025-06-02 | 2025-06-08 | 2025-06-08 | 2025-06-09 | 2025-06-13 | 2025-06-14 | 2025-06-19 | 2025-06-19 | 2025-06-21 | 2025-06-23 | 2025-06-26 | 2025-06-26 | 2025-06-29 | 2025-07-02 | 2025-07-03 | 2025-07-04 | 2025-07-10 | 2025-07-14 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-26 | 2025-07-26 | 2025-07-28 | 2025-08-02 | 2025-08-10 | 2025-07-04 | 2025-07-21 | 2025-07-24 | 2025-08-15 | 2025-08-09 | 2025-08-15 | 2025-08-20 | 2025-08-24 | 2025-08-30
V_429 | 2025-01-17 | 2025-01-24 | 2025-01-26 | 2025-02-01 | 2025-02-06 | 2025-02-09 | 2025-02-10 | 2025-02-14 | 2025-02-19 | 2025-02-22 | 2025-02-26 | 2025-02-26 | 2025-05-03 | 2025-05-11 | 2025-05-18 | 2025-05-18 | 2025-05-25 | 2025-06-01 | 2025-06-01 | 2025-06-05 | 2025-06-05 | 2025-06-06 | 2025-06-12 | 2025-06-12 | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-23 | 2025-06-28 | 2025-07-05 | 2025-07-10 | 2025-07-14 | 2025-07-21 | 2025-07-21 | 2025-07-26 | 2025-07-28 | 2025-07-28 | 2025-07-28 | 2025-08-02 | 2025-08-03 | 2025-08-08 | 2025-08-15 | 2025-05-11 | 2025-05-14 | 2025-05-21 | 2025-05-28 | 2025-06-01 | 2025-06-02 | 2025-06-08 | 2025-06-08 | 2025-06-09 | 2025-06-13 | 2025-06-14 | 2025-06-19 | 2025-06-19 | 2025-06-21 | 2025-06-23 | 2025-06-26 | 2025-06-26 | 2025-06-29 | 2025-07-02 | 2025-07-03 | 2025-07-04 | 2025-07-10 | 2025-07-14 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-26 | 2025-07-26 | 2025-07-28 | 2025-08-02 | 2025-08-10 | 2025-07-04 | 2025-07-21 | 2025-07-24 | 2025-08-15 | 2025-08-09 | 2025-08-15 | 2025-08-20 | 2025-08-24 | 2025-08-30
V_430 | 2025-01-17 | 2025-01-24 | 2025-01-26 | 2025-02-01 | 2025-02-06 | 2025-02-09 | 2025-02-10 | 2025-02-14 | 2025-02-19 | 2025-02-22 | 2025-02-26 | 2025-02-26 | 2025-05-03 | 2025-05-11 | 2025-05-18 | 2025-05-18 | 2025-05-25 | 2025-06-01 | 2025-06-01 | 2025-06-05 | 2025-06-05 | 2025-06-06 | 2025-06-12 | 2025-06-12 | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-23 | 2025-06-28 | 2025-07-05 | 2025-07-10 | 2025-07-14 | 2025-07-21 | 2025-07-21 | 2025-07-26 | 2025-07-28 | 2025-07-28 | 2025-07-28 | 2025-08-02 | 2025-08-03 | 2025-08-08 | 2025-08-15 | 2025-05-11 | 2025-05-14 | 2025-05-21 | 2025-05-28 | 2025-06-01 | 2025-06-02 | 2025-06-08 | 2025-06-08 | 2025-06-09 | 2025-06-13 | 2025-06-14 | 2025-06-19 | 2025-06-19 | 2025-06-21 | 2025-06-23 | 2025-06-26 | 2025-06-26 | 2025-06-29 | 2025-07-02 | 2025-07-03 | 2025-07-04 | 2025-07-10 | 2025-07-14 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-26 | 2025-07-26 | 2025-07-28 | 2025-08-02 | 2025-08-10 | 2025-07-04 | 2025-07-21 | 2025-07-24 | 2025-08-15 | 2025-08-09 | 2025-08-15 | 2025-08-20 | 2025-08-24 | 2025-08-30
V_431 | 2025-01-17 | 2025-01-24 | 2025-01-26 | 2025-02-01 | 2025-02-06 | 2025-02-09 | 2025-02-10 | 2025-02-14 | 2025-02-19 | 2025-02-22 | 2025-02-26 | 2025-02-26 | 2025-05-03 | 2025-05-11 | 2025-05-18 | 2025-05-18 | 2025-05-25 | 2025-06-01 | 2025-06-01 | 2025-06-05 | 2025-06-05 | 2025-06-06 | 2025-06-12 | 2025-06-12 | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-23 | 2025-06-28 | 2025-07-05 | 2025-07-10 | 2025-07-14 | 2025-07-21 | 2025-07-21 | 2025-07-26 | 2025-07-28 | 2025-07-28 | 2025-07-28 | 2025-08-02 | 2025-08-03 | 2025-08-08 | 2025-08-15 | 2025-05-11 | 2025-05-14 | 2025-05-21 | 2025-05-28 | 2025-06-01 | 2025-06-02 | 2025-06-08 | 2025-06-08 | 2025-06-09 | 2025-06-13 | 2025-06-14 | 2025-06-19 | 2025-06-19 | 2025-06-21 | 2025-06-23 | 2025-06-26 | 2025-06-26 | 2025-06-29 | 2025-07-02 | 2025-07-03 | 2025-07-04 | 2025-07-10 | 2025-07-14 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-26 | 2025-07-26 | 2025-07-28 | 2025-08-02 | 2025-08-10 | 2025-07-04 | 2025-07-21 | 2025-07-24 | 2025-08-15 | 2025-08-09 | 2025-08-15 | 2025-08-20 | 2025-08-24 | 2025-08-30
V_432 | 2025-01-17 | 2025-01-24 | 2025-01-26 | 2025-02-01 | 2025-02-06 | 2025-02-09 | 2025-02-10 | 2025-02-14 | 2025-02-19 | 2025-02-22 | 2025-02-26 | 2025-02-26 | 2025-05-03 | 2025-05-11 | 2025-05-18 | 2025-05-18 | 2025-05-25 | 2025-06-01 | 2025-06-01 | 2025-06-05 | 2025-06-05 | 2025-06-06 | 2025-06-12 | 2025-06-12 | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-23 | 2025-06-28 | 2025-07-05 | 2025-07-10 | 2025-07-14 | 2025-07-21 | 2025-07-21 | 2025-07-26 | 2025-07-28 | 2025-07-28 | 2025-07-28 | 2025-08-02 | 2025-08-03 | 2025-08-08 | 2025-08-15 | 2025-05-11 | 2025-05-14 | 2025-05-21 | 2025-05-28 | 2025-06-01 | 2025-06-02 | 2025-06-08 | 2025-06-08 | 2025-06-09 | 2025-06-13 | 2025-06-14 | 2025-06-19 | 2025-06-19 | 2025-06-21 | 2025-06-23 | 2025-06-26 | 2025-06-26 | 2025-06-29 | 2025-07-02 | 2025-07-03 | 2025-07-04 | 2025-07-10 | 2025-07-14 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-26 | 2025-07-26 | 2025-07-28 | 2025-08-02 | 2025-08-10 | 2025-07-04 | 2025-07-21 | 2025-07-24 | 2025-08-15 | 2025-08-09 | 2025-08-15 | 2025-08-20 | 2025-08-24 | 2025-08-30
V_433 | 2025-01-24 | 2025-01-31 | 2025-02-02 | 2025-02-08 | 2025-02-13 | 2025-02-16 | 2025-02-17 | 2025-02-21 | 2025-02-26 | 2025-03-01 | 2025-03-05 | 2025-03-05 | 2025-05-11 | 2025-05-19 | 2025-05-26 | 2025-05-26 | 2025-06-02 | 2025-06-09 | 2025-06-09 | 2025-06-13 | 2025-06-13 | 2025-06-14 | 2025-06-20 | 2025-06-20 | 2025-06-27 | 2025-06-27 | 2025-06-27 | 2025-07-02 | 2025-07-06 | 2025-07-13 | 2025-07-18 | 2025-07-23 | 2025-07-30 | 2025-07-30 | 2025-08-03 | 2025-08-06 | 2025-08-06 | 2025-08-06 | 2025-08-10 | 2025-08-11 | 2025-08-16 | 2025-08-23 | 2025-05-19 | 2025-05-22 | 2025-05-29 | 2025-06-05 | 2025-06-09 | 2025-06-11 | 2025-06-16 | 2025-06-16 | 2025-06-18 | 2025-06-21 | 2025-06-22 | 2025-06-27 | 2025-06-27 | 2025-06-29 | 2025-07-02 | 2025-07-04 | 2025-07-04 | 2025-07-07 | 2025-07-10 | 2025-07-11 | 2025-07-12 | 2025-07-18 | 2025-07-23 | 2025-07-30 | 2025-07-30 | 2025-07-30 | 2025-08-03 | 2025-08-03 | 2025-08-06 | 2025-08-10 | 2025-08-18 | 2025-07-12 | 2025-07-30 | 2025-08-01 | 2025-08-23 | 2025-08-17 | 2025-08-23 | 2025-08-28 | 2025-09-01 | 2025-09-07
V_434 | 2025-01-24 | 2025-01-31 | 2025-02-02 | 2025-02-08 | 2025-02-13 | 2025-02-16 | 2025-02-17 | 2025-02-21 | 2025-02-26 | 2025-03-01 | 2025-03-05 | 2025-03-05 | 2025-05-11 | 2025-05-19 | 2025-05-26 | 2025-05-26 | 2025-06-02 | 2025-06-09 | 2025-06-09 | 2025-06-13 | 2025-06-13 | 2025-06-14 | 2025-06-20 | 2025-06-20 | 2025-06-27 | 2025-06-27 | 2025-06-27 | 2025-07-02 | 2025-07-06 | 2025-07-13 | 2025-07-18 | 2025-07-23 | 2025-07-30 | 2025-07-30 | 2025-08-03 | 2025-08-06 | 2025-08-06 | 2025-08-06 | 2025-08-10 | 2025-08-11 | 2025-08-16 | 2025-08-23 | 2025-05-19 | 2025-05-22 | 2025-05-29 | 2025-06-05 | 2025-06-09 | 2025-06-11 | 2025-06-16 | 2025-06-16 | 2025-06-18 | 2025-06-21 | 2025-06-22 | 2025-06-27 | 2025-06-27 | 2025-06-29 | 2025-07-02 | 2025-07-04 | 2025-07-04 | 2025-07-07 | 2025-07-10 | 2025-07-11 | 2025-07-12 | 2025-07-18 | 2025-07-23 | 2025-07-30 | 2025-07-30 | 2025-07-30 | 2025-08-03 | 2025-08-03 | 2025-08-06 | 2025-08-10 | 2025-08-18 | 2025-07-12 | 2025-07-30 | 2025-08-01 | 2025-08-23 | 2025-08-17 | 2025-08-23 | 2025-08-28 | 2025-09-01 | 2025-09-07
V_435 | 2025-01-24 | 2025-01-31 | 2025-02-02 | 2025-02-08 | 2025-02-13 | 2025-02-16 | 2025-02-17 | 2025-02-21 | 2025-02-26 | 2025-03-01 | 2025-03-05 | 2025-03-05 | 2025-05-11 | 2025-05-19 | 2025-05-26 | 2025-05-26 | 2025-06-02 | 2025-06-09 | 2025-06-09 | 2025-06-13 | 2025-06-13 | 2025-06-14 | 2025-06-20 | 2025-06-20 | 2025-06-27 | 2025-06-27 | 2025-06-27 | 2025-07-02 | 2025-07-06 | 2025-07-13 | 2025-07-18 | 2025-07-23 | 2025-07-30 | 2025-07-30 | 2025-08-03 | 2025-08-06 | 2025-08-06 | 2025-08-06 | 2025-08-10 | 2025-08-11 | 2025-08-16 | 2025-08-23 | 2025-05-19 | 2025-05-22 | 2025-05-29 | 2025-06-05 | 2025-06-09 | 2025-06-11 | 2025-06-16 | 2025-06-16 | 2025-06-18 | 2025-06-21 | 2025-06-22 | 2025-06-27 | 2025-06-27 | 2025-06-29 | 2025-07-02 | 2025-07-04 | 2025-07-04 | 2025-07-07 | 2025-07-10 | 2025-07-11 | 2025-07-12 | 2025-07-18 | 2025-07-23 | 2025-07-30 | 2025-07-30 | 2025-07-30 | 2025-08-03 | 2025-08-03 | 2025-08-06 | 2025-08-10 | 2025-08-18 | 2025-07-12 | 2025-07-30 | 2025-08-01 | 2025-08-23 | 2025-08-17 | 2025-08-23 | 2025-08-28 | 2025-09-01 | 2025-09-07
V_436 | 2025-01-24 | 2025-01-31 | 2025-02-02 | 2025-02-08 | 2025-02-13 | 2025-02-16 | 2025-02-17 | 2025-02-21 | 2025-02-26 | 2025-03-01 | 2025-03-05 | 2025-03-05 | 2025-05-11 | 2025-05-19 | 2025-05-26 | 2025-05-26 | 2025-06-02 | 2025-06-09 | 2025-06-09 | 2025-06-13 | 2025-06-13 | 2025-06-14 | 2025-06-20 | 2025-06-20 | 2025-06-27 | 2025-06-27 | 2025-06-27 | 2025-07-02 | 2025-07-06 | 2025-07-13 | 2025-07-18 | 2025-07-23 | 2025-07-30 | 2025-07-30 | 2025-08-03 | 2025-08-06 | 2025-08-06 | 2025-08-06 | 2025-08-10 | 2025-08-11 | 2025-08-16 | 2025-08-23 | 2025-05-19 | 2025-05-22 | 2025-05-29 | 2025-06-05 | 2025-06-09 | 2025-06-11 | 2025-06-16 | 2025-06-16 | 2025-06-18 | 2025-06-21 | 2025-06-22 | 2025-06-27 | 2025-06-27 | 2025-06-29 | 2025-07-02 | 2025-07-04 | 2025-07-04 | 2025-07-07 | 2025-07-10 | 2025-07-11 | 2025-07-12 | 2025-07-18 | 2025-07-23 | 2025-07-30 | 2025-07-30 | 2025-07-30 | 2025-08-03 | 2025-08-03 | 2025-08-06 | 2025-08-10 | 2025-08-18 | 2025-07-12 | 2025-07-30 | 2025-08-01 | 2025-08-23 | 2025-08-17 | 2025-08-23 | 2025-08-28 | 2025-09-01 | 2025-09-07
V_437 | 2025-01-24 | 2025-01-31 | 2025-02-02 | 2025-02-08 | 2025-02-13 | 2025-02-16 | 2025-02-17 | 2025-02-21 | 2025-02-26 | 2025-03-01 | 2025-03-05 | 2025-03-05 | 2025-05-11 | 2025-05-19 | 2025-05-26 | 2025-05-26 | 2025-06-02 | 2025-06-09 | 2025-06-09 | 2025-06-13 | 2025-06-13 | 2025-06-14 | 2025-06-20 | 2025-06-20 | 2025-06-27 | 2025-06-27 | 2025-06-27 | 2025-07-02 | 2025-07-06 | 2025-07-13 | 2025-07-18 | 2025-07-23 | 2025-07-30 | 2025-07-30 | 2025-08-03 | 2025-08-06 | 2025-08-06 | 2025-08-06 | 2025-08-10 | 2025-08-11 | 2025-08-16 | 2025-08-23 | 2025-05-19 | 2025-05-22 | 2025-05-29 | 2025-06-05 | 2025-06-09 | 2025-06-11 | 2025-06-16 | 2025-06-16 | 2025-06-18 | 2025-06-21 | 2025-06-22 | 2025-06-27 | 2025-06-27 | 2025-06-29 | 2025-07-02 | 2025-07-04 | 2025-07-04 | 2025-07-07 | 2025-07-10 | 2025-07-11 | 2025-07-12 | 2025-07-18 | 2025-07-23 | 2025-07-30 | 2025-07-30 | 2025-07-30 | 2025-08-03 | 2025-08-03 | 2025-08-06 | 2025-08-10 | 2025-08-18 | 2025-07-12 | 2025-07-30 | 2025-08-01 | 2025-08-23 | 2025-08-17 | 2025-08-23 | 2025-08-28 | 2025-09-01 | 2025-09-07
V_438 | 2025-01-24 | 2025-01-31 | 2025-02-02 | 2025-02-08 | 2025-02-13 | 2025-02-16 | 2025-02-17 | 2025-02-21 | 2025-02-26 | 2025-03-01 | 2025-03-05 | 2025-03-05 | 2025-05-11 | 2025-05-19 | 2025-05-26 | 2025-05-26 | 2025-06-02 | 2025-06-09 | 2025-06-09 | 2025-06-13 | 2025-06-13 | 2025-06-14 | 2025-06-20 | 2025-06-20 | 2025-06-27 | 2025-06-27 | 2025-06-27 | 2025-07-02 | 2025-07-06 | 2025-07-13 | 2025-07-18 | 2025-07-23 | 2025-07-30 | 2025-07-30 | 2025-08-03 | 2025-08-06 | 2025-08-06 | 2025-08-06 | 2025-08-10 | 2025-08-11 | 2025-08-16 | 2025-08-23 | 2025-05-19 | 2025-05-22 | 2025-05-29 | 2025-06-05 | 2025-06-09 | 2025-06-11 | 2025-06-16 | 2025-06-16 | 2025-06-18 | 2025-06-21 | 2025-06-22 | 2025-06-27 | 2025-06-27 | 2025-06-29 | 2025-07-02 | 2025-07-04 | 2025-07-04 | 2025-07-07 | 2025-07-10 | 2025-07-11 | 2025-07-12 | 2025-07-18 | 2025-07-23 | 2025-07-30 | 2025-07-30 | 2025-07-30 | 2025-08-03 | 2025-08-03 | 2025-08-06 | 2025-08-10 | 2025-08-18 | 2025-07-12 | 2025-07-30 | 2025-08-01 | 2025-08-23 | 2025-08-17 | 2025-08-23 | 2025-08-28 | 2025-09-01 | 2025-09-07
V_439 | 2025-01-24 | 2025-01-31 | 2025-02-02 | 2025-02-08 | 2025-02-13 | 2025-02-16 | 2025-02-17 | 2025-02-21 | 2025-02-26 | 2025-03-01 | 2025-03-05 | 2025-03-05 | 2025-05-11 | 2025-05-19 | 2025-05-26 | 2025-05-26 | 2025-06-02 | 2025-06-09 | 2025-06-09 | 2025-06-13 | 2025-06-13 | 2025-06-14 | 2025-06-20 | 2025-06-20 | 2025-06-27 | 2025-06-27 | 2025-06-27 | 2025-07-02 | 2025-07-06 | 2025-07-13 | 2025-07-18 | 2025-07-23 | 2025-07-30 | 2025-07-30 | 2025-08-03 | 2025-08-06 | 2025-08-06 | 2025-08-06 | 2025-08-10 | 2025-08-11 | 2025-08-16 | 2025-08-23 | 2025-05-19 | 2025-05-22 | 2025-05-29 | 2025-06-05 | 2025-06-09 | 2025-06-11 | 2025-06-16 | 2025-06-16 | 2025-06-18 | 2025-06-21 | 2025-06-22 | 2025-06-27 | 2025-06-27 | 2025-06-29 | 2025-07-02 | 2025-07-04 | 2025-07-04 | 2025-07-07 | 2025-07-10 | 2025-07-11 | 2025-07-12 | 2025-07-18 | 2025-07-23 | 2025-07-30 | 2025-07-30 | 2025-07-30 | 2025-08-03 | 2025-08-03 | 2025-08-06 | 2025-08-10 | 2025-08-18 | 2025-07-12 | 2025-07-30 | 2025-08-01 | 2025-08-23 | 2025-08-17 | 2025-08-23 | 2025-08-28 | 2025-09-01 | 2025-09-07
V_440 | 2025-01-24 | 2025-01-31 | 2025-02-02 | 2025-02-08 | 2025-02-13 | 2025-02-16 | 2025-02-17 | 2025-02-21 | 2025-02-26 | 2025-03-01 | 2025-03-05 | 2025-03-05 | 2025-05-11 | 2025-05-19 | 2025-05-26 | 2025-05-26 | 2025-06-02 | 2025-06-09 | 2025-06-09 | 2025-06-13 | 2025-06-13 | 2025-06-14 | 2025-06-20 | 2025-06-20 | 2025-06-27 | 2025-06-27 | 2025-06-27 | 2025-07-02 | 2025-07-06 | 2025-07-13 | 2025-07-18 | 2025-07-23 | 2025-07-30 | 2025-07-30 | 2025-08-03 | 2025-08-06 | 2025-08-06 | 2025-08-06 | 2025-08-10 | 2025-08-11 | 2025-08-16 | 2025-08-23 | 2025-05-19 | 2025-05-22 | 2025-05-29 | 2025-06-05 | 2025-06-09 | 2025-06-11 | 2025-06-16 | 2025-06-16 | 2025-06-18 | 2025-06-21 | 2025-06-22 | 2025-06-27 | 2025-06-27 | 2025-06-29 | 2025-07-02 | 2025-07-04 | 2025-07-04 | 2025-07-07 | 2025-07-10 | 2025-07-11 | 2025-07-12 | 2025-07-18 | 2025-07-23 | 2025-07-30 | 2025-07-30 | 2025-07-30 | 2025-08-03 | 2025-08-03 | 2025-08-06 | 2025-08-10 | 2025-08-18 | 2025-07-12 | 2025-07-30 | 2025-08-01 | 2025-08-23 | 2025-08-17 | 2025-08-23 | 2025-08-28 | 2025-09-01 | 2025-09-07
V_441 | 2025-01-31 | 2025-02-07 | 2025-02-09 | 2025-02-15 | 2025-02-20 | 2025-02-23 | 2025-02-24 | 2025-02-28 | 2025-03-05 | 2025-03-08 | 2025-03-12 | 2025-03-12 | 2025-05-19 | 2025-05-28 | 2025-06-04 | 2025-06-04 | 2025-06-11 | 2025-06-18 | 2025-06-18 | 2025-06-21 | 2025-06-21 | 2025-06-22 | 2025-06-28 | 2025-06-28 | 2025-07-05 | 2025-07-05 | 2025-07-05 | 2025-07-10 | 2025-07-14 | 2025-07-21 | 2025-07-26 | 2025-07-31 | 2025-08-07 | 2025-08-07 | 2025-08-11 | 2025-08-14 | 2025-08-14 | 2025-08-14 | 2025-08-18 | 2025-08-20 | 2025-08-24 | 2025-08-31 | 2025-05-28 | 2025-05-30 | 2025-06-06 | 2025-06-13 | 2025-06-18 | 2025-06-19 | 2025-06-25 | 2025-06-25 | 2025-06-26 | 2025-06-29 | 2025-06-30 | 2025-07-05 | 2025-07-05 | 2025-07-07 | 2025-07-10 | 2025-07-12 | 2025-07-12 | 2025-07-16 | 2025-07-18 | 2025-07-19 | 2025-07-20 | 2025-07-26 | 2025-07-31 | 2025-08-07 | 2025-08-07 | 2025-08-07 | 2025-08-11 | 2025-08-11 | 2025-08-14 | 2025-08-18 | 2025-08-27 | 2025-07-20 | 2025-08-07 | 2025-08-09 | 2025-08-31 | 2025-08-25 | 2025-08-31 | 2025-09-05 | 2025-09-10 | 2025-09-15
V_442 | 2025-01-31 | 2025-02-07 | 2025-02-09 | 2025-02-15 | 2025-02-20 | 2025-02-23 | 2025-02-24 | 2025-02-28 | 2025-03-05 | 2025-03-08 | 2025-03-12 | 2025-03-12 | 2025-05-19 | 2025-05-28 | 2025-06-04 | 2025-06-04 | 2025-06-11 | 2025-06-18 | 2025-06-18 | 2025-06-21 | 2025-06-21 | 2025-06-22 | 2025-06-28 | 2025-06-28 | 2025-07-05 | 2025-07-05 | 2025-07-05 | 2025-07-10 | 2025-07-14 | 2025-07-21 | 2025-07-26 | 2025-07-31 | 2025-08-07 | 2025-08-07 | 2025-08-11 | 2025-08-14 | 2025-08-14 | 2025-08-14 | 2025-08-18 | 2025-08-20 | 2025-08-24 | 2025-08-31 | 2025-05-28 | 2025-05-30 | 2025-06-06 | 2025-06-13 | 2025-06-18 | 2025-06-19 | 2025-06-25 | 2025-06-25 | 2025-06-26 | 2025-06-29 | 2025-06-30 | 2025-07-05 | 2025-07-05 | 2025-07-07 | 2025-07-10 | 2025-07-12 | 2025-07-12 | 2025-07-16 | 2025-07-18 | 2025-07-19 | 2025-07-20 | 2025-07-26 | 2025-07-31 | 2025-08-07 | 2025-08-07 | 2025-08-07 | 2025-08-11 | 2025-08-11 | 2025-08-14 | 2025-08-18 | 2025-08-27 | 2025-07-20 | 2025-08-07 | 2025-08-09 | 2025-08-31 | 2025-08-25 | 2025-08-31 | 2025-09-05 | 2025-09-10 | 2025-09-15
V_443 | 2025-01-31 | 2025-02-07 | 2025-02-09 | 2025-02-15 | 2025-02-20 | 2025-02-23 | 2025-02-24 | 2025-02-28 | 2025-03-05 | 2025-03-08 | 2025-03-12 | 2025-03-12 | 2025-05-19 | 2025-05-28 | 2025-06-04 | 2025-06-04 | 2025-06-11 | 2025-06-18 | 2025-06-18 | 2025-06-21 | 2025-06-21 | 2025-06-22 | 2025-06-28 | 2025-06-28 | 2025-07-05 | 2025-07-05 | 2025-07-05 | 2025-07-10 | 2025-07-14 | 2025-07-21 | 2025-07-26 | 2025-07-31 | 2025-08-07 | 2025-08-07 | 2025-08-11 | 2025-08-14 | 2025-08-14 | 2025-08-14 | 2025-08-18 | 2025-08-20 | 2025-08-24 | 2025-08-31 | 2025-05-28 | 2025-05-30 | 2025-06-06 | 2025-06-13 | 2025-06-18 | 2025-06-19 | 2025-06-25 | 2025-06-25 | 2025-06-26 | 2025-06-29 | 2025-06-30 | 2025-07-05 | 2025-07-05 | 2025-07-07 | 2025-07-10 | 2025-07-12 | 2025-07-12 | 2025-07-16 | 2025-07-18 | 2025-07-19 | 2025-07-20 | 2025-07-26 | 2025-07-31 | 2025-08-07 | 2025-08-07 | 2025-08-07 | 2025-08-11 | 2025-08-11 | 2025-08-14 | 2025-08-18 | 2025-08-27 | 2025-07-20 | 2025-08-07 | 2025-08-09 | 2025-08-31 | 2025-08-25 | 2025-08-31 | 2025-09-05 | 2025-09-10 | 2025-09-15
V_444 | 2025-01-31 | 2025-02-07 | 2025-02-09 | 2025-02-15 | 2025-02-20 | 2025-02-23 | 2025-02-24 | 2025-02-28 | 2025-03-05 | 2025-03-08 | 2025-03-12 | 2025-03-12 | 2025-05-19 | 2025-05-28 | 2025-06-04 | 2025-06-04 | 2025-06-11 | 2025-06-18 | 2025-06-18 | 2025-06-21 | 2025-06-21 | 2025-06-22 | 2025-06-28 | 2025-06-28 | 2025-07-05 | 2025-07-05 | 2025-07-05 | 2025-07-10 | 2025-07-14 | 2025-07-21 | 2025-07-26 | 2025-07-31 | 2025-08-07 | 2025-08-07 | 2025-08-11 | 2025-08-14 | 2025-08-14 | 2025-08-14 | 2025-08-18 | 2025-08-20 | 2025-08-24 | 2025-08-31 | 2025-05-28 | 2025-05-30 | 2025-06-06 | 2025-06-13 | 2025-06-18 | 2025-06-19 | 2025-06-25 | 2025-06-25 | 2025-06-26 | 2025-06-29 | 2025-06-30 | 2025-07-05 | 2025-07-05 | 2025-07-07 | 2025-07-10 | 2025-07-12 | 2025-07-12 | 2025-07-16 | 2025-07-18 | 2025-07-19 | 2025-07-20 | 2025-07-26 | 2025-07-31 | 2025-08-07 | 2025-08-07 | 2025-08-07 | 2025-08-11 | 2025-08-11 | 2025-08-14 | 2025-08-18 | 2025-08-27 | 2025-07-20 | 2025-08-07 | 2025-08-09 | 2025-08-31 | 2025-08-25 | 2025-08-31 | 2025-09-05 | 2025-09-10 | 2025-09-15
V_445 | 2025-01-31 | 2025-02-07 | 2025-02-09 | 2025-02-15 | 2025-02-20 | 2025-02-23 | 2025-02-24 | 2025-02-28 | 2025-03-05 | 2025-03-08 | 2025-03-12 | 2025-03-12 | 2025-05-19 | 2025-05-28 | 2025-06-04 | 2025-06-04 | 2025-06-11 | 2025-06-18 | 2025-06-18 | 2025-06-21 | 2025-06-21 | 2025-06-22 | 2025-06-28 | 2025-06-28 | 2025-07-05 | 2025-07-05 | 2025-07-05 | 2025-07-10 | 2025-07-14 | 2025-07-21 | 2025-07-26 | 2025-07-31 | 2025-08-07 | 2025-08-07 | 2025-08-11 | 2025-08-14 | 2025-08-14 | 2025-08-14 | 2025-08-18 | 2025-08-20 | 2025-08-24 | 2025-08-31 | 2025-05-28 | 2025-05-30 | 2025-06-06 | 2025-06-13 | 2025-06-18 | 2025-06-19 | 2025-06-25 | 2025-06-25 | 2025-06-26 | 2025-06-29 | 2025-06-30 | 2025-07-05 | 2025-07-05 | 2025-07-07 | 2025-07-10 | 2025-07-12 | 2025-07-12 | 2025-07-16 | 2025-07-18 | 2025-07-19 | 2025-07-20 | 2025-07-26 | 2025-07-31 | 2025-08-07 | 2025-08-07 | 2025-08-07 | 2025-08-11 | 2025-08-11 | 2025-08-14 | 2025-08-18 | 2025-08-27 | 2025-07-20 | 2025-08-07 | 2025-08-09 | 2025-08-31 | 2025-08-25 | 2025-08-31 | 2025-09-05 | 2025-09-10 | 2025-09-15
V_446 | 2025-01-31 | 2025-02-07 | 2025-02-09 | 2025-02-15 | 2025-02-20 | 2025-02-23 | 2025-02-24 | 2025-02-28 | 2025-03-05 | 2025-03-08 | 2025-03-12 | 2025-03-12 | 2025-05-19 | 2025-05-28 | 2025-06-04 | 2025-06-04 | 2025-06-11 | 2025-06-18 | 2025-06-18 | 2025-06-21 | 2025-06-21 | 2025-06-22 | 2025-06-28 | 2025-06-28 | 2025-07-05 | 2025-07-05 | 2025-07-05 | 2025-07-10 | 2025-07-14 | 2025-07-21 | 2025-07-26 | 2025-07-31 | 2025-08-07 | 2025-08-07 | 2025-08-11 | 2025-08-14 | 2025-08-14 | 2025-08-14 | 2025-08-18 | 2025-08-20 | 2025-08-24 | 2025-08-31 | 2025-05-28 | 2025-05-30 | 2025-06-06 | 2025-06-13 | 2025-06-18 | 2025-06-19 | 2025-06-25 | 2025-06-25 | 2025-06-26 | 2025-06-29 | 2025-06-30 | 2025-07-05 | 2025-07-05 | 2025-07-07 | 2025-07-10 | 2025-07-12 | 2025-07-12 | 2025-07-16 | 2025-07-18 | 2025-07-19 | 2025-07-20 | 2025-07-26 | 2025-07-31 | 2025-08-07 | 2025-08-07 | 2025-08-07 | 2025-08-11 | 2025-08-11 | 2025-08-14 | 2025-08-18 | 2025-08-27 | 2025-07-20 | 2025-08-07 | 2025-08-09 | 2025-08-31 | 2025-08-25 | 2025-08-31 | 2025-09-05 | 2025-09-10 | 2025-09-15
V_447 | 2025-01-31 | 2025-02-07 | 2025-02-09 | 2025-02-15 | 2025-02-20 | 2025-02-23 | 2025-02-24 | 2025-02-28 | 2025-03-05 | 2025-03-08 | 2025-03-12 | 2025-03-12 | 2025-05-19 | 2025-05-28 | 2025-06-04 | 2025-06-04 | 2025-06-11 | 2025-06-18 | 2025-06-18 | 2025-06-21 | 2025-06-21 | 2025-06-22 | 2025-06-28 | 2025-06-28 | 2025-07-05 | 2025-07-05 | 2025-07-05 | 2025-07-10 | 2025-07-14 | 2025-07-21 | 2025-07-26 | 2025-07-31 | 2025-08-07 | 2025-08-07 | 2025-08-11 | 2025-08-14 | 2025-08-14 | 2025-08-14 | 2025-08-18 | 2025-08-20 | 2025-08-24 | 2025-08-31 | 2025-05-28 | 2025-05-30 | 2025-06-06 | 2025-06-13 | 2025-06-18 | 2025-06-19 | 2025-06-25 | 2025-06-25 | 2025-06-26 | 2025-06-29 | 2025-06-30 | 2025-07-05 | 2025-07-05 | 2025-07-07 | 2025-07-10 | 2025-07-12 | 2025-07-12 | 2025-07-16 | 2025-07-18 | 2025-07-19 | 2025-07-20 | 2025-07-26 | 2025-07-31 | 2025-08-07 | 2025-08-07 | 2025-08-07 | 2025-08-11 | 2025-08-11 | 2025-08-14 | 2025-08-18 | 2025-08-27 | 2025-07-20 | 2025-08-07 | 2025-08-09 | 2025-08-31 | 2025-08-25 | 2025-08-31 | 2025-09-05 | 2025-09-10 | 2025-09-15
V_448 | 2025-01-31 | 2025-02-07 | 2025-02-09 | 2025-02-15 | 2025-02-20 | 2025-02-23 | 2025-02-24 | 2025-02-28 | 2025-03-05 | 2025-03-08 | 2025-03-12 | 2025-03-12 | 2025-05-19 | 2025-05-28 | 2025-06-04 | 2025-06-04 | 2025-06-11 | 2025-06-18 | 2025-06-18 | 2025-06-21 | 2025-06-21 | 2025-06-22 | 2025-06-28 | 2025-06-28 | 2025-07-05 | 2025-07-05 | 2025-07-05 | 2025-07-10 | 2025-07-14 | 2025-07-21 | 2025-07-26 | 2025-07-31 | 2025-08-07 | 2025-08-07 | 2025-08-11 | 2025-08-14 | 2025-08-14 | 2025-08-14 | 2025-08-18 | 2025-08-20 | 2025-08-24 | 2025-08-31 | 2025-05-28 | 2025-05-30 | 2025-06-06 | 2025-06-13 | 2025-06-18 | 2025-06-19 | 2025-06-25 | 2025-06-25 | 2025-06-26 | 2025-06-29 | 2025-06-30 | 2025-07-05 | 2025-07-05 | 2025-07-07 | 2025-07-10 | 2025-07-12 | 2025-07-12 | 2025-07-16 | 2025-07-18 | 2025-07-19 | 2025-07-20 | 2025-07-26 | 2025-07-31 | 2025-08-07 | 2025-08-07 | 2025-08-07 | 2025-08-11 | 2025-08-11 | 2025-08-14 | 2025-08-18 | 2025-08-27 | 2025-07-20 | 2025-08-07 | 2025-08-09 | 2025-08-31 | 2025-08-25 | 2025-08-31 | 2025-09-05 | 2025-09-10 | 2025-09-15
V_449 | 2025-02-07 | 2025-02-14 | 2025-02-16 | 2025-02-22 | 2025-02-27 | 2025-03-02 | 2025-03-03 | 2025-03-07 | 2025-03-12 | 2025-03-15 | 2025-03-19 | 2025-03-19 | 2025-05-28 | 2025-06-04 | 2025-06-11 | 2025-06-11 | 2025-06-18 | 2025-06-25 | 2025-06-25 | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-07-05 | 2025-07-05 | 2025-07-12 | 2025-07-12 | 2025-07-12 | 2025-07-17 | 2025-07-21 | 2025-07-28 | 2025-08-02 | 2025-08-07 | 2025-08-14 | 2025-08-14 | 2025-08-18 | 2025-08-21 | 2025-08-21 | 2025-08-21 | 2025-08-25 | 2025-08-27 | 2025-08-31 | 2025-09-07 | 2025-06-04 | 2025-06-06 | 2025-06-13 | 2025-06-20 | 2025-06-25 | 2025-06-26 | 2025-07-02 | 2025-07-02 | 2025-07-03 | 2025-07-06 | 2025-07-07 | 2025-07-12 | 2025-07-12 | 2025-07-14 | 2025-07-17 | 2025-07-19 | 2025-07-19 | 2025-07-23 | 2025-07-25 | 2025-07-26 | 2025-07-27 | 2025-08-02 | 2025-08-07 | 2025-08-14 | 2025-08-14 | 2025-08-14 | 2025-08-18 | 2025-08-18 | 2025-08-21 | 2025-08-27 | 2025-09-03 | 2025-07-27 | 2025-08-14 | 2025-08-16 | 2025-09-07 | 2025-09-01 | 2025-09-07 | 2025-09-12 | 2025-09-15 | 2025-09-21
V_450 | 2025-02-07 | 2025-02-14 | 2025-02-16 | 2025-02-22 | 2025-02-27 | 2025-03-02 | 2025-03-03 | 2025-03-07 | 2025-03-12 | 2025-03-15 | 2025-03-19 | 2025-03-19 | 2025-05-28 | 2025-06-04 | 2025-06-11 | 2025-06-11 | 2025-06-18 | 2025-06-25 | 2025-06-25 | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-07-05 | 2025-07-05 | 2025-07-12 | 2025-07-12 | 2025-07-12 | 2025-07-17 | 2025-07-21 | 2025-07-28 | 2025-08-02 | 2025-08-07 | 2025-08-14 | 2025-08-14 | 2025-08-18 | 2025-08-21 | 2025-08-21 | 2025-08-21 | 2025-08-25 | 2025-08-27 | 2025-08-31 | 2025-09-07 | 2025-06-04 | 2025-06-06 | 2025-06-13 | 2025-06-20 | 2025-06-25 | 2025-06-26 | 2025-07-02 | 2025-07-02 | 2025-07-03 | 2025-07-06 | 2025-07-07 | 2025-07-12 | 2025-07-12 | 2025-07-14 | 2025-07-17 | 2025-07-19 | 2025-07-19 | 2025-07-23 | 2025-07-25 | 2025-07-26 | 2025-07-27 | 2025-08-02 | 2025-08-07 | 2025-08-14 | 2025-08-14 | 2025-08-14 | 2025-08-18 | 2025-08-18 | 2025-08-21 | 2025-08-27 | 2025-09-03 | 2025-07-27 | 2025-08-14 | 2025-08-16 | 2025-09-07 | 2025-09-01 | 2025-09-07 | 2025-09-12 | 2025-09-15 | 2025-09-21
V_451 | 2025-02-07 | 2025-02-14 | 2025-02-16 | 2025-02-22 | 2025-02-27 | 2025-03-02 | 2025-03-03 | 2025-03-07 | 2025-03-12 | 2025-03-15 | 2025-03-19 | 2025-03-19 | 2025-05-28 | 2025-06-04 | 2025-06-11 | 2025-06-11 | 2025-06-18 | 2025-06-25 | 2025-06-25 | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-07-05 | 2025-07-05 | 2025-07-12 | 2025-07-12 | 2025-07-12 | 2025-07-17 | 2025-07-21 | 2025-07-28 | 2025-08-02 | 2025-08-07 | 2025-08-14 | 2025-08-14 | 2025-08-18 | 2025-08-21 | 2025-08-21 | 2025-08-21 | 2025-08-25 | 2025-08-27 | 2025-08-31 | 2025-09-07 | 2025-06-04 | 2025-06-06 | 2025-06-13 | 2025-06-20 | 2025-06-25 | 2025-06-26 | 2025-07-02 | 2025-07-02 | 2025-07-03 | 2025-07-06 | 2025-07-07 | 2025-07-12 | 2025-07-12 | 2025-07-14 | 2025-07-17 | 2025-07-19 | 2025-07-19 | 2025-07-23 | 2025-07-25 | 2025-07-26 | 2025-07-27 | 2025-08-02 | 2025-08-07 | 2025-08-14 | 2025-08-14 | 2025-08-14 | 2025-08-18 | 2025-08-18 | 2025-08-21 | 2025-08-27 | 2025-09-03 | 2025-07-27 | 2025-08-14 | 2025-08-16 | 2025-09-07 | 2025-09-01 | 2025-09-07 | 2025-09-12 | 2025-09-15 | 2025-09-21
V_452 | 2025-02-07 | 2025-02-14 | 2025-02-16 | 2025-02-22 | 2025-02-27 | 2025-03-02 | 2025-03-03 | 2025-03-07 | 2025-03-12 | 2025-03-15 | 2025-03-19 | 2025-03-19 | 2025-05-28 | 2025-06-04 | 2025-06-11 | 2025-06-11 | 2025-06-18 | 2025-06-25 | 2025-06-25 | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-07-05 | 2025-07-05 | 2025-07-12 | 2025-07-12 | 2025-07-12 | 2025-07-17 | 2025-07-21 | 2025-07-28 | 2025-08-02 | 2025-08-07 | 2025-08-14 | 2025-08-14 | 2025-08-18 | 2025-08-21 | 2025-08-21 | 2025-08-21 | 2025-08-25 | 2025-08-27 | 2025-08-31 | 2025-09-07 | 2025-06-04 | 2025-06-06 | 2025-06-13 | 2025-06-20 | 2025-06-25 | 2025-06-26 | 2025-07-02 | 2025-07-02 | 2025-07-03 | 2025-07-06 | 2025-07-07 | 2025-07-12 | 2025-07-12 | 2025-07-14 | 2025-07-17 | 2025-07-19 | 2025-07-19 | 2025-07-23 | 2025-07-25 | 2025-07-26 | 2025-07-27 | 2025-08-02 | 2025-08-07 | 2025-08-14 | 2025-08-14 | 2025-08-14 | 2025-08-18 | 2025-08-18 | 2025-08-21 | 2025-08-27 | 2025-09-03 | 2025-07-27 | 2025-08-14 | 2025-08-16 | 2025-09-07 | 2025-09-01 | 2025-09-07 | 2025-09-12 | 2025-09-15 | 2025-09-21
V_453 | 2025-02-07 | 2025-02-14 | 2025-02-16 | 2025-02-22 | 2025-02-27 | 2025-03-02 | 2025-03-03 | 2025-03-07 | 2025-03-12 | 2025-03-15 | 2025-03-19 | 2025-03-19 | 2025-05-28 | 2025-06-04 | 2025-06-11 | 2025-06-11 | 2025-06-18 | 2025-06-25 | 2025-06-25 | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-07-05 | 2025-07-05 | 2025-07-12 | 2025-07-12 | 2025-07-12 | 2025-07-17 | 2025-07-21 | 2025-07-28 | 2025-08-02 | 2025-08-07 | 2025-08-14 | 2025-08-14 | 2025-08-18 | 2025-08-21 | 2025-08-21 | 2025-08-21 | 2025-08-25 | 2025-08-27 | 2025-08-31 | 2025-09-07 | 2025-06-04 | 2025-06-06 | 2025-06-13 | 2025-06-20 | 2025-06-25 | 2025-06-26 | 2025-07-02 | 2025-07-02 | 2025-07-03 | 2025-07-06 | 2025-07-07 | 2025-07-12 | 2025-07-12 | 2025-07-14 | 2025-07-17 | 2025-07-19 | 2025-07-19 | 2025-07-23 | 2025-07-25 | 2025-07-26 | 2025-07-27 | 2025-08-02 | 2025-08-07 | 2025-08-14 | 2025-08-14 | 2025-08-14 | 2025-08-18 | 2025-08-18 | 2025-08-21 | 2025-08-27 | 2025-09-03 | 2025-07-27 | 2025-08-14 | 2025-08-16 | 2025-09-07 | 2025-09-01 | 2025-09-07 | 2025-09-12 | 2025-09-15 | 2025-09-21
V_454 | 2025-02-07 | 2025-02-14 | 2025-02-16 | 2025-02-22 | 2025-02-27 | 2025-03-02 | 2025-03-03 | 2025-03-07 | 2025-03-12 | 2025-03-15 | 2025-03-19 | 2025-03-19 | 2025-05-28 | 2025-06-04 | 2025-06-11 | 2025-06-11 | 2025-06-18 | 2025-06-25 | 2025-06-25 | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-07-05 | 2025-07-05 | 2025-07-12 | 2025-07-12 | 2025-07-12 | 2025-07-17 | 2025-07-21 | 2025-07-28 | 2025-08-02 | 2025-08-07 | 2025-08-14 | 2025-08-14 | 2025-08-18 | 2025-08-21 | 2025-08-21 | 2025-08-21 | 2025-08-25 | 2025-08-27 | 2025-08-31 | 2025-09-07 | 2025-06-04 | 2025-06-06 | 2025-06-13 | 2025-06-20 | 2025-06-25 | 2025-06-26 | 2025-07-02 | 2025-07-02 | 2025-07-03 | 2025-07-06 | 2025-07-07 | 2025-07-12 | 2025-07-12 | 2025-07-14 | 2025-07-17 | 2025-07-19 | 2025-07-19 | 2025-07-23 | 2025-07-25 | 2025-07-26 | 2025-07-27 | 2025-08-02 | 2025-08-07 | 2025-08-14 | 2025-08-14 | 2025-08-14 | 2025-08-18 | 2025-08-18 | 2025-08-21 | 2025-08-27 | 2025-09-03 | 2025-07-27 | 2025-08-14 | 2025-08-16 | 2025-09-07 | 2025-09-01 | 2025-09-07 | 2025-09-12 | 2025-09-15 | 2025-09-21
V_455 | 2025-02-07 | 2025-02-14 | 2025-02-16 | 2025-02-22 | 2025-02-27 | 2025-03-02 | 2025-03-03 | 2025-03-07 | 2025-03-12 | 2025-03-15 | 2025-03-19 | 2025-03-19 | 2025-05-28 | 2025-06-04 | 2025-06-11 | 2025-06-11 | 2025-06-18 | 2025-06-25 | 2025-06-25 | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-07-05 | 2025-07-05 | 2025-07-12 | 2025-07-12 | 2025-07-12 | 2025-07-17 | 2025-07-21 | 2025-07-28 | 2025-08-02 | 2025-08-07 | 2025-08-14 | 2025-08-14 | 2025-08-18 | 2025-08-21 | 2025-08-21 | 2025-08-21 | 2025-08-25 | 2025-08-27 | 2025-08-31 | 2025-09-07 | 2025-06-04 | 2025-06-06 | 2025-06-13 | 2025-06-20 | 2025-06-25 | 2025-06-26 | 2025-07-02 | 2025-07-02 | 2025-07-03 | 2025-07-06 | 2025-07-07 | 2025-07-12 | 2025-07-12 | 2025-07-14 | 2025-07-17 | 2025-07-19 | 2025-07-19 | 2025-07-23 | 2025-07-25 | 2025-07-26 | 2025-07-27 | 2025-08-02 | 2025-08-07 | 2025-08-14 | 2025-08-14 | 2025-08-14 | 2025-08-18 | 2025-08-18 | 2025-08-21 | 2025-08-27 | 2025-09-03 | 2025-07-27 | 2025-08-14 | 2025-08-16 | 2025-09-07 | 2025-09-01 | 2025-09-07 | 2025-09-12 | 2025-09-15 | 2025-09-21
V_456 | 2025-02-07 | 2025-02-14 | 2025-02-16 | 2025-02-22 | 2025-02-27 | 2025-03-02 | 2025-03-03 | 2025-03-07 | 2025-03-12 | 2025-03-15 | 2025-03-19 | 2025-03-19 | 2025-05-28 | 2025-06-04 | 2025-06-11 | 2025-06-11 | 2025-06-18 | 2025-06-25 | 2025-06-25 | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-07-05 | 2025-07-05 | 2025-07-12 | 2025-07-12 | 2025-07-12 | 2025-07-17 | 2025-07-21 | 2025-07-28 | 2025-08-02 | 2025-08-07 | 2025-08-14 | 2025-08-14 | 2025-08-18 | 2025-08-21 | 2025-08-21 | 2025-08-21 | 2025-08-25 | 2025-08-27 | 2025-08-31 | 2025-09-07 | 2025-06-04 | 2025-06-06 | 2025-06-13 | 2025-06-20 | 2025-06-25 | 2025-06-26 | 2025-07-02 | 2025-07-02 | 2025-07-03 | 2025-07-06 | 2025-07-07 | 2025-07-12 | 2025-07-12 | 2025-07-14 | 2025-07-17 | 2025-07-19 | 2025-07-19 | 2025-07-23 | 2025-07-25 | 2025-07-26 | 2025-07-27 | 2025-08-02 | 2025-08-07 | 2025-08-14 | 2025-08-14 | 2025-08-14 | 2025-08-18 | 2025-08-18 | 2025-08-21 | 2025-08-27 | 2025-09-03 | 2025-07-27 | 2025-08-14 | 2025-08-16 | 2025-09-07 | 2025-09-01 | 2025-09-07 | 2025-09-12 | 2025-09-15 | 2025-09-21
V_457 | 2025-02-14 | 2025-02-21 | 2025-02-23 | 2025-03-01 | 2025-03-06 | 2025-03-09 | 2025-03-10 | 2025-03-14 | 2025-03-19 | 2025-03-22 | 2025-03-26 | 2025-03-26 | 2025-06-04 | 2025-06-11 | 2025-06-18 | 2025-06-18 | 2025-06-25 | 2025-07-02 | 2025-07-02 | 2025-07-05 | 2025-07-05 | 2025-07-06 | 2025-07-12 | 2025-07-12 | 2025-07-19 | 2025-07-19 | 2025-07-19 | 2025-07-24 | 2025-07-28 | 2025-08-04 | 2025-08-09 | 2025-08-14 | 2025-08-21 | 2025-08-21 | 2025-08-25 | 2025-08-28 | 2025-08-28 | 2025-08-28 | 2025-09-01 | 2025-09-03 | 2025-09-07 | 2025-09-14 | 2025-06-11 | 2025-06-13 | 2025-06-20 | 2025-06-27 | 2025-07-02 | 2025-07-03 | 2025-07-09 | 2025-07-09 | 2025-07-10 | 2025-07-13 | 2025-07-14 | 2025-07-19 | 2025-07-19 | 2025-07-21 | 2025-07-24 | 2025-07-26 | 2025-07-26 | 2025-07-30 | 2025-08-01 | 2025-08-02 | 2025-08-03 | 2025-08-09 | 2025-08-14 | 2025-08-21 | 2025-08-21 | 2025-08-21 | 2025-08-25 | 2025-08-25 | 2025-08-28 | 2025-09-03 | 2025-09-10 | 2025-08-03 | 2025-08-21 | 2025-08-23 | 2025-09-14 | 2025-09-08 | 2025-09-14 | 2025-09-19 | 2025-09-22 | 2025-09-27
V_458 | 2025-02-14 | 2025-02-21 | 2025-02-23 | 2025-03-01 | 2025-03-06 | 2025-03-09 | 2025-03-10 | 2025-03-14 | 2025-03-19 | 2025-03-22 | 2025-03-26 | 2025-03-26 | 2025-06-04 | 2025-06-11 | 2025-06-18 | 2025-06-18 | 2025-06-25 | 2025-07-02 | 2025-07-02 | 2025-07-05 | 2025-07-05 | 2025-07-06 | 2025-07-12 | 2025-07-12 | 2025-07-19 | 2025-07-19 | 2025-07-19 | 2025-07-24 | 2025-07-28 | 2025-08-04 | 2025-08-09 | 2025-08-14 | 2025-08-21 | 2025-08-21 | 2025-08-25 | 2025-08-28 | 2025-08-28 | 2025-08-28 | 2025-09-01 | 2025-09-03 | 2025-09-07 | 2025-09-14 | 2025-06-11 | 2025-06-13 | 2025-06-20 | 2025-06-27 | 2025-07-02 | 2025-07-03 | 2025-07-09 | 2025-07-09 | 2025-07-10 | 2025-07-13 | 2025-07-14 | 2025-07-19 | 2025-07-19 | 2025-07-21 | 2025-07-24 | 2025-07-26 | 2025-07-26 | 2025-07-30 | 2025-08-01 | 2025-08-02 | 2025-08-03 | 2025-08-09 | 2025-08-14 | 2025-08-21 | 2025-08-21 | 2025-08-21 | 2025-08-25 | 2025-08-25 | 2025-08-28 | 2025-09-03 | 2025-09-10 | 2025-08-03 | 2025-08-21 | 2025-08-23 | 2025-09-14 | 2025-09-08 | 2025-09-14 | 2025-09-19 | 2025-09-22 | 2025-09-27
V_459 | 2025-02-14 | 2025-02-21 | 2025-02-23 | 2025-03-01 | 2025-03-06 | 2025-03-09 | 2025-03-10 | 2025-03-14 | 2025-03-19 | 2025-03-22 | 2025-03-26 | 2025-03-26 | 2025-06-04 | 2025-06-11 | 2025-06-18 | 2025-06-18 | 2025-06-25 | 2025-07-02 | 2025-07-02 | 2025-07-05 | 2025-07-05 | 2025-07-06 | 2025-07-12 | 2025-07-12 | 2025-07-19 | 2025-07-19 | 2025-07-19 | 2025-07-24 | 2025-07-28 | 2025-08-04 | 2025-08-09 | 2025-08-14 | 2025-08-21 | 2025-08-21 | 2025-08-25 | 2025-08-28 | 2025-08-28 | 2025-08-28 | 2025-09-01 | 2025-09-03 | 2025-09-07 | 2025-09-14 | 2025-06-11 | 2025-06-13 | 2025-06-20 | 2025-06-27 | 2025-07-02 | 2025-07-03 | 2025-07-09 | 2025-07-09 | 2025-07-10 | 2025-07-13 | 2025-07-14 | 2025-07-19 | 2025-07-19 | 2025-07-21 | 2025-07-24 | 2025-07-26 | 2025-07-26 | 2025-07-30 | 2025-08-01 | 2025-08-02 | 2025-08-03 | 2025-08-09 | 2025-08-14 | 2025-08-21 | 2025-08-21 | 2025-08-21 | 2025-08-25 | 2025-08-25 | 2025-08-28 | 2025-09-03 | 2025-09-10 | 2025-08-03 | 2025-08-21 | 2025-08-23 | 2025-09-14 | 2025-09-08 | 2025-09-14 | 2025-09-19 | 2025-09-22 | 2025-09-27
V_460 | 2025-02-14 | 2025-02-21 | 2025-02-23 | 2025-03-01 | 2025-03-06 | 2025-03-09 | 2025-03-10 | 2025-03-14 | 2025-03-19 | 2025-03-22 | 2025-03-26 | 2025-03-26 | 2025-06-04 | 2025-06-11 | 2025-06-18 | 2025-06-18 | 2025-06-25 | 2025-07-02 | 2025-07-02 | 2025-07-05 | 2025-07-05 | 2025-07-06 | 2025-07-12 | 2025-07-12 | 2025-07-19 | 2025-07-19 | 2025-07-19 | 2025-07-24 | 2025-07-28 | 2025-08-04 | 2025-08-09 | 2025-08-14 | 2025-08-21 | 2025-08-21 | 2025-08-25 | 2025-08-28 | 2025-08-28 | 2025-08-28 | 2025-09-01 | 2025-09-03 | 2025-09-07 | 2025-09-14 | 2025-06-11 | 2025-06-13 | 2025-06-20 | 2025-06-27 | 2025-07-02 | 2025-07-03 | 2025-07-09 | 2025-07-09 | 2025-07-10 | 2025-07-13 | 2025-07-14 | 2025-07-19 | 2025-07-19 | 2025-07-21 | 2025-07-24 | 2025-07-26 | 2025-07-26 | 2025-07-30 | 2025-08-01 | 2025-08-02 | 2025-08-03 | 2025-08-09 | 2025-08-14 | 2025-08-21 | 2025-08-21 | 2025-08-21 | 2025-08-25 | 2025-08-25 | 2025-08-28 | 2025-09-03 | 2025-09-10 | 2025-08-03 | 2025-08-21 | 2025-08-23 | 2025-09-14 | 2025-09-08 | 2025-09-14 | 2025-09-19 | 2025-09-22 | 2025-09-27
V_461 | 2025-02-14 | 2025-02-21 | 2025-02-23 | 2025-03-01 | 2025-03-06 | 2025-03-09 | 2025-03-10 | 2025-03-14 | 2025-03-19 | 2025-03-22 | 2025-03-26 | 2025-03-26 | 2025-06-04 | 2025-06-11 | 2025-06-18 | 2025-06-18 | 2025-06-25 | 2025-07-02 | 2025-07-02 | 2025-07-05 | 2025-07-05 | 2025-07-06 | 2025-07-12 | 2025-07-12 | 2025-07-19 | 2025-07-19 | 2025-07-19 | 2025-07-24 | 2025-07-28 | 2025-08-04 | 2025-08-09 | 2025-08-14 | 2025-08-21 | 2025-08-21 | 2025-08-25 | 2025-08-28 | 2025-08-28 | 2025-08-28 | 2025-09-01 | 2025-09-03 | 2025-09-07 | 2025-09-14 | 2025-06-11 | 2025-06-13 | 2025-06-20 | 2025-06-27 | 2025-07-02 | 2025-07-03 | 2025-07-09 | 2025-07-09 | 2025-07-10 | 2025-07-13 | 2025-07-14 | 2025-07-19 | 2025-07-19 | 2025-07-21 | 2025-07-24 | 2025-07-26 | 2025-07-26 | 2025-07-30 | 2025-08-01 | 2025-08-02 | 2025-08-03 | 2025-08-09 | 2025-08-14 | 2025-08-21 | 2025-08-21 | 2025-08-21 | 2025-08-25 | 2025-08-25 | 2025-08-28 | 2025-09-03 | 2025-09-10 | 2025-08-03 | 2025-08-21 | 2025-08-23 | 2025-09-14 | 2025-09-08 | 2025-09-14 | 2025-09-19 | 2025-09-22 | 2025-09-27
V_462 | 2025-02-14 | 2025-02-21 | 2025-02-23 | 2025-03-01 | 2025-03-06 | 2025-03-09 | 2025-03-10 | 2025-03-14 | 2025-03-19 | 2025-03-22 | 2025-03-26 | 2025-03-26 | 2025-06-04 | 2025-06-11 | 2025-06-18 | 2025-06-18 | 2025-06-25 | 2025-07-02 | 2025-07-02 | 2025-07-05 | 2025-07-05 | 2025-07-06 | 2025-07-12 | 2025-07-12 | 2025-07-19 | 2025-07-19 | 2025-07-19 | 2025-07-24 | 2025-07-28 | 2025-08-04 | 2025-08-09 | 2025-08-14 | 2025-08-21 | 2025-08-21 | 2025-08-25 | 2025-08-28 | 2025-08-28 | 2025-08-28 | 2025-09-01 | 2025-09-03 | 2025-09-07 | 2025-09-14 | 2025-06-11 | 2025-06-13 | 2025-06-20 | 2025-06-27 | 2025-07-02 | 2025-07-03 | 2025-07-09 | 2025-07-09 | 2025-07-10 | 2025-07-13 | 2025-07-14 | 2025-07-19 | 2025-07-19 | 2025-07-21 | 2025-07-24 | 2025-07-26 | 2025-07-26 | 2025-07-30 | 2025-08-01 | 2025-08-02 | 2025-08-03 | 2025-08-09 | 2025-08-14 | 2025-08-21 | 2025-08-21 | 2025-08-21 | 2025-08-25 | 2025-08-25 | 2025-08-28 | 2025-09-03 | 2025-09-10 | 2025-08-03 | 2025-08-21 | 2025-08-23 | 2025-09-14 | 2025-09-08 | 2025-09-14 | 2025-09-19 | 2025-09-22 | 2025-09-27
V_463 | 2025-02-14 | 2025-02-21 | 2025-02-23 | 2025-03-01 | 2025-03-06 | 2025-03-09 | 2025-03-10 | 2025-03-14 | 2025-03-19 | 2025-03-22 | 2025-03-26 | 2025-03-26 | 2025-06-04 | 2025-06-11 | 2025-06-18 | 2025-06-18 | 2025-06-25 | 2025-07-02 | 2025-07-02 | 2025-07-05 | 2025-07-05 | 2025-07-06 | 2025-07-12 | 2025-07-12 | 2025-07-19 | 2025-07-19 | 2025-07-19 | 2025-07-24 | 2025-07-28 | 2025-08-04 | 2025-08-09 | 2025-08-14 | 2025-08-21 | 2025-08-21 | 2025-08-25 | 2025-08-28 | 2025-08-28 | 2025-08-28 | 2025-09-01 | 2025-09-03 | 2025-09-07 | 2025-09-14 | 2025-06-11 | 2025-06-13 | 2025-06-20 | 2025-06-27 | 2025-07-02 | 2025-07-03 | 2025-07-09 | 2025-07-09 | 2025-07-10 | 2025-07-13 | 2025-07-14 | 2025-07-19 | 2025-07-19 | 2025-07-21 | 2025-07-24 | 2025-07-26 | 2025-07-26 | 2025-07-30 | 2025-08-01 | 2025-08-02 | 2025-08-03 | 2025-08-09 | 2025-08-14 | 2025-08-21 | 2025-08-21 | 2025-08-21 | 2025-08-25 | 2025-08-25 | 2025-08-28 | 2025-09-03 | 2025-09-10 | 2025-08-03 | 2025-08-21 | 2025-08-23 | 2025-09-14 | 2025-09-08 | 2025-09-14 | 2025-09-19 | 2025-09-22 | 2025-09-27
V_464 | 2025-02-14 | 2025-02-21 | 2025-02-23 | 2025-03-01 | 2025-03-06 | 2025-03-09 | 2025-03-10 | 2025-03-14 | 2025-03-19 | 2025-03-22 | 2025-03-26 | 2025-03-26 | 2025-06-04 | 2025-06-11 | 2025-06-18 | 2025-06-18 | 2025-06-25 | 2025-07-02 | 2025-07-02 | 2025-07-05 | 2025-07-05 | 2025-07-06 | 2025-07-12 | 2025-07-12 | 2025-07-19 | 2025-07-19 | 2025-07-19 | 2025-07-24 | 2025-07-28 | 2025-08-04 | 2025-08-09 | 2025-08-14 | 2025-08-21 | 2025-08-21 | 2025-08-25 | 2025-08-28 | 2025-08-28 | 2025-08-28 | 2025-09-01 | 2025-09-03 | 2025-09-07 | 2025-09-14 | 2025-06-11 | 2025-06-13 | 2025-06-20 | 2025-06-27 | 2025-07-02 | 2025-07-03 | 2025-07-09 | 2025-07-09 | 2025-07-10 | 2025-07-13 | 2025-07-14 | 2025-07-19 | 2025-07-19 | 2025-07-21 | 2025-07-24 | 2025-07-26 | 2025-07-26 | 2025-07-30 | 2025-08-01 | 2025-08-02 | 2025-08-03 | 2025-08-09 | 2025-08-14 | 2025-08-21 | 2025-08-21 | 2025-08-21 | 2025-08-25 | 2025-08-25 | 2025-08-28 | 2025-09-03 | 2025-09-10 | 2025-08-03 | 2025-08-21 | 2025-08-23 | 2025-09-14 | 2025-09-08 | 2025-09-14 | 2025-09-19 | 2025-09-22 | 2025-09-27
V_465 | 2025-02-21 | 2025-02-28 | 2025-03-02 | 2025-03-08 | 2025-03-13 | 2025-03-16 | 2025-03-17 | 2025-03-21 | 2025-03-26 | 2025-03-29 | 2025-04-02 | 2025-04-02 | 2025-06-11 | 2025-06-18 | 2025-06-25 | 2025-06-25 | 2025-07-02 | 2025-07-09 | 2025-07-09 | 2025-07-12 | 2025-07-12 | 2025-07-13 | 2025-07-19 | 2025-07-19 | 2025-07-26 | 2025-07-26 | 2025-07-26 | 2025-07-31 | 2025-08-04 | 2025-08-11 | 2025-08-16 | 2025-08-21 | 2025-08-28 | 2025-08-28 | 2025-09-01 | 2025-09-04 | 2025-09-04 | 2025-09-04 | 2025-09-08 | 2025-09-10 | 2025-09-14 | 2025-09-21 | 2025-06-18 | 2025-06-20 | 2025-06-27 | 2025-07-04 | 2025-07-09 | 2025-07-10 | 2025-07-16 | 2025-07-16 | 2025-07-17 | 2025-07-20 | 2025-07-21 | 2025-07-26 | 2025-07-26 | 2025-07-28 | 2025-07-31 | 2025-08-02 | 2025-08-02 | 2025-08-06 | 2025-08-08 | 2025-08-09 | 2025-08-10 | 2025-08-16 | 2025-08-21 | 2025-08-28 | 2025-08-28 | 2025-08-28 | 2025-09-01 | 2025-09-01 | 2025-09-04 | 2025-09-10 | 2025-09-17 | 2025-08-10 | 2025-08-28 | 2025-08-30 | 2025-09-21 | 2025-09-15 | 2025-09-21 | 2025-09-26 | 2025-09-29 | 2025-10-04
V_466 | 2025-02-21 | 2025-02-28 | 2025-03-02 | 2025-03-08 | 2025-03-13 | 2025-03-16 | 2025-03-17 | 2025-03-21 | 2025-03-26 | 2025-03-29 | 2025-04-02 | 2025-04-02 | 2025-06-11 | 2025-06-18 | 2025-06-25 | 2025-06-25 | 2025-07-02 | 2025-07-09 | 2025-07-09 | 2025-07-12 | 2025-07-12 | 2025-07-13 | 2025-07-19 | 2025-07-19 | 2025-07-26 | 2025-07-26 | 2025-07-26 | 2025-07-31 | 2025-08-04 | 2025-08-11 | 2025-08-16 | 2025-08-21 | 2025-08-28 | 2025-08-28 | 2025-09-01 | 2025-09-04 | 2025-09-04 | 2025-09-04 | 2025-09-08 | 2025-09-10 | 2025-09-14 | 2025-09-21 | 2025-06-18 | 2025-06-20 | 2025-06-27 | 2025-07-04 | 2025-07-09 | 2025-07-10 | 2025-07-16 | 2025-07-16 | 2025-07-17 | 2025-07-20 | 2025-07-21 | 2025-07-26 | 2025-07-26 | 2025-07-28 | 2025-07-31 | 2025-08-02 | 2025-08-02 | 2025-08-06 | 2025-08-08 | 2025-08-09 | 2025-08-10 | 2025-08-16 | 2025-08-21 | 2025-08-28 | 2025-08-28 | 2025-08-28 | 2025-09-01 | 2025-09-01 | 2025-09-04 | 2025-09-10 | 2025-09-17 | 2025-08-10 | 2025-08-28 | 2025-08-30 | 2025-09-21 | 2025-09-15 | 2025-09-21 | 2025-09-26 | 2025-09-29 | 2025-10-04
V_467 | 2025-02-21 | 2025-02-28 | 2025-03-02 | 2025-03-08 | 2025-03-13 | 2025-03-16 | 2025-03-17 | 2025-03-21 | 2025-03-26 | 2025-03-29 | 2025-04-02 | 2025-04-02 | 2025-06-11 | 2025-06-18 | 2025-06-25 | 2025-06-25 | 2025-07-02 | 2025-07-09 | 2025-07-09 | 2025-07-12 | 2025-07-12 | 2025-07-13 | 2025-07-19 | 2025-07-19 | 2025-07-26 | 2025-07-26 | 2025-07-26 | 2025-07-31 | 2025-08-04 | 2025-08-11 | 2025-08-16 | 2025-08-21 | 2025-08-28 | 2025-08-28 | 2025-09-01 | 2025-09-04 | 2025-09-04 | 2025-09-04 | 2025-09-08 | 2025-09-10 | 2025-09-14 | 2025-09-21 | 2025-06-18 | 2025-06-20 | 2025-06-27 | 2025-07-04 | 2025-07-09 | 2025-07-10 | 2025-07-16 | 2025-07-16 | 2025-07-17 | 2025-07-20 | 2025-07-21 | 2025-07-26 | 2025-07-26 | 2025-07-28 | 2025-07-31 | 2025-08-02 | 2025-08-02 | 2025-08-06 | 2025-08-08 | 2025-08-09 | 2025-08-10 | 2025-08-16 | 2025-08-21 | 2025-08-28 | 2025-08-28 | 2025-08-28 | 2025-09-01 | 2025-09-01 | 2025-09-04 | 2025-09-10 | 2025-09-17 | 2025-08-10 | 2025-08-28 | 2025-08-30 | 2025-09-21 | 2025-09-15 | 2025-09-21 | 2025-09-26 | 2025-09-29 | 2025-10-04
V_468 | 2025-02-21 | 2025-02-28 | 2025-03-02 | 2025-03-08 | 2025-03-13 | 2025-03-16 | 2025-03-17 | 2025-03-21 | 2025-03-26 | 2025-03-29 | 2025-04-02 | 2025-04-02 | 2025-06-11 | 2025-06-18 | 2025-06-25 | 2025-06-25 | 2025-07-02 | 2025-07-09 | 2025-07-09 | 2025-07-12 | 2025-07-12 | 2025-07-13 | 2025-07-19 | 2025-07-19 | 2025-07-26 | 2025-07-26 | 2025-07-26 | 2025-07-31 | 2025-08-04 | 2025-08-11 | 2025-08-16 | 2025-08-21 | 2025-08-28 | 2025-08-28 | 2025-09-01 | 2025-09-04 | 2025-09-04 | 2025-09-04 | 2025-09-08 | 2025-09-10 | 2025-09-14 | 2025-09-21 | 2025-06-18 | 2025-06-20 | 2025-06-27 | 2025-07-04 | 2025-07-09 | 2025-07-10 | 2025-07-16 | 2025-07-16 | 2025-07-17 | 2025-07-20 | 2025-07-21 | 2025-07-26 | 2025-07-26 | 2025-07-28 | 2025-07-31 | 2025-08-02 | 2025-08-02 | 2025-08-06 | 2025-08-08 | 2025-08-09 | 2025-08-10 | 2025-08-16 | 2025-08-21 | 2025-08-28 | 2025-08-28 | 2025-08-28 | 2025-09-01 | 2025-09-01 | 2025-09-04 | 2025-09-10 | 2025-09-17 | 2025-08-10 | 2025-08-28 | 2025-08-30 | 2025-09-21 | 2025-09-15 | 2025-09-21 | 2025-09-26 | 2025-09-29 | 2025-10-04
V_469 | 2025-02-21 | 2025-02-28 | 2025-03-02 | 2025-03-08 | 2025-03-13 | 2025-03-16 | 2025-03-17 | 2025-03-21 | 2025-03-26 | 2025-03-29 | 2025-04-02 | 2025-04-02 | 2025-06-11 | 2025-06-18 | 2025-06-25 | 2025-06-25 | 2025-07-02 | 2025-07-09 | 2025-07-09 | 2025-07-12 | 2025-07-12 | 2025-07-13 | 2025-07-19 | 2025-07-19 | 2025-07-26 | 2025-07-26 | 2025-07-26 | 2025-07-31 | 2025-08-04 | 2025-08-11 | 2025-08-16 | 2025-08-21 | 2025-08-28 | 2025-08-28 | 2025-09-01 | 2025-09-04 | 2025-09-04 | 2025-09-04 | 2025-09-08 | 2025-09-10 | 2025-09-14 | 2025-09-21 | 2025-06-18 | 2025-06-20 | 2025-06-27 | 2025-07-04 | 2025-07-09 | 2025-07-10 | 2025-07-16 | 2025-07-16 | 2025-07-17 | 2025-07-20 | 2025-07-21 | 2025-07-26 | 2025-07-26 | 2025-07-28 | 2025-07-31 | 2025-08-02 | 2025-08-02 | 2025-08-06 | 2025-08-08 | 2025-08-09 | 2025-08-10 | 2025-08-16 | 2025-08-21 | 2025-08-28 | 2025-08-28 | 2025-08-28 | 2025-09-01 | 2025-09-01 | 2025-09-04 | 2025-09-10 | 2025-09-17 | 2025-08-10 | 2025-08-28 | 2025-08-30 | 2025-09-21 | 2025-09-15 | 2025-09-21 | 2025-09-26 | 2025-09-29 | 2025-10-04
V_470 | 2025-02-21 | 2025-02-28 | 2025-03-02 | 2025-03-08 | 2025-03-13 | 2025-03-16 | 2025-03-17 | 2025-03-21 | 2025-03-26 | 2025-03-29 | 2025-04-02 | 2025-04-02 | 2025-06-11 | 2025-06-18 | 2025-06-25 | 2025-06-25 | 2025-07-02 | 2025-07-09 | 2025-07-09 | 2025-07-12 | 2025-07-12 | 2025-07-13 | 2025-07-19 | 2025-07-19 | 2025-07-26 | 2025-07-26 | 2025-07-26 | 2025-07-31 | 2025-08-04 | 2025-08-11 | 2025-08-16 | 2025-08-21 | 2025-08-28 | 2025-08-28 | 2025-09-01 | 2025-09-04 | 2025-09-04 | 2025-09-04 | 2025-09-08 | 2025-09-10 | 2025-09-14 | 2025-09-21 | 2025-06-18 | 2025-06-20 | 2025-06-27 | 2025-07-04 | 2025-07-09 | 2025-07-10 | 2025-07-16 | 2025-07-16 | 2025-07-17 | 2025-07-20 | 2025-07-21 | 2025-07-26 | 2025-07-26 | 2025-07-28 | 2025-07-31 | 2025-08-02 | 2025-08-02 | 2025-08-06 | 2025-08-08 | 2025-08-09 | 2025-08-10 | 2025-08-16 | 2025-08-21 | 2025-08-28 | 2025-08-28 | 2025-08-28 | 2025-09-01 | 2025-09-01 | 2025-09-04 | 2025-09-10 | 2025-09-17 | 2025-08-10 | 2025-08-28 | 2025-08-30 | 2025-09-21 | 2025-09-15 | 2025-09-21 | 2025-09-26 | 2025-09-29 | 2025-10-04
V_471 | 2025-02-21 | 2025-02-28 | 2025-03-02 | 2025-03-08 | 2025-03-13 | 2025-03-16 | 2025-03-17 | 2025-03-21 | 2025-03-26 | 2025-03-29 | 2025-04-02 | 2025-04-02 | 2025-06-11 | 2025-06-18 | 2025-06-25 | 2025-06-25 | 2025-07-02 | 2025-07-09 | 2025-07-09 | 2025-07-12 | 2025-07-12 | 2025-07-13 | 2025-07-19 | 2025-07-19 | 2025-07-26 | 2025-07-26 | 2025-07-26 | 2025-07-31 | 2025-08-04 | 2025-08-11 | 2025-08-16 | 2025-08-21 | 2025-08-28 | 2025-08-28 | 2025-09-01 | 2025-09-04 | 2025-09-04 | 2025-09-04 | 2025-09-08 | 2025-09-10 | 2025-09-14 | 2025-09-21 | 2025-06-18 | 2025-06-20 | 2025-06-27 | 2025-07-04 | 2025-07-09 | 2025-07-10 | 2025-07-16 | 2025-07-16 | 2025-07-17 | 2025-07-20 | 2025-07-21 | 2025-07-26 | 2025-07-26 | 2025-07-28 | 2025-07-31 | 2025-08-02 | 2025-08-02 | 2025-08-06 | 2025-08-08 | 2025-08-09 | 2025-08-10 | 2025-08-16 | 2025-08-21 | 2025-08-28 | 2025-08-28 | 2025-08-28 | 2025-09-01 | 2025-09-01 | 2025-09-04 | 2025-09-10 | 2025-09-17 | 2025-08-10 | 2025-08-28 | 2025-08-30 | 2025-09-21 | 2025-09-15 | 2025-09-21 | 2025-09-26 | 2025-09-29 | 2025-10-04
V_472 | 2025-02-21 | 2025-02-28 | 2025-03-02 | 2025-03-08 | 2025-03-13 | 2025-03-16 | 2025-03-17 | 2025-03-21 | 2025-03-26 | 2025-03-29 | 2025-04-02 | 2025-04-02 | 2025-06-11 | 2025-06-18 | 2025-06-25 | 2025-06-25 | 2025-07-02 | 2025-07-09 | 2025-07-09 | 2025-07-12 | 2025-07-12 | 2025-07-13 | 2025-07-19 | 2025-07-19 | 2025-07-26 | 2025-07-26 | 2025-07-26 | 2025-07-31 | 2025-08-04 | 2025-08-11 | 2025-08-16 | 2025-08-21 | 2025-08-28 | 2025-08-28 | 2025-09-01 | 2025-09-04 | 2025-09-04 | 2025-09-04 | 2025-09-08 | 2025-09-10 | 2025-09-14 | 2025-09-21 | 2025-06-18 | 2025-06-20 | 2025-06-27 | 2025-07-04 | 2025-07-09 | 2025-07-10 | 2025-07-16 | 2025-07-16 | 2025-07-17 | 2025-07-20 | 2025-07-21 | 2025-07-26 | 2025-07-26 | 2025-07-28 | 2025-07-31 | 2025-08-02 | 2025-08-02 | 2025-08-06 | 2025-08-08 | 2025-08-09 | 2025-08-10 | 2025-08-16 | 2025-08-21 | 2025-08-28 | 2025-08-28 | 2025-08-28 | 2025-09-01 | 2025-09-01 | 2025-09-04 | 2025-09-10 | 2025-09-17 | 2025-08-10 | 2025-08-28 | 2025-08-30 | 2025-09-21 | 2025-09-15 | 2025-09-21 | 2025-09-26 | 2025-09-29 | 2025-10-04
V_473 | 2025-02-28 | 2025-03-07 | 2025-03-09 | 2025-03-15 | 2025-03-20 | 2025-03-23 | 2025-03-24 | 2025-03-28 | 2025-04-02 | 2025-04-05 | 2025-04-09 | 2025-04-09 | 2025-06-18 | 2025-06-25 | 2025-07-02 | 2025-07-02 | 2025-07-09 | 2025-07-16 | 2025-07-16 | 2025-07-19 | 2025-07-19 | 2025-07-20 | 2025-07-26 | 2025-07-26 | 2025-08-02 | 2025-08-02 | 2025-08-02 | 2025-08-07 | 2025-08-11 | 2025-08-18 | 2025-08-23 | 2025-08-28 | 2025-09-04 | 2025-09-04 | 2025-09-08 | 2025-09-11 | 2025-09-11 | 2025-09-11 | 2025-09-15 | 2025-09-17 | 2025-09-21 | 2025-09-28 | 2025-06-25 | 2025-06-27 | 2025-07-04 | 2025-07-11 | 2025-07-16 | 2025-07-17 | 2025-07-23 | 2025-07-23 | 2025-07-24 | 2025-07-27 | 2025-07-28 | 2025-08-02 | 2025-08-02 | 2025-08-04 | 2025-08-07 | 2025-08-09 | 2025-08-09 | 2025-08-13 | 2025-08-15 | 2025-08-16 | 2025-08-17 | 2025-08-23 | 2025-08-28 | 2025-09-04 | 2025-09-04 | 2025-09-04 | 2025-09-08 | 2025-09-08 | 2025-09-11 | 2025-09-17 | 2025-09-24 | 2025-08-17 | 2025-09-04 | 2025-09-06 | 2025-09-28 | 2025-09-22 | 2025-09-28 | 2025-10-03 | 2025-10-06 | 2025-10-11
V_474 | 2025-02-28 | 2025-03-07 | 2025-03-09 | 2025-03-15 | 2025-03-20 | 2025-03-23 | 2025-03-24 | 2025-03-28 | 2025-04-02 | 2025-04-05 | 2025-04-09 | 2025-04-09 | 2025-06-18 | 2025-06-25 | 2025-07-02 | 2025-07-02 | 2025-07-09 | 2025-07-16 | 2025-07-16 | 2025-07-19 | 2025-07-19 | 2025-07-20 | 2025-07-26 | 2025-07-26 | 2025-08-02 | 2025-08-02 | 2025-08-02 | 2025-08-07 | 2025-08-11 | 2025-08-18 | 2025-08-23 | 2025-08-28 | 2025-09-04 | 2025-09-04 | 2025-09-08 | 2025-09-11 | 2025-09-11 | 2025-09-11 | 2025-09-15 | 2025-09-17 | 2025-09-21 | 2025-09-28 | 2025-06-25 | 2025-06-27 | 2025-07-04 | 2025-07-11 | 2025-07-16 | 2025-07-17 | 2025-07-23 | 2025-07-23 | 2025-07-24 | 2025-07-27 | 2025-07-28 | 2025-08-02 | 2025-08-02 | 2025-08-04 | 2025-08-07 | 2025-08-09 | 2025-08-09 | 2025-08-13 | 2025-08-15 | 2025-08-16 | 2025-08-17 | 2025-08-23 | 2025-08-28 | 2025-09-04 | 2025-09-04 | 2025-09-04 | 2025-09-08 | 2025-09-08 | 2025-09-11 | 2025-09-17 | 2025-09-24 | 2025-08-17 | 2025-09-04 | 2025-09-06 | 2025-09-28 | 2025-09-22 | 2025-09-28 | 2025-10-03 | 2025-10-06 | 2025-10-11
V_475 | 2025-02-28 | 2025-03-07 | 2025-03-09 | 2025-03-15 | 2025-03-20 | 2025-03-23 | 2025-03-24 | 2025-03-28 | 2025-04-02 | 2025-04-05 | 2025-04-09 | 2025-04-09 | 2025-06-18 | 2025-06-25 | 2025-07-02 | 2025-07-02 | 2025-07-09 | 2025-07-16 | 2025-07-16 | 2025-07-19 | 2025-07-19 | 2025-07-20 | 2025-07-26 | 2025-07-26 | 2025-08-02 | 2025-08-02 | 2025-08-02 | 2025-08-07 | 2025-08-11 | 2025-08-18 | 2025-08-23 | 2025-08-28 | 2025-09-04 | 2025-09-04 | 2025-09-08 | 2025-09-11 | 2025-09-11 | 2025-09-11 | 2025-09-15 | 2025-09-17 | 2025-09-21 | 2025-09-28 | 2025-06-25 | 2025-06-27 | 2025-07-04 | 2025-07-11 | 2025-07-16 | 2025-07-17 | 2025-07-23 | 2025-07-23 | 2025-07-24 | 2025-07-27 | 2025-07-28 | 2025-08-02 | 2025-08-02 | 2025-08-04 | 2025-08-07 | 2025-08-09 | 2025-08-09 | 2025-08-13 | 2025-08-15 | 2025-08-16 | 2025-08-17 | 2025-08-23 | 2025-08-28 | 2025-09-04 | 2025-09-04 | 2025-09-04 | 2025-09-08 | 2025-09-08 | 2025-09-11 | 2025-09-17 | 2025-09-24 | 2025-08-17 | 2025-09-04 | 2025-09-06 | 2025-09-28 | 2025-09-22 | 2025-09-28 | 2025-10-03 | 2025-10-06 | 2025-10-11
V_476 | 2025-02-28 | 2025-03-07 | 2025-03-09 | 2025-03-15 | 2025-03-20 | 2025-03-23 | 2025-03-24 | 2025-03-28 | 2025-04-02 | 2025-04-05 | 2025-04-09 | 2025-04-09 | 2025-06-18 | 2025-06-25 | 2025-07-02 | 2025-07-02 | 2025-07-09 | 2025-07-16 | 2025-07-16 | 2025-07-19 | 2025-07-19 | 2025-07-20 | 2025-07-26 | 2025-07-26 | 2025-08-02 | 2025-08-02 | 2025-08-02 | 2025-08-07 | 2025-08-11 | 2025-08-18 | 2025-08-23 | 2025-08-28 | 2025-09-04 | 2025-09-04 | 2025-09-08 | 2025-09-11 | 2025-09-11 | 2025-09-11 | 2025-09-15 | 2025-09-17 | 2025-09-21 | 2025-09-28 | 2025-06-25 | 2025-06-27 | 2025-07-04 | 2025-07-11 | 2025-07-16 | 2025-07-17 | 2025-07-23 | 2025-07-23 | 2025-07-24 | 2025-07-27 | 2025-07-28 | 2025-08-02 | 2025-08-02 | 2025-08-04 | 2025-08-07 | 2025-08-09 | 2025-08-09 | 2025-08-13 | 2025-08-15 | 2025-08-16 | 2025-08-17 | 2025-08-23 | 2025-08-28 | 2025-09-04 | 2025-09-04 | 2025-09-04 | 2025-09-08 | 2025-09-08 | 2025-09-11 | 2025-09-17 | 2025-09-24 | 2025-08-17 | 2025-09-04 | 2025-09-06 | 2025-09-28 | 2025-09-22 | 2025-09-28 | 2025-10-03 | 2025-10-06 | 2025-10-11
V_477 | 2025-02-28 | 2025-03-07 | 2025-03-09 | 2025-03-15 | 2025-03-20 | 2025-03-23 | 2025-03-24 | 2025-03-28 | 2025-04-02 | 2025-04-05 | 2025-04-09 | 2025-04-09 | 2025-06-18 | 2025-06-25 | 2025-07-02 | 2025-07-02 | 2025-07-09 | 2025-07-16 | 2025-07-16 | 2025-07-19 | 2025-07-19 | 2025-07-20 | 2025-07-26 | 2025-07-26 | 2025-08-02 | 2025-08-02 | 2025-08-02 | 2025-08-07 | 2025-08-11 | 2025-08-18 | 2025-08-23 | 2025-08-28 | 2025-09-04 | 2025-09-04 | 2025-09-08 | 2025-09-11 | 2025-09-11 | 2025-09-11 | 2025-09-15 | 2025-09-17 | 2025-09-21 | 2025-09-28 | 2025-06-25 | 2025-06-27 | 2025-07-04 | 2025-07-11 | 2025-07-16 | 2025-07-17 | 2025-07-23 | 2025-07-23 | 2025-07-24 | 2025-07-27 | 2025-07-28 | 2025-08-02 | 2025-08-02 | 2025-08-04 | 2025-08-07 | 2025-08-09 | 2025-08-09 | 2025-08-13 | 2025-08-15 | 2025-08-16 | 2025-08-17 | 2025-08-23 | 2025-08-28 | 2025-09-04 | 2025-09-04 | 2025-09-04 | 2025-09-08 | 2025-09-08 | 2025-09-11 | 2025-09-17 | 2025-09-24 | 2025-08-17 | 2025-09-04 | 2025-09-06 | 2025-09-28 | 2025-09-22 | 2025-09-28 | 2025-10-03 | 2025-10-06 | 2025-10-11
V_478 | 2025-02-28 | 2025-03-07 | 2025-03-09 | 2025-03-15 | 2025-03-20 | 2025-03-23 | 2025-03-24 | 2025-03-28 | 2025-04-02 | 2025-04-05 | 2025-04-09 | 2025-04-09 | 2025-06-18 | 2025-06-25 | 2025-07-02 | 2025-07-02 | 2025-07-09 | 2025-07-16 | 2025-07-16 | 2025-07-19 | 2025-07-19 | 2025-07-20 | 2025-07-26 | 2025-07-26 | 2025-08-02 | 2025-08-02 | 2025-08-02 | 2025-08-07 | 2025-08-11 | 2025-08-18 | 2025-08-23 | 2025-08-28 | 2025-09-04 | 2025-09-04 | 2025-09-08 | 2025-09-11 | 2025-09-11 | 2025-09-11 | 2025-09-15 | 2025-09-17 | 2025-09-21 | 2025-09-28 | 2025-06-25 | 2025-06-27 | 2025-07-04 | 2025-07-11 | 2025-07-16 | 2025-07-17 | 2025-07-23 | 2025-07-23 | 2025-07-24 | 2025-07-27 | 2025-07-28 | 2025-08-02 | 2025-08-02 | 2025-08-04 | 2025-08-07 | 2025-08-09 | 2025-08-09 | 2025-08-13 | 2025-08-15 | 2025-08-16 | 2025-08-17 | 2025-08-23 | 2025-08-28 | 2025-09-04 | 2025-09-04 | 2025-09-04 | 2025-09-08 | 2025-09-08 | 2025-09-11 | 2025-09-17 | 2025-09-24 | 2025-08-17 | 2025-09-04 | 2025-09-06 | 2025-09-28 | 2025-09-22 | 2025-09-28 | 2025-10-03 | 2025-10-06 | 2025-10-11
V_479 | 2025-02-28 | 2025-03-07 | 2025-03-09 | 2025-03-15 | 2025-03-20 | 2025-03-23 | 2025-03-24 | 2025-03-28 | 2025-04-02 | 2025-04-05 | 2025-04-09 | 2025-04-09 | 2025-06-18 | 2025-06-25 | 2025-07-02 | 2025-07-02 | 2025-07-09 | 2025-07-16 | 2025-07-16 | 2025-07-19 | 2025-07-19 | 2025-07-20 | 2025-07-26 | 2025-07-26 | 2025-08-02 | 2025-08-02 | 2025-08-02 | 2025-08-07 | 2025-08-11 | 2025-08-18 | 2025-08-23 | 2025-08-28 | 2025-09-04 | 2025-09-04 | 2025-09-08 | 2025-09-11 | 2025-09-11 | 2025-09-11 | 2025-09-15 | 2025-09-17 | 2025-09-21 | 2025-09-28 | 2025-06-25 | 2025-06-27 | 2025-07-04 | 2025-07-11 | 2025-07-16 | 2025-07-17 | 2025-07-23 | 2025-07-23 | 2025-07-24 | 2025-07-27 | 2025-07-28 | 2025-08-02 | 2025-08-02 | 2025-08-04 | 2025-08-07 | 2025-08-09 | 2025-08-09 | 2025-08-13 | 2025-08-15 | 2025-08-16 | 2025-08-17 | 2025-08-23 | 2025-08-28 | 2025-09-04 | 2025-09-04 | 2025-09-04 | 2025-09-08 | 2025-09-08 | 2025-09-11 | 2025-09-17 | 2025-09-24 | 2025-08-17 | 2025-09-04 | 2025-09-06 | 2025-09-28 | 2025-09-22 | 2025-09-28 | 2025-10-03 | 2025-10-06 | 2025-10-11
V_480 | 2025-02-28 | 2025-03-07 | 2025-03-09 | 2025-03-15 | 2025-03-20 | 2025-03-23 | 2025-03-24 | 2025-03-28 | 2025-04-02 | 2025-04-05 | 2025-04-09 | 2025-04-09 | 2025-06-18 | 2025-06-25 | 2025-07-02 | 2025-07-02 | 2025-07-09 | 2025-07-16 | 2025-07-16 | 2025-07-19 | 2025-07-19 | 2025-07-20 | 2025-07-26 | 2025-07-26 | 2025-08-02 | 2025-08-02 | 2025-08-02 | 2025-08-07 | 2025-08-11 | 2025-08-18 | 2025-08-23 | 2025-08-28 | 2025-09-04 | 2025-09-04 | 2025-09-08 | 2025-09-11 | 2025-09-11 | 2025-09-11 | 2025-09-15 | 2025-09-17 | 2025-09-21 | 2025-09-28 | 2025-06-25 | 2025-06-27 | 2025-07-04 | 2025-07-11 | 2025-07-16 | 2025-07-17 | 2025-07-23 | 2025-07-23 | 2025-07-24 | 2025-07-27 | 2025-07-28 | 2025-08-02 | 2025-08-02 | 2025-08-04 | 2025-08-07 | 2025-08-09 | 2025-08-09 | 2025-08-13 | 2025-08-15 | 2025-08-16 | 2025-08-17 | 2025-08-23 | 2025-08-28 | 2025-09-04 | 2025-09-04 | 2025-09-04 | 2025-09-08 | 2025-09-08 | 2025-09-11 | 2025-09-17 | 2025-09-24 | 2025-08-17 | 2025-09-04 | 2025-09-06 | 2025-09-28 | 2025-09-22 | 2025-09-28 | 2025-10-03 | 2025-10-06 | 2025-10-11
V_481 | 2025-03-07 | 2025-03-14 | 2025-03-16 | 2025-03-22 | 2025-03-27 | 2025-03-30 | 2025-03-31 | 2025-04-04 | 2025-04-09 | 2025-04-12 | 2025-04-16 | 2025-04-16 | 2025-06-25 | 2025-07-02 | 2025-07-09 | 2025-07-09 | 2025-07-16 | 2025-07-23 | 2025-07-23 | 2025-07-26 | 2025-07-26 | 2025-07-27 | 2025-08-02 | 2025-08-02 | 2025-08-09 | 2025-08-09 | 2025-08-09 | 2025-08-14 | 2025-08-18 | 2025-08-25 | 2025-08-30 | 2025-09-04 | 2025-09-11 | 2025-09-11 | 2025-09-15 | 2025-09-18 | 2025-09-18 | 2025-09-18 | 2025-09-22 | 2025-09-24 | 2025-09-28 | 2025-10-05 | 2025-07-02 | 2025-07-04 | 2025-07-11 | 2025-07-18 | 2025-07-23 | 2025-07-24 | 2025-07-30 | 2025-07-30 | 2025-07-31 | 2025-08-03 | 2025-08-04 | 2025-08-09 | 2025-08-09 | 2025-08-11 | 2025-08-14 | 2025-08-16 | 2025-08-16 | 2025-08-20 | 2025-08-22 | 2025-08-23 | 2025-08-24 | 2025-08-30 | 2025-09-04 | 2025-09-11 | 2025-09-11 | 2025-09-11 | 2025-09-15 | 2025-09-15 | 2025-09-18 | 2025-09-24 | 2025-10-01 | 2025-08-24 | 2025-09-11 | 2025-09-13 | 2025-10-05 | 2025-09-29 | 2025-10-05 | 2025-10-10 | 2025-10-13 | 2025-10-18
V_482 | 2025-03-07 | 2025-03-14 | 2025-03-16 | 2025-03-22 | 2025-03-27 | 2025-03-30 | 2025-03-31 | 2025-04-04 | 2025-04-09 | 2025-04-12 | 2025-04-16 | 2025-04-16 | 2025-06-25 | 2025-07-02 | 2025-07-09 | 2025-07-09 | 2025-07-16 | 2025-07-23 | 2025-07-23 | 2025-07-26 | 2025-07-26 | 2025-07-27 | 2025-08-02 | 2025-08-02 | 2025-08-09 | 2025-08-09 | 2025-08-09 | 2025-08-14 | 2025-08-18 | 2025-08-25 | 2025-08-30 | 2025-09-04 | 2025-09-11 | 2025-09-11 | 2025-09-15 | 2025-09-18 | 2025-09-18 | 2025-09-18 | 2025-09-22 | 2025-09-24 | 2025-09-28 | 2025-10-05 | 2025-07-02 | 2025-07-04 | 2025-07-11 | 2025-07-18 | 2025-07-23 | 2025-07-24 | 2025-07-30 | 2025-07-30 | 2025-07-31 | 2025-08-03 | 2025-08-04 | 2025-08-09 | 2025-08-09 | 2025-08-11 | 2025-08-14 | 2025-08-16 | 2025-08-16 | 2025-08-20 | 2025-08-22 | 2025-08-23 | 2025-08-24 | 2025-08-30 | 2025-09-04 | 2025-09-11 | 2025-09-11 | 2025-09-11 | 2025-09-15 | 2025-09-15 | 2025-09-18 | 2025-09-24 | 2025-10-01 | 2025-08-24 | 2025-09-11 | 2025-09-13 | 2025-10-05 | 2025-09-29 | 2025-10-05 | 2025-10-10 | 2025-10-13 | 2025-10-18
V_483 | 2025-03-07 | 2025-03-14 | 2025-03-16 | 2025-03-22 | 2025-03-27 | 2025-03-30 | 2025-03-31 | 2025-04-04 | 2025-04-09 | 2025-04-12 | 2025-04-16 | 2025-04-16 | 2025-06-25 | 2025-07-02 | 2025-07-09 | 2025-07-09 | 2025-07-16 | 2025-07-23 | 2025-07-23 | 2025-07-26 | 2025-07-26 | 2025-07-27 | 2025-08-02 | 2025-08-02 | 2025-08-09 | 2025-08-09 | 2025-08-09 | 2025-08-14 | 2025-08-18 | 2025-08-25 | 2025-08-30 | 2025-09-04 | 2025-09-11 | 2025-09-11 | 2025-09-15 | 2025-09-18 | 2025-09-18 | 2025-09-18 | 2025-09-22 | 2025-09-24 | 2025-09-28 | 2025-10-05 | 2025-07-02 | 2025-07-04 | 2025-07-11 | 2025-07-18 | 2025-07-23 | 2025-07-24 | 2025-07-30 | 2025-07-30 | 2025-07-31 | 2025-08-03 | 2025-08-04 | 2025-08-09 | 2025-08-09 | 2025-08-11 | 2025-08-14 | 2025-08-16 | 2025-08-16 | 2025-08-20 | 2025-08-22 | 2025-08-23 | 2025-08-24 | 2025-08-30 | 2025-09-04 | 2025-09-11 | 2025-09-11 | 2025-09-11 | 2025-09-15 | 2025-09-15 | 2025-09-18 | 2025-09-24 | 2025-10-01 | 2025-08-24 | 2025-09-11 | 2025-09-13 | 2025-10-05 | 2025-09-29 | 2025-10-05 | 2025-10-10 | 2025-10-13 | 2025-10-18
V_484 | 2025-03-07 | 2025-03-14 | 2025-03-16 | 2025-03-22 | 2025-03-27 | 2025-03-30 | 2025-03-31 | 2025-04-04 | 2025-04-09 | 2025-04-12 | 2025-04-16 | 2025-04-16 | 2025-06-25 | 2025-07-02 | 2025-07-09 | 2025-07-09 | 2025-07-16 | 2025-07-23 | 2025-07-23 | 2025-07-26 | 2025-07-26 | 2025-07-27 | 2025-08-02 | 2025-08-02 | 2025-08-09 | 2025-08-09 | 2025-08-09 | 2025-08-14 | 2025-08-18 | 2025-08-25 | 2025-08-30 | 2025-09-04 | 2025-09-11 | 2025-09-11 | 2025-09-15 | 2025-09-18 | 2025-09-18 | 2025-09-18 | 2025-09-22 | 2025-09-24 | 2025-09-28 | 2025-10-05 | 2025-07-02 | 2025-07-04 | 2025-07-11 | 2025-07-18 | 2025-07-23 | 2025-07-24 | 2025-07-30 | 2025-07-30 | 2025-07-31 | 2025-08-03 | 2025-08-04 | 2025-08-09 | 2025-08-09 | 2025-08-11 | 2025-08-14 | 2025-08-16 | 2025-08-16 | 2025-08-20 | 2025-08-22 | 2025-08-23 | 2025-08-24 | 2025-08-30 | 2025-09-04 | 2025-09-11 | 2025-09-11 | 2025-09-11 | 2025-09-15 | 2025-09-15 | 2025-09-18 | 2025-09-24 | 2025-10-01 | 2025-08-24 | 2025-09-11 | 2025-09-13 | 2025-10-05 | 2025-09-29 | 2025-10-05 | 2025-10-10 | 2025-10-13 | 2025-10-18
V_485 | 2025-03-07 | 2025-03-14 | 2025-03-16 | 2025-03-22 | 2025-03-27 | 2025-03-30 | 2025-03-31 | 2025-04-04 | 2025-04-09 | 2025-04-12 | 2025-04-16 | 2025-04-16 | 2025-06-25 | 2025-07-02 | 2025-07-09 | 2025-07-09 | 2025-07-16 | 2025-07-23 | 2025-07-23 | 2025-07-26 | 2025-07-26 | 2025-07-27 | 2025-08-02 | 2025-08-02 | 2025-08-09 | 2025-08-09 | 2025-08-09 | 2025-08-14 | 2025-08-18 | 2025-08-25 | 2025-08-30 | 2025-09-04 | 2025-09-11 | 2025-09-11 | 2025-09-15 | 2025-09-18 | 2025-09-18 | 2025-09-18 | 2025-09-22 | 2025-09-24 | 2025-09-28 | 2025-10-05 | 2025-07-02 | 2025-07-04 | 2025-07-11 | 2025-07-18 | 2025-07-23 | 2025-07-24 | 2025-07-30 | 2025-07-30 | 2025-07-31 | 2025-08-03 | 2025-08-04 | 2025-08-09 | 2025-08-09 | 2025-08-11 | 2025-08-14 | 2025-08-16 | 2025-08-16 | 2025-08-20 | 2025-08-22 | 2025-08-23 | 2025-08-24 | 2025-08-30 | 2025-09-04 | 2025-09-11 | 2025-09-11 | 2025-09-11 | 2025-09-15 | 2025-09-15 | 2025-09-18 | 2025-09-24 | 2025-10-01 | 2025-08-24 | 2025-09-11 | 2025-09-13 | 2025-10-05 | 2025-09-29 | 2025-10-05 | 2025-10-10 | 2025-10-13 | 2025-10-18
V_486 | 2025-03-07 | 2025-03-14 | 2025-03-16 | 2025-03-22 | 2025-03-27 | 2025-03-30 | 2025-03-31 | 2025-04-04 | 2025-04-09 | 2025-04-12 | 2025-04-16 | 2025-04-16 | 2025-06-25 | 2025-07-02 | 2025-07-09 | 2025-07-09 | 2025-07-16 | 2025-07-23 | 2025-07-23 | 2025-07-26 | 2025-07-26 | 2025-07-27 | 2025-08-02 | 2025-08-02 | 2025-08-09 | 2025-08-09 | 2025-08-09 | 2025-08-14 | 2025-08-18 | 2025-08-25 | 2025-08-30 | 2025-09-04 | 2025-09-11 | 2025-09-11 | 2025-09-15 | 2025-09-18 | 2025-09-18 | 2025-09-18 | 2025-09-22 | 2025-09-24 | 2025-09-28 | 2025-10-05 | 2025-07-02 | 2025-07-04 | 2025-07-11 | 2025-07-18 | 2025-07-23 | 2025-07-24 | 2025-07-30 | 2025-07-30 | 2025-07-31 | 2025-08-03 | 2025-08-04 | 2025-08-09 | 2025-08-09 | 2025-08-11 | 2025-08-14 | 2025-08-16 | 2025-08-16 | 2025-08-20 | 2025-08-22 | 2025-08-23 | 2025-08-24 | 2025-08-30 | 2025-09-04 | 2025-09-11 | 2025-09-11 | 2025-09-11 | 2025-09-15 | 2025-09-15 | 2025-09-18 | 2025-09-24 | 2025-10-01 | 2025-08-24 | 2025-09-11 | 2025-09-13 | 2025-10-05 | 2025-09-29 | 2025-10-05 | 2025-10-10 | 2025-10-13 | 2025-10-18
V_487 | 2025-03-07 | 2025-03-14 | 2025-03-16 | 2025-03-22 | 2025-03-27 | 2025-03-30 | 2025-03-31 | 2025-04-04 | 2025-04-09 | 2025-04-12 | 2025-04-16 | 2025-04-16 | 2025-06-25 | 2025-07-02 | 2025-07-09 | 2025-07-09 | 2025-07-16 | 2025-07-23 | 2025-07-23 | 2025-07-26 | 2025-07-26 | 2025-07-27 | 2025-08-02 | 2025-08-02 | 2025-08-09 | 2025-08-09 | 2025-08-09 | 2025-08-14 | 2025-08-18 | 2025-08-25 | 2025-08-30 | 2025-09-04 | 2025-09-11 | 2025-09-11 | 2025-09-15 | 2025-09-18 | 2025-09-18 | 2025-09-18 | 2025-09-22 | 2025-09-24 | 2025-09-28 | 2025-10-05 | 2025-07-02 | 2025-07-04 | 2025-07-11 | 2025-07-18 | 2025-07-23 | 2025-07-24 | 2025-07-30 | 2025-07-30 | 2025-07-31 | 2025-08-03 | 2025-08-04 | 2025-08-09 | 2025-08-09 | 2025-08-11 | 2025-08-14 | 2025-08-16 | 2025-08-16 | 2025-08-20 | 2025-08-22 | 2025-08-23 | 2025-08-24 | 2025-08-30 | 2025-09-04 | 2025-09-11 | 2025-09-11 | 2025-09-11 | 2025-09-15 | 2025-09-15 | 2025-09-18 | 2025-09-24 | 2025-10-01 | 2025-08-24 | 2025-09-11 | 2025-09-13 | 2025-10-05 | 2025-09-29 | 2025-10-05 | 2025-10-10 | 2025-10-13 | 2025-10-18
V_488 | 2025-03-07 | 2025-03-14 | 2025-03-16 | 2025-03-22 | 2025-03-27 | 2025-03-30 | 2025-03-31 | 2025-04-04 | 2025-04-09 | 2025-04-12 | 2025-04-16 | 2025-04-16 | 2025-06-25 | 2025-07-02 | 2025-07-09 | 2025-07-09 | 2025-07-16 | 2025-07-23 | 2025-07-23 | 2025-07-26 | 2025-07-26 | 2025-07-27 | 2025-08-02 | 2025-08-02 | 2025-08-09 | 2025-08-09 | 2025-08-09 | 2025-08-14 | 2025-08-18 | 2025-08-25 | 2025-08-30 | 2025-09-04 | 2025-09-11 | 2025-09-11 | 2025-09-15 | 2025-09-18 | 2025-09-18 | 2025-09-18 | 2025-09-22 | 2025-09-24 | 2025-09-28 | 2025-10-05 | 2025-07-02 | 2025-07-04 | 2025-07-11 | 2025-07-18 | 2025-07-23 | 2025-07-24 | 2025-07-30 | 2025-07-30 | 2025-07-31 | 2025-08-03 | 2025-08-04 | 2025-08-09 | 2025-08-09 | 2025-08-11 | 2025-08-14 | 2025-08-16 | 2025-08-16 | 2025-08-20 | 2025-08-22 | 2025-08-23 | 2025-08-24 | 2025-08-30 | 2025-09-04 | 2025-09-11 | 2025-09-11 | 2025-09-11 | 2025-09-15 | 2025-09-15 | 2025-09-18 | 2025-09-24 | 2025-10-01 | 2025-08-24 | 2025-09-11 | 2025-09-13 | 2025-10-05 | 2025-09-29 | 2025-10-05 | 2025-10-10 | 2025-10-13 | 2025-10-18
V_489 | 2025-03-14 | 2025-03-21 | 2025-03-23 | 2025-03-29 | 2025-04-03 | 2025-04-06 | 2025-04-07 | 2025-04-11 | 2025-04-16 | 2025-04-19 | 2025-04-23 | 2025-04-23 | 2025-07-02 | 2025-07-09 | 2025-07-16 | 2025-07-16 | 2025-07-23 | 2025-07-30 | 2025-07-30 | 2025-08-02 | 2025-08-02 | 2025-08-03 | 2025-08-09 | 2025-08-09 | 2025-08-16 | 2025-08-16 | 2025-08-16 | 2025-08-21 | 2025-08-25 | 2025-09-01 | 2025-09-06 | 2025-09-11 | 2025-09-18 | 2025-09-18 | 2025-09-22 | 2025-09-25 | 2025-09-25 | 2025-09-25 | 2025-09-29 | 2025-10-01 | 2025-10-05 | 2025-10-12 | 2025-07-09 | 2025-07-11 | 2025-07-18 | 2025-07-25 | 2025-07-30 | 2025-07-31 | 2025-08-06 | 2025-08-06 | 2025-08-07 | 2025-08-10 | 2025-08-11 | 2025-08-16 | 2025-08-16 | 2025-08-18 | 2025-08-21 | 2025-08-23 | 2025-08-23 | 2025-08-27 | 2025-08-29 | 2025-08-30 | 2025-08-31 | 2025-09-06 | 2025-09-11 | 2025-09-18 | 2025-09-18 | 2025-09-18 | 2025-09-22 | 2025-09-22 | 2025-09-25 | 2025-10-01 | 2025-10-08 | 2025-08-31 | 2025-09-18 | 2025-09-20 | 2025-10-12 | 2025-10-06 | 2025-10-12 | 2025-10-17 | 2025-10-20 | 2025-10-25
V_490 | 2025-03-14 | 2025-03-21 | 2025-03-23 | 2025-03-29 | 2025-04-03 | 2025-04-06 | 2025-04-07 | 2025-04-11 | 2025-04-16 | 2025-04-19 | 2025-04-23 | 2025-04-23 | 2025-07-02 | 2025-07-09 | 2025-07-16 | 2025-07-16 | 2025-07-23 | 2025-07-30 | 2025-07-30 | 2025-08-02 | 2025-08-02 | 2025-08-03 | 2025-08-09 | 2025-08-09 | 2025-08-16 | 2025-08-16 | 2025-08-16 | 2025-08-21 | 2025-08-25 | 2025-09-01 | 2025-09-06 | 2025-09-11 | 2025-09-18 | 2025-09-18 | 2025-09-22 | 2025-09-25 | 2025-09-25 | 2025-09-25 | 2025-09-29 | 2025-10-01 | 2025-10-05 | 2025-10-12 | 2025-07-09 | 2025-07-11 | 2025-07-18 | 2025-07-25 | 2025-07-30 | 2025-07-31 | 2025-08-06 | 2025-08-06 | 2025-08-07 | 2025-08-10 | 2025-08-11 | 2025-08-16 | 2025-08-16 | 2025-08-18 | 2025-08-21 | 2025-08-23 | 2025-08-23 | 2025-08-27 | 2025-08-29 | 2025-08-30 | 2025-08-31 | 2025-09-06 | 2025-09-11 | 2025-09-18 | 2025-09-18 | 2025-09-18 | 2025-09-22 | 2025-09-22 | 2025-09-25 | 2025-10-01 | 2025-10-08 | 2025-08-31 | 2025-09-18 | 2025-09-20 | 2025-10-12 | 2025-10-06 | 2025-10-12 | 2025-10-17 | 2025-10-20 | 2025-10-25
V_491 | 2025-03-14 | 2025-03-21 | 2025-03-23 | 2025-03-29 | 2025-04-03 | 2025-04-06 | 2025-04-07 | 2025-04-11 | 2025-04-16 | 2025-04-19 | 2025-04-23 | 2025-04-23 | 2025-07-02 | 2025-07-09 | 2025-07-16 | 2025-07-16 | 2025-07-23 | 2025-07-30 | 2025-07-30 | 2025-08-02 | 2025-08-02 | 2025-08-03 | 2025-08-09 | 2025-08-09 | 2025-08-16 | 2025-08-16 | 2025-08-16 | 2025-08-21 | 2025-08-25 | 2025-09-01 | 2025-09-06 | 2025-09-11 | 2025-09-18 | 2025-09-18 | 2025-09-22 | 2025-09-25 | 2025-09-25 | 2025-09-25 | 2025-09-29 | 2025-10-01 | 2025-10-05 | 2025-10-12 | 2025-07-09 | 2025-07-11 | 2025-07-18 | 2025-07-25 | 2025-07-30 | 2025-07-31 | 2025-08-06 | 2025-08-06 | 2025-08-07 | 2025-08-10 | 2025-08-11 | 2025-08-16 | 2025-08-16 | 2025-08-18 | 2025-08-21 | 2025-08-23 | 2025-08-23 | 2025-08-27 | 2025-08-29 | 2025-08-30 | 2025-08-31 | 2025-09-06 | 2025-09-11 | 2025-09-18 | 2025-09-18 | 2025-09-18 | 2025-09-22 | 2025-09-22 | 2025-09-25 | 2025-10-01 | 2025-10-08 | 2025-08-31 | 2025-09-18 | 2025-09-20 | 2025-10-12 | 2025-10-06 | 2025-10-12 | 2025-10-17 | 2025-10-20 | 2025-10-25
V_492 | 2025-03-14 | 2025-03-21 | 2025-03-23 | 2025-03-29 | 2025-04-03 | 2025-04-06 | 2025-04-07 | 2025-04-11 | 2025-04-16 | 2025-04-19 | 2025-04-23 | 2025-04-23 | 2025-07-02 | 2025-07-09 | 2025-07-16 | 2025-07-16 | 2025-07-23 | 2025-07-30 | 2025-07-30 | 2025-08-02 | 2025-08-02 | 2025-08-03 | 2025-08-09 | 2025-08-09 | 2025-08-16 | 2025-08-16 | 2025-08-16 | 2025-08-21 | 2025-08-25 | 2025-09-01 | 2025-09-06 | 2025-09-11 | 2025-09-18 | 2025-09-18 | 2025-09-22 | 2025-09-25 | 2025-09-25 | 2025-09-25 | 2025-09-29 | 2025-10-01 | 2025-10-05 | 2025-10-12 | 2025-07-09 | 2025-07-11 | 2025-07-18 | 2025-07-25 | 2025-07-30 | 2025-07-31 | 2025-08-06 | 2025-08-06 | 2025-08-07 | 2025-08-10 | 2025-08-11 | 2025-08-16 | 2025-08-16 | 2025-08-18 | 2025-08-21 | 2025-08-23 | 2025-08-23 | 2025-08-27 | 2025-08-29 | 2025-08-30 | 2025-08-31 | 2025-09-06 | 2025-09-11 | 2025-09-18 | 2025-09-18 | 2025-09-18 | 2025-09-22 | 2025-09-22 | 2025-09-25 | 2025-10-01 | 2025-10-08 | 2025-08-31 | 2025-09-18 | 2025-09-20 | 2025-10-12 | 2025-10-06 | 2025-10-12 | 2025-10-17 | 2025-10-20 | 2025-10-25
V_493 | 2025-03-14 | 2025-03-21 | 2025-03-23 | 2025-03-29 | 2025-04-03 | 2025-04-06 | 2025-04-07 | 2025-04-11 | 2025-04-16 | 2025-04-19 | 2025-04-23 | 2025-04-23 | 2025-07-02 | 2025-07-09 | 2025-07-16 | 2025-07-16 | 2025-07-23 | 2025-07-30 | 2025-07-30 | 2025-08-02 | 2025-08-02 | 2025-08-03 | 2025-08-09 | 2025-08-09 | 2025-08-16 | 2025-08-16 | 2025-08-16 | 2025-08-21 | 2025-08-25 | 2025-09-01 | 2025-09-06 | 2025-09-11 | 2025-09-18 | 2025-09-18 | 2025-09-22 | 2025-09-25 | 2025-09-25 | 2025-09-25 | 2025-09-29 | 2025-10-01 | 2025-10-05 | 2025-10-12 | 2025-07-09 | 2025-07-11 | 2025-07-18 | 2025-07-25 | 2025-07-30 | 2025-07-31 | 2025-08-06 | 2025-08-06 | 2025-08-07 | 2025-08-10 | 2025-08-11 | 2025-08-16 | 2025-08-16 | 2025-08-18 | 2025-08-21 | 2025-08-23 | 2025-08-23 | 2025-08-27 | 2025-08-29 | 2025-08-30 | 2025-08-31 | 2025-09-06 | 2025-09-11 | 2025-09-18 | 2025-09-18 | 2025-09-18 | 2025-09-22 | 2025-09-22 | 2025-09-25 | 2025-10-01 | 2025-10-08 | 2025-08-31 | 2025-09-18 | 2025-09-20 | 2025-10-12 | 2025-10-06 | 2025-10-12 | 2025-10-17 | 2025-10-20 | 2025-10-25
V_494 | 2025-03-14 | 2025-03-21 | 2025-03-23 | 2025-03-29 | 2025-04-03 | 2025-04-06 | 2025-04-07 | 2025-04-11 | 2025-04-16 | 2025-04-19 | 2025-04-23 | 2025-04-23 | 2025-07-02 | 2025-07-09 | 2025-07-16 | 2025-07-16 | 2025-07-23 | 2025-07-30 | 2025-07-30 | 2025-08-02 | 2025-08-02 | 2025-08-03 | 2025-08-09 | 2025-08-09 | 2025-08-16 | 2025-08-16 | 2025-08-16 | 2025-08-21 | 2025-08-25 | 2025-09-01 | 2025-09-06 | 2025-09-11 | 2025-09-18 | 2025-09-18 | 2025-09-22 | 2025-09-25 | 2025-09-25 | 2025-09-25 | 2025-09-29 | 2025-10-01 | 2025-10-05 | 2025-10-12 | 2025-07-09 | 2025-07-11 | 2025-07-18 | 2025-07-25 | 2025-07-30 | 2025-07-31 | 2025-08-06 | 2025-08-06 | 2025-08-07 | 2025-08-10 | 2025-08-11 | 2025-08-16 | 2025-08-16 | 2025-08-18 | 2025-08-21 | 2025-08-23 | 2025-08-23 | 2025-08-27 | 2025-08-29 | 2025-08-30 | 2025-08-31 | 2025-09-06 | 2025-09-11 | 2025-09-18 | 2025-09-18 | 2025-09-18 | 2025-09-22 | 2025-09-22 | 2025-09-25 | 2025-10-01 | 2025-10-08 | 2025-08-31 | 2025-09-18 | 2025-09-20 | 2025-10-12 | 2025-10-06 | 2025-10-12 | 2025-10-17 | 2025-10-20 | 2025-10-25
V_495 | 2025-03-14 | 2025-03-21 | 2025-03-23 | 2025-03-29 | 2025-04-03 | 2025-04-06 | 2025-04-07 | 2025-04-11 | 2025-04-16 | 2025-04-19 | 2025-04-23 | 2025-04-23 | 2025-07-02 | 2025-07-09 | 2025-07-16 | 2025-07-16 | 2025-07-23 | 2025-07-30 | 2025-07-30 | 2025-08-02 | 2025-08-02 | 2025-08-03 | 2025-08-09 | 2025-08-09 | 2025-08-16 | 2025-08-16 | 2025-08-16 | 2025-08-21 | 2025-08-25 | 2025-09-01 | 2025-09-06 | 2025-09-11 | 2025-09-18 | 2025-09-18 | 2025-09-22 | 2025-09-25 | 2025-09-25 | 2025-09-25 | 2025-09-29 | 2025-10-01 | 2025-10-05 | 2025-10-12 | 2025-07-09 | 2025-07-11 | 2025-07-18 | 2025-07-25 | 2025-07-30 | 2025-07-31 | 2025-08-06 | 2025-08-06 | 2025-08-07 | 2025-08-10 | 2025-08-11 | 2025-08-16 | 2025-08-16 | 2025-08-18 | 2025-08-21 | 2025-08-23 | 2025-08-23 | 2025-08-27 | 2025-08-29 | 2025-08-30 | 2025-08-31 | 2025-09-06 | 2025-09-11 | 2025-09-18 | 2025-09-18 | 2025-09-18 | 2025-09-22 | 2025-09-22 | 2025-09-25 | 2025-10-01 | 2025-10-08 | 2025-08-31 | 2025-09-18 | 2025-09-20 | 2025-10-12 | 2025-10-06 | 2025-10-12 | 2025-10-17 | 2025-10-20 | 2025-10-25
V_496 | 2025-03-14 | 2025-03-21 | 2025-03-23 | 2025-03-29 | 2025-04-03 | 2025-04-06 | 2025-04-07 | 2025-04-11 | 2025-04-16 | 2025-04-19 | 2025-04-23 | 2025-04-23 | 2025-07-02 | 2025-07-09 | 2025-07-16 | 2025-07-16 | 2025-07-23 | 2025-07-30 | 2025-07-30 | 2025-08-02 | 2025-08-02 | 2025-08-03 | 2025-08-09 | 2025-08-09 | 2025-08-16 | 2025-08-16 | 2025-08-16 | 2025-08-21 | 2025-08-25 | 2025-09-01 | 2025-09-06 | 2025-09-11 | 2025-09-18 | 2025-09-18 | 2025-09-22 | 2025-09-25 | 2025-09-25 | 2025-09-25 | 2025-09-29 | 2025-10-01 | 2025-10-05 | 2025-10-12 | 2025-07-09 | 2025-07-11 | 2025-07-18 | 2025-07-25 | 2025-07-30 | 2025-07-31 | 2025-08-06 | 2025-08-06 | 2025-08-07 | 2025-08-10 | 2025-08-11 | 2025-08-16 | 2025-08-16 | 2025-08-18 | 2025-08-21 | 2025-08-23 | 2025-08-23 | 2025-08-27 | 2025-08-29 | 2025-08-30 | 2025-08-31 | 2025-09-06 | 2025-09-11 | 2025-09-18 | 2025-09-18 | 2025-09-18 | 2025-09-22 | 2025-09-22 | 2025-09-25 | 2025-10-01 | 2025-10-08 | 2025-08-31 | 2025-09-18 | 2025-09-20 | 2025-10-12 | 2025-10-06 | 2025-10-12 | 2025-10-17 | 2025-10-20 | 2025-10-25
V_497 | 2025-03-21 | 2025-03-28 | 2025-03-30 | 2025-04-05 | 2025-04-10 | 2025-04-13 | 2025-04-14 | 2025-04-18 | 2025-04-23 | 2025-04-26 | 2025-04-30 | 2025-04-30 | 2025-07-09 | 2025-07-16 | 2025-07-23 | 2025-07-23 | 2025-07-30 | 2025-08-06 | 2025-08-06 | 2025-08-09 | 2025-08-09 | 2025-08-10 | 2025-08-16 | 2025-08-16 | 2025-08-23 | 2025-08-23 | 2025-08-23 | 2025-08-28 | 2025-09-01 | 2025-09-08 | 2025-09-13 | 2025-09-18 | 2025-09-25 | 2025-09-25 | 2025-09-29 | 2025-10-02 | 2025-10-02 | 2025-10-02 | 2025-10-06 | 2025-10-08 | 2025-10-12 | 2025-10-19 | 2025-07-16 | 2025-07-18 | 2025-07-25 | 2025-08-01 | 2025-08-06 | 2025-08-07 | 2025-08-13 | 2025-08-13 | 2025-08-14 | 2025-08-17 | 2025-08-18 | 2025-08-23 | 2025-08-23 | 2025-08-25 | 2025-08-28 | 2025-08-30 | 2025-08-30 | 2025-09-03 | 2025-09-05 | 2025-09-06 | 2025-09-07 | 2025-09-13 | 2025-09-18 | 2025-09-25 | 2025-09-25 | 2025-09-25 | 2025-09-29 | 2025-09-29 | 2025-10-02 | 2025-10-08 | 2025-10-15 | 2025-09-07 | 2025-09-25 | 2025-09-27 | 2025-10-19 | 2025-10-13 | 2025-10-19 | 2025-10-24 | 2025-10-27 | 2025-11-01
V_498 | 2025-03-21 | 2025-03-28 | 2025-03-30 | 2025-04-05 | 2025-04-10 | 2025-04-13 | 2025-04-14 | 2025-04-18 | 2025-04-23 | 2025-04-26 | 2025-04-30 | 2025-04-30 | 2025-07-09 | 2025-07-16 | 2025-07-23 | 2025-07-23 | 2025-07-30 | 2025-08-06 | 2025-08-06 | 2025-08-09 | 2025-08-09 | 2025-08-10 | 2025-08-16 | 2025-08-16 | 2025-08-23 | 2025-08-23 | 2025-08-23 | 2025-08-28 | 2025-09-01 | 2025-09-08 | 2025-09-13 | 2025-09-18 | 2025-09-25 | 2025-09-25 | 2025-09-29 | 2025-10-02 | 2025-10-02 | 2025-10-02 | 2025-10-06 | 2025-10-08 | 2025-10-12 | 2025-10-19 | 2025-07-16 | 2025-07-18 | 2025-07-25 | 2025-08-01 | 2025-08-06 | 2025-08-07 | 2025-08-13 | 2025-08-13 | 2025-08-14 | 2025-08-17 | 2025-08-18 | 2025-08-23 | 2025-08-23 | 2025-08-25 | 2025-08-28 | 2025-08-30 | 2025-08-30 | 2025-09-03 | 2025-09-05 | 2025-09-06 | 2025-09-07 | 2025-09-13 | 2025-09-18 | 2025-09-25 | 2025-09-25 | 2025-09-25 | 2025-09-29 | 2025-09-29 | 2025-10-02 | 2025-10-08 | 2025-10-15 | 2025-09-07 | 2025-09-25 | 2025-09-27 | 2025-10-19 | 2025-10-13 | 2025-10-19 | 2025-10-24 | 2025-10-27 | 2025-11-01
V_499 | 2025-03-21 | 2025-03-28 | 2025-03-30 | 2025-04-05 | 2025-04-10 | 2025-04-13 | 2025-04-14 | 2025-04-18 | 2025-04-23 | 2025-04-26 | 2025-04-30 | 2025-04-30 | 2025-07-09 | 2025-07-16 | 2025-07-23 | 2025-07-23 | 2025-07-30 | 2025-08-06 | 2025-08-06 | 2025-08-09 | 2025-08-09 | 2025-08-10 | 2025-08-16 | 2025-08-16 | 2025-08-23 | 2025-08-23 | 2025-08-23 | 2025-08-28 | 2025-09-01 | 2025-09-08 | 2025-09-13 | 2025-09-18 | 2025-09-25 | 2025-09-25 | 2025-09-29 | 2025-10-02 | 2025-10-02 | 2025-10-02 | 2025-10-06 | 2025-10-08 | 2025-10-12 | 2025-10-19 | 2025-07-16 | 2025-07-18 | 2025-07-25 | 2025-08-01 | 2025-08-06 | 2025-08-07 | 2025-08-13 | 2025-08-13 | 2025-08-14 | 2025-08-17 | 2025-08-18 | 2025-08-23 | 2025-08-23 | 2025-08-25 | 2025-08-28 | 2025-08-30 | 2025-08-30 | 2025-09-03 | 2025-09-05 | 2025-09-06 | 2025-09-07 | 2025-09-13 | 2025-09-18 | 2025-09-25 | 2025-09-25 | 2025-09-25 | 2025-09-29 | 2025-09-29 | 2025-10-02 | 2025-10-08 | 2025-10-15 | 2025-09-07 | 2025-09-25 | 2025-09-27 | 2025-10-19 | 2025-10-13 | 2025-10-19 | 2025-10-24 | 2025-10-27 | 2025-11-01
V_500 | 2025-03-21 | 2025-03-28 | 2025-03-30 | 2025-04-05 | 2025-04-10 | 2025-04-13 | 2025-04-14 | 2025-04-18 | 2025-04-23 | 2025-04-26 | 2025-04-30 | 2025-04-30 | 2025-07-09 | 2025-07-16 | 2025-07-23 | 2025-07-23 | 2025-07-30 | 2025-08-06 | 2025-08-06 | 2025-08-09 | 2025-08-09 | 2025-08-10 | 2025-08-16 | 2025-08-16 | 2025-08-23 | 2025-08-23 | 2025-08-23 | 2025-08-28 | 2025-09-01 | 2025-09-08 | 2025-09-13 | 2025-09-18 | 2025-09-25 | 2025-09-25 | 2025-09-29 | 2025-10-02 | 2025-10-02 | 2025-10-02 | 2025-10-06 | 2025-10-08 | 2025-10-12 | 2025-10-19 | 2025-07-16 | 2025-07-18 | 2025-07-25 | 2025-08-01 | 2025-08-06 | 2025-08-07 | 2025-08-13 | 2025-08-13 | 2025-08-14 | 2025-08-17 | 2025-08-18 | 2025-08-23 | 2025-08-23 | 2025-08-25 | 2025-08-28 | 2025-08-30 | 2025-08-30 | 2025-09-03 | 2025-09-05 | 2025-09-06 | 2025-09-07 | 2025-09-13 | 2025-09-18 | 2025-09-25 | 2025-09-25 | 2025-09-25 | 2025-09-29 | 2025-09-29 | 2025-10-02 | 2025-10-08 | 2025-10-15 | 2025-09-07 | 2025-09-25 | 2025-09-27 | 2025-10-19 | 2025-10-13 | 2025-10-19 | 2025-10-24 | 2025-10-27 | 2025-11-01
V_501 | 2025-03-21 | 2025-03-28 | 2025-03-30 | 2025-04-05 | 2025-04-10 | 2025-04-13 | 2025-04-14 | 2025-04-18 | 2025-04-23 | 2025-04-26 | 2025-04-30 | 2025-04-30 | 2025-07-09 | 2025-07-16 | 2025-07-23 | 2025-07-23 | 2025-07-30 | 2025-08-06 | 2025-08-06 | 2025-08-09 | 2025-08-09 | 2025-08-10 | 2025-08-16 | 2025-08-16 | 2025-08-23 | 2025-08-23 | 2025-08-23 | 2025-08-28 | 2025-09-01 | 2025-09-08 | 2025-09-13 | 2025-09-18 | 2025-09-25 | 2025-09-25 | 2025-09-29 | 2025-10-02 | 2025-10-02 | 2025-10-02 | 2025-10-06 | 2025-10-08 | 2025-10-12 | 2025-10-19 | 2025-07-16 | 2025-07-18 | 2025-07-25 | 2025-08-01 | 2025-08-06 | 2025-08-07 | 2025-08-13 | 2025-08-13 | 2025-08-14 | 2025-08-17 | 2025-08-18 | 2025-08-23 | 2025-08-23 | 2025-08-25 | 2025-08-28 | 2025-08-30 | 2025-08-30 | 2025-09-03 | 2025-09-05 | 2025-09-06 | 2025-09-07 | 2025-09-13 | 2025-09-18 | 2025-09-25 | 2025-09-25 | 2025-09-25 | 2025-09-29 | 2025-09-29 | 2025-10-02 | 2025-10-08 | 2025-10-15 | 2025-09-07 | 2025-09-25 | 2025-09-27 | 2025-10-19 | 2025-10-13 | 2025-10-19 | 2025-10-24 | 2025-10-27 | 2025-11-01
V_502 | 2025-03-21 | 2025-03-28 | 2025-03-30 | 2025-04-05 | 2025-04-10 | 2025-04-13 | 2025-04-14 | 2025-04-18 | 2025-04-23 | 2025-04-26 | 2025-04-30 | 2025-04-30 | 2025-07-09 | 2025-07-16 | 2025-07-23 | 2025-07-23 | 2025-07-30 | 2025-08-06 | 2025-08-06 | 2025-08-09 | 2025-08-09 | 2025-08-10 | 2025-08-16 | 2025-08-16 | 2025-08-23 | 2025-08-23 | 2025-08-23 | 2025-08-28 | 2025-09-01 | 2025-09-08 | 2025-09-13 | 2025-09-18 | 2025-09-25 | 2025-09-25 | 2025-09-29 | 2025-10-02 | 2025-10-02 | 2025-10-02 | 2025-10-06 | 2025-10-08 | 2025-10-12 | 2025-10-19 | 2025-07-16 | 2025-07-18 | 2025-07-25 | 2025-08-01 | 2025-08-06 | 2025-08-07 | 2025-08-13 | 2025-08-13 | 2025-08-14 | 2025-08-17 | 2025-08-18 | 2025-08-23 | 2025-08-23 | 2025-08-25 | 2025-08-28 | 2025-08-30 | 2025-08-30 | 2025-09-03 | 2025-09-05 | 2025-09-06 | 2025-09-07 | 2025-09-13 | 2025-09-18 | 2025-09-25 | 2025-09-25 | 2025-09-25 | 2025-09-29 | 2025-09-29 | 2025-10-02 | 2025-10-08 | 2025-10-15 | 2025-09-07 | 2025-09-25 | 2025-09-27 | 2025-10-19 | 2025-10-13 | 2025-10-19 | 2025-10-24 | 2025-10-27 | 2025-11-01
V_503 | 2025-03-21 | 2025-03-28 | 2025-03-30 | 2025-04-05 | 2025-04-10 | 2025-04-13 | 2025-04-14 | 2025-04-18 | 2025-04-23 | 2025-04-26 | 2025-04-30 | 2025-04-30 | 2025-07-09 | 2025-07-16 | 2025-07-23 | 2025-07-23 | 2025-07-30 | 2025-08-06 | 2025-08-06 | 2025-08-09 | 2025-08-09 | 2025-08-10 | 2025-08-16 | 2025-08-16 | 2025-08-23 | 2025-08-23 | 2025-08-23 | 2025-08-28 | 2025-09-01 | 2025-09-08 | 2025-09-13 | 2025-09-18 | 2025-09-25 | 2025-09-25 | 2025-09-29 | 2025-10-02 | 2025-10-02 | 2025-10-02 | 2025-10-06 | 2025-10-08 | 2025-10-12 | 2025-10-19 | 2025-07-16 | 2025-07-18 | 2025-07-25 | 2025-08-01 | 2025-08-06 | 2025-08-07 | 2025-08-13 | 2025-08-13 | 2025-08-14 | 2025-08-17 | 2025-08-18 | 2025-08-23 | 2025-08-23 | 2025-08-25 | 2025-08-28 | 2025-08-30 | 2025-08-30 | 2025-09-03 | 2025-09-05 | 2025-09-06 | 2025-09-07 | 2025-09-13 | 2025-09-18 | 2025-09-25 | 2025-09-25 | 2025-09-25 | 2025-09-29 | 2025-09-29 | 2025-10-02 | 2025-10-08 | 2025-10-15 | 2025-09-07 | 2025-09-25 | 2025-09-27 | 2025-10-19 | 2025-10-13 | 2025-10-19 | 2025-10-24 | 2025-10-27 | 2025-11-01
V_504 | 2025-03-21 | 2025-03-28 | 2025-03-30 | 2025-04-05 | 2025-04-10 | 2025-04-13 | 2025-04-14 | 2025-04-18 | 2025-04-23 | 2025-04-26 | 2025-04-30 | 2025-04-30 | 2025-07-09 | 2025-07-16 | 2025-07-23 | 2025-07-23 | 2025-07-30 | 2025-08-06 | 2025-08-06 | 2025-08-09 | 2025-08-09 | 2025-08-10 | 2025-08-16 | 2025-08-16 | 2025-08-23 | 2025-08-23 | 2025-08-23 | 2025-08-28 | 2025-09-01 | 2025-09-08 | 2025-09-13 | 2025-09-18 | 2025-09-25 | 2025-09-25 | 2025-09-29 | 2025-10-02 | 2025-10-02 | 2025-10-02 | 2025-10-06 | 2025-10-08 | 2025-10-12 | 2025-10-19 | 2025-07-16 | 2025-07-18 | 2025-07-25 | 2025-08-01 | 2025-08-06 | 2025-08-07 | 2025-08-13 | 2025-08-13 | 2025-08-14 | 2025-08-17 | 2025-08-18 | 2025-08-23 | 2025-08-23 | 2025-08-25 | 2025-08-28 | 2025-08-30 | 2025-08-30 | 2025-09-03 | 2025-09-05 | 2025-09-06 | 2025-09-07 | 2025-09-13 | 2025-09-18 | 2025-09-25 | 2025-09-25 | 2025-09-25 | 2025-09-29 | 2025-09-29 | 2025-10-02 | 2025-10-08 | 2025-10-15 | 2025-09-07 | 2025-09-25 | 2025-09-27 | 2025-10-19 | 2025-10-13 | 2025-10-19 | 2025-10-24 | 2025-10-27 | 2025-11-01
V_505 | 2025-03-28 | 2025-04-04 | 2025-04-06 | 2025-04-12 | 2025-04-17 | 2025-04-20 | 2025-04-21 | 2025-04-25 | 2025-04-30 | 2025-05-03 | 2025-05-07 | 2025-05-07 | 2025-07-16 | 2025-07-23 | 2025-07-30 | 2025-07-30 | 2025-08-06 | 2025-08-13 | 2025-08-13 | 2025-08-16 | 2025-08-16 | 2025-08-17 | 2025-08-23 | 2025-08-23 | 2025-08-30 | 2025-08-30 | 2025-08-30 | 2025-09-04 | 2025-09-08 | 2025-09-15 | 2025-09-20 | 2025-09-25 | 2025-10-02 | 2025-10-02 | 2025-10-06 | 2025-10-09 | 2025-10-09 | 2025-10-09 | 2025-10-13 | 2025-10-15 | 2025-10-19 | 2025-10-26 | 2025-07-23 | 2025-07-25 | 2025-08-01 | 2025-08-08 | 2025-08-13 | 2025-08-14 | 2025-08-20 | 2025-08-20 | 2025-08-21 | 2025-08-24 | 2025-08-25 | 2025-08-30 | 2025-08-30 | 2025-09-01 | 2025-09-04 | 2025-09-06 | 2025-09-06 | 2025-09-10 | 2025-09-12 | 2025-09-13 | 2025-09-14 | 2025-09-20 | 2025-09-25 | 2025-10-02 | 2025-10-02 | 2025-10-02 | 2025-10-06 | 2025-10-06 | 2025-10-09 | 2025-10-15 | 2025-10-22 | 2025-09-14 | 2025-10-02 | 2025-10-04 | 2025-10-26 | 2025-10-20 | 2025-10-26 | 2025-10-31 | 2025-11-03 | 2025-11-08
V_506 | 2025-03-28 | 2025-04-04 | 2025-04-06 | 2025-04-12 | 2025-04-17 | 2025-04-20 | 2025-04-21 | 2025-04-25 | 2025-04-30 | 2025-05-03 | 2025-05-07 | 2025-05-07 | 2025-07-16 | 2025-07-23 | 2025-07-30 | 2025-07-30 | 2025-08-06 | 2025-08-13 | 2025-08-13 | 2025-08-16 | 2025-08-16 | 2025-08-17 | 2025-08-23 | 2025-08-23 | 2025-08-30 | 2025-08-30 | 2025-08-30 | 2025-09-04 | 2025-09-08 | 2025-09-15 | 2025-09-20 | 2025-09-25 | 2025-10-02 | 2025-10-02 | 2025-10-06 | 2025-10-09 | 2025-10-09 | 2025-10-09 | 2025-10-13 | 2025-10-15 | 2025-10-19 | 2025-10-26 | 2025-07-23 | 2025-07-25 | 2025-08-01 | 2025-08-08 | 2025-08-13 | 2025-08-14 | 2025-08-20 | 2025-08-20 | 2025-08-21 | 2025-08-24 | 2025-08-25 | 2025-08-30 | 2025-08-30 | 2025-09-01 | 2025-09-04 | 2025-09-06 | 2025-09-06 | 2025-09-10 | 2025-09-12 | 2025-09-13 | 2025-09-14 | 2025-09-20 | 2025-09-25 | 2025-10-02 | 2025-10-02 | 2025-10-02 | 2025-10-06 | 2025-10-06 | 2025-10-09 | 2025-10-15 | 2025-10-22 | 2025-09-14 | 2025-10-02 | 2025-10-04 | 2025-10-26 | 2025-10-20 | 2025-10-26 | 2025-10-31 | 2025-11-03 | 2025-11-08
V_507 | 2025-03-28 | 2025-04-04 | 2025-04-06 | 2025-04-12 | 2025-04-17 | 2025-04-20 | 2025-04-21 | 2025-04-25 | 2025-04-30 | 2025-05-03 | 2025-05-07 | 2025-05-07 | 2025-07-16 | 2025-07-23 | 2025-07-30 | 2025-07-30 | 2025-08-06 | 2025-08-13 | 2025-08-13 | 2025-08-16 | 2025-08-16 | 2025-08-17 | 2025-08-23 | 2025-08-23 | 2025-08-30 | 2025-08-30 | 2025-08-30 | 2025-09-04 | 2025-09-08 | 2025-09-15 | 2025-09-20 | 2025-09-25 | 2025-10-02 | 2025-10-02 | 2025-10-06 | 2025-10-09 | 2025-10-09 | 2025-10-09 | 2025-10-13 | 2025-10-15 | 2025-10-19 | 2025-10-26 | 2025-07-23 | 2025-07-25 | 2025-08-01 | 2025-08-08 | 2025-08-13 | 2025-08-14 | 2025-08-20 | 2025-08-20 | 2025-08-21 | 2025-08-24 | 2025-08-25 | 2025-08-30 | 2025-08-30 | 2025-09-01 | 2025-09-04 | 2025-09-06 | 2025-09-06 | 2025-09-10 | 2025-09-12 | 2025-09-13 | 2025-09-14 | 2025-09-20 | 2025-09-25 | 2025-10-02 | 2025-10-02 | 2025-10-02 | 2025-10-06 | 2025-10-06 | 2025-10-09 | 2025-10-15 | 2025-10-22 | 2025-09-14 | 2025-10-02 | 2025-10-04 | 2025-10-26 | 2025-10-20 | 2025-10-26 | 2025-10-31 | 2025-11-03 | 2025-11-08
V_508 | 2025-03-28 | 2025-04-04 | 2025-04-06 | 2025-04-12 | 2025-04-17 | 2025-04-20 | 2025-04-21 | 2025-04-25 | 2025-04-30 | 2025-05-03 | 2025-05-07 | 2025-05-07 | 2025-07-16 | 2025-07-23 | 2025-07-30 | 2025-07-30 | 2025-08-06 | 2025-08-13 | 2025-08-13 | 2025-08-16 | 2025-08-16 | 2025-08-17 | 2025-08-23 | 2025-08-23 | 2025-08-30 | 2025-08-30 | 2025-08-30 | 2025-09-04 | 2025-09-08 | 2025-09-15 | 2025-09-20 | 2025-09-25 | 2025-10-02 | 2025-10-02 | 2025-10-06 | 2025-10-09 | 2025-10-09 | 2025-10-09 | 2025-10-13 | 2025-10-15 | 2025-10-19 | 2025-10-26 | 2025-07-23 | 2025-07-25 | 2025-08-01 | 2025-08-08 | 2025-08-13 | 2025-08-14 | 2025-08-20 | 2025-08-20 | 2025-08-21 | 2025-08-24 | 2025-08-25 | 2025-08-30 | 2025-08-30 | 2025-09-01 | 2025-09-04 | 2025-09-06 | 2025-09-06 | 2025-09-10 | 2025-09-12 | 2025-09-13 | 2025-09-14 | 2025-09-20 | 2025-09-25 | 2025-10-02 | 2025-10-02 | 2025-10-02 | 2025-10-06 | 2025-10-06 | 2025-10-09 | 2025-10-15 | 2025-10-22 | 2025-09-14 | 2025-10-02 | 2025-10-04 | 2025-10-26 | 2025-10-20 | 2025-10-26 | 2025-10-31 | 2025-11-03 | 2025-11-08
V_509 | 2025-03-28 | 2025-04-04 | 2025-04-06 | 2025-04-12 | 2025-04-17 | 2025-04-20 | 2025-04-21 | 2025-04-25 | 2025-04-30 | 2025-05-03 | 2025-05-07 | 2025-05-07 | 2025-07-16 | 2025-07-23 | 2025-07-30 | 2025-07-30 | 2025-08-06 | 2025-08-13 | 2025-08-13 | 2025-08-16 | 2025-08-16 | 2025-08-17 | 2025-08-23 | 2025-08-23 | 2025-08-30 | 2025-08-30 | 2025-08-30 | 2025-09-04 | 2025-09-08 | 2025-09-15 | 2025-09-20 | 2025-09-25 | 2025-10-02 | 2025-10-02 | 2025-10-06 | 2025-10-09 | 2025-10-09 | 2025-10-09 | 2025-10-13 | 2025-10-15 | 2025-10-19 | 2025-10-26 | 2025-07-23 | 2025-07-25 | 2025-08-01 | 2025-08-08 | 2025-08-13 | 2025-08-14 | 2025-08-20 | 2025-08-20 | 2025-08-21 | 2025-08-24 | 2025-08-25 | 2025-08-30 | 2025-08-30 | 2025-09-01 | 2025-09-04 | 2025-09-06 | 2025-09-06 | 2025-09-10 | 2025-09-12 | 2025-09-13 | 2025-09-14 | 2025-09-20 | 2025-09-25 | 2025-10-02 | 2025-10-02 | 2025-10-02 | 2025-10-06 | 2025-10-06 | 2025-10-09 | 2025-10-15 | 2025-10-22 | 2025-09-14 | 2025-10-02 | 2025-10-04 | 2025-10-26 | 2025-10-20 | 2025-10-26 | 2025-10-31 | 2025-11-03 | 2025-11-08
V_510 | 2025-03-28 | 2025-04-04 | 2025-04-06 | 2025-04-12 | 2025-04-17 | 2025-04-20 | 2025-04-21 | 2025-04-25 | 2025-04-30 | 2025-05-03 | 2025-05-07 | 2025-05-07 | 2025-07-16 | 2025-07-23 | 2025-07-30 | 2025-07-30 | 2025-08-06 | 2025-08-13 | 2025-08-13 | 2025-08-16 | 2025-08-16 | 2025-08-17 | 2025-08-23 | 2025-08-23 | 2025-08-30 | 2025-08-30 | 2025-08-30 | 2025-09-04 | 2025-09-08 | 2025-09-15 | 2025-09-20 | 2025-09-25 | 2025-10-02 | 2025-10-02 | 2025-10-06 | 2025-10-09 | 2025-10-09 | 2025-10-09 | 2025-10-13 | 2025-10-15 | 2025-10-19 | 2025-10-26 | 2025-07-23 | 2025-07-25 | 2025-08-01 | 2025-08-08 | 2025-08-13 | 2025-08-14 | 2025-08-20 | 2025-08-20 | 2025-08-21 | 2025-08-24 | 2025-08-25 | 2025-08-30 | 2025-08-30 | 2025-09-01 | 2025-09-04 | 2025-09-06 | 2025-09-06 | 2025-09-10 | 2025-09-12 | 2025-09-13 | 2025-09-14 | 2025-09-20 | 2025-09-25 | 2025-10-02 | 2025-10-02 | 2025-10-02 | 2025-10-06 | 2025-10-06 | 2025-10-09 | 2025-10-15 | 2025-10-22 | 2025-09-14 | 2025-10-02 | 2025-10-04 | 2025-10-26 | 2025-10-20 | 2025-10-26 | 2025-10-31 | 2025-11-03 | 2025-11-08
V_511 | 2025-03-28 | 2025-04-04 | 2025-04-06 | 2025-04-12 | 2025-04-17 | 2025-04-20 | 2025-04-21 | 2025-04-25 | 2025-04-30 | 2025-05-03 | 2025-05-07 | 2025-05-07 | 2025-07-16 | 2025-07-23 | 2025-07-30 | 2025-07-30 | 2025-08-06 | 2025-08-13 | 2025-08-13 | 2025-08-16 | 2025-08-16 | 2025-08-17 | 2025-08-23 | 2025-08-23 | 2025-08-30 | 2025-08-30 | 2025-08-30 | 2025-09-04 | 2025-09-08 | 2025-09-15 | 2025-09-20 | 2025-09-25 | 2025-10-02 | 2025-10-02 | 2025-10-06 | 2025-10-09 | 2025-10-09 | 2025-10-09 | 2025-10-13 | 2025-10-15 | 2025-10-19 | 2025-10-26 | 2025-07-23 | 2025-07-25 | 2025-08-01 | 2025-08-08 | 2025-08-13 | 2025-08-14 | 2025-08-20 | 2025-08-20 | 2025-08-21 | 2025-08-24 | 2025-08-25 | 2025-08-30 | 2025-08-30 | 2025-09-01 | 2025-09-04 | 2025-09-06 | 2025-09-06 | 2025-09-10 | 2025-09-12 | 2025-09-13 | 2025-09-14 | 2025-09-20 | 2025-09-25 | 2025-10-02 | 2025-10-02 | 2025-10-02 | 2025-10-06 | 2025-10-06 | 2025-10-09 | 2025-10-15 | 2025-10-22 | 2025-09-14 | 2025-10-02 | 2025-10-04 | 2025-10-26 | 2025-10-20 | 2025-10-26 | 2025-10-31 | 2025-11-03 | 2025-11-08
V_512 | 2025-03-28 | 2025-04-04 | 2025-04-06 | 2025-04-12 | 2025-04-17 | 2025-04-20 | 2025-04-21 | 2025-04-25 | 2025-04-30 | 2025-05-03 | 2025-05-07 | 2025-05-07 | 2025-07-16 | 2025-07-23 | 2025-07-30 | 2025-07-30 | 2025-08-06 | 2025-08-13 | 2025-08-13 | 2025-08-16 | 2025-08-16 | 2025-08-17 | 2025-08-23 | 2025-08-23 | 2025-08-30 | 2025-08-30 | 2025-08-30 | 2025-09-04 | 2025-09-08 | 2025-09-15 | 2025-09-20 | 2025-09-25 | 2025-10-02 | 2025-10-02 | 2025-10-06 | 2025-10-09 | 2025-10-09 | 2025-10-09 | 2025-10-13 | 2025-10-15 | 2025-10-19 | 2025-10-26 | 2025-07-23 | 2025-07-25 | 2025-08-01 | 2025-08-08 | 2025-08-13 | 2025-08-14 | 2025-08-20 | 2025-08-20 | 2025-08-21 | 2025-08-24 | 2025-08-25 | 2025-08-30 | 2025-08-30 | 2025-09-01 | 2025-09-04 | 2025-09-06 | 2025-09-06 | 2025-09-10 | 2025-09-12 | 2025-09-13 | 2025-09-14 | 2025-09-20 | 2025-09-25 | 2025-10-02 | 2025-10-02 | 2025-10-02 | 2025-10-06 | 2025-10-06 | 2025-10-09 | 2025-10-15 | 2025-10-22 | 2025-09-14 | 2025-10-02 | 2025-10-04 | 2025-10-26 | 2025-10-20 | 2025-10-26 | 2025-10-31 | 2025-11-03 | 2025-11-08
V_513 | 2025-04-04 | 2025-04-11 | 2025-04-13 | 2025-04-19 | 2025-04-24 | 2025-04-27 | 2025-04-28 | 2025-05-02 | 2025-05-07 | 2025-05-10 | 2025-05-14 | 2025-05-14 | 2025-07-23 | 2025-07-30 | 2025-08-06 | 2025-08-06 | 2025-08-13 | 2025-08-20 | 2025-08-20 | 2025-08-23 | 2025-08-23 | 2025-08-24 | 2025-08-30 | 2025-08-30 | 2025-09-06 | 2025-09-06 | 2025-09-06 | 2025-09-11 | 2025-09-15 | 2025-09-22 | 2025-09-27 | 2025-10-02 | 2025-10-09 | 2025-10-09 | 2025-10-13 | 2025-10-16 | 2025-10-16 | 2025-10-16 | 2025-10-20 | 2025-10-22 | 2025-10-26 | 2025-11-02 | 2025-07-30 | 2025-08-01 | 2025-08-08 | 2025-08-14 | 2025-08-18 | 2025-08-20 | 2025-08-24 | 2025-08-24 | 2025-08-25 | 2025-08-30 | 2025-08-30 | 2025-09-04 | 2025-09-04 | 2025-09-06 | 2025-09-08 | 2025-09-11 | 2025-09-12 | 2025-09-14 | 2025-09-17 | 2025-09-18 | 2025-09-20 | 2025-09-25 | 2025-10-02 | 2025-10-06 | 2025-10-06 | 2025-10-08 | 2025-10-11 | 2025-10-11 | 2025-10-13 | 2025-10-22 | 2025-10-27 | 2025-09-19 | 2025-10-06 | 2025-10-09 | 2025-11-01 | 2025-10-27 | 2025-11-02 | 2025-11-06 | 2025-11-09 | 2025-11-14
V_514 | 2025-04-04 | 2025-04-11 | 2025-04-13 | 2025-04-19 | 2025-04-24 | 2025-04-27 | 2025-04-28 | 2025-05-02 | 2025-05-07 | 2025-05-10 | 2025-05-14 | 2025-05-14 | 2025-07-23 | 2025-07-30 | 2025-08-06 | 2025-08-06 | 2025-08-13 | 2025-08-20 | 2025-08-20 | 2025-08-23 | 2025-08-23 | 2025-08-24 | 2025-08-30 | 2025-08-30 | 2025-09-06 | 2025-09-06 | 2025-09-06 | 2025-09-11 | 2025-09-15 | 2025-09-22 | 2025-09-27 | 2025-10-02 | 2025-10-09 | 2025-10-09 | 2025-10-13 | 2025-10-16 | 2025-10-16 | 2025-10-16 | 2025-10-20 | 2025-10-22 | 2025-10-26 | 2025-11-02 | 2025-07-30 | 2025-08-01 | 2025-08-08 | 2025-08-14 | 2025-08-18 | 2025-08-20 | 2025-08-24 | 2025-08-24 | 2025-08-25 | 2025-08-30 | 2025-08-30 | 2025-09-04 | 2025-09-04 | 2025-09-06 | 2025-09-08 | 2025-09-11 | 2025-09-12 | 2025-09-14 | 2025-09-17 | 2025-09-18 | 2025-09-20 | 2025-09-25 | 2025-10-02 | 2025-10-06 | 2025-10-06 | 2025-10-08 | 2025-10-11 | 2025-10-11 | 2025-10-13 | 2025-10-22 | 2025-10-27 | 2025-09-19 | 2025-10-06 | 2025-10-09 | 2025-11-01 | 2025-10-27 | 2025-11-02 | 2025-11-06 | 2025-11-09 | 2025-11-14
V_515 | 2025-04-04 | 2025-04-11 | 2025-04-13 | 2025-04-19 | 2025-04-24 | 2025-04-27 | 2025-04-28 | 2025-05-02 | 2025-05-07 | 2025-05-10 | 2025-05-14 | 2025-05-14 | 2025-07-23 | 2025-07-30 | 2025-08-06 | 2025-08-06 | 2025-08-13 | 2025-08-20 | 2025-08-20 | 2025-08-23 | 2025-08-23 | 2025-08-24 | 2025-08-30 | 2025-08-30 | 2025-09-06 | 2025-09-06 | 2025-09-06 | 2025-09-11 | 2025-09-15 | 2025-09-22 | 2025-09-27 | 2025-10-02 | 2025-10-09 | 2025-10-09 | 2025-10-13 | 2025-10-16 | 2025-10-16 | 2025-10-16 | 2025-10-20 | 2025-10-22 | 2025-10-26 | 2025-11-02 | 2025-07-30 | 2025-08-01 | 2025-08-08 | 2025-08-14 | 2025-08-18 | 2025-08-20 | 2025-08-24 | 2025-08-24 | 2025-08-25 | 2025-08-30 | 2025-08-30 | 2025-09-04 | 2025-09-04 | 2025-09-06 | 2025-09-08 | 2025-09-11 | 2025-09-12 | 2025-09-14 | 2025-09-17 | 2025-09-18 | 2025-09-20 | 2025-09-25 | 2025-10-02 | 2025-10-06 | 2025-10-06 | 2025-10-08 | 2025-10-11 | 2025-10-11 | 2025-10-13 | 2025-10-22 | 2025-10-27 | 2025-09-19 | 2025-10-06 | 2025-10-09 | 2025-11-01 | 2025-10-27 | 2025-11-02 | 2025-11-06 | 2025-11-09 | 2025-11-14
V_516 | 2025-04-04 | 2025-04-11 | 2025-04-13 | 2025-04-19 | 2025-04-24 | 2025-04-27 | 2025-04-28 | 2025-05-02 | 2025-05-07 | 2025-05-10 | 2025-05-14 | 2025-05-14 | 2025-07-23 | 2025-07-30 | 2025-08-06 | 2025-08-06 | 2025-08-13 | 2025-08-20 | 2025-08-20 | 2025-08-23 | 2025-08-23 | 2025-08-24 | 2025-08-30 | 2025-08-30 | 2025-09-06 | 2025-09-06 | 2025-09-06 | 2025-09-11 | 2025-09-15 | 2025-09-22 | 2025-09-27 | 2025-10-02 | 2025-10-09 | 2025-10-09 | 2025-10-13 | 2025-10-16 | 2025-10-16 | 2025-10-16 | 2025-10-20 | 2025-10-22 | 2025-10-26 | 2025-11-02 | 2025-07-30 | 2025-08-01 | 2025-08-08 | 2025-08-14 | 2025-08-18 | 2025-08-20 | 2025-08-24 | 2025-08-24 | 2025-08-25 | 2025-08-30 | 2025-08-30 | 2025-09-04 | 2025-09-04 | 2025-09-06 | 2025-09-08 | 2025-09-11 | 2025-09-12 | 2025-09-14 | 2025-09-17 | 2025-09-18 | 2025-09-20 | 2025-09-25 | 2025-10-02 | 2025-10-06 | 2025-10-06 | 2025-10-08 | 2025-10-11 | 2025-10-11 | 2025-10-13 | 2025-10-22 | 2025-10-27 | 2025-09-19 | 2025-10-06 | 2025-10-09 | 2025-11-01 | 2025-10-27 | 2025-11-02 | 2025-11-06 | 2025-11-09 | 2025-11-14
V_517 | 2025-04-04 | 2025-04-11 | 2025-04-13 | 2025-04-19 | 2025-04-24 | 2025-04-27 | 2025-04-28 | 2025-05-02 | 2025-05-07 | 2025-05-10 | 2025-05-14 | 2025-05-14 | 2025-07-23 | 2025-07-30 | 2025-08-06 | 2025-08-06 | 2025-08-13 | 2025-08-20 | 2025-08-20 | 2025-08-23 | 2025-08-23 | 2025-08-24 | 2025-08-30 | 2025-08-30 | 2025-09-06 | 2025-09-06 | 2025-09-06 | 2025-09-11 | 2025-09-15 | 2025-09-22 | 2025-09-27 | 2025-10-02 | 2025-10-09 | 2025-10-09 | 2025-10-13 | 2025-10-16 | 2025-10-16 | 2025-10-16 | 2025-10-20 | 2025-10-22 | 2025-10-26 | 2025-11-02 | 2025-07-30 | 2025-08-01 | 2025-08-08 | 2025-08-14 | 2025-08-18 | 2025-08-20 | 2025-08-24 | 2025-08-24 | 2025-08-25 | 2025-08-30 | 2025-08-30 | 2025-09-04 | 2025-09-04 | 2025-09-06 | 2025-09-08 | 2025-09-11 | 2025-09-12 | 2025-09-14 | 2025-09-17 | 2025-09-18 | 2025-09-20 | 2025-09-25 | 2025-10-02 | 2025-10-06 | 2025-10-06 | 2025-10-08 | 2025-10-11 | 2025-10-11 | 2025-10-13 | 2025-10-22 | 2025-10-27 | 2025-09-19 | 2025-10-06 | 2025-10-09 | 2025-11-01 | 2025-10-27 | 2025-11-02 | 2025-11-06 | 2025-11-09 | 2025-11-14
V_518 | 2025-04-04 | 2025-04-11 | 2025-04-13 | 2025-04-19 | 2025-04-24 | 2025-04-27 | 2025-04-28 | 2025-05-02 | 2025-05-07 | 2025-05-10 | 2025-05-14 | 2025-05-14 | 2025-07-23 | 2025-07-30 | 2025-08-06 | 2025-08-06 | 2025-08-13 | 2025-08-20 | 2025-08-20 | 2025-08-23 | 2025-08-23 | 2025-08-24 | 2025-08-30 | 2025-08-30 | 2025-09-06 | 2025-09-06 | 2025-09-06 | 2025-09-11 | 2025-09-15 | 2025-09-22 | 2025-09-27 | 2025-10-02 | 2025-10-09 | 2025-10-09 | 2025-10-13 | 2025-10-16 | 2025-10-16 | 2025-10-16 | 2025-10-20 | 2025-10-22 | 2025-10-26 | 2025-11-02 | 2025-07-30 | 2025-08-01 | 2025-08-08 | 2025-08-14 | 2025-08-18 | 2025-08-20 | 2025-08-24 | 2025-08-24 | 2025-08-25 | 2025-08-30 | 2025-08-30 | 2025-09-04 | 2025-09-04 | 2025-09-06 | 2025-09-08 | 2025-09-11 | 2025-09-12 | 2025-09-14 | 2025-09-17 | 2025-09-18 | 2025-09-20 | 2025-09-25 | 2025-10-02 | 2025-10-06 | 2025-10-06 | 2025-10-08 | 2025-10-11 | 2025-10-11 | 2025-10-13 | 2025-10-22 | 2025-10-27 | 2025-09-19 | 2025-10-06 | 2025-10-09 | 2025-11-01 | 2025-10-27 | 2025-11-02 | 2025-11-06 | 2025-11-09 | 2025-11-14
V_519 | 2025-04-04 | 2025-04-11 | 2025-04-13 | 2025-04-19 | 2025-04-24 | 2025-04-27 | 2025-04-28 | 2025-05-02 | 2025-05-07 | 2025-05-10 | 2025-05-14 | 2025-05-14 | 2025-07-23 | 2025-07-30 | 2025-08-06 | 2025-08-06 | 2025-08-13 | 2025-08-20 | 2025-08-20 | 2025-08-23 | 2025-08-23 | 2025-08-24 | 2025-08-30 | 2025-08-30 | 2025-09-06 | 2025-09-06 | 2025-09-06 | 2025-09-11 | 2025-09-15 | 2025-09-22 | 2025-09-27 | 2025-10-02 | 2025-10-09 | 2025-10-09 | 2025-10-13 | 2025-10-16 | 2025-10-16 | 2025-10-16 | 2025-10-20 | 2025-10-22 | 2025-10-26 | 2025-11-02 | 2025-07-30 | 2025-08-01 | 2025-08-08 | 2025-08-14 | 2025-08-18 | 2025-08-20 | 2025-08-24 | 2025-08-24 | 2025-08-25 | 2025-08-30 | 2025-08-30 | 2025-09-04 | 2025-09-04 | 2025-09-06 | 2025-09-08 | 2025-09-11 | 2025-09-12 | 2025-09-14 | 2025-09-17 | 2025-09-18 | 2025-09-20 | 2025-09-25 | 2025-10-02 | 2025-10-06 | 2025-10-06 | 2025-10-08 | 2025-10-11 | 2025-10-11 | 2025-10-13 | 2025-10-22 | 2025-10-27 | 2025-09-19 | 2025-10-06 | 2025-10-09 | 2025-11-01 | 2025-10-27 | 2025-11-02 | 2025-11-06 | 2025-11-09 | 2025-11-14
V_520 | 2025-04-04 | 2025-04-11 | 2025-04-13 | 2025-04-19 | 2025-04-24 | 2025-04-27 | 2025-04-28 | 2025-05-02 | 2025-05-07 | 2025-05-10 | 2025-05-14 | 2025-05-14 | 2025-07-23 | 2025-07-30 | 2025-08-06 | 2025-08-06 | 2025-08-13 | 2025-08-20 | 2025-08-20 | 2025-08-23 | 2025-08-23 | 2025-08-24 | 2025-08-30 | 2025-08-30 | 2025-09-06 | 2025-09-06 | 2025-09-06 | 2025-09-11 | 2025-09-15 | 2025-09-22 | 2025-09-27 | 2025-10-02 | 2025-10-09 | 2025-10-09 | 2025-10-13 | 2025-10-16 | 2025-10-16 | 2025-10-16 | 2025-10-20 | 2025-10-22 | 2025-10-26 | 2025-11-02 | 2025-07-30 | 2025-08-01 | 2025-08-08 | 2025-08-14 | 2025-08-18 | 2025-08-20 | 2025-08-24 | 2025-08-24 | 2025-08-25 | 2025-08-30 | 2025-08-30 | 2025-09-04 | 2025-09-04 | 2025-09-06 | 2025-09-08 | 2025-09-11 | 2025-09-12 | 2025-09-14 | 2025-09-17 | 2025-09-18 | 2025-09-20 | 2025-09-25 | 2025-10-02 | 2025-10-06 | 2025-10-06 | 2025-10-08 | 2025-10-11 | 2025-10-11 | 2025-10-13 | 2025-10-22 | 2025-10-27 | 2025-09-19 | 2025-10-06 | 2025-10-09 | 2025-11-01 | 2025-10-27 | 2025-11-02 | 2025-11-06 | 2025-11-09 | 2025-11-14
V_521 | 2025-04-11 | 2025-04-18 | 2025-04-20 | 2025-04-26 | 2025-05-01 | 2025-05-04 | 2025-05-05 | 2025-05-09 | 2025-05-14 | 2025-05-17 | 2025-05-21 | 2025-05-21 | 2025-07-30 | 2025-08-06 | 2025-08-13 | 2025-08-13 | 2025-08-20 | 2025-08-27 | 2025-08-27 | 2025-08-30 | 2025-08-30 | 2025-08-31 | 2025-09-06 | 2025-09-06 | 2025-09-13 | 2025-09-13 | 2025-09-13 | 2025-09-18 | 2025-09-22 | 2025-09-29 | 2025-10-04 | 2025-10-09 | 2025-10-16 | 2025-10-16 | 2025-10-20 | 2025-10-23 | 2025-10-23 | 2025-10-23 | 2025-10-27 | 2025-10-29 | 2025-11-02 | 2025-11-09 | 2025-08-06 | 2025-08-08 | 2025-08-14 | 2025-08-20 | 2025-08-24 | 2025-08-25 | 2025-08-30 | 2025-08-30 | 2025-08-31 | 2025-09-04 | 2025-09-05 | 2025-09-08 | 2025-09-10 | 2025-09-11 | 2025-09-14 | 2025-09-17 | 2025-09-17 | 2025-09-20 | 2025-09-21 | 2025-09-22 | 2025-09-25 | 2025-09-29 | 2025-10-06 | 2025-10-11 | 2025-10-11 | 2025-10-13 | 2025-10-16 | 2025-10-16 | 2025-10-18 | 2025-10-27 | 2025-11-02 | 2025-09-25 | 2025-10-11 | 2025-10-13 | 2025-11-07 | 2025-11-03 | 2025-11-09 | 2025-11-12 | 2025-11-16 | 2025-11-21
V_522 | 2025-04-11 | 2025-04-18 | 2025-04-20 | 2025-04-26 | 2025-05-01 | 2025-05-04 | 2025-05-05 | 2025-05-09 | 2025-05-14 | 2025-05-17 | 2025-05-21 | 2025-05-21 | 2025-07-30 | 2025-08-06 | 2025-08-13 | 2025-08-13 | 2025-08-20 | 2025-08-27 | 2025-08-27 | 2025-08-30 | 2025-08-30 | 2025-08-31 | 2025-09-06 | 2025-09-06 | 2025-09-13 | 2025-09-13 | 2025-09-13 | 2025-09-18 | 2025-09-22 | 2025-09-29 | 2025-10-04 | 2025-10-09 | 2025-10-16 | 2025-10-16 | 2025-10-20 | 2025-10-23 | 2025-10-23 | 2025-10-23 | 2025-10-27 | 2025-10-29 | 2025-11-02 | 2025-11-09 | 2025-08-06 | 2025-08-08 | 2025-08-14 | 2025-08-20 | 2025-08-24 | 2025-08-25 | 2025-08-30 | 2025-08-30 | 2025-08-31 | 2025-09-04 | 2025-09-05 | 2025-09-08 | 2025-09-10 | 2025-09-11 | 2025-09-14 | 2025-09-17 | 2025-09-17 | 2025-09-20 | 2025-09-21 | 2025-09-22 | 2025-09-25 | 2025-09-29 | 2025-10-06 | 2025-10-11 | 2025-10-11 | 2025-10-13 | 2025-10-16 | 2025-10-16 | 2025-10-18 | 2025-10-27 | 2025-11-02 | 2025-09-25 | 2025-10-11 | 2025-10-13 | 2025-11-07 | 2025-11-03 | 2025-11-09 | 2025-11-12 | 2025-11-16 | 2025-11-21
V_523 | 2025-04-11 | 2025-04-18 | 2025-04-20 | 2025-04-26 | 2025-05-01 | 2025-05-04 | 2025-05-05 | 2025-05-09 | 2025-05-14 | 2025-05-17 | 2025-05-21 | 2025-05-21 | 2025-07-30 | 2025-08-06 | 2025-08-13 | 2025-08-13 | 2025-08-20 | 2025-08-27 | 2025-08-27 | 2025-08-30 | 2025-08-30 | 2025-08-31 | 2025-09-06 | 2025-09-06 | 2025-09-13 | 2025-09-13 | 2025-09-13 | 2025-09-18 | 2025-09-22 | 2025-09-29 | 2025-10-04 | 2025-10-09 | 2025-10-16 | 2025-10-16 | 2025-10-20 | 2025-10-23 | 2025-10-23 | 2025-10-23 | 2025-10-27 | 2025-10-29 | 2025-11-02 | 2025-11-09 | 2025-08-06 | 2025-08-08 | 2025-08-14 | 2025-08-20 | 2025-08-24 | 2025-08-25 | 2025-08-30 | 2025-08-30 | 2025-08-31 | 2025-09-04 | 2025-09-05 | 2025-09-08 | 2025-09-10 | 2025-09-11 | 2025-09-14 | 2025-09-17 | 2025-09-17 | 2025-09-20 | 2025-09-21 | 2025-09-22 | 2025-09-25 | 2025-09-29 | 2025-10-06 | 2025-10-11 | 2025-10-11 | 2025-10-13 | 2025-10-16 | 2025-10-16 | 2025-10-18 | 2025-10-27 | 2025-11-02 | 2025-09-25 | 2025-10-11 | 2025-10-13 | 2025-11-07 | 2025-11-03 | 2025-11-09 | 2025-11-12 | 2025-11-16 | 2025-11-21
V_524 | 2025-04-11 | 2025-04-18 | 2025-04-20 | 2025-04-26 | 2025-05-01 | 2025-05-04 | 2025-05-05 | 2025-05-09 | 2025-05-14 | 2025-05-17 | 2025-05-21 | 2025-05-21 | 2025-07-30 | 2025-08-06 | 2025-08-13 | 2025-08-13 | 2025-08-20 | 2025-08-27 | 2025-08-27 | 2025-08-30 | 2025-08-30 | 2025-08-31 | 2025-09-06 | 2025-09-06 | 2025-09-13 | 2025-09-13 | 2025-09-13 | 2025-09-18 | 2025-09-22 | 2025-09-29 | 2025-10-04 | 2025-10-09 | 2025-10-16 | 2025-10-16 | 2025-10-20 | 2025-10-23 | 2025-10-23 | 2025-10-23 | 2025-10-27 | 2025-10-29 | 2025-11-02 | 2025-11-09 | 2025-08-06 | 2025-08-08 | 2025-08-14 | 2025-08-20 | 2025-08-24 | 2025-08-25 | 2025-08-30 | 2025-08-30 | 2025-08-31 | 2025-09-04 | 2025-09-05 | 2025-09-08 | 2025-09-10 | 2025-09-11 | 2025-09-14 | 2025-09-17 | 2025-09-17 | 2025-09-20 | 2025-09-21 | 2025-09-22 | 2025-09-25 | 2025-09-29 | 2025-10-06 | 2025-10-11 | 2025-10-11 | 2025-10-13 | 2025-10-16 | 2025-10-16 | 2025-10-18 | 2025-10-27 | 2025-11-02 | 2025-09-25 | 2025-10-11 | 2025-10-13 | 2025-11-07 | 2025-11-03 | 2025-11-09 | 2025-11-12 | 2025-11-16 | 2025-11-21
V_525 | 2025-04-11 | 2025-04-18 | 2025-04-20 | 2025-04-26 | 2025-05-01 | 2025-05-04 | 2025-05-05 | 2025-05-09 | 2025-05-14 | 2025-05-17 | 2025-05-21 | 2025-05-21 | 2025-07-30 | 2025-08-06 | 2025-08-13 | 2025-08-13 | 2025-08-20 | 2025-08-27 | 2025-08-27 | 2025-08-30 | 2025-08-30 | 2025-08-31 | 2025-09-06 | 2025-09-06 | 2025-09-13 | 2025-09-13 | 2025-09-13 | 2025-09-18 | 2025-09-22 | 2025-09-29 | 2025-10-04 | 2025-10-09 | 2025-10-16 | 2025-10-16 | 2025-10-20 | 2025-10-23 | 2025-10-23 | 2025-10-23 | 2025-10-27 | 2025-10-29 | 2025-11-02 | 2025-11-09 | 2025-08-06 | 2025-08-08 | 2025-08-14 | 2025-08-20 | 2025-08-24 | 2025-08-25 | 2025-08-30 | 2025-08-30 | 2025-08-31 | 2025-09-04 | 2025-09-05 | 2025-09-08 | 2025-09-10 | 2025-09-11 | 2025-09-14 | 2025-09-17 | 2025-09-17 | 2025-09-20 | 2025-09-21 | 2025-09-22 | 2025-09-25 | 2025-09-29 | 2025-10-06 | 2025-10-11 | 2025-10-11 | 2025-10-13 | 2025-10-16 | 2025-10-16 | 2025-10-18 | 2025-10-27 | 2025-11-02 | 2025-09-25 | 2025-10-11 | 2025-10-13 | 2025-11-07 | 2025-11-03 | 2025-11-09 | 2025-11-12 | 2025-11-16 | 2025-11-21
V_526 | 2025-04-11 | 2025-04-18 | 2025-04-20 | 2025-04-26 | 2025-05-01 | 2025-05-04 | 2025-05-05 | 2025-05-09 | 2025-05-14 | 2025-05-17 | 2025-05-21 | 2025-05-21 | 2025-07-30 | 2025-08-06 | 2025-08-13 | 2025-08-13 | 2025-08-20 | 2025-08-27 | 2025-08-27 | 2025-08-30 | 2025-08-30 | 2025-08-31 | 2025-09-06 | 2025-09-06 | 2025-09-13 | 2025-09-13 | 2025-09-13 | 2025-09-18 | 2025-09-22 | 2025-09-29 | 2025-10-04 | 2025-10-09 | 2025-10-16 | 2025-10-16 | 2025-10-20 | 2025-10-23 | 2025-10-23 | 2025-10-23 | 2025-10-27 | 2025-10-29 | 2025-11-02 | 2025-11-09 | 2025-08-06 | 2025-08-08 | 2025-08-14 | 2025-08-20 | 2025-08-24 | 2025-08-25 | 2025-08-30 | 2025-08-30 | 2025-08-31 | 2025-09-04 | 2025-09-05 | 2025-09-08 | 2025-09-10 | 2025-09-11 | 2025-09-14 | 2025-09-17 | 2025-09-17 | 2025-09-20 | 2025-09-21 | 2025-09-22 | 2025-09-25 | 2025-09-29 | 2025-10-06 | 2025-10-11 | 2025-10-11 | 2025-10-13 | 2025-10-16 | 2025-10-16 | 2025-10-18 | 2025-10-27 | 2025-11-02 | 2025-09-25 | 2025-10-11 | 2025-10-13 | 2025-11-07 | 2025-11-03 | 2025-11-09 | 2025-11-12 | 2025-11-16 | 2025-11-21
V_527 | 2025-04-11 | 2025-04-18 | 2025-04-20 | 2025-04-26 | 2025-05-01 | 2025-05-04 | 2025-05-05 | 2025-05-09 | 2025-05-14 | 2025-05-17 | 2025-05-21 | 2025-05-21 | 2025-07-30 | 2025-08-06 | 2025-08-13 | 2025-08-13 | 2025-08-20 | 2025-08-27 | 2025-08-27 | 2025-08-30 | 2025-08-30 | 2025-08-31 | 2025-09-06 | 2025-09-06 | 2025-09-13 | 2025-09-13 | 2025-09-13 | 2025-09-18 | 2025-09-22 | 2025-09-29 | 2025-10-04 | 2025-10-09 | 2025-10-16 | 2025-10-16 | 2025-10-20 | 2025-10-23 | 2025-10-23 | 2025-10-23 | 2025-10-27 | 2025-10-29 | 2025-11-02 | 2025-11-09 | 2025-08-06 | 2025-08-08 | 2025-08-14 | 2025-08-20 | 2025-08-24 | 2025-08-25 | 2025-08-30 | 2025-08-30 | 2025-08-31 | 2025-09-04 | 2025-09-05 | 2025-09-08 | 2025-09-10 | 2025-09-11 | 2025-09-14 | 2025-09-17 | 2025-09-17 | 2025-09-20 | 2025-09-21 | 2025-09-22 | 2025-09-25 | 2025-09-29 | 2025-10-06 | 2025-10-11 | 2025-10-11 | 2025-10-13 | 2025-10-16 | 2025-10-16 | 2025-10-18 | 2025-10-27 | 2025-11-02 | 2025-09-25 | 2025-10-11 | 2025-10-13 | 2025-11-07 | 2025-11-03 | 2025-11-09 | 2025-11-12 | 2025-11-16 | 2025-11-21
V_528 | 2025-04-11 | 2025-04-18 | 2025-04-20 | 2025-04-26 | 2025-05-01 | 2025-05-04 | 2025-05-05 | 2025-05-09 | 2025-05-14 | 2025-05-17 | 2025-05-21 | 2025-05-21 | 2025-07-30 | 2025-08-06 | 2025-08-13 | 2025-08-13 | 2025-08-20 | 2025-08-27 | 2025-08-27 | 2025-08-30 | 2025-08-30 | 2025-08-31 | 2025-09-06 | 2025-09-06 | 2025-09-13 | 2025-09-13 | 2025-09-13 | 2025-09-18 | 2025-09-22 | 2025-09-29 | 2025-10-04 | 2025-10-09 | 2025-10-16 | 2025-10-16 | 2025-10-20 | 2025-10-23 | 2025-10-23 | 2025-10-23 | 2025-10-27 | 2025-10-29 | 2025-11-02 | 2025-11-09 | 2025-08-06 | 2025-08-08 | 2025-08-14 | 2025-08-20 | 2025-08-24 | 2025-08-25 | 2025-08-30 | 2025-08-30 | 2025-08-31 | 2025-09-04 | 2025-09-05 | 2025-09-08 | 2025-09-10 | 2025-09-11 | 2025-09-14 | 2025-09-17 | 2025-09-17 | 2025-09-20 | 2025-09-21 | 2025-09-22 | 2025-09-25 | 2025-09-29 | 2025-10-06 | 2025-10-11 | 2025-10-11 | 2025-10-13 | 2025-10-16 | 2025-10-16 | 2025-10-18 | 2025-10-27 | 2025-11-02 | 2025-09-25 | 2025-10-11 | 2025-10-13 | 2025-11-07 | 2025-11-03 | 2025-11-09 | 2025-11-12 | 2025-11-16 | 2025-11-21
V_529 | 2025-04-18 | 2025-04-25 | 2025-04-27 | 2025-05-03 | 2025-05-08 | 2025-05-11 | 2025-05-12 | 2025-05-16 | 2025-05-21 | 2025-05-24 | 2025-05-28 | 2025-05-28 | 2025-08-06 | 2025-08-13 | 2025-08-20 | 2025-08-20 | 2025-08-27 | 2025-09-03 | 2025-09-03 | 2025-09-06 | 2025-09-06 | 2025-09-07 | 2025-09-13 | 2025-09-13 | 2025-09-20 | 2025-09-20 | 2025-09-20 | 2025-09-25 | 2025-09-29 | 2025-10-06 | 2025-10-11 | 2025-10-16 | 2025-10-23 | 2025-10-23 | 2025-10-27 | 2025-10-30 | 2025-10-30 | 2025-10-30 | 2025-11-03 | 2025-11-05 | 2025-11-09 | 2025-11-16 | 2025-08-13 | 2025-08-15 | 2025-08-21 | 2025-08-27 | 2025-08-31 | 2025-09-01 | 2025-09-06 | 2025-09-06 | 2025-09-07 | 2025-09-11 | 2025-09-12 | 2025-09-15 | 2025-09-17 | 2025-09-18 | 2025-09-21 | 2025-09-22 | 2025-09-24 | 2025-09-27 | 2025-09-27 | 2025-09-28 | 2025-09-29 | 2025-10-04 | 2025-10-11 | 2025-10-16 | 2025-10-16 | 2025-10-19 | 2025-10-20 | 2025-10-20 | 2025-10-23 | 2025-11-02 | 2025-11-08 | 2025-10-02 | 2025-10-16 | 2025-10-18 | 2025-11-13 | 2025-11-10 | 2025-11-16 | 2025-11-17 | 2025-11-23 | 2025-11-28
V_530 | 2025-04-18 | 2025-04-25 | 2025-04-27 | 2025-05-03 | 2025-05-08 | 2025-05-11 | 2025-05-12 | 2025-05-16 | 2025-05-21 | 2025-05-24 | 2025-05-28 | 2025-05-28 | 2025-08-06 | 2025-08-13 | 2025-08-20 | 2025-08-20 | 2025-08-27 | 2025-09-03 | 2025-09-03 | 2025-09-06 | 2025-09-06 | 2025-09-07 | 2025-09-13 | 2025-09-13 | 2025-09-20 | 2025-09-20 | 2025-09-20 | 2025-09-25 | 2025-09-29 | 2025-10-06 | 2025-10-11 | 2025-10-16 | 2025-10-23 | 2025-10-23 | 2025-10-27 | 2025-10-30 | 2025-10-30 | 2025-10-30 | 2025-11-03 | 2025-11-05 | 2025-11-09 | 2025-11-16 | 2025-08-13 | 2025-08-15 | 2025-08-21 | 2025-08-27 | 2025-08-31 | 2025-09-01 | 2025-09-06 | 2025-09-06 | 2025-09-07 | 2025-09-11 | 2025-09-12 | 2025-09-15 | 2025-09-17 | 2025-09-18 | 2025-09-21 | 2025-09-22 | 2025-09-24 | 2025-09-27 | 2025-09-27 | 2025-09-28 | 2025-09-29 | 2025-10-04 | 2025-10-11 | 2025-10-16 | 2025-10-16 | 2025-10-19 | 2025-10-20 | 2025-10-20 | 2025-10-23 | 2025-11-02 | 2025-11-08 | 2025-10-02 | 2025-10-16 | 2025-10-18 | 2025-11-13 | 2025-11-10 | 2025-11-16 | 2025-11-17 | 2025-11-23 | 2025-11-28
V_531 | 2025-04-18 | 2025-04-25 | 2025-04-27 | 2025-05-03 | 2025-05-08 | 2025-05-11 | 2025-05-12 | 2025-05-16 | 2025-05-21 | 2025-05-24 | 2025-05-28 | 2025-05-28 | 2025-08-06 | 2025-08-13 | 2025-08-20 | 2025-08-20 | 2025-08-27 | 2025-09-03 | 2025-09-03 | 2025-09-06 | 2025-09-06 | 2025-09-07 | 2025-09-13 | 2025-09-13 | 2025-09-20 | 2025-09-20 | 2025-09-20 | 2025-09-25 | 2025-09-29 | 2025-10-06 | 2025-10-11 | 2025-10-16 | 2025-10-23 | 2025-10-23 | 2025-10-27 | 2025-10-30 | 2025-10-30 | 2025-10-30 | 2025-11-03 | 2025-11-05 | 2025-11-09 | 2025-11-16 | 2025-08-13 | 2025-08-15 | 2025-08-21 | 2025-08-27 | 2025-08-31 | 2025-09-01 | 2025-09-06 | 2025-09-06 | 2025-09-07 | 2025-09-11 | 2025-09-12 | 2025-09-15 | 2025-09-17 | 2025-09-18 | 2025-09-21 | 2025-09-22 | 2025-09-24 | 2025-09-27 | 2025-09-27 | 2025-09-28 | 2025-09-29 | 2025-10-04 | 2025-10-11 | 2025-10-16 | 2025-10-16 | 2025-10-19 | 2025-10-20 | 2025-10-20 | 2025-10-23 | 2025-11-02 | 2025-11-08 | 2025-10-02 | 2025-10-16 | 2025-10-18 | 2025-11-13 | 2025-11-10 | 2025-11-16 | 2025-11-17 | 2025-11-23 | 2025-11-28
V_532 | 2025-04-18 | 2025-04-25 | 2025-04-27 | 2025-05-03 | 2025-05-08 | 2025-05-11 | 2025-05-12 | 2025-05-16 | 2025-05-21 | 2025-05-24 | 2025-05-28 | 2025-05-28 | 2025-08-06 | 2025-08-13 | 2025-08-20 | 2025-08-20 | 2025-08-27 | 2025-09-03 | 2025-09-03 | 2025-09-06 | 2025-09-06 | 2025-09-07 | 2025-09-13 | 2025-09-13 | 2025-09-20 | 2025-09-20 | 2025-09-20 | 2025-09-25 | 2025-09-29 | 2025-10-06 | 2025-10-11 | 2025-10-16 | 2025-10-23 | 2025-10-23 | 2025-10-27 | 2025-10-30 | 2025-10-30 | 2025-10-30 | 2025-11-03 | 2025-11-05 | 2025-11-09 | 2025-11-16 | 2025-08-13 | 2025-08-15 | 2025-08-21 | 2025-08-27 | 2025-08-31 | 2025-09-01 | 2025-09-06 | 2025-09-06 | 2025-09-07 | 2025-09-11 | 2025-09-12 | 2025-09-15 | 2025-09-17 | 2025-09-18 | 2025-09-21 | 2025-09-22 | 2025-09-24 | 2025-09-27 | 2025-09-27 | 2025-09-28 | 2025-09-29 | 2025-10-04 | 2025-10-11 | 2025-10-16 | 2025-10-16 | 2025-10-19 | 2025-10-20 | 2025-10-20 | 2025-10-23 | 2025-11-02 | 2025-11-08 | 2025-10-02 | 2025-10-16 | 2025-10-18 | 2025-11-13 | 2025-11-10 | 2025-11-16 | 2025-11-17 | 2025-11-23 | 2025-11-28
V_533 | 2025-04-18 | 2025-04-25 | 2025-04-27 | 2025-05-03 | 2025-05-08 | 2025-05-11 | 2025-05-12 | 2025-05-16 | 2025-05-21 | 2025-05-24 | 2025-05-28 | 2025-05-28 | 2025-08-06 | 2025-08-13 | 2025-08-20 | 2025-08-20 | 2025-08-27 | 2025-09-03 | 2025-09-03 | 2025-09-06 | 2025-09-06 | 2025-09-07 | 2025-09-13 | 2025-09-13 | 2025-09-20 | 2025-09-20 | 2025-09-20 | 2025-09-25 | 2025-09-29 | 2025-10-06 | 2025-10-11 | 2025-10-16 | 2025-10-23 | 2025-10-23 | 2025-10-27 | 2025-10-30 | 2025-10-30 | 2025-10-30 | 2025-11-03 | 2025-11-05 | 2025-11-09 | 2025-11-16 | 2025-08-13 | 2025-08-15 | 2025-08-21 | 2025-08-27 | 2025-08-31 | 2025-09-01 | 2025-09-06 | 2025-09-06 | 2025-09-07 | 2025-09-11 | 2025-09-12 | 2025-09-15 | 2025-09-17 | 2025-09-18 | 2025-09-21 | 2025-09-22 | 2025-09-24 | 2025-09-27 | 2025-09-27 | 2025-09-28 | 2025-09-29 | 2025-10-04 | 2025-10-11 | 2025-10-16 | 2025-10-16 | 2025-10-19 | 2025-10-20 | 2025-10-20 | 2025-10-23 | 2025-11-02 | 2025-11-08 | 2025-10-02 | 2025-10-16 | 2025-10-18 | 2025-11-13 | 2025-11-10 | 2025-11-16 | 2025-11-17 | 2025-11-23 | 2025-11-28
V_534 | 2025-04-18 | [78 empty] | 2025-11-17 | 2025-11-23 | 2025-11-28
V_535 | 2025-04-18 | [78 empty] | 2025-11-17 | 2025-11-23 | 2025-11-28
V_536 | 2025-04-18 | [78 empty] | 2025-11-17 | 2025-11-23 | 2025-11-28
V_537 | 2025-04-25 | [78 empty] | 2025-11-23 | 2025-11-30 | 2025-12-05
V_538 | 2025-04-25 | [78 empty] | 2025-11-23 | 2025-11-30 | 2025-12-05
V_539 | 2025-04-25 | [78 empty] | 2025-11-23 | 2025-11-30 | 2025-12-05
V_540 | 2025-04-25 | 2025-05-02 | 2025-05-04 | 2025-05-10 | 2025-05-15 | 2025-05-18 | 2025-05-19 | 2025-05-23 | 2025-05-28 | 2025-05-31 | 2025-06-04 | 2025-06-04 | 2025-08-13 | 2025-08-20 | 2025-08-27 | 2025-08-27 | 2025-09-03 | 2025-09-10 | 2025-09-10 | 2025-09-13 | 2025-09-13 | 2025-09-14 | 2025-09-20 | 2025-09-20 | 2025-09-27 | 2025-09-27 | 2025-09-27 | 2025-10-02 | 2025-10-06 | 2025-10-13 | 2025-10-18 | 2025-10-23 | 2025-10-30 | 2025-10-30 | 2025-11-03 | 2025-11-06 | 2025-11-06 | 2025-11-06 | 2025-11-10 | 2025-11-12 | 2025-11-16 | 2025-11-23 | 2025-08-20 | 2025-08-22 | 2025-08-28 | 2025-09-03 | 2025-09-07 | 2025-09-08 | 2025-09-13 | 2025-09-13 | 2025-09-14 | 2025-09-18 | 2025-09-19 | 2025-09-22 | 2025-09-24 | 2025-09-25 | 2025-09-28 | 2025-09-29 | 2025-10-01 | 2025-10-04 | 2025-10-04 | 2025-10-05 | 2025-10-06 | 2025-10-11 | 2025-10-16 | 2025-10-20 | 2025-10-20 | 2025-10-25 | 2025-10-25 | 2025-10-25 | 2025-10-27 | 2025-11-08 | 2025-11-14 | 2025-10-09 | 2025-10-20 | 2025-10-23 | 2025-11-19 | 2025-11-17 | 2025-11-23 | 2025-11-23 | 2025-11-30 | 2025-12-05
V_541 | 2025-04-25 | 2025-05-02 | 2025-05-04 | 2025-05-10 | 2025-05-15 | 2025-05-18 | 2025-05-19 | 2025-05-23 | 2025-05-28 | 2025-05-31 | 2025-06-04 | 2025-06-04 | 2025-08-13 | 2025-08-20 | 2025-08-27 | 2025-08-27 | 2025-09-03 | 2025-09-10 | 2025-09-10 | 2025-09-13 | 2025-09-13 | 2025-09-14 | 2025-09-20 | 2025-09-20 | 2025-09-27 | 2025-09-27 | 2025-09-27 | 2025-10-02 | 2025-10-06 | 2025-10-13 | 2025-10-18 | 2025-10-23 | 2025-10-30 | 2025-10-30 | 2025-11-03 | 2025-11-06 | 2025-11-06 | 2025-11-06 | 2025-11-10 | 2025-11-12 | 2025-11-16 | 2025-11-23 | 2025-08-20 | 2025-08-22 | 2025-08-28 | 2025-09-03 | 2025-09-07 | 2025-09-08 | 2025-09-13 | 2025-09-13 | 2025-09-14 | 2025-09-18 | 2025-09-19 | 2025-09-22 | 2025-09-24 | 2025-09-25 | 2025-09-28 | 2025-09-29 | 2025-10-01 | 2025-10-04 | 2025-10-04 | 2025-10-05 | 2025-10-06 | 2025-10-11 | 2025-10-16 | 2025-10-20 | 2025-10-20 | 2025-10-25 | 2025-10-25 | 2025-10-25 | 2025-10-27 | 2025-11-08 | 2025-11-14 | 2025-10-09 | 2025-10-20 | 2025-10-23 | 2025-11-19 | 2025-11-17 | 2025-11-23 | 2025-11-23 | 2025-11-30 | 2025-12-05
V_542 | 2025-04-25 | 2025-05-02 | 2025-05-04 | 2025-05-10 | 2025-05-15 | 2025-05-18 | 2025-05-19 | 2025-05-23 | 2025-05-28 | 2025-05-31 | 2025-06-04 | 2025-06-04 | 2025-08-13 | 2025-08-20 | 2025-08-27 | 2025-08-27 | 2025-09-03 | 2025-09-10 | 2025-09-10 | 2025-09-13 | 2025-09-13 | 2025-09-14 | 2025-09-20 | 2025-09-20 | 2025-09-27 | 2025-09-27 | 2025-09-27 | 2025-10-02 | 2025-10-06 | 2025-10-13 | 2025-10-18 | 2025-10-23 | 2025-10-30 | 2025-10-30 | 2025-11-03 | 2025-11-06 | 2025-11-06 | 2025-11-06 | 2025-11-10 | 2025-11-12 | 2025-11-16 | 2025-11-23 | 2025-08-20 | 2025-08-22 | 2025-08-28 | 2025-09-03 | 2025-09-07 | 2025-09-08 | 2025-09-13 | 2025-09-13 | 2025-09-14 | 2025-09-18 | 2025-09-19 | 2025-09-22 | 2025-09-24 | 2025-09-25 | 2025-09-28 | 2025-09-29 | 2025-10-01 | 2025-10-04 | 2025-10-04 | 2025-10-05 | 2025-10-06 | 2025-10-11 | 2025-10-16 | 2025-10-20 | 2025-10-20 | 2025-10-25 | 2025-10-25 | 2025-10-25 | 2025-10-27 | 2025-11-08 | 2025-11-14 | 2025-10-09 | 2025-10-20 | 2025-10-23 | 2025-11-19 | 2025-11-17 | 2025-11-23 | 2025-11-23 | 2025-11-30 | 2025-12-05
V_543 | 2025-04-25 | 2025-05-02 | 2025-05-04 | 2025-05-10 | 2025-05-15 | 2025-05-18 | 2025-05-19 | 2025-05-23 | 2025-05-28 | 2025-05-31 | 2025-06-04 | 2025-06-04 | 2025-08-13 | 2025-08-20 | 2025-08-27 | 2025-08-27 | 2025-09-03 | 2025-09-10 | 2025-09-10 | 2025-09-13 | 2025-09-13 | 2025-09-14 | 2025-09-20 | 2025-09-20 | 2025-09-27 | 2025-09-27 | 2025-09-27 | 2025-10-02 | 2025-10-06 | 2025-10-13 | 2025-10-18 | 2025-10-23 | 2025-10-30 | 2025-10-30 | 2025-11-03 | 2025-11-06 | 2025-11-06 | 2025-11-06 | 2025-11-10 | 2025-11-12 | 2025-11-16 | 2025-11-23 | 2025-08-20 | 2025-08-22 | 2025-08-28 | 2025-09-03 | 2025-09-07 | 2025-09-08 | 2025-09-13 | 2025-09-13 | 2025-09-14 | 2025-09-18 | 2025-09-19 | 2025-09-22 | 2025-09-24 | 2025-09-25 | 2025-09-28 | 2025-09-29 | 2025-10-01 | 2025-10-04 | 2025-10-04 | 2025-10-05 | 2025-10-06 | 2025-10-11 | 2025-10-16 | 2025-10-20 | 2025-10-20 | 2025-10-25 | 2025-10-25 | 2025-10-25 | 2025-10-27 | 2025-11-08 | 2025-11-14 | 2025-10-09 | 2025-10-20 | 2025-10-23 | 2025-11-19 | 2025-11-17 | 2025-11-23 | 2025-11-23 | 2025-11-30 | 2025-12-05
V_544 | 2025-04-25 | 2025-05-02 | 2025-05-04 | 2025-05-10 | 2025-05-15 | 2025-05-18 | 2025-05-19 | 2025-05-23 | 2025-05-28 | 2025-05-31 | 2025-06-04 | 2025-06-04 | 2025-08-13 | 2025-08-20 | 2025-08-27 | 2025-08-27 | 2025-09-03 | 2025-09-10 | 2025-09-10 | 2025-09-13 | 2025-09-13 | 2025-09-14 | 2025-09-20 | 2025-09-20 | 2025-09-27 | 2025-09-27 | 2025-09-27 | 2025-10-02 | 2025-10-06 | 2025-10-13 | 2025-10-18 | 2025-10-23 | 2025-10-30 | 2025-10-30 | 2025-11-03 | 2025-11-06 | 2025-11-06 | 2025-11-06 | 2025-11-10 | 2025-11-12 | 2025-11-16 | 2025-11-23 | 2025-08-20 | 2025-08-22 | 2025-08-28 | 2025-09-03 | 2025-09-07 | 2025-09-08 | 2025-09-13 | 2025-09-13 | 2025-09-14 | 2025-09-18 | 2025-09-19 | 2025-09-22 | 2025-09-24 | 2025-09-25 | 2025-09-28 | 2025-09-29 | 2025-10-01 | 2025-10-04 | 2025-10-04 | 2025-10-05 | 2025-10-06 | 2025-10-11 | 2025-10-16 | 2025-10-20 | 2025-10-20 | 2025-10-25 | 2025-10-25 | 2025-10-25 | 2025-10-27 | 2025-11-08 | 2025-11-14 | 2025-10-09 | 2025-10-20 | 2025-10-23 | 2025-11-19 | 2025-11-17 | 2025-11-23 | 2025-11-23 | 2025-11-30 | 2025-12-05
V_545 | 2025-05-02 | 2025-05-09 | 2025-05-11 | 2025-05-17 | 2025-05-22 | 2025-05-25 | 2025-05-26 | 2025-05-30 | 2025-06-04 | 2025-06-07 | 2025-06-11 | 2025-06-11 | 2025-08-20 | 2025-08-27 | 2025-09-03 | 2025-09-03 | 2025-09-10 | 2025-09-17 | 2025-09-17 | 2025-09-20 | 2025-09-20 | 2025-09-21 | 2025-09-27 | 2025-09-27 | 2025-10-04 | 2025-10-04 | 2025-10-04 | 2025-10-09 | 2025-10-13 | 2025-10-20 | 2025-10-25 | 2025-10-30 | 2025-11-06 | 2025-11-06 | 2025-11-10 | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-11-17 | 2025-11-19 | 2025-11-23 | 2025-11-30 | 2025-08-27 | 2025-08-29 | 2025-09-04 | 2025-09-10 | 2025-09-14 | 2025-09-15 | 2025-09-20 | 2025-09-20 | 2025-09-21 | 2025-09-25 | 2025-09-26 | 2025-09-29 | 2025-10-01 | 2025-10-02 | 2025-10-05 | 2025-10-06 | 2025-10-08 | 2025-10-11 | 2025-10-11 | 2025-10-12 | 2025-10-13 | 2025-10-18 | 2025-10-23 | 2025-10-27 | 2025-10-27 | 2025-10-31 | 2025-11-01 | 2025-11-01 | 2025-11-03 | 2025-11-14 | 2025-11-20 | 2025-10-16 | 2025-10-27 | 2025-10-30 | 2025-11-24 | 2025-11-24 | 2025-11-29 | 2025-11-30 | 2025-12-07 | 2025-12-12
V_546 | 2025-05-02 | 2025-05-09 | 2025-05-11 | 2025-05-17 | 2025-05-22 | 2025-05-25 | 2025-05-26 | 2025-05-30 | 2025-06-04 | 2025-06-07 | 2025-06-11 | 2025-06-11 | 2025-08-20 | 2025-08-27 | 2025-09-03 | 2025-09-03 | 2025-09-10 | 2025-09-17 | 2025-09-17 | 2025-09-20 | 2025-09-20 | 2025-09-21 | 2025-09-27 | 2025-09-27 | 2025-10-04 | 2025-10-04 | 2025-10-04 | 2025-10-09 | 2025-10-13 | 2025-10-20 | 2025-10-25 | 2025-10-30 | 2025-11-06 | 2025-11-06 | 2025-11-10 | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-11-17 | 2025-11-19 | 2025-11-23 | 2025-11-30 | 2025-08-27 | 2025-08-29 | 2025-09-04 | 2025-09-10 | 2025-09-14 | 2025-09-15 | 2025-09-20 | 2025-09-20 | 2025-09-21 | 2025-09-25 | 2025-09-26 | 2025-09-29 | 2025-10-01 | 2025-10-02 | 2025-10-05 | 2025-10-06 | 2025-10-08 | 2025-10-11 | 2025-10-11 | 2025-10-12 | 2025-10-13 | 2025-10-18 | 2025-10-23 | 2025-10-27 | 2025-10-27 | 2025-10-31 | 2025-11-01 | 2025-11-01 | 2025-11-03 | 2025-11-14 | 2025-11-20 | 2025-10-16 | 2025-10-27 | 2025-10-30 | 2025-11-24 | 2025-11-24 | 2025-11-29 | 2025-11-30 | 2025-12-07 | 2025-12-12
V_547 | 2025-05-02 | 2025-05-09 | 2025-05-11 | 2025-05-17 | 2025-05-22 | 2025-05-25 | 2025-05-26 | 2025-05-30 | 2025-06-04 | 2025-06-07 | 2025-06-11 | 2025-06-11 | 2025-08-20 | 2025-08-27 | 2025-09-03 | 2025-09-03 | 2025-09-10 | 2025-09-17 | 2025-09-17 | 2025-09-20 | 2025-09-20 | 2025-09-21 | 2025-09-27 | 2025-09-27 | 2025-10-04 | 2025-10-04 | 2025-10-04 | 2025-10-09 | 2025-10-13 | 2025-10-20 | 2025-10-25 | 2025-10-30 | 2025-11-06 | 2025-11-06 | 2025-11-10 | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-11-17 | 2025-11-19 | 2025-11-23 | 2025-11-30 | 2025-08-27 | 2025-08-29 | 2025-09-04 | 2025-09-10 | 2025-09-14 | 2025-09-15 | 2025-09-20 | 2025-09-20 | 2025-09-21 | 2025-09-25 | 2025-09-26 | 2025-09-29 | 2025-10-01 | 2025-10-02 | 2025-10-05 | 2025-10-06 | 2025-10-08 | 2025-10-11 | 2025-10-11 | 2025-10-12 | 2025-10-13 | 2025-10-18 | 2025-10-23 | 2025-10-27 | 2025-10-27 | 2025-10-31 | 2025-11-01 | 2025-11-01 | 2025-11-03 | 2025-11-14 | 2025-11-20 | 2025-10-16 | 2025-10-27 | 2025-10-30 | 2025-11-24 | 2025-11-24 | 2025-11-29 | 2025-11-30 | 2025-12-07 | 2025-12-12
V_548 | 2025-05-02 | 2025-05-09 | 2025-05-11 | 2025-05-17 | 2025-05-22 | 2025-05-25 | 2025-05-26 | 2025-05-30 | 2025-06-04 | 2025-06-07 | 2025-06-11 | 2025-06-11 | 2025-08-20 | 2025-08-27 | 2025-09-03 | 2025-09-03 | 2025-09-10 | 2025-09-17 | 2025-09-17 | 2025-09-20 | 2025-09-20 | 2025-09-21 | 2025-09-27 | 2025-09-27 | 2025-10-04 | 2025-10-04 | 2025-10-04 | 2025-10-09 | 2025-10-13 | 2025-10-20 | 2025-10-25 | 2025-10-30 | 2025-11-06 | 2025-11-06 | 2025-11-10 | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-11-17 | 2025-11-19 | 2025-11-23 | 2025-11-30 | 2025-08-27 | 2025-08-29 | 2025-09-04 | 2025-09-10 | 2025-09-14 | 2025-09-15 | 2025-09-20 | 2025-09-20 | 2025-09-21 | 2025-09-25 | 2025-09-26 | 2025-09-29 | 2025-10-01 | 2025-10-02 | 2025-10-05 | 2025-10-06 | 2025-10-08 | 2025-10-11 | 2025-10-11 | 2025-10-12 | 2025-10-13 | 2025-10-18 | 2025-10-23 | 2025-10-27 | 2025-10-27 | 2025-10-31 | 2025-11-01 | 2025-11-01 | 2025-11-03 | 2025-11-14 | 2025-11-20 | 2025-10-16 | 2025-10-27 | 2025-10-30 | 2025-11-24 | 2025-11-24 | 2025-11-29 | 2025-11-30 | 2025-12-07 | 2025-12-12
V_549 | 2025-05-02 | 2025-05-09 | 2025-05-11 | 2025-05-17 | 2025-05-22 | 2025-05-25 | 2025-05-26 | 2025-05-30 | 2025-06-04 | 2025-06-07 | 2025-06-11 | 2025-06-11 | 2025-08-20 | 2025-08-27 | 2025-09-03 | 2025-09-03 | 2025-09-10 | 2025-09-17 | 2025-09-17 | 2025-09-20 | 2025-09-20 | 2025-09-21 | 2025-09-27 | 2025-09-27 | 2025-10-04 | 2025-10-04 | 2025-10-04 | 2025-10-09 | 2025-10-13 | 2025-10-20 | 2025-10-25 | 2025-10-30 | 2025-11-06 | 2025-11-06 | 2025-11-10 | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-11-17 | 2025-11-19 | 2025-11-23 | 2025-11-30 | 2025-08-27 | 2025-08-29 | 2025-09-04 | 2025-09-10 | 2025-09-14 | 2025-09-15 | 2025-09-20 | 2025-09-20 | 2025-09-21 | 2025-09-25 | 2025-09-26 | 2025-09-29 | 2025-10-01 | 2025-10-02 | 2025-10-05 | 2025-10-06 | 2025-10-08 | 2025-10-11 | 2025-10-11 | 2025-10-12 | 2025-10-13 | 2025-10-18 | 2025-10-23 | 2025-10-27 | 2025-10-27 | 2025-10-31 | 2025-11-01 | 2025-11-01 | 2025-11-03 | 2025-11-14 | 2025-11-20 | 2025-10-16 | 2025-10-27 | 2025-10-30 | 2025-11-24 | 2025-11-24 | 2025-11-29 | 2025-11-30 | 2025-12-07 | 2025-12-12
V_550 | 2025-05-02 | 2025-05-09 | 2025-05-11 | 2025-05-17 | 2025-05-22 | 2025-05-25 | 2025-05-26 | 2025-05-30 | 2025-06-04 | 2025-06-07 | 2025-06-11 | 2025-06-11 | 2025-08-20 | 2025-08-27 | 2025-09-03 | 2025-09-03 | 2025-09-10 | 2025-09-17 | 2025-09-17 | 2025-09-20 | 2025-09-20 | 2025-09-21 | 2025-09-27 | 2025-09-27 | 2025-10-04 | 2025-10-04 | 2025-10-04 | 2025-10-09 | 2025-10-13 | 2025-10-20 | 2025-10-25 | 2025-10-30 | 2025-11-06 | 2025-11-06 | 2025-11-10 | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-11-17 | 2025-11-19 | 2025-11-23 | 2025-11-30 | 2025-08-27 | 2025-08-29 | 2025-09-04 | 2025-09-10 | 2025-09-14 | 2025-09-15 | 2025-09-20 | 2025-09-20 | 2025-09-21 | 2025-09-25 | 2025-09-26 | 2025-09-29 | 2025-10-01 | 2025-10-02 | 2025-10-05 | 2025-10-06 | 2025-10-08 | 2025-10-11 | 2025-10-11 | 2025-10-12 | 2025-10-13 | 2025-10-18 | 2025-10-23 | 2025-10-27 | 2025-10-27 | 2025-10-31 | 2025-11-01 | 2025-11-01 | 2025-11-03 | 2025-11-14 | 2025-11-20 | 2025-10-16 | 2025-10-27 | 2025-10-30 | 2025-11-24 | 2025-11-24 | 2025-11-29 | 2025-11-30 | 2025-12-07 | 2025-12-12
V_551 | 2025-05-02 | 2025-05-09 | 2025-05-11 | 2025-05-17 | 2025-05-22 | 2025-05-25 | 2025-05-26 | 2025-05-30 | 2025-06-04 | 2025-06-07 | 2025-06-11 | 2025-06-11 | 2025-08-20 | 2025-08-27 | 2025-09-03 | 2025-09-03 | 2025-09-10 | 2025-09-17 | 2025-09-17 | 2025-09-20 | 2025-09-20 | 2025-09-21 | 2025-09-27 | 2025-09-27 | 2025-10-04 | 2025-10-04 | 2025-10-04 | 2025-10-09 | 2025-10-13 | 2025-10-20 | 2025-10-25 | 2025-10-30 | 2025-11-06 | 2025-11-06 | 2025-11-10 | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-11-17 | 2025-11-19 | 2025-11-23 | 2025-11-30 | 2025-08-27 | 2025-08-29 | 2025-09-04 | 2025-09-10 | 2025-09-14 | 2025-09-15 | 2025-09-20 | 2025-09-20 | 2025-09-21 | 2025-09-25 | 2025-09-26 | 2025-09-29 | 2025-10-01 | 2025-10-02 | 2025-10-05 | 2025-10-06 | 2025-10-08 | 2025-10-11 | 2025-10-11 | 2025-10-12 | 2025-10-13 | 2025-10-18 | 2025-10-23 | 2025-10-27 | 2025-10-27 | 2025-10-31 | 2025-11-01 | 2025-11-01 | 2025-11-03 | 2025-11-14 | 2025-11-20 | 2025-10-16 | 2025-10-27 | 2025-10-30 | 2025-11-24 | 2025-11-24 | 2025-11-29 | 2025-11-30 | 2025-12-07 | 2025-12-12
V_552 | 2025-05-02 | 2025-05-09 | 2025-05-11 | 2025-05-17 | 2025-05-22 | 2025-05-25 | 2025-05-26 | 2025-05-30 | 2025-06-04 | 2025-06-07 | 2025-06-11 | 2025-06-11 | 2025-08-20 | 2025-08-27 | 2025-09-03 | 2025-09-03 | 2025-09-10 | 2025-09-17 | 2025-09-17 | 2025-09-20 | 2025-09-20 | 2025-09-21 | 2025-09-27 | 2025-09-27 | 2025-10-04 | 2025-10-04 | 2025-10-04 | 2025-10-09 | 2025-10-13 | 2025-10-20 | 2025-10-25 | 2025-10-30 | 2025-11-06 | 2025-11-06 | 2025-11-10 | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-11-17 | 2025-11-19 | 2025-11-23 | 2025-11-30 | 2025-08-27 | 2025-08-29 | 2025-09-04 | 2025-09-10 | 2025-09-14 | 2025-09-15 | 2025-09-20 | 2025-09-20 | 2025-09-21 | 2025-09-25 | 2025-09-26 | 2025-09-29 | 2025-10-01 | 2025-10-02 | 2025-10-05 | 2025-10-06 | 2025-10-08 | 2025-10-11 | 2025-10-11 | 2025-10-12 | 2025-10-13 | 2025-10-18 | 2025-10-23 | 2025-10-27 | 2025-10-27 | 2025-10-31 | 2025-11-01 | 2025-11-01 | 2025-11-03 | 2025-11-14 | 2025-11-20 | 2025-10-16 | 2025-10-27 | 2025-10-30 | 2025-11-24 | 2025-11-24 | 2025-11-29 | 2025-11-30 | 2025-12-07 | 2025-12-12
V_553 | 2025-05-09 | 2025-05-16 | 2025-05-18 | 2025-05-24 | 2025-05-29 | 2025-06-01 | 2025-06-02 | 2025-06-06 | 2025-06-11 | 2025-06-14 | 2025-06-18 | 2025-06-18 | 2025-08-27 | 2025-09-03 | 2025-09-10 | 2025-09-10 | 2025-09-17 | 2025-09-24 | 2025-09-24 | 2025-09-27 | 2025-09-27 | 2025-09-28 | 2025-10-04 | 2025-10-04 | 2025-10-11 | 2025-10-11 | 2025-10-11 | 2025-10-16 | 2025-10-20 | 2025-10-27 | 2025-11-01 | 2025-11-06 | 2025-11-13 | 2025-11-13 | 2025-11-17 | 2025-11-20 | 2025-11-20 | 2025-11-20 | 2025-11-24 | 2025-11-26 | 2025-11-30 | 2025-12-07 | 2025-09-03 | 2025-09-05 | 2025-09-11 | 2025-09-17 | 2025-09-21 | 2025-09-22 | 2025-09-27 | 2025-09-27 | 2025-09-28 | 2025-10-02 | 2025-10-03 | 2025-10-06 | 2025-10-08 | 2025-10-09 | 2025-10-12 | 2025-10-13 | 2025-10-15 | 2025-10-18 | 2025-10-18 | 2025-10-19 | 2025-10-20 | 2025-10-25 | 2025-10-30 | 2025-11-03 | 2025-11-03 | 2025-11-06 | 2025-11-08 | 2025-11-08 | 2025-11-10 | 2025-11-20 | 2025-11-26 | 2025-10-23 | 2025-11-03 | 2025-11-06 | 2025-11-30 | 2025-12-01 | 2025-12-05 | 2025-12-07 | 2025-12-14 | 2025-12-19
V_554 | 2025-05-09 | 2025-05-16 | 2025-05-18 | 2025-05-24 | 2025-05-29 | 2025-06-01 | 2025-06-02 | 2025-06-06 | 2025-06-11 | 2025-06-14 | 2025-06-18 | 2025-06-18 | 2025-08-27 | 2025-09-03 | 2025-09-10 | 2025-09-10 | 2025-09-17 | 2025-09-24 | 2025-09-24 | 2025-09-27 | 2025-09-27 | 2025-09-28 | 2025-10-04 | 2025-10-04 | 2025-10-11 | 2025-10-11 | 2025-10-11 | 2025-10-16 | 2025-10-20 | 2025-10-27 | 2025-11-01 | 2025-11-06 | 2025-11-13 | 2025-11-13 | 2025-11-17 | 2025-11-20 | 2025-11-20 | 2025-11-20 | 2025-11-24 | 2025-11-26 | 2025-11-30 | 2025-12-07 | 2025-09-03 | 2025-09-05 | 2025-09-11 | 2025-09-17 | 2025-09-21 | 2025-09-22 | 2025-09-27 | 2025-09-27 | 2025-09-28 | 2025-10-02 | 2025-10-03 | 2025-10-06 | 2025-10-08 | 2025-10-09 | 2025-10-12 | 2025-10-13 | 2025-10-15 | 2025-10-18 | 2025-10-18 | 2025-10-19 | 2025-10-20 | 2025-10-25 | 2025-10-30 | 2025-11-03 | 2025-11-03 | 2025-11-06 | 2025-11-08 | 2025-11-08 | 2025-11-10 | 2025-11-20 | 2025-11-26 | 2025-10-23 | 2025-11-03 | 2025-11-06 | 2025-11-30 | 2025-12-01 | 2025-12-05 | 2025-12-07 | 2025-12-14 | 2025-12-19
V_555 | 2025-05-09 | 2025-05-16 | 2025-05-18 | 2025-05-24 | 2025-05-29 | 2025-06-01 | 2025-06-02 | 2025-06-06 | 2025-06-11 | 2025-06-14 | 2025-06-18 | 2025-06-18 | 2025-08-27 | 2025-09-03 | 2025-09-10 | 2025-09-10 | 2025-09-17 | 2025-09-24 | 2025-09-24 | 2025-09-27 | 2025-09-27 | 2025-09-28 | 2025-10-04 | 2025-10-04 | 2025-10-11 | 2025-10-11 | 2025-10-11 | 2025-10-16 | 2025-10-20 | 2025-10-27 | 2025-11-01 | 2025-11-06 | 2025-11-13 | 2025-11-13 | 2025-11-17 | 2025-11-20 | 2025-11-20 | 2025-11-20 | 2025-11-24 | 2025-11-26 | 2025-11-30 | 2025-12-07 | 2025-09-03 | 2025-09-05 | 2025-09-11 | 2025-09-17 | 2025-09-21 | 2025-09-22 | 2025-09-27 | 2025-09-27 | 2025-09-28 | 2025-10-02 | 2025-10-03 | 2025-10-06 | 2025-10-08 | 2025-10-09 | 2025-10-12 | 2025-10-13 | 2025-10-15 | 2025-10-18 | 2025-10-18 | 2025-10-19 | 2025-10-20 | 2025-10-25 | 2025-10-30 | 2025-11-03 | 2025-11-03 | 2025-11-06 | 2025-11-08 | 2025-11-08 | 2025-11-10 | 2025-11-20 | 2025-11-26 | 2025-10-23 | 2025-11-03 | 2025-11-06 | 2025-11-30 | 2025-12-01 | 2025-12-05 | 2025-12-07 | 2025-12-14 | 2025-12-19
V_556 | 2025-05-09 | 2025-05-16 | 2025-05-18 | 2025-05-24 | 2025-05-29 | 2025-06-01 | 2025-06-02 | 2025-06-06 | 2025-06-11 | 2025-06-14 | 2025-06-18 | 2025-06-18 | 2025-08-27 | 2025-09-03 | 2025-09-10 | 2025-09-10 | 2025-09-17 | 2025-09-24 | 2025-09-24 | 2025-09-27 | 2025-09-27 | 2025-09-28 | 2025-10-04 | 2025-10-04 | 2025-10-11 | 2025-10-11 | 2025-10-11 | 2025-10-16 | 2025-10-20 | 2025-10-27 | 2025-11-01 | 2025-11-06 | 2025-11-13 | 2025-11-13 | 2025-11-17 | 2025-11-20 | 2025-11-20 | 2025-11-20 | 2025-11-24 | 2025-11-26 | 2025-11-30 | 2025-12-07 | 2025-09-03 | 2025-09-05 | 2025-09-11 | 2025-09-17 | 2025-09-21 | 2025-09-22 | 2025-09-27 | 2025-09-27 | 2025-09-28 | 2025-10-02 | 2025-10-03 | 2025-10-06 | 2025-10-08 | 2025-10-09 | 2025-10-12 | 2025-10-13 | 2025-10-15 | 2025-10-18 | 2025-10-18 | 2025-10-19 | 2025-10-20 | 2025-10-25 | 2025-10-30 | 2025-11-03 | 2025-11-03 | 2025-11-06 | 2025-11-08 | 2025-11-08 | 2025-11-10 | 2025-11-20 | 2025-11-26 | 2025-10-23 | 2025-11-03 | 2025-11-06 | 2025-11-30 | 2025-12-01 | 2025-12-05 | 2025-12-07 | 2025-12-14 | 2025-12-19
V_557 | 2025-05-09 | 2025-05-16 | 2025-05-18 | 2025-05-24 | 2025-05-29 | 2025-06-01 | 2025-06-02 | 2025-06-06 | 2025-06-11 | 2025-06-14 | 2025-06-18 | 2025-06-18 | 2025-08-27 | 2025-09-03 | 2025-09-10 | 2025-09-10 | 2025-09-17 | 2025-09-24 | 2025-09-24 | 2025-09-27 | 2025-09-27 | 2025-09-28 | 2025-10-04 | 2025-10-04 | 2025-10-11 | 2025-10-11 | 2025-10-11 | 2025-10-16 | 2025-10-20 | 2025-10-27 | 2025-11-01 | 2025-11-06 | 2025-11-13 | 2025-11-13 | 2025-11-17 | 2025-11-20 | 2025-11-20 | 2025-11-20 | 2025-11-24 | 2025-11-26 | 2025-11-30 | 2025-12-07 | 2025-09-03 | 2025-09-05 | 2025-09-11 | 2025-09-17 | 2025-09-21 | 2025-09-22 | 2025-09-27 | 2025-09-27 | 2025-09-28 | 2025-10-02 | 2025-10-03 | 2025-10-06 | 2025-10-08 | 2025-10-09 | 2025-10-12 | 2025-10-13 | 2025-10-15 | 2025-10-18 | 2025-10-18 | 2025-10-19 | 2025-10-20 | 2025-10-25 | 2025-10-30 | 2025-11-03 | 2025-11-03 | 2025-11-06 | 2025-11-08 | 2025-11-08 | 2025-11-10 | 2025-11-20 | 2025-11-26 | 2025-10-23 | 2025-11-03 | 2025-11-06 | 2025-11-30 | 2025-12-01 | 2025-12-05 | 2025-12-07 | 2025-12-14 | 2025-12-19
V_558 | 2025-05-09 | 2025-05-16 | 2025-05-18 | 2025-05-24 | 2025-05-29 | 2025-06-01 | 2025-06-02 | 2025-06-06 | 2025-06-11 | 2025-06-14 | 2025-06-18 | 2025-06-18 | 2025-08-27 | 2025-09-03 | 2025-09-10 | 2025-09-10 | 2025-09-17 | 2025-09-24 | 2025-09-24 | 2025-09-27 | 2025-09-27 | 2025-09-28 | 2025-10-04 | 2025-10-04 | 2025-10-11 | 2025-10-11 | 2025-10-11 | 2025-10-16 | 2025-10-20 | 2025-10-27 | 2025-11-01 | 2025-11-06 | 2025-11-13 | 2025-11-13 | 2025-11-17 | 2025-11-20 | 2025-11-20 | 2025-11-20 | 2025-11-24 | 2025-11-26 | 2025-11-30 | 2025-12-07 | 2025-09-03 | 2025-09-05 | 2025-09-11 | 2025-09-17 | 2025-09-21 | 2025-09-22 | 2025-09-27 | 2025-09-27 | 2025-09-28 | 2025-10-02 | [29 empty] | 2025-12-19
V_559 | 2025-05-09 | 2025-05-16 | 2025-05-18 | 2025-05-24 | 2025-05-29 | 2025-06-01 | 2025-06-02 | 2025-06-06 | 2025-06-11 | 2025-06-14 | 2025-06-18 | 2025-06-18 | 2025-08-27 | 2025-09-03 | 2025-09-10 | 2025-09-10 | 2025-09-17 | 2025-09-24 | 2025-09-24 | 2025-09-27 | 2025-09-27 | 2025-09-28 | 2025-10-04 | 2025-10-04 | 2025-10-11 | 2025-10-11 | 2025-10-11 | 2025-10-16 | 2025-10-20 | 2025-10-27 | 2025-11-01 | 2025-11-06 | 2025-11-13 | 2025-11-13 | 2025-11-17 | 2025-11-20 | 2025-11-20 | 2025-11-20 | 2025-11-24 | 2025-11-26 | 2025-11-30 | 2025-12-07 | 2025-09-03 | 2025-09-05 | 2025-09-11 | 2025-09-17 | 2025-09-21 | 2025-09-22 | 2025-09-27 | 2025-09-27 | 2025-09-28 | 2025-10-02 | [29 empty] | 2025-12-19
V_560 | 2025-05-09 | 2025-05-16 | 2025-05-18 | 2025-05-24 | 2025-05-29 | 2025-06-01 | 2025-06-02 | 2025-06-06 | 2025-06-11 | 2025-06-14 | 2025-06-18 | 2025-06-18 | 2025-08-27 | 2025-09-03 | 2025-09-10 | 2025-09-10 | 2025-09-17 | 2025-09-24 | 2025-09-24 | 2025-09-27 | 2025-09-27 | 2025-09-28 | 2025-10-04 | 2025-10-04 | 2025-10-11 | 2025-10-11 | 2025-10-11 | 2025-10-16 | 2025-10-20 | 2025-10-27 | 2025-11-01 | 2025-11-06 | 2025-11-13 | 2025-11-13 | 2025-11-17 | 2025-11-20 | 2025-11-20 | 2025-11-20 | 2025-11-24 | 2025-11-26 | 2025-11-30 | 2025-12-07 | 2025-09-03 | 2025-09-05 | 2025-09-11 | 2025-09-17 | 2025-09-21 | 2025-09-22 | 2025-09-27 | 2025-09-27 | 2025-09-28 | 2025-10-02 | [29 empty] | 2025-12-19
V_561 | 2025-05-16 | 2025-05-23 | 2025-05-25 | 2025-05-31 | 2025-06-05 | 2025-06-08 | 2025-06-09 | 2025-06-13 | 2025-06-18 | 2025-06-21 | 2025-06-25 | 2025-06-25 | 2025-09-03 | 2025-09-10 | 2025-09-17 | 2025-09-17 | 2025-09-24 | 2025-10-01 | 2025-10-01 | 2025-10-04 | 2025-10-04 | 2025-10-05 | 2025-10-11 | 2025-10-11 | 2025-10-18 | 2025-10-18 | 2025-10-18 | 2025-10-23 | 2025-10-27 | 2025-11-03 | 2025-11-08 | 2025-11-13 | 2025-11-20 | 2025-11-20 | 2025-11-24 | 2025-11-27 | 2025-11-27 | 2025-11-27 | 2025-12-01 | 2025-12-03 | 2025-12-07 | 2025-12-14 | 2025-09-10 | 2025-09-12 | 2025-09-18 | 2025-09-24 | 2025-09-28 | 2025-09-29 | 2025-10-04 | 2025-10-04 | 2025-10-05 | 2025-10-09 | [29 empty] | 2025-12-26
V_562 | 2025-05-16 | 2025-05-23 | 2025-05-25 | 2025-05-31 | 2025-06-05 | 2025-06-08 | 2025-06-09 | 2025-06-13 | 2025-06-18 | 2025-06-21 | 2025-06-25 | 2025-06-25 | 2025-09-03 | 2025-09-10 | 2025-09-17 | 2025-09-17 | 2025-09-24 | 2025-10-01 | 2025-10-01 | 2025-10-04 | 2025-10-04 | 2025-10-05 | 2025-10-11 | 2025-10-11 | 2025-10-18 | 2025-10-18 | 2025-10-18 | 2025-10-23 | 2025-10-27 | 2025-11-03 | 2025-11-08 | 2025-11-13 | 2025-11-20 | 2025-11-20 | 2025-11-24 | 2025-11-27 | 2025-11-27 | 2025-11-27 | 2025-12-01 | 2025-12-03 | 2025-12-07 | 2025-12-14 | 2025-09-10 | 2025-09-12 | 2025-09-18 | 2025-09-24 | 2025-09-28 | 2025-09-29 | 2025-10-04 | 2025-10-04 | 2025-10-05 | 2025-10-09 | [29 empty] | 2025-12-26
V_563 | 2025-05-16 | 2025-05-23 | 2025-05-25 | 2025-05-31 | 2025-06-05 | 2025-06-08 | 2025-06-09 | 2025-06-13 | 2025-06-18 | 2025-06-21 | 2025-06-25 | 2025-06-25 | 2025-09-03 | 2025-09-10 | 2025-09-17 | 2025-09-17 | 2025-09-24 | 2025-10-01 | 2025-10-01 | 2025-10-04 | 2025-10-04 | 2025-10-05 | 2025-10-11 | 2025-10-11 | 2025-10-18 | 2025-10-18 | 2025-10-18 | 2025-10-23 | 2025-10-27 | 2025-11-03 | 2025-11-08 | 2025-11-13 | 2025-11-20 | 2025-11-20 | 2025-11-24 | 2025-11-27 | 2025-11-27 | 2025-11-27 | 2025-12-01 | 2025-12-03 | 2025-12-07 | 2025-12-14 | 2025-09-10 | 2025-09-12 | 2025-09-18 | 2025-09-24 | 2025-09-28 | 2025-09-29 | 2025-10-04 | 2025-10-04 | 2025-10-05 | 2025-10-09 | [29 empty] | 2025-12-26
V_564 | 2025-05-16 | 2025-05-23 | 2025-05-25 | 2025-05-31 | 2025-06-05 | 2025-06-08 | 2025-06-09 | 2025-06-13 | 2025-06-18 | 2025-06-21 | 2025-06-25 | 2025-06-25 | 2025-09-03 | 2025-09-10 | 2025-09-17 | 2025-09-17 | 2025-09-24 | 2025-10-01 | 2025-10-01 | 2025-10-04 | 2025-10-04 | 2025-10-05 | 2025-10-11 | 2025-10-11 | 2025-10-18 | 2025-10-18 | 2025-10-18 | 2025-10-23 | 2025-10-27 | 2025-11-03 | 2025-11-08 | 2025-11-13 | 2025-11-20 | 2025-11-20 | 2025-11-24 | 2025-11-27 | 2025-11-27 | 2025-11-27 | 2025-12-01 | 2025-12-03 | 2025-12-07 | 2025-12-14 | 2025-09-10 | 2025-09-12 | 2025-09-18 | 2025-09-24 | 2025-09-28 | 2025-09-29 | 2025-10-04 | 2025-10-04 | 2025-10-05 | 2025-10-09 | [29 empty] | 2025-12-26
V_565 | 2025-05-16 | 2025-05-23 | 2025-05-25 | 2025-05-31 | 2025-06-05 | 2025-06-08 | 2025-06-09 | 2025-06-13 | 2025-06-18 | 2025-06-21 | 2025-06-25 | 2025-06-25 | 2025-09-03 | 2025-09-10 | 2025-09-17 | 2025-09-17 | 2025-09-24 | 2025-10-01 | 2025-10-01 | 2025-10-04 | 2025-10-04 | 2025-10-05 | 2025-10-11 | 2025-10-11 | 2025-10-18 | 2025-10-18 | 2025-10-18 | 2025-10-23 | 2025-10-27 | 2025-11-03 | 2025-11-08 | 2025-11-13 | 2025-11-20 | 2025-11-20 | 2025-11-24 | 2025-11-27 | 2025-11-27 | 2025-11-27 | 2025-12-01 | 2025-12-03 | 2025-12-07 | 2025-12-14 | 2025-09-10 | 2025-09-12 | 2025-09-18 | 2025-09-24 | 2025-09-28 | 2025-09-29 | 2025-10-04 | 2025-10-04 | 2025-10-05 | 2025-10-09 | [29 empty] | 2025-12-26
V_566 | 2025-05-16 | 2025-05-23 | 2025-05-25 | 2025-05-31 | 2025-06-05 | 2025-06-08 | 2025-06-09 | 2025-06-13 | 2025-06-18 | 2025-06-21 | 2025-06-25 | 2025-06-25 | 2025-09-03 | 2025-09-10 | 2025-09-17 | 2025-09-17 | 2025-09-24 | 2025-10-01 | 2025-10-01 | 2025-10-04 | 2025-10-04 | 2025-10-05 | 2025-10-11 | 2025-10-11 | 2025-10-18 | 2025-10-18 | 2025-10-18 | 2025-10-23 | 2025-10-27 | 2025-11-03 | 2025-11-08 | 2025-11-13 | 2025-11-20 | 2025-11-20 | 2025-11-24 | 2025-11-27 | 2025-11-27 | 2025-11-27 | 2025-12-01 | 2025-12-03 | 2025-12-07 | 2025-12-14 | 2025-09-10 | 2025-09-12 | 2025-09-18 | 2025-09-24 | 2025-09-28 | 2025-09-29 | 2025-10-04 | 2025-10-04 | 2025-10-05 | 2025-10-09 | [29 empty] | 2025-12-26
V_567 | 2025-05-16 | 2025-05-23 | 2025-05-25 | 2025-05-31 | 2025-06-05 | 2025-06-08 | 2025-06-09 | 2025-06-13 | 2025-06-18 | 2025-06-21 | 2025-06-25 | 2025-06-25 | 2025-09-03 | 2025-09-10 | 2025-09-17 | 2025-09-17 | 2025-09-24 | 2025-10-01 | 2025-10-01 | 2025-10-04 | 2025-10-04 | 2025-10-05 | 2025-10-11 | 2025-10-11 | 2025-10-18 | 2025-10-18 | 2025-10-18 | 2025-10-23 | 2025-10-27 | 2025-11-03 | 2025-11-08 | 2025-11-13 | 2025-11-20 | 2025-11-20 | 2025-11-24 | 2025-11-27 | 2025-11-27 | 2025-11-27 | 2025-12-01 | 2025-12-03 | 2025-12-07 | 2025-12-14 | 2025-09-10 | 2025-09-12 | 2025-09-18 | 2025-09-24 | 2025-09-28 | 2025-09-29 | 2025-10-04 | 2025-10-04 | 2025-10-05 | 2025-10-09 | [29 empty] | 2025-12-26
V_568 | 2025-05-16 | 2025-05-23 | 2025-05-25 | 2025-05-31 | 2025-06-05 | 2025-06-08 | 2025-06-09 | 2025-06-13 | 2025-06-18 | 2025-06-21 | 2025-06-25 | 2025-06-25 | 2025-09-03 | 2025-09-10 | 2025-09-17 | 2025-09-17 | 2025-09-24 | 2025-10-01 | 2025-10-01 | 2025-10-04 | 2025-10-04 | 2025-10-05 | 2025-10-11 | 2025-10-11 | 2025-10-18 | 2025-10-18 | 2025-10-18 | 2025-10-23 | 2025-10-27 | 2025-11-03 | 2025-11-08 | 2025-11-13 | 2025-11-20 | 2025-11-20 | 2025-11-24 | 2025-11-27 | 2025-11-27 | 2025-11-27 | 2025-12-01 | 2025-12-03 | 2025-12-07 | 2025-12-14 | 2025-09-10 | 2025-09-12 | 2025-09-18 | 2025-09-24 | 2025-09-28 | 2025-09-29 | 2025-10-04 | 2025-10-04 | 2025-10-05 | 2025-10-09 | [29 empty] | 2025-12-26
V_569 | 2025-05-23 | 2025-05-30 | 2025-06-01 | 2025-06-07 | 2025-06-12 | 2025-06-15 | 2025-06-16 | 2025-06-20 | 2025-06-25 | 2025-06-28 | 2025-07-02 | 2025-07-02 | 2025-09-10 | 2025-09-17 | 2025-09-24 | 2025-09-24 | 2025-10-01 | 2025-10-08 | 2025-10-08 | 2025-10-11 | 2025-10-11 | 2025-10-12 | 2025-10-18 | 2025-10-18 | 2025-10-25 | 2025-10-25 | 2025-10-25 | 2025-10-30 | 2025-11-03 | 2025-11-10 | 2025-11-15 | 2025-11-20 | 2025-11-27 | 2025-11-27 | 2025-12-01 | 2025-12-04 | 2025-12-04 | 2025-12-04 | 2025-12-08 | 2025-12-10 | 2025-12-14 | 2025-12-21 | 2025-09-17 | 2025-09-19 | 2025-09-25 | 2025-10-01 | 2025-10-05 | 2025-10-06 | 2025-10-11 | 2025-10-11 | 2025-10-12 | 2025-10-16 | [29 empty] | 2026-01-02
V_570 | 2025-05-23 | 2025-05-30 | 2025-06-01 | 2025-06-07 | 2025-06-12 | 2025-06-15 | 2025-06-16 | 2025-06-20 | 2025-06-25 | 2025-06-28 | 2025-07-02 | 2025-07-02 | 2025-09-10 | 2025-09-17 | 2025-09-24 | 2025-09-24 | 2025-10-01 | 2025-10-08 | 2025-10-08 | 2025-10-11 | 2025-10-11 | 2025-10-12 | 2025-10-18 | 2025-10-18 | 2025-10-25 | 2025-10-25 | 2025-10-25 | 2025-10-30 | 2025-11-03 | 2025-11-10 | 2025-11-15 | 2025-11-20 | 2025-11-27 | 2025-11-27 | 2025-12-01 | 2025-12-04 | 2025-12-04 | 2025-12-04 | 2025-12-08 | 2025-12-10 | 2025-12-14 | 2025-12-21 | 2025-09-17 | 2025-09-19 | 2025-09-25 | 2025-10-01 | 2025-10-05 | 2025-10-06 | 2025-10-11 | 2025-10-11 | 2025-10-12 | 2025-10-16 | [29 empty] | 2026-01-02
V_571 | 2025-05-23 | 2025-05-30 | 2025-06-01 | 2025-06-07 | 2025-06-12 | 2025-06-15 | 2025-06-16 | 2025-06-20 | 2025-06-25 | 2025-06-28 | 2025-07-02 | 2025-07-02 | 2025-09-10 | 2025-09-17 | 2025-09-24 | 2025-09-24 | 2025-10-01 | 2025-10-08 | 2025-10-08 | 2025-10-11 | 2025-10-11 | 2025-10-12 | 2025-10-18 | 2025-10-18 | 2025-10-25 | 2025-10-25 | 2025-10-25 | 2025-10-30 | 2025-11-03 | 2025-11-10 | 2025-11-15 | 2025-11-20 | 2025-11-27 | 2025-11-27 | 2025-12-01 | 2025-12-04 | 2025-12-04 | 2025-12-04 | 2025-12-08 | 2025-12-10 | 2025-12-14 | 2025-12-21 | 2025-09-17 | 2025-09-19 | 2025-09-25 | 2025-10-01 | 2025-10-05 | 2025-10-06 | 2025-10-11 | 2025-10-11 | 2025-10-12 | 2025-10-16 | 2025-10-17 | 2025-10-20 | 2025-10-22 | 2025-10-23 | 2025-10-26 | 2025-10-27 | 2025-10-29 | 2025-11-01 | 2025-11-01 | 2025-11-02 | 2025-11-03 | 2025-11-08 | 2025-11-13 | 2025-11-17 | 2025-11-17 | 2025-11-17 | 2025-11-22 | 2025-11-22 | 2025-11-24 | 2025-12-01 | 2025-12-07 | 2025-11-06 | 2025-11-17 | 2025-11-20 | 2025-12-12 | 2025-12-15 | 2025-12-17 | 2025-12-21 | 2025-12-28 | 2026-01-02
V_572 | 2025-05-23 | 2025-05-30 | 2025-06-01 | 2025-06-07 | 2025-06-12 | 2025-06-15 | 2025-06-16 | 2025-06-20 | 2025-06-25 | 2025-06-28 | 2025-07-02 | 2025-07-02 | 2025-09-10 | 2025-09-17 | 2025-09-24 | 2025-09-24 | 2025-10-01 | 2025-10-08 | 2025-10-08 | 2025-10-11 | 2025-10-11 | 2025-10-12 | 2025-10-18 | 2025-10-18 | 2025-10-25 | 2025-10-25 | 2025-10-25 | 2025-10-30 | 2025-11-03 | 2025-11-10 | 2025-11-15 | 2025-11-20 | 2025-11-27 | 2025-11-27 | 2025-12-01 | 2025-12-04 | 2025-12-04 | 2025-12-04 | 2025-12-08 | 2025-12-10 | 2025-12-14 | 2025-12-21 | 2025-09-17 | 2025-09-19 | 2025-09-25 | 2025-10-01 | 2025-10-05 | 2025-10-06 | 2025-10-11 | 2025-10-11 | 2025-10-12 | 2025-10-16 | 2025-10-17 | 2025-10-20 | 2025-10-22 | 2025-10-23 | 2025-10-26 | 2025-10-27 | 2025-10-29 | 2025-11-01 | 2025-11-01 | 2025-11-02 | 2025-11-03 | 2025-11-08 | 2025-11-13 | 2025-11-17 | 2025-11-17 | 2025-11-17 | 2025-11-22 | 2025-11-22 | 2025-11-24 | 2025-12-01 | 2025-12-07 | 2025-11-06 | 2025-11-17 | 2025-11-20 | 2025-12-12 | 2025-12-15 | 2025-12-17 | 2025-12-21 | 2025-12-28 | 2026-01-02
V_573 | 2025-05-23 | 2025-05-30 | 2025-06-01 | 2025-06-07 | 2025-06-12 | 2025-06-15 | 2025-06-16 | 2025-06-20 | 2025-06-25 | 2025-06-28 | 2025-07-02 | 2025-07-02 | 2025-09-10 | 2025-09-17 | 2025-09-24 | 2025-09-24 | 2025-10-01 | 2025-10-08 | 2025-10-08 | 2025-10-11 | 2025-10-11 | 2025-10-12 | 2025-10-18 | 2025-10-18 | 2025-10-25 | 2025-10-25 | 2025-10-25 | 2025-10-30 | 2025-11-03 | 2025-11-10 | 2025-11-15 | 2025-11-20 | 2025-11-27 | 2025-11-27 | 2025-12-01 | 2025-12-04 | 2025-12-04 | 2025-12-04 | 2025-12-08 | 2025-12-10 | 2025-12-14 | 2025-12-21 | 2025-09-17 | 2025-09-19 | 2025-09-25 | 2025-10-01 | 2025-10-05 | 2025-10-06 | 2025-10-11 | 2025-10-11 | 2025-10-12 | 2025-10-16 | 2025-10-17 | 2025-10-20 | 2025-10-22 | 2025-10-23 | 2025-10-26 | 2025-10-27 | 2025-10-29 | 2025-11-01 | 2025-11-01 | 2025-11-02 | 2025-11-03 | 2025-11-08 | 2025-11-13 | 2025-11-17 | 2025-11-17 | 2025-11-17 | 2025-11-22 | 2025-11-22 | 2025-11-24 | 2025-12-01 | 2025-12-07 | 2025-11-06 | 2025-11-17 | 2025-11-20 | 2025-12-12 | 2025-12-15 | 2025-12-17 | 2025-12-21 | 2025-12-28 | 2026-01-02
V_574 | 2025-05-23 | 2025-05-30 | 2025-06-01 | 2025-06-07 | 2025-06-12 | 2025-06-15 | 2025-06-16 | 2025-06-20 | 2025-06-25 | 2025-06-28 | 2025-07-02 | 2025-07-02 | 2025-09-10 | 2025-09-17 | 2025-09-24 | 2025-09-24 | 2025-10-01 | 2025-10-08 | 2025-10-08 | 2025-10-11 | 2025-10-11 | 2025-10-12 | 2025-10-18 | 2025-10-18 | 2025-10-25 | 2025-10-25 | 2025-10-25 | 2025-10-30 | 2025-11-03 | 2025-11-10 | 2025-11-15 | 2025-11-20 | 2025-11-27 | 2025-11-27 | 2025-12-01 | 2025-12-04 | 2025-12-04 | 2025-12-04 | 2025-12-08 | 2025-12-10 | 2025-12-14 | 2025-12-21 | 2025-09-17 | 2025-09-19 | 2025-09-25 | 2025-10-01 | 2025-10-05 | 2025-10-06 | 2025-10-11 | 2025-10-11 | 2025-10-12 | 2025-10-16 | 2025-10-17 | 2025-10-20 | 2025-10-22 | 2025-10-23 | 2025-10-26 | 2025-10-27 | 2025-10-29 | 2025-11-01 | 2025-11-01 | 2025-11-02 | 2025-11-03 | 2025-11-08 | 2025-11-13 | 2025-11-17 | 2025-11-17 | 2025-11-17 | 2025-11-22 | 2025-11-22 | 2025-11-24 | 2025-12-01 | 2025-12-07 | 2025-11-06 | 2025-11-17 | 2025-11-20 | 2025-12-12 | 2025-12-15 | 2025-12-17 | 2025-12-21 | 2025-12-28 | 2026-01-02
V_575 | 2025-05-23 | 2025-05-30 | 2025-06-01 | 2025-06-07 | 2025-06-12 | 2025-06-15 | 2025-06-16 | 2025-06-20 | 2025-06-25 | 2025-06-28 | 2025-07-02 | 2025-07-02 | 2025-09-10 | 2025-09-17 | 2025-09-24 | 2025-09-24 | 2025-10-01 | 2025-10-08 | 2025-10-08 | 2025-10-11 | 2025-10-11 | 2025-10-12 | 2025-10-18 | 2025-10-18 | 2025-10-25 | 2025-10-25 | 2025-10-25 | 2025-10-30 | 2025-11-03 | 2025-11-10 | 2025-11-15 | 2025-11-20 | 2025-11-27 | 2025-11-27 | 2025-12-01 | 2025-12-04 | 2025-12-04 | 2025-12-04 | 2025-12-08 | 2025-12-10 | 2025-12-14 | 2025-12-21 | 2025-09-17 | 2025-09-19 | 2025-09-25 | 2025-10-01 | 2025-10-05 | 2025-10-06 | 2025-10-11 | 2025-10-11 | 2025-10-12 | 2025-10-16 | 2025-10-17 | 2025-10-20 | 2025-10-22 | 2025-10-23 | 2025-10-26 | 2025-10-27 | 2025-10-29 | 2025-11-01 | 2025-11-01 | 2025-11-02 | 2025-11-03 | 2025-11-08 | 2025-11-13 | 2025-11-17 | 2025-11-17 | 2025-11-17 | 2025-11-22 | 2025-11-22 | 2025-11-24 | 2025-12-01 | 2025-12-07 | 2025-11-06 | 2025-11-17 | 2025-11-20 | 2025-12-12 | 2025-12-15 | 2025-12-17 | 2025-12-21 | 2025-12-28 | 2026-01-02
V_576 | 2025-05-23 | 2025-05-30 | 2025-06-01 | 2025-06-07 | 2025-06-12 | 2025-06-15 | 2025-06-16 | 2025-06-20 | 2025-06-25 | 2025-06-28 | 2025-07-02 | 2025-07-02 | 2025-09-10 | 2025-09-17 | 2025-09-24 | 2025-09-24 | 2025-10-01 | 2025-10-08 | 2025-10-08 | 2025-10-11 | 2025-10-11 | 2025-10-12 | 2025-10-18 | 2025-10-18 | 2025-10-25 | 2025-10-25 | 2025-10-25 | 2025-10-30 | 2025-11-03 | 2025-11-10 | 2025-11-15 | 2025-11-20 | 2025-11-27 | 2025-11-27 | 2025-12-01 | 2025-12-04 | 2025-12-04 | 2025-12-04 | 2025-12-08 | 2025-12-10 | 2025-12-14 | 2025-12-21 | 2025-09-17 | 2025-09-19 | 2025-09-25 | 2025-10-01 | 2025-10-05 | 2025-10-06 | 2025-10-11 | 2025-10-11 | 2025-10-12 | 2025-10-16 | 2025-10-17 | 2025-10-20 | 2025-10-22 | 2025-10-23 | 2025-10-26 | 2025-10-27 | 2025-10-29 | 2025-11-01 | 2025-11-01 | 2025-11-02 | 2025-11-03 | 2025-11-08 | 2025-11-13 | 2025-11-17 | 2025-11-17 | 2025-11-17 | 2025-11-22 | 2025-11-22 | 2025-11-24 | 2025-12-01 | 2025-12-07 | 2025-11-06 | 2025-11-17 | 2025-11-20 | 2025-12-12 | 2025-12-15 | 2025-12-17 | 2025-12-21 | 2025-12-28 | 2026-01-02
V_577 | 2025-05-30 | 2025-06-06 | 2025-06-08 | 2025-06-14 | 2025-06-19 | 2025-06-22 | 2025-06-23 | 2025-06-27 | 2025-07-02 | 2025-07-05 | 2025-07-09 | 2025-07-09 | 2025-09-17 | 2025-09-24 | 2025-10-01 | 2025-10-01 | 2025-10-08 | 2025-10-15 | 2025-10-15 | 2025-10-18 | 2025-10-18 | 2025-10-19 | 2025-10-25 | 2025-10-25 | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-11-06 | 2025-11-10 | 2025-11-17 | 2025-11-22 | 2025-11-27 | 2025-12-04 | 2025-12-04 | 2025-12-08 | 2025-12-11 | 2025-12-11 | 2025-12-11 | 2025-12-15 | 2025-12-17 | 2025-12-21 | 2025-12-28 | 2025-09-24 | 2025-09-26 | 2025-10-02 | 2025-10-08 | 2025-10-12 | 2025-10-13 | 2025-10-18 | 2025-10-18 | 2025-10-19 | 2025-10-23 | 2025-10-24 | 2025-10-27 | 2025-10-29 | 2025-10-30 | 2025-11-02 | 2025-11-03 | 2025-11-05 | 2025-11-08 | 2025-11-08 | 2025-11-09 | 2025-11-10 | 2025-11-15 | 2025-11-20 | 2025-11-24 | 2025-11-24 | 2025-11-24 | 2025-11-29 | 2025-11-29 | 2025-12-01 | 2025-12-07 | 2025-12-13 | 2025-11-13 | 2025-11-24 | 2025-11-27 | 2025-12-18 | 2025-12-22 | 2025-12-22 | 2025-12-28 | 2026-01-04 | 2026-01-09
V_578 | 2025-05-30 | 2025-06-06 | 2025-06-08 | 2025-06-14 | 2025-06-19 | 2025-06-22 | 2025-06-23 | 2025-06-27 | 2025-07-02 | 2025-07-05 | 2025-07-09 | 2025-07-09 | 2025-09-17 | 2025-09-24 | 2025-10-01 | 2025-10-01 | 2025-10-08 | 2025-10-15 | 2025-10-15 | 2025-10-18 | 2025-10-18 | 2025-10-19 | 2025-10-25 | 2025-10-25 | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-11-06 | 2025-11-10 | 2025-11-17 | 2025-11-22 | 2025-11-27 | 2025-12-04 | 2025-12-04 | 2025-12-08 | 2025-12-11 | 2025-12-11 | 2025-12-11 | 2025-12-15 | 2025-12-17 | 2025-12-21 | 2025-12-28 | 2025-09-24 | 2025-09-26 | 2025-10-02 | 2025-10-08 | 2025-10-12 | 2025-10-13 | 2025-10-18 | 2025-10-18 | 2025-10-19 | 2025-10-23 | 2025-10-24 | 2025-10-27 | 2025-10-29 | 2025-10-30 | 2025-11-02 | 2025-11-03 | 2025-11-05 | 2025-11-08 | 2025-11-08 | 2025-11-09 | 2025-11-10 | 2025-11-15 | 2025-11-20 | 2025-11-24 | 2025-11-24 | 2025-11-24 | 2025-11-29 | 2025-11-29 | 2025-12-01 | 2025-12-07 | 2025-12-13 | 2025-11-13 | 2025-11-24 | 2025-11-27 | 2025-12-18 | 2025-12-22 | 2025-12-22 | 2025-12-28 | 2026-01-04 | 2026-01-09
V_579 | 2025-05-30 | 2025-06-06 | 2025-06-08 | 2025-06-14 | 2025-06-19 | 2025-06-22 | 2025-06-23 | 2025-06-27 | 2025-07-02 | 2025-07-05 | 2025-07-09 | 2025-07-09 | 2025-09-17 | 2025-09-24 | 2025-10-01 | 2025-10-01 | 2025-10-08 | 2025-10-15 | 2025-10-15 | 2025-10-18 | 2025-10-18 | 2025-10-19 | 2025-10-25 | 2025-10-25 | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-11-06 | 2025-11-10 | 2025-11-17 | 2025-11-22 | 2025-11-27 | 2025-12-04 | 2025-12-04 | 2025-12-08 | 2025-12-11 | 2025-12-11 | 2025-12-11 | 2025-12-15 | 2025-12-17 | 2025-12-21 | 2025-12-28 | 2025-09-24 | 2025-09-26 | 2025-10-02 | 2025-10-08 | 2025-10-12 | 2025-10-13 | 2025-10-18 | 2025-10-18 | 2025-10-19 | 2025-10-23 | 2025-10-24 | 2025-10-27 | 2025-10-29 | 2025-10-30 | 2025-11-02 | 2025-11-03 | 2025-11-05 | 2025-11-08 | 2025-11-08 | 2025-11-09 | 2025-11-10 | 2025-11-15 | 2025-11-20 | 2025-11-24 | 2025-11-24 | 2025-11-24 | 2025-11-29 | 2025-11-29 | 2025-12-01 | 2025-12-07 | 2025-12-13 | 2025-11-13 | 2025-11-24 | 2025-11-27 | 2025-12-18 | 2025-12-22 | 2025-12-22 | 2025-12-28 | 2026-01-04 | 2026-01-09
V_580 | 2025-05-30 | 2025-06-06 | 2025-06-08 | 2025-06-14 | 2025-06-19 | 2025-06-22 | 2025-06-23 | 2025-06-27 | 2025-07-02 | 2025-07-05 | 2025-07-09 | 2025-07-09 | 2025-09-17 | 2025-09-24 | 2025-10-01 | 2025-10-01 | 2025-10-08 | 2025-10-15 | 2025-10-15 | 2025-10-18 | 2025-10-18 | 2025-10-19 | 2025-10-25 | 2025-10-25 | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-11-06 | 2025-11-10 | 2025-11-17 | 2025-11-22 | 2025-11-27 | 2025-12-04 | 2025-12-04 | 2025-12-08 | 2025-12-11 | 2025-12-11 | 2025-12-11 | 2025-12-15 | 2025-12-17 | 2025-12-21 | 2025-12-28 | 2025-09-24 | 2025-09-26 | 2025-10-02 | 2025-10-08 | 2025-10-12 | 2025-10-13 | 2025-10-18 | 2025-10-18 | 2025-10-19 | 2025-10-23 | 2025-10-24 | 2025-10-27 | 2025-10-29 | 2025-10-30 | 2025-11-02 | 2025-11-03 | 2025-11-05 | 2025-11-08 | 2025-11-08 | 2025-11-09 | 2025-11-10 | 2025-11-15 | 2025-11-20 | 2025-11-24 | 2025-11-24 | 2025-11-24 | 2025-11-29 | 2025-11-29 | 2025-12-01 | 2025-12-07 | 2025-12-13 | 2025-11-13 | 2025-11-24 | 2025-11-27 | 2025-12-18 | 2025-12-22 | 2025-12-22 | 2025-12-28 | 2026-01-04 | 2026-01-09
V_581 | 2025-05-30 | 2025-06-06 | 2025-06-08 | 2025-06-14 | 2025-06-19 | 2025-06-22 | 2025-06-23 | 2025-06-27 | 2025-07-02 | 2025-07-05 | 2025-07-09 | 2025-07-09 | 2025-09-17 | 2025-09-24 | 2025-10-01 | 2025-10-01 | 2025-10-08 | 2025-10-15 | 2025-10-15 | 2025-10-18 | 2025-10-18 | 2025-10-19 | 2025-10-25 | 2025-10-25 | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-11-06 | 2025-11-10 | 2025-11-17 | 2025-11-22 | 2025-11-27 | 2025-12-04 | 2025-12-04 | 2025-12-08 | 2025-12-11 | 2025-12-11 | 2025-12-11 | 2025-12-15 | 2025-12-17 | 2025-12-21 | 2025-12-28 | 2025-09-24 | 2025-09-26 | 2025-10-02 | 2025-10-08 | 2025-10-12 | 2025-10-13 | 2025-10-18 | 2025-10-18 | 2025-10-19 | 2025-10-23 | 2025-10-24 | 2025-10-27 | 2025-10-29 | 2025-10-30 | 2025-11-02 | 2025-11-03 | 2025-11-05 | 2025-11-08 | 2025-11-08 | 2025-11-09 | 2025-11-10 | 2025-11-15 | 2025-11-20 | 2025-11-24 | 2025-11-24 | 2025-11-24 | 2025-11-29 | 2025-11-29 | 2025-12-01 | 2025-12-07 | 2025-12-13 | 2025-11-13 | 2025-11-24 | 2025-11-27 | 2025-12-18 | 2025-12-22 | 2025-12-22 | 2025-12-28 | 2026-01-04 | 2026-01-09
V_582 | 2025-05-30 | 2025-06-06 | 2025-06-08 | 2025-06-14 | 2025-06-19 | 2025-06-22 | 2025-06-23 | 2025-06-27 | 2025-07-02 | 2025-07-05 | 2025-07-09 | 2025-07-09 | 2025-09-17 | 2025-09-24 | 2025-10-01 | 2025-10-01 | 2025-10-08 | 2025-10-15 | 2025-10-15 | 2025-10-18 | 2025-10-18 | 2025-10-19 | 2025-10-25 | 2025-10-25 | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-11-06 | 2025-11-10 | 2025-11-17 | 2025-11-22 | 2025-11-27 | 2025-12-04 | 2025-12-04 | 2025-12-08 | 2025-12-11 | 2025-12-11 | 2025-12-11 | 2025-12-15 | 2025-12-17 | 2025-12-21 | 2025-12-28 | 2025-09-24 | 2025-09-26 | 2025-10-02 | 2025-10-08 | 2025-10-12 | 2025-10-13 | 2025-10-18 | 2025-10-18 | 2025-10-19 | 2025-10-23 | 2025-10-24 | 2025-10-27 | 2025-10-29 | 2025-10-30 | 2025-11-02 | 2025-11-03 | 2025-11-05 | 2025-11-08 | 2025-11-08 | 2025-11-09 | 2025-11-10 | 2025-11-15 | 2025-11-20 | 2025-11-24 | 2025-11-24 | 2025-11-24 | 2025-11-29 | 2025-11-29 | 2025-12-01 | 2025-12-07 | 2025-12-13 | 2025-11-13 | 2025-11-24 | 2025-11-27 | 2025-12-18 | 2025-12-22 | 2025-12-22 | 2025-12-28 | 2026-01-04 | 2026-01-09
V_583 | 2025-05-30 | 2025-06-06 | 2025-06-08 | 2025-06-14 | 2025-06-19 | 2025-06-22 | 2025-06-23 | 2025-06-27 | 2025-07-02 | 2025-07-05 | 2025-07-09 | 2025-07-09 | 2025-09-17 | 2025-09-24 | 2025-10-01 | 2025-10-01 | 2025-10-08 | 2025-10-15 | 2025-10-15 | 2025-10-18 | 2025-10-18 | 2025-10-19 | 2025-10-25 | 2025-10-25 | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-11-06 | 2025-11-10 | 2025-11-17 | 2025-11-22 | 2025-11-27 | 2025-12-04 | 2025-12-04 | 2025-12-08 | 2025-12-11 | 2025-12-11 | 2025-12-11 | 2025-12-15 | 2025-12-17 | 2025-12-21 | 2025-12-28 | 2025-09-24 | 2025-09-26 | 2025-10-02 | 2025-10-08 | 2025-10-12 | 2025-10-13 | 2025-10-18 | 2025-10-18 | 2025-10-19 | 2025-10-23 | 2025-10-24 | 2025-10-27 | 2025-10-29 | 2025-10-30 | 2025-11-02 | 2025-11-03 | 2025-11-05 | 2025-11-08 | 2025-11-08 | 2025-11-09 | 2025-11-10 | 2025-11-15 | 2025-11-20 | 2025-11-24 | 2025-11-24 | 2025-11-24 | 2025-11-29 | 2025-11-29 | 2025-12-01 | 2025-12-07 | 2025-12-13 | 2025-11-13 | 2025-11-24 | 2025-11-27 | 2025-12-18 | 2025-12-22 | 2025-12-22 | 2025-12-28 | 2026-01-04 | 2026-01-09
V_584 | 2025-05-30 | 2025-06-06 | 2025-06-08 | 2025-06-14 | 2025-06-19 | 2025-06-22 | 2025-06-23 | 2025-06-27 | 2025-07-02 | 2025-07-05 | 2025-07-09 | 2025-07-09 | 2025-09-17 | 2025-09-24 | 2025-10-01 | 2025-10-01 | 2025-10-08 | 2025-10-15 | 2025-10-15 | 2025-10-18 | 2025-10-18 | 2025-10-19 | 2025-10-25 | 2025-10-25 | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-11-06 | 2025-11-10 | 2025-11-17 | 2025-11-22 | 2025-11-27 | 2025-12-04 | 2025-12-04 | 2025-12-08 | 2025-12-11 | 2025-12-11 | 2025-12-11 | 2025-12-15 | 2025-12-17 | 2025-12-21 | 2025-12-28 | 2025-09-24 | 2025-09-26 | 2025-10-02 | 2025-10-08 | 2025-10-12 | 2025-10-13 | 2025-10-18 | 2025-10-18 | 2025-10-19 | 2025-10-23 | 2025-10-24 | 2025-10-27 | 2025-10-29 | 2025-10-30 | 2025-11-02 | 2025-11-03 | 2025-11-05 | 2025-11-08 | 2025-11-08 | 2025-11-09 | 2025-11-10 | 2025-11-15 | 2025-11-20 | 2025-11-24 | 2025-11-24 | 2025-11-24 | 2025-11-29 | 2025-11-29 | 2025-12-01 | 2025-12-07 | 2025-12-13 | 2025-11-13 | 2025-11-24 | 2025-11-27 | 2025-12-18 | 2025-12-22 | 2025-12-22 | 2025-12-28 | 2026-01-04 | 2026-01-09
V_585 | 2025-06-06 | 2025-06-13 | 2025-06-15 | 2025-06-21 | 2025-06-26 | 2025-06-29 | 2025-06-30 | 2025-07-04 | 2025-07-09 | 2025-07-12 | 2025-07-16 | 2025-07-16 | 2025-09-24 | 2025-10-01 | 2025-10-08 | 2025-10-08 | 2025-10-15 | 2025-10-22 | 2025-10-22 | 2025-10-25 | 2025-10-25 | 2025-10-26 | 2025-11-01 | 2025-11-01 | 2025-11-08 | 2025-11-08 | 2025-11-08 | 2025-11-13 | 2025-11-17 | 2025-11-24 | 2025-11-29 | 2025-12-04 | 2025-12-11 | 2025-12-11 | 2025-12-15 | 2025-12-18 | 2025-12-18 | 2025-12-18 | 2025-12-22 | 2025-12-24 | 2025-12-28 | 2026-01-04 | 2025-10-01 | 2025-10-03 | 2025-10-09 | 2025-10-15 | 2025-10-19 | 2025-10-20 | 2025-10-25 | 2025-10-25 | 2025-10-26 | 2025-10-30 | 2025-10-31 | 2025-11-03 | 2025-11-05 | 2025-11-06 | 2025-11-09 | 2025-11-10 | 2025-11-12 | 2025-11-15 | 2025-11-15 | 2025-11-16 | 2025-11-17 | 2025-11-22 | 2025-11-27 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-06 | 2025-12-06 | 2025-12-08 | 2025-12-13 | 2025-12-19 | 2025-11-20 | 2025-12-01 | 2025-12-04 | 2025-12-24 | 2025-12-28 | 2025-12-29 | 2026-01-04 | 2026-01-11 | 2026-01-16
V_586 | 2025-06-06 | 2025-06-13 | 2025-06-15 | 2025-06-21 | 2025-06-26 | 2025-06-29 | 2025-06-30 | 2025-07-04 | 2025-07-09 | 2025-07-12 | 2025-07-16 | 2025-07-16 | 2025-09-24 | 2025-10-01 | 2025-10-08 | 2025-10-08 | 2025-10-15 | 2025-10-22 | 2025-10-22 | 2025-10-25 | 2025-10-25 | 2025-10-26 | 2025-11-01 | 2025-11-01 | 2025-11-08 | 2025-11-08 | 2025-11-08 | 2025-11-13 | 2025-11-17 | 2025-11-24 | 2025-11-29 | 2025-12-04 | 2025-12-11 | 2025-12-11 | 2025-12-15 | 2025-12-18 | 2025-12-18 | 2025-12-18 | 2025-12-22 | 2025-12-24 | 2025-12-28 | 2026-01-04 | 2025-10-01 | 2025-10-03 | 2025-10-09 | 2025-10-15 | 2025-10-19 | 2025-10-20 | 2025-10-25 | 2025-10-25 | 2025-10-26 | 2025-10-30 | 2025-10-31 | 2025-11-03 | 2025-11-05 | 2025-11-06 | 2025-11-09 | 2025-11-10 | 2025-11-12 | 2025-11-15 | 2025-11-15 | 2025-11-16 | 2025-11-17 | 2025-11-22 | 2025-11-27 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-06 | 2025-12-06 | 2025-12-08 | 2025-12-13 | 2025-12-19 | 2025-11-20 | 2025-12-01 | 2025-12-04 | 2025-12-24 | 2025-12-28 | 2025-12-29 | 2026-01-04 | 2026-01-11 | 2026-01-16
V_587 | 2025-06-06 | 2025-06-13 | 2025-06-15 | 2025-06-21 | 2025-06-26 | 2025-06-29 | 2025-06-30 | 2025-07-04 | 2025-07-09 | 2025-07-12 | 2025-07-16 | 2025-07-16 | 2025-09-24 | 2025-10-01 | 2025-10-08 | 2025-10-08 | 2025-10-15 | 2025-10-22 | 2025-10-22 | 2025-10-25 | 2025-10-25 | 2025-10-26 | 2025-11-01 | 2025-11-01 | 2025-11-08 | 2025-11-08 | 2025-11-08 | 2025-11-13 | 2025-11-17 | 2025-11-24 | 2025-11-29 | 2025-12-04 | 2025-12-11 | 2025-12-11 | 2025-12-15 | 2025-12-18 | 2025-12-18 | 2025-12-18 | 2025-12-22 | 2025-12-24 | 2025-12-28 | 2026-01-04 | 2025-10-01 | 2025-10-03 | 2025-10-09 | 2025-10-15 | 2025-10-19 | 2025-10-20 | 2025-10-25 | 2025-10-25 | 2025-10-26 | 2025-10-30 | 2025-10-31 | 2025-11-03 | 2025-11-05 | 2025-11-06 | 2025-11-09 | 2025-11-10 | 2025-11-12 | 2025-11-15 | 2025-11-15 | 2025-11-16 | 2025-11-17 | 2025-11-22 | 2025-11-27 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-06 | 2025-12-06 | 2025-12-08 | 2025-12-13 | 2025-12-19 | 2025-11-20 | 2025-12-01 | 2025-12-04 | 2025-12-24 | 2025-12-28 | 2025-12-29 | 2026-01-04 | 2026-01-11 | 2026-01-16
V_588 | 2025-06-06 | 2025-06-13 | 2025-06-15 | 2025-06-21 | 2025-06-26 | 2025-06-29 | 2025-06-30 | 2025-07-04 | 2025-07-09 | 2025-07-12 | 2025-07-16 | 2025-07-16 | 2025-09-24 | 2025-10-01 | 2025-10-08 | 2025-10-08 | 2025-10-15 | 2025-10-22 | 2025-10-22 | 2025-10-25 | 2025-10-25 | 2025-10-26 | 2025-11-01 | 2025-11-01 | 2025-11-08 | 2025-11-08 | 2025-11-08 | 2025-11-13 | 2025-11-17 | 2025-11-24 | 2025-11-29 | 2025-12-04 | 2025-12-11 | 2025-12-11 | 2025-12-15 | 2025-12-18 | 2025-12-18 | 2025-12-18 | 2025-12-22 | 2025-12-24 | 2025-12-28 | 2026-01-04 | 2025-10-01 | 2025-10-03 | 2025-10-09 | 2025-10-15 | 2025-10-19 | 2025-10-20 | 2025-10-25 | 2025-10-25 | 2025-10-26 | 2025-10-30 | 2025-10-31 | 2025-11-03 | 2025-11-05 | 2025-11-06 | 2025-11-09 | 2025-11-10 | 2025-11-12 | 2025-11-15 | 2025-11-15 | 2025-11-16 | 2025-11-17 | 2025-11-22 | 2025-11-27 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-06 | 2025-12-06 | 2025-12-08 | 2025-12-13 | 2025-12-19 | 2025-11-20 | 2025-12-01 | 2025-12-04 | 2025-12-24 | 2025-12-28 | 2025-12-29 | 2026-01-04 | 2026-01-11 | 2026-01-16
V_589 | 2025-06-06 | 2025-06-13 | 2025-06-15 | 2025-06-21 | 2025-06-26 | 2025-06-29 | 2025-06-30 | 2025-07-04 | 2025-07-09 | 2025-07-12 | 2025-07-16 | 2025-07-16 | 2025-09-24 | 2025-10-01 | 2025-10-08 | 2025-10-08 | 2025-10-15 | 2025-10-22 | 2025-10-22 | 2025-10-25 | 2025-10-25 | 2025-10-26 | 2025-11-01 | 2025-11-01 | 2025-11-08 | 2025-11-08 | 2025-11-08 | 2025-11-13 | 2025-11-17 | 2025-11-24 | 2025-11-29 | 2025-12-04 | 2025-12-11 | 2025-12-11 | 2025-12-15 | 2025-12-18 | 2025-12-18 | 2025-12-18 | 2025-12-22 | 2025-12-24 | 2025-12-28 | 2026-01-04 | 2025-10-01 | 2025-10-03 | 2025-10-09 | 2025-10-15 | 2025-10-19 | 2025-10-20 | 2025-10-25 | 2025-10-25 | 2025-10-26 | 2025-10-30 | 2025-10-31 | 2025-11-03 | 2025-11-05 | 2025-11-06 | 2025-11-09 | 2025-11-10 | 2025-11-12 | 2025-11-15 | 2025-11-15 | 2025-11-16 | 2025-11-17 | 2025-11-22 | 2025-11-27 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-06 | 2025-12-06 | 2025-12-08 | 2025-12-13 | 2025-12-19 | 2025-11-20 | 2025-12-01 | 2025-12-04 | 2025-12-24 | 2025-12-28 | 2025-12-29 | 2026-01-04 | 2026-01-11 | 2026-01-16
V_590 | 2025-06-06 | 2025-06-13 | 2025-06-15 | 2025-06-21 | 2025-06-26 | 2025-06-29 | 2025-06-30 | 2025-07-04 | 2025-07-09 | 2025-07-12 | 2025-07-16 | 2025-07-16 | 2025-09-24 | 2025-10-01 | 2025-10-08 | 2025-10-08 | 2025-10-15 | 2025-10-22 | 2025-10-22 | 2025-10-25 | 2025-10-25 | 2025-10-26 | 2025-11-01 | 2025-11-01 | 2025-11-08 | 2025-11-08 | 2025-11-08 | 2025-11-13 | 2025-11-17 | 2025-11-24 | 2025-11-29 | 2025-12-04 | 2025-12-11 | 2025-12-11 | 2025-12-15 | 2025-12-18 | 2025-12-18 | 2025-12-18 | 2025-12-22 | 2025-12-24 | 2025-12-28 | 2026-01-04 | 2025-10-01 | 2025-10-03 | 2025-10-09 | 2025-10-15 | 2025-10-19 | 2025-10-20 | 2025-10-25 | 2025-10-25 | 2025-10-26 | 2025-10-30 | 2025-10-31 | 2025-11-03 | 2025-11-05 | 2025-11-06 | 2025-11-09 | 2025-11-10 | 2025-11-12 | 2025-11-15 | 2025-11-15 | 2025-11-16 | 2025-11-17 | 2025-11-22 | 2025-11-27 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-06 | 2025-12-06 | 2025-12-08 | 2025-12-13 | 2025-12-19 | 2025-11-20 | 2025-12-01 | 2025-12-04 | 2025-12-24 | 2025-12-28 | 2025-12-29 | 2026-01-04 | 2026-01-11 | 2026-01-16

## COST
villaID | Civil-1 | Civil-2 | Civil-3 | Civil-4 | Mechanical-1 | Civil-5 | Civil-6 | Civil-7 | Mechanical-2 | Civil-8 | Civil-9 | Civil-10 | Civil-11 | Architectural-1 | Mechanical-3 | Electerical-1 | Architectural-2 | Mechanical-4 | Architectural-3 | Mechanical-5 | Electerical-2 | Architectural-4 | Architectural-5 | Architectural-6 | Architectural-7 | Architectural-8 | Electerical-3 | Architectural-9 | Architectural-10 | Architectural-11 | Architectural-12 | Architectural-13 | Architectural-14 | Architectural-15 | Mechanical-6 | Architectural-16 | Architectural-17 | Electerical-4 | Mechanical-7 | Architectural-18 | Architectural-19 | Architectural-20 | Fence-1 | Fence-2 | Fence-3 | Electerical-5 | Fence-4 | Fence-5 | Fence-6 | Fence-7 | Fence-8 | Mechanical-8 | Fence-9 | Electerical-6 | Electerical-7 | Fence-10 | Fence-11 | Fence-12 | Architectural-21 | Fence-13 | Fence-14 | Fence-15 | Architectural-22 | Architectural-23 | Architectural-24 | Architectural-25 | Architectural-26 | Mechanical-9 | Architectural-27 | Fence-16 | Fence-17 | Architectural-28 | Electerical-8 | Mechanical-10 | Architectural-29 | Architectural-30 | Electerical-9 | Mechanical-11 | Architectural-31 | Electerical-10 | Architectural-32 | Architectural-33
name | Excavation&Compaction of Fondation | Pouring Concrete For Bedding | Reinforcement Concrete For Foundation | Steel Fixing& Carpenter work for Beams | Mech&Elec Establishment for Beams | Pouring Concrete For Beams | Bitmen Coating For Fondation&Beams | Backfilling Inside Fondations | Mech Works Under Grond Slap | Steel Fixing& Carpenter work for Ground Slap | Anti Termite Treatment For Ground Slap | Pouring Concrete For Ground Slap | Precast Constrction | Block Work For GF & Estabishment 1F | L.L & H.L Drainage | Elec Establishment For GF & 1F | Screed Work For 1F & Roof | Water Tank & Heater Foundations | Block Works For 1F | Water Line Network | Continue Elec Establishment For GF & 1F | Thermal Insulation For Roof | Roof Floor Tiles | Plaster Work For Villa | Marbale Stairs & Handrails | Water Proofing Of Bathrooms | Pulling The Elec Wires | Bathroom Tiles | Structure For Gypsum | Gypsum Board For Room | Installation Of Gypsum Board For Bathroom & Kitchen | Putty Filler For Gypsm Board Ceiling | Fixing Shower Glass | Interior Wall Putty Filler | Installation Of Sanitry Fixture | 1st Face Paint | Installation Of Aluminum Windows | Installation Of Elec Fixture & Accessories | Installation Of Water Tank-Heater & Pumps | Installation Of Parquet | Installation Of Wooden Doors | Final Face Paint | Pouring Bedding Concrete For Fence Fondations | RC Concrete For Fence Fondations | Steel Fixing & Carpentry For Fence Columns | Establishing Elec For Fence Columns | Pouring Concrete For Fence Columns | Installation Precast Panel For Fence | Bitumen Coating For Fence Fondations | Pouring Bedding Concrete For 'Front' Fence Fondations | RC Concrete For 'Front' Fence Fondations | Outdoor Drainage & Water Line | Steel Fixing & Carpentry For 'Front' Fence Columns | Establishing Elec For 'Front' Fence Columns | Establishing Elec For Fence & Yard | Backfilling the Yard | Pouring Concrete Wall Of 'Front' Fence Columns | Pouring Concrete Crown Of 'Front' Fence Columns | Bardoura Works For Yard | Pouring Concrete Flower Basin Of 'Front' Fence Columns | Antitermite Treatment For Yard | Pouring Concrete For Yard | Block Work For Flower Basin | Plastering Work For Flower Basin | Interlock Works For The Yard | External Grading Works For The Villa | Installation The Exterior Door & Garage Door | Fixing Floor Drain For The Yard | Granite Surronds Around The Villa | Painting The Base Surface Of The Fence | Painting The Final Face Of The Fence | Exterior Painting Of The Villa | Installation Elec Fixtures & Accessories For The Yard | Connection The Drain To The Piblic Network | Pardora Works For The External Sidewalk | Interlock Works For The Exerrnal Sidewalk | Pulling The Villa's Main Elec Cable | Mech Work Testing & Handover | Arch Snaglist & Handover | ElecWork Testing & Handover | Final Handover Of The Villa To The Consltant | Customer Delivery
nameArabic | انشائي - الحفر ودمك الأساس | انشائي - صب الخرسانة للفرشة | انشائي - خرسانة مسلحة للأساس | انشائي - تركيب حديد ونجارة للكمرات | ميكانيك - التأسيس الميكانيكي والكهربائي للكمرات | انشائي - صب الخرسانة للكمرات | انشائي - طلاء بيتومين للأساس والكمرات | انشائي - ردم داخل الأساسات | ميكانيك - أعمال ميكانيكية تحت البلاطة الأرضية | انشائي - تركيب حديد ونجارة للبلاطة الأرضية | انشائي - معالجة ضد النمل الأبيض للبلاطة الأرضية | انشائي - صب الخرسانة للبلاطة الأرضية | انشائي - إنشاء مسبق الصنع | معماري - بناء الطابق الأرضي والأول | ميكانيك - صرف الدور الارضي والعلوي | كهرباء - التأسيس الكهربائي للطابق الأرضي والأول | معماري - أعمال التسوية للطابق الأول والسقف | ميكانيك - أساسات خزان المياه والسخان | معماري - بناء الطابق الأول | ميكانيك - شبكة خطوط المياه | كهرباء - استكمال التأسيس الكهربائي للطابق الأرضي والأول | معماري - عزل حراري للسقف | معماري - بلاط الأسطح | معماري - لياسة الفيلا | معماري - السلالم الرخامية والدرابزين | معماري - عزل مائي للحمامات | كهرباء - سحب الأسلاك الكهربائية | معماري - بلاط الحمامات | معماري - هيكل الجبس | معماري - ألواح الجبس للغرف | معماري - تركيب ألواح الجبس للحمام والمطبخ | معماري - معجون سقف ألواح الجبس | معماري - تركيب زجاج الحمام | معماري - معجون الجدران الداخلية | ميكانيك - تركيب الأدوات الصحية | معماري - الدهان الأولي | معماري - تركيب نوافذ الألمنيوم | كهرباء - تركيب الأدوات الكهربائية والملحقات | ميكانيك - تركيب خزان المياه والسخان والمضخات | معماري - تركيب الباركيه | معماري - تركيب الأبواب الخشبية | معماري - الدهان النهائي | سور - صب الخرسانة للفرشة لأساسات السور | سور - خرسانة مسلحة لأساسات السور | سور - تركيب حديد ونجارة لأعمدة السور | كهرباء - التأسيس الكهربائي لأعمدة السور | سور - صب الخرسانة لأعمدة السور | سور - تركيب ألواح مسبقة الصنع للسور | سور - طلاء بيتومين لأساسات السور | سور - صب الخرسانة للفرشة لأساسات السور الأمامي | سور - خرسانة مسلحة لأساسات السور الأمامي | ميكانيك - صرف المياه الخارجي وخطوط المياه | سور - تركيب حديد ونجارة لأعمدة السور الأمامي | كهرباء - التأسيس الكهربائي لأعمدة السور الأمامي | كهرباء - التأسيس الكهربائي للسور والفناء | سور - ردم الفناء | سور - صب الخرسانة لجدار أعمدة السور الأمامي | سور - صب الخرسانة لتاج أعمدة السور الأمامي | معماري - أعمال الباردورا للفناء | سور - صب الخرسانة لحوض الزهور لأعمدة السور الأمامي | سور - معالجة ضد النمل الأبيض للفناء | سور - صب الخرسانة للفناء | معماري - بناء حوض الزهور | معماري - لياسة حوض الزهور | معماري - أعمال الإنترلوك للفناء | معماري - أعمال التسوية الخارجية للفيلا | معماري - تركيب الباب الخارجي وباب الجراج | ميكانيك - تركيب الصرف للفناء | معماري - أعمال الجرانيت حول الفيلا | سور - دهان السطح الأساسي للسور | سور - دهان الوجه النهائي للسور | معماري - دهان الواجهة الخارجية للفيلا | كهرباء - تركيب الأدوات الكهربائية والملحقات للفناء | ميكانيك - ربط الصرف والمياه بالشبكة العامة | معماري - أعمال الباردورا للرصيف الخارجي | معماري - أعمال الإنترلوك للرصيف الخارجي | كهرباء - سحب الكابل الكهربائي الرئيسي للفيلا | ميكانيك - اختبار الأعمال الميكانيكية وتسليمها | معماري - قائمة الأعمال المتبقية وتسليمها | كهرباء - اختبار الأعمال الكهربائية وتسليمها | معماري - التسليم النهائي للفيلا للعميل | معماري - تسليم العميل
id | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82
predecessors | [] | [1] | [2] | [3] | [4] | [5] | [6] | [7] | [8] | [9] | [10] | [11, 10] | [12] | [13] | [14] | [14] | [15, 16] | [17] | [17] | [19] | [19] | [18] | [22] | [20, 21] | [24] | [24] | [24] | [26, 23] | [28] | [29, 27] | [30] | [31] | [32] | [32, 25] | [33] | [34] | [34] | [32, 34, 27] | [35, 23] | [36] | [40] | [37, 41] | [13] | [43] | [44] | [45] | [46] | [47] | [48] | [48] | [50] | [49, 15] | [51] | [53] | [52] | [55] | [54] | [57] | [56] | [58] | [59] | [61] | [62] | [63] | [64] | [65] | [65] | [65] | [66] | [76] | [70] | [69, 71, 67, 68] | [71, 72] | [52, 60] | [65, 74] | [75] | [76, 73] | [74, 35, 39] | [76, 72, 41] | [77, 38] | [79, 80, 78, 42] | [81]
V_122 | 1535.2988 | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 30202.6331 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | 3659.643 | 7107.6802 | 5542.1786 | 10293.1526 | 15.102 | 8235.459 | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 | 1152.7358 | 251.694 | 3019.5821 | 2975.59 | 3019.5821 | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 | 4529.3771 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_449 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.8787 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56764.7512 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_451 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.8787 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56764.7512 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_423 | [25 empty] | 0 | 0 | [6 empty] | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | [6 empty] | 2975.59
V_473 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.5825 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_318 | [19 empty] | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [7 empty] | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 503.3782
V_222 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_429 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_286 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_430 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_32 | 852.9438 | [10 empty] | 16779.2406 |  | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 1283.6131 | 0 | 9665.08 | 0 | 0 | 2033.135 | 3948.7112 |  |  |  |  | 20443.22 | 3635.595 | 94610.1794 | 4737.46 | 25169.49 | 2796.61 | 4821.355 | 1398.305 | 699.15 | 640.425 | 139.83 | 1677.5456 | 2975.59 | 1677.5456 |  |  |  | 0 | 2237.29 | 2796.61 | 2852.48 |  | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 |  |  |  | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 838.9638 | 5593.08 | 0 | 2516.3206 |  |  | 1677.96 | 1677.97
V_273 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_507 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.5825 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_265 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_211 |  | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 2745.153 | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 |  | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_552 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 413.7962 | 0 | 0 | 4598.19 | 402.71 | 1677.97 | 3227.29 | 13211.18 | 0 | 1925.4197 | 0 | 2975.515 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 9665.08 | 2516.3184 | 7550.85 | 6711.86 | 0 | 2237.29 | 0 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 1801.02 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 5000.34
V_107 | 1535.2988 | [10 empty] | 30202.6331 |  |  | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 | 1152.7358 | 251.694 | 3019.5821 | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [5 empty] | 0 | 0 | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 |  |  |  |  | 1677.97
V_480 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.5825 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_262 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_494 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.5825 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_483 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.5825 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_395 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_382 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | [7 empty] | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 |  | 1677.54 | 1789.83 |  | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_241 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_165 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_106 | 1535.2988 | [10 empty] | 30202.6331 |  |  | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 | 1152.7358 | 251.694 | 3019.5821 | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [5 empty] | 0 | 0 | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 |  |  |  |  | 1677.97
V_103 | 1535.2988 | [10 empty] | 30202.6331 |  |  | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 | 1152.7358 | 251.694 | 3019.5821 | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [5 empty] | 0 | 0 | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 |  |  |  |  | 1677.97
V_62 | 1535.2988 | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 30202.6331 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | 3659.643 | 7107.6802 | 5542.1786 | 10293.1526 | 15.102 | 8235.459 | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.949 | 1258.47 | 1152.765 | 251.694 | 3019.5821 | 2975.59 | 3019.5821 | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 | 4529.3771 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_132 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_69 | 1535.2988 | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 30202.6331 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | 3659.643 | 7107.6802 | 5542.1786 | 10293.1526 | 15.102 | 8235.459 | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.949 | 1258.47 | 1152.765 | 251.694 | 3019.5821 | 2975.59 | 3019.5821 | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 | 4529.3771 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_156 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_338 | [19 empty] | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [7 empty] | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 503.3782
V_488 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.5825 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_206 |  | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 2745.153 | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 |  | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_268 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_554 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 413.7962 | 0 | 0 | 4598.19 | 402.71 | 1677.97 | 3227.29 | 13211.18 | 0 | 1925.4197 | 0 | 2975.515 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 9665.08 | 2516.3184 | 7550.85 | 6711.86 | 0 | 2237.29 | 0 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 1801.02 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 5000.34
V_433 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_296 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_515 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4598.19 | 402.71 | 1677.97 | 3227.29 | 13211.18 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6711.86 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 1677.96 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 0 | 5000.34
V_459 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.5825 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_40 | 852.9438 | 2096.9256 | 2237.29 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 16779.2406 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 1283.6131 | 0 | 9665.08 | 0 | 0 | 2033.135 | 3948.7112 | 3078.9881 | 5718.4181 | 8.39 | 4575.255 | 20443.22 | 3635.595 | 94610.1794 | 4737.46 | 25169.49 | 2796.61 | 4821.355 | 1398.305 | 699.15 | 640.425 | 139.83 | 1677.5456 | 2975.59 | 1677.5456 | 5033.9 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 838.9638 | 5593.08 | 0 | 2516.3206 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_310 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_470 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.5825 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_224 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_560 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | [9 empty] | 1925.4197 |  |  |  | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 |  | 2516.3184 | 7550.85 | 6711.86 | 0 |  |  |  |  | 564.91 | [8 empty] | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 |  | 0 |  |  | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96
V_579 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 413.7962 | 0 | 0 | 4598.19 | 402.71 | 5000.34 | 3227.29 | 13211.18 | 0 | 1925.4197 | 0 | 2975.515 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 9665.08 | 2516.3184 | 7550.85 | 6711.86 | 0 | 2237.29 | 0 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 1801.02 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_102 | 1535.2988 | [10 empty] | 30202.6331 |  |  | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 | 1152.7358 | 251.694 | 3019.5821 | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [5 empty] | 0 | 0 | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 |  |  |  |  | 1677.97
V_341 | [19 empty] | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [7 empty] | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 503.3782
V_501 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.5825 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_479 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.5825 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_134 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_474 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.5825 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_271 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_231 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_546 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 413.7962 | 0 | 0 | 4598.19 | 402.71 | 1677.97 | 3227.29 | 13211.18 | 0 | 1925.4197 | 0 | 2975.515 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 9665.08 | 2516.3184 | 7550.85 | 6711.86 | 0 | 2237.29 | 0 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 1801.02 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 5000.34
V_487 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.5825 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_250 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_236 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_584 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 413.7962 | 0 | 0 | 4598.19 | 402.71 | 5000.34 | 3227.29 | 13211.18 | 0 | 1925.4197 | 0 | 2975.515 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 9665.08 | 2516.3184 | 7550.85 | 6711.86 | 0 | 2237.29 | 0 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 1801.02 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_119 | 1535.2988 | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 30202.6331 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | 3659.643 | 7107.6802 | 5542.1786 | 10293.1526 | 15.102 | 8235.459 | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 | 1152.7358 | 251.694 | 3019.5821 | 2975.59 | 3019.5821 | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 | 4529.3771 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_37 | 852.9438 | 2096.9256 | 2237.29 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 16779.2406 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 1283.6131 | 0 | 9665.08 | 0 | 0 | 2033.135 | 3948.7112 | 3078.9881 | 5718.4181 | 8.39 | 4575.255 | 20443.22 | 3635.595 | 94610.1794 | 4737.46 | 25169.49 | 2796.61 | 4821.355 | 1398.305 | 699.15 | 640.425 | 139.83 | 1677.5456 | 2975.59 | 1677.5456 | 5033.9 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 838.9638 | 5593.08 | 0 | 2516.3206 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_105 | 1535.2988 | [10 empty] | 30202.6331 |  |  | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 | 1152.7358 | 251.694 | 3019.5821 | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [5 empty] | 0 | 0 | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 |  |  |  |  | 1677.97
V_345 | [19 empty] | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [7 empty] | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 503.3782
V_572 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 413.7962 | 0 | 0 | 4598.19 | 402.71 | 5000.34 | 3227.29 | 13211.18 | 0 | 1925.4197 | 0 | 2975.515 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8578.59 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 9665.08 | 2516.3184 | 7550.85 | 6711.86 | 0 | 2237.29 | 0 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 1801.02 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_261 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_428 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_527 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4598.19 | 402.71 | 1677.97 | 3227.29 | 13211.18 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6711.86 | 0 | 2237.29 | 0 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 5000.34
V_254 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_29 | 852.9438 | [10 empty] | 16779.2406 |  | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 1283.6131 | 0 | 9665.08 | 0 | 0 | 2033.135 | 3948.7112 |  |  |  |  | 20443.22 | 3635.595 | 94610.1794 | 4737.46 | 25169.49 | 2796.61 | 4821.355 | 1398.305 | 699.15 | 640.425 | 139.83 | 1677.5456 | 2975.59 | 1677.5456 |  |  |  | 0 | 2237.29 | 2796.61 | 2852.48 |  | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 |  |  |  | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 838.9638 | 5593.08 | 0 | 2516.3206 |  |  | 1677.96 | 1677.97
V_287 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_468 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.5825 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_243 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_255 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_588 | 1279.4475 | 3146.175 | 3355.935 | 1381.53 | 7774.57 | 2796.61 | 7768.97 | 0 | 10599.99 | 6622.37 | 17764.07 | 25169.49 | 3887.29 | 413.9 | 0 | 0 | 4598.19 | 402.71 | 5000.34 | 3227.29 | 13211.18 | 0 | 1925.4675 | 0 | 1789.83 | 0 | 0 | 3049.7025 | 5923.215 | 4618.5975 | 8578.59 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141922.365 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.4575 | 1048.725 | 960.6375 | 209.745 | 2516.9475 | 9665.08 | 2516.9475 | 7550.85 | 6711.86 | 0 | 2237.29 | 0 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 1801.02 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.96 | 2975.59 | 1258.4775 | 8389.83 | 0 | 3775.425 | 12305.07 | 16220.34 | 1677.96 | 1677.97
V_83 | 1535.2988 | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 30202.6331 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | 3659.643 | 7107.6802 | 5542.1786 | 10293.1526 | 15.102 | 8235.459 | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 | 1152.7358 | 251.694 | 3019.5821 | 2975.59 | 3019.5821 | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 | 4529.3771 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_454 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.8787 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56764.7512 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_326 | [19 empty] | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [7 empty] | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 503.3782
V_409 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_23 | 852.9438 | 2096.9256 | 2237.29 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 16779.2406 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 1283.6131 | 0 | 9665.08 | 0 | 0 | 2033.135 | 3948.7112 | 3078.9881 | 5718.4181 | 8.39 | 4575.255 | 20443.22 | 3635.595 | 94614.91 | 4737.46 | 25169.49 | 2796.61 | 4821.355 | 1398.305 | 699.15 | 640.425 | 139.83 | 1677.5456 | 2975.59 | 1677.5456 | 5033.9 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 838.9638 | 5593.08 | 0 | 2516.3206 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_214 |  | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 2745.153 | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 |  | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_114 | 1535.2988 | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 30202.6331 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | 3659.643 | 7107.6802 | 5542.1786 | 10293.1526 | 15.102 | 8235.459 | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 | 1152.7358 | 251.694 | 3019.5821 | 2975.59 | 3019.5821 | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 | 4529.3771 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_350 | [19 empty] | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [7 empty] | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 503.3782
V_408 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_493 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.5825 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_445 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_38 | 852.9438 | 2096.9256 | 2237.29 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 16779.2406 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 1283.6131 | 0 | 9665.08 | 0 | 0 | 2033.135 | 3948.7112 | 3078.9881 | 5718.4181 | 8.39 | 4575.255 | 20443.22 | 3635.595 | 94610.1794 | 4737.46 | 25169.49 | 2796.61 | 4821.355 | 1398.305 | 699.15 | 640.425 | 139.83 | 1677.5456 | 2975.59 | 1677.5456 | 5033.9 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 838.9638 | 5593.08 | 0 | 2516.3206 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_374 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_131 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_28 | 852.9438 | 2096.9256 | 2237.29 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 16779.2406 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 1283.6131 | 0 | 9665.08 | 0 | 0 | 2033.135 | 3948.7112 | 3078.9881 | 5718.4181 | 8.39 | 4575.255 | 20443.22 | 3635.595 | 94610.1794 | 4737.46 | 25169.49 | 2796.61 | 4821.355 | 1398.305 | 699.15 | 640.425 | 139.83 | 1677.5456 | 2975.59 | 1677.5456 | 5033.9 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 838.9638 | 5593.08 | 0 | 2516.3206 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_509 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.5825 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_437 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_285 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_506 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.5825 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_524 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4598.19 | 402.71 | 1677.97 | 3227.29 | 13211.18 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6711.86 | 0 | 2237.29 | 0 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 5000.34
V_440 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_80 | 1535.2988 | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 30202.6331 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | 3659.643 | 7107.6802 | 5542.1786 | 10293.1526 | 15.102 | 8235.459 | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 | 1152.7358 | 251.694 | 3019.5821 | 2975.59 | 3019.5821 | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 | 4529.3771 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_202 |  | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 2745.153 | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 |  | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_266 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_372 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_538 | [25 empty] | 0 | 0 | [6 empty] | 20443.22 | [11 empty] | 9665.08
V_419 | [25 empty] | 0 | 0 | [6 empty] | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | [6 empty] | 2975.59
V_354 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_144 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_71 | 1535.2988 | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 30202.6331 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | 3659.643 | 7107.6802 | 5542.1786 | 10293.1526 | 15.102 | 8235.459 | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.949 | 1258.47 | 1152.765 | 251.694 | 3019.5821 | 2975.59 | 3019.5821 | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 | 4529.3771 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_456 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.8787 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56764.7512 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_27 | 852.9438 | 2096.9256 | 2237.29 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 16779.2406 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 1283.6131 | 0 | 9665.08 | 0 | 0 | 2033.135 | 3948.7112 | 3078.9881 | 5718.4181 | 8.39 | 4575.255 | 20443.22 | 3635.595 | 94610.1794 | 4737.46 | 25169.49 | 2796.61 | 4821.355 | 1398.305 | 699.15 | 640.425 | 139.83 | 1677.5456 | 2975.59 | 1677.5456 | 5033.9 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 838.9638 | 5593.08 | 0 | 2516.3206 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_589 | 1279.4475 | 3146.175 | 3355.935 | 1381.53 | 7774.57 | 2796.61 | 7768.97 | 0 | 10599.99 | 6622.37 | 17764.07 | 25169.49 | 3887.29 | 413.9 | 0 | 0 | 4598.19 | 402.71 | 5000.34 | 3227.29 | 13211.18 | 0 | 1925.4675 | 0 | 1789.83 | 0 | 0 | 3049.7025 | 5923.215 | 4618.5975 | 8578.59 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141922.365 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.4575 | 1048.725 | 960.6375 | 209.745 | 2516.9475 | 9665.08 | 2516.9475 | 7550.85 | 6711.86 | 0 | 2237.29 | 0 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 1801.02 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.96 | 2975.59 | 1258.4775 | 8389.83 | 0 | 3775.425 | 12305.07 | 16220.34 | 1677.96 | 1677.97
V_137 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_176 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_523 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4598.19 | 402.71 | 1677.97 | 3227.29 | 13211.18 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6711.86 | 0 | 2237.29 | 0 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 5000.34
V_346 | [19 empty] | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [7 empty] | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 503.3782
V_511 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.5825 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_77 |  |  | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 | 1152.7358 |  |  | 2975.59 |  |  | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1510.1347 |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_233 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_529 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 413.7962 | 0 | 0 | 4598.19 | 402.71 | 1677.97 | 3227.29 | 13211.18 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6711.86 | 0 | 2237.29 | 0 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 1801.02 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 5000.34
V_358 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_369 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_404 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_555 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 413.7962 | 0 | 0 | 4598.19 | 402.71 | 1677.97 | 3227.29 | 13211.18 | 0 | 1925.4197 | 0 | 2975.515 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 9665.08 | 2516.3184 | 7550.85 | 6711.86 | 0 | 2237.29 | 0 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 1801.02 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 5000.34
V_35 | 852.9438 | [10 empty] | 16779.2406 |  | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 1283.6131 | 0 | 9665.08 | 0 | 0 | 2033.135 | 3948.7112 |  |  |  |  | 20443.22 | 3635.595 | 94610.1794 | 4737.46 | 25169.49 | 2796.61 | 4821.355 | 1398.305 | 699.15 | 640.425 | 139.83 | 1677.5456 | 2975.59 | 1677.5456 |  |  |  | 0 | 2237.29 | 2796.61 | 2852.48 |  | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 |  |  |  | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 838.9638 | 5593.08 | 0 | 2516.3206 |  |  | 1677.96 | 1677.97
V_11 |  |  | 2237.29 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 | 3635.595 | 94614.91 | 4737.46 | 25169.49 | 2796.61 | 4821.355 | 1398.305 | 699.15 | 640.425 | 139.83 |  | 2975.59 |  |  | 6711.6637 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 838.985 |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_498 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.5825 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_446 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_355 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_389 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | [7 empty] | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 |  | 1677.54 | 1789.83 |  | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_291 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_585 | 1279.4475 | 3146.175 | 3355.935 | 1381.53 | 7774.57 | 2796.61 | 7768.97 | 0 | 10599.99 | 6622.37 | 17764.07 | 25169.49 | 3887.29 | 413.9 | 0 | 0 | 4598.19 | 402.71 | 5000.34 | 3227.29 | 13211.18 | 0 | 1925.4675 | 0 | 1789.83 | 0 | 0 | 3049.7025 | 5923.215 | 4618.5975 | 8578.59 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141922.365 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.4575 | 1048.725 | 960.6375 | 209.745 | 2516.9475 | 9665.08 | 2516.9475 | 7550.85 | 6711.86 | 0 | 2237.29 | 0 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 1801.02 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.96 | 2975.59 | 1258.4775 | 8389.83 | 0 | 3775.425 | 12305.07 | 16220.34 | 1677.96 | 1677.97
V_570 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | [9 empty] | 1925.4197 |  |  |  | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8578.59 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 |  | 2516.3184 | 7550.85 | 6711.86 | 0 |  |  |  |  | 564.91 | [8 empty] | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 |  | 0 |  |  | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96
V_335 | [19 empty] | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [7 empty] | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 503.3782
V_453 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.8787 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56764.7512 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_125 | 1535.2988 | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 30202.6331 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | 3659.643 | 7107.6802 | 5542.1786 | 10293.1526 | 15.102 | 8235.459 | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 | 1152.7358 | 251.694 | 3019.5821 | 2975.59 | 3019.5821 | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 | 4529.3771 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_260 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_158 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_63 | 1535.2988 | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 30202.6331 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | 3659.643 | 7107.6802 | 5542.1786 | 10293.1526 | 15.102 | 8235.459 | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.949 | 1258.47 | 1152.765 | 251.694 | 3019.5821 | 2975.59 | 3019.5821 | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 | 4529.3771 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_417 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_203 |  | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 2745.153 | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 |  | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_61 | 1535.2988 | [10 empty] | 30202.6331 | [7 empty] | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | 3659.643 | 7107.6802 | 5542.1786 | 10293.1526 | 15.102 |  | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.949 | 1258.47 | 1152.765 | 251.694 | 3019.5821 | 2975.59 | 3019.5821 | 9061.02 |  |  |  |  | 2796.61 | 2852.48 | [7 empty] | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 | 4529.3771 |  |  |  | 1677.97
V_398 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_356 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_242 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_45 | 852.9438 | 2096.9256 | 2237.29 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 16779.2406 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 1283.6131 | 0 | 9665.08 | 0 | 0 | 2033.135 | 3948.7112 | 3078.9881 | 5718.4181 | 8.39 | 4575.255 | 20443.22 | 3635.595 | 94610.1794 | 4737.46 | 25169.49 | 2796.61 | 4821.355 | 1398.305 | 699.15 | 640.425 | 139.83 | 1677.5456 | 2975.59 | 1677.5456 | 5033.9 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 838.9638 | 5593.08 | 0 | 2516.3206 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_34 | 852.9438 | [10 empty] | 16779.2406 |  | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 1283.6131 | 0 | 9665.08 | 0 | 0 | 2033.135 | 3948.7112 |  |  |  |  | 20443.22 | 3635.595 | 94610.1794 | 4737.46 | 25169.49 | 2796.61 | 4821.355 | 1398.305 | 699.15 | 640.425 | 139.83 | 1677.5456 | 2975.59 | 1677.5456 |  |  |  | 0 | 2237.29 | 2796.61 | 2852.48 |  | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 |  |  |  | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 838.9638 | 5593.08 | 0 | 2516.3206 |  |  | 1677.96 | 1677.97
V_181 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_155 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_301 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_179 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_333 | [19 empty] | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [7 empty] | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 503.3782
V_257 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_289 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_292 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_438 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_133 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_175 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_316 | [19 empty] | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [7 empty] | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 503.3782
V_564 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | [9 empty] | 1925.4197 |  |  |  | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 |  | 2516.3184 | 7550.85 | 6711.86 | 0 |  |  |  |  | 564.91 | [8 empty] | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 |  | 0 |  |  | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96
V_94 | 1535.2988 | [10 empty] | 30202.6331 |  |  | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 | 1152.7358 | 251.694 | 3019.5821 | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [5 empty] | 0 | 0 | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 |  |  |  |  | 1677.97
V_548 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 413.7962 | 0 | 0 | 4598.19 | 402.71 | 1677.97 | 3227.29 | 13211.18 | 0 | 1925.4197 | 0 | 2975.515 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 9665.08 | 2516.3184 | 7550.85 | 6711.86 | 0 | 2237.29 | 0 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 1801.02 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 5000.34
V_406 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_19 | 852.9438 | 2096.9256 | 2237.29 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 16779.2406 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 1283.6131 | 0 | 9665.08 | 0 | 0 | 2033.135 | 3948.7112 | 3078.9881 | 5718.4181 | 8.39 | 4575.255 | 20443.22 | 3635.595 | 94614.91 | 4737.46 | 25169.49 | 2796.61 | 4821.355 | 1398.305 | 699.15 | 640.425 | 139.83 | 1677.5456 | 2975.59 | 1677.5456 | 5033.9 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 838.9638 | 5593.08 | 0 | 2516.3206 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_139 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_74 |  |  | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 | 1152.7358 |  |  | 2975.59 |  |  | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1510.1347 |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_247 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_118 | 1535.2988 | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 30202.6331 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | 3659.643 | 7107.6802 | 5542.1786 | 10293.1526 | 15.102 | 8235.459 | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 | 1152.7358 | 251.694 | 3019.5821 | 2975.59 | 3019.5821 | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 | 4529.3771 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_267 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_343 | [19 empty] | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [7 empty] | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 503.3782
V_497 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.5825 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_21 | 852.9438 | 2096.9256 | 2237.29 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 16779.2406 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 1283.6131 | 0 | 9665.08 | 0 | 0 | 2033.135 | 3948.7112 | 3078.9881 | 5718.4181 | 8.39 | 4575.255 | 20443.22 | 3635.595 | 94614.91 | 4737.46 | 25169.49 | 2796.61 | 4821.355 | 1398.305 | 699.15 | 640.425 | 139.83 | 1677.5456 | 2975.59 | 1677.5456 | 5033.9 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 838.9638 | 5593.08 | 0 | 2516.3206 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_48 | 852.9438 | 2096.9256 | 2237.29 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 16779.2406 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 1283.6131 | 0 | 9665.08 | 0 | 0 | 2033.135 | 3948.7112 | 3078.9881 | 5718.4181 | 8.39 | 4575.255 | 20443.22 | 3635.595 | 94610.1794 | 4737.46 | 25169.49 | 2796.61 | 4821.355 | 1398.305 | 699.15 | 640.425 | 139.83 | 1677.5456 | 2975.59 | 1677.5456 | 5033.9 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 838.9638 | 5593.08 | 0 | 2516.3206 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_12 |  |  | 2237.29 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 | 3635.595 | 94614.91 | 4737.46 | 25169.49 | 2796.61 | 4821.355 | 1398.305 | 699.15 | 640.425 | 139.83 |  | 2975.59 |  |  | 6711.6637 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 838.985 |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_123 | 1535.2988 | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 30202.6331 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | 3659.643 | 7107.6802 | 5542.1786 | 10293.1526 | 15.102 | 8235.459 | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 | 1152.7358 | 251.694 | 3019.5821 | 2975.59 | 3019.5821 | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 | 4529.3771 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_426 | [25 empty] | 0 | 0 | [6 empty] | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | [6 empty] | 2975.59
V_435 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_490 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.5825 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_539 | [25 empty] | 0 | 0 | [6 empty] | 20443.22 | [11 empty] | 9665.08
V_508 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.5825 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_461 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.5825 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_159 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_55 | 1535.2988 | [10 empty] | 30202.6331 | [7 empty] | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | 3659.643 | 7107.6802 | 5542.1786 | 10293.1526 | 15.102 |  | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.949 | 1258.47 | 1152.765 | 251.694 | 3019.5821 | 2975.59 | 3019.5821 | 9061.02 |  |  |  |  | 2796.61 | 2852.48 | [7 empty] | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 | 4529.3771 |  |  |  | 1677.97
V_547 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 413.7962 | 0 | 0 | 4598.19 | 402.71 | 1677.97 | 3227.29 | 13211.18 | 0 | 1925.4197 | 0 | 2975.515 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 9665.08 | 2516.3184 | 7550.85 | 6711.86 | 0 | 2237.29 | 0 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 1801.02 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 5000.34
V_177 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_311 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_259 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_399 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_495 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.5825 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_421 | [25 empty] | 0 | 0 | [6 empty] | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | [6 empty] | 2975.59
V_569 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | [9 empty] | 1925.4197 |  |  |  | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8578.59 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 |  | 2516.3184 | 7550.85 | 6711.86 | 0 |  |  |  |  | 564.91 | [8 empty] | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 |  | 0 |  |  | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96
V_365 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_571 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 413.7962 | 0 | 0 | 4598.19 | 402.71 | 5000.34 | 3227.29 | 13211.18 | 0 | 1925.4197 | 0 | 2975.515 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8578.59 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 9665.08 | 2516.3184 | 7550.85 | 6711.86 | 0 | 2237.29 | 0 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 1801.02 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_466 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.5825 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_368 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_163 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_270 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_192 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_121 | 1535.2988 | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 30202.6331 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | 3659.643 | 7107.6802 | 5542.1786 | 10293.1526 | 15.102 | 8235.459 | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 | 1152.7358 | 251.694 | 3019.5821 | 2975.59 | 3019.5821 | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 | 4529.3771 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_535 | [25 empty] | 0 | 0 | [6 empty] | 20443.22 | [11 empty] | 2975.515
V_136 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_209 |  | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 2745.153 | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 |  | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_138 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_388 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | [7 empty] | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 |  | 1677.54 | 1789.83 |  | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_364 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_396 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_117 | 1535.2988 | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 30202.6331 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | 3659.643 | 7107.6802 | 5542.1786 | 10293.1526 | 15.102 | 8235.459 | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 | 1152.7358 | 251.694 | 3019.5821 | 2975.59 | 3019.5821 | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 | 4529.3771 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_405 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_116 | 1535.2988 | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 30202.6331 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | 3659.643 | 7107.6802 | 5542.1786 | 10293.1526 | 15.102 | 8235.459 | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 | 1152.7358 | 251.694 | 3019.5821 | 2975.59 | 3019.5821 | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 | 4529.3771 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_115 | 1535.2988 | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 30202.6331 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | 3659.643 | 7107.6802 | 5542.1786 | 10293.1526 | 15.102 | 8235.459 | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 | 1152.7358 | 251.694 | 3019.5821 | 2975.59 | 3019.5821 | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 | 4529.3771 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_72 | 1535.2988 | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 30202.6331 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | 3659.643 | 7107.6802 | 5542.1786 | 10293.1526 | 15.102 | 8235.459 | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.949 | 1258.47 | 1152.765 | 251.694 | 3019.5821 | 2975.59 | 3019.5821 | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 | 4529.3771 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_91 | 1535.2988 | [10 empty] | 30202.6331 |  |  | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 | 1152.7358 | 251.694 | 3019.5821 | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [5 empty] | 0 | 0 | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 |  |  |  |  | 1677.97
V_357 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_315 | [19 empty] | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [7 empty] | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 503.3782
V_337 | [19 empty] | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [7 empty] | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 503.3782
V_582 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 413.7962 | 0 | 0 | 4598.19 | 402.71 | 5000.34 | 3227.29 | 13211.18 | 0 | 1925.4197 | 0 | 2975.515 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 9665.08 | 2516.3184 | 7550.85 | 6711.86 | 0 | 2237.29 | 0 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 1801.02 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_455 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.8787 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56764.7512 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_325 | [19 empty] | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [7 empty] | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 503.3782
V_464 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.5825 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_541 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 413.7962 | 0 | 0 | 4598.19 | 402.71 | 1677.97 | 0 | 13211.18 | 0 | 1925.4197 | 0 | 2975.515 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 9665.08 | 2516.3184 | 7550.85 | 6711.86 | 0 | 2237.29 | 0 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 1801.02 | 0 | 0 | 0 | 5000.34 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 3227.29
V_146 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_253 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_375 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_532 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 413.7962 | 0 | 0 | 4598.19 | 402.71 | 1677.97 | 3227.29 | 13211.18 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6711.86 | 0 | 2237.29 | 0 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 1801.02 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 5000.34
V_414 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_416 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_407 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_442 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_512 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.5825 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_323 | [19 empty] | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [7 empty] | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 503.3782
V_471 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.5825 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_31 | 852.9438 | [10 empty] | 16779.2406 |  | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 1283.6131 | 0 | 9665.08 | 0 | 0 | 2033.135 | 3948.7112 |  |  |  |  | 20443.22 | 3635.595 | 94610.1794 | 4737.46 | 25169.49 | 2796.61 | 4821.355 | 1398.305 | 699.15 | 640.425 | 139.83 | 1677.5456 | 2975.59 | 1677.5456 |  |  |  | 0 | 2237.29 | 2796.61 | 2852.48 |  | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 |  |  |  | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 838.9638 | 5593.08 | 0 | 2516.3206 |  |  | 1677.96 | 1677.97
V_274 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_525 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4598.19 | 402.71 | 1677.97 | 3227.29 | 13211.18 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6711.86 | 0 | 2237.29 | 0 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 5000.34
V_193 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_127 | 1535.2988 | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 30202.6331 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | 3659.643 | 7107.6802 | 5542.1786 | 10293.1526 | 15.102 | 8235.459 | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 | 1152.7358 | 251.694 | 3019.5821 | 2975.59 | 3019.5821 | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 | 4529.3771 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_500 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.5825 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_162 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_89 | 1535.2988 | [10 empty] | 30202.6331 |  |  | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 | 1152.7358 | 251.694 | 3019.5821 | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [5 empty] | 0 | 0 | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 |  |  |  |  | 1677.97
V_108 | 1535.2988 | [10 empty] | 30202.6331 |  |  | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 | 1152.7358 | 251.694 | 3019.5821 | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [5 empty] | 0 | 0 | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 |  |  |  |  | 1677.97
V_336 | [19 empty] | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [7 empty] | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 503.3782
V_213 |  | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 2745.153 | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 |  | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_152 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_380 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | [7 empty] | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 |  | 1677.54 | 1789.83 |  | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_422 | [25 empty] | 0 | 0 | [6 empty] | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | [6 empty] | 2975.59
V_302 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_300 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_537 | [25 empty] | 0 | 0 | [6 empty] | 20443.22 | [11 empty] | 9665.08
V_513 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4598.19 | 402.71 | 1677.97 | 3227.29 | 13211.18 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6711.86 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 1677.96 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 0 | 5000.34
V_324 | [19 empty] | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [7 empty] | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 503.3782
V_586 | 1279.4475 | 3146.175 | 3355.935 | 1381.53 | 7774.57 | 2796.61 | 7768.97 | 0 | 10599.99 | 6622.37 | 17764.07 | 25169.49 | 3887.29 | 413.9 | 0 | 0 | 4598.19 | 402.71 | 5000.34 | 3227.29 | 13211.18 | 0 | 1925.4675 | 0 | 1789.83 | 0 | 0 | 3049.7025 | 5923.215 | 4618.5975 | 8578.59 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141922.365 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.4575 | 1048.725 | 960.6375 | 209.745 | 2516.9475 | 9665.08 | 2516.9475 | 7550.85 | 6711.86 | 0 | 2237.29 | 0 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 1801.02 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.96 | 2975.59 | 1258.4775 | 8389.83 | 0 | 3775.425 | 12305.07 | 16220.34 | 1677.96 | 1677.97
V_536 | [25 empty] | 0 | 0 | [6 empty] | 20443.22 | [11 empty] | 2975.515
V_476 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.5825 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_113 | 1535.2988 | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 30202.6331 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | 3659.643 | 7107.6802 | 5542.1786 | 10293.1526 | 15.102 | 8235.459 | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 | 1152.7358 | 251.694 | 3019.5821 | 2975.59 | 3019.5821 | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 | 4529.3771 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_272 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_99 | 1535.2988 | [10 empty] | 30202.6331 |  |  | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 | 1152.7358 | 251.694 | 3019.5821 | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [5 empty] | 0 | 0 | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 |  |  |  |  | 1677.97
V_182 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_51 | 852.9438 | [10 empty] | 16779.2406 | [7 empty] | 3227.29 | 13210.52 | 0 | 1283.6131 | 0 | 9665.08 | 0 | 0 | 2033.135 | 3948.7112 | 3078.9881 | 5718.4181 | 8.39 |  | 20443.22 | 3635.595 | 94610.1794 | 4737.46 | 25169.49 | 2796.61 | 4821.355 | 1398.305 | 699.15 | 640.425 | 139.83 | 1677.5456 | 2975.59 | 1677.5456 | 5033.9 |  |  |  |  | 2796.61 | 2852.48 | [7 empty] | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 838.9638 | 5593.08 | 0 | 2516.3206 |  |  |  | 1677.97
V_412 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_112 | 1535.2988 | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 30202.6331 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | 3659.643 | 7107.6802 | 5542.1786 | 10293.1526 | 15.102 | 8235.459 | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 | 1152.7358 | 251.694 | 3019.5821 | 2975.59 | 3019.5821 | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 | 4529.3771 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_376 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_66 | 1535.2988 | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 30202.6331 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | 3659.643 | 7107.6802 | 5542.1786 | 10293.1526 | 15.102 | 8235.459 | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.949 | 1258.47 | 1152.765 | 251.694 | 3019.5821 | 2975.59 | 3019.5821 | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 | 4529.3771 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_60 | 1535.2988 | [10 empty] | 30202.6331 | [7 empty] | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | 3659.643 | 7107.6802 | 5542.1786 | 10293.1526 | 15.102 |  | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.949 | 1258.47 | 1152.765 | 251.694 | 3019.5821 | 2975.59 | 3019.5821 | 9061.02 |  |  |  |  | 2796.61 | 2852.48 | [7 empty] | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 | 4529.3771 |  |  |  | 1677.97
V_244 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_186 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_161 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_199 |  | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 2745.153 | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 |  | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_308 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_467 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.5825 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_371 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_557 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 413.7962 | 0 | 0 | 4598.19 | 402.71 | 1677.97 | 3227.29 | 13211.18 | 0 | 1925.4197 | 0 | 2975.515 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 9665.08 | 2516.3184 | 7550.85 | 6711.86 | 0 | 2237.29 | 0 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 1801.02 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 5000.34
V_24 | 852.9438 | 2096.9256 | 2237.29 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 16779.2406 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 1283.6131 | 0 | 9665.08 | 0 | 0 | 2033.135 | 3948.7112 | 3078.9881 | 5718.4181 | 8.39 | 4575.255 | 20443.22 | 3635.595 | 94614.91 | 4737.46 | 25169.49 | 2796.61 | 4821.355 | 1398.305 | 699.15 | 640.425 | 139.83 | 1677.5456 | 2975.59 | 1677.5456 | 5033.9 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 838.9638 | 5593.08 | 0 | 2516.3206 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_100 | 1535.2988 | [10 empty] | 30202.6331 |  |  | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 | 1152.7358 | 251.694 | 3019.5821 | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [5 empty] | 0 | 0 | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 |  |  |  |  | 1677.97
V_104 | 1535.2988 | [10 empty] | 30202.6331 |  |  | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 | 1152.7358 | 251.694 | 3019.5821 | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [5 empty] | 0 | 0 | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 |  |  |  |  | 1677.97
V_82 | 1535.2988 | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 30202.6331 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | 3659.643 | 7107.6802 | 5542.1786 | 10293.1526 | 15.102 | 8235.459 | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 | 1152.7358 | 251.694 | 3019.5821 | 2975.59 | 3019.5821 | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 | 4529.3771 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_510 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.5825 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_293 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_160 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_332 | [19 empty] | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [7 empty] | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 503.3782
V_331 | [19 empty] | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [7 empty] | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 503.3782
V_575 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 413.7962 | 0 | 0 | 4598.19 | 402.71 | 5000.34 | 3227.29 | 13211.18 | 0 | 1925.4197 | 0 | 2975.515 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8578.59 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 9665.08 | 2516.3184 | 7550.85 | 6711.86 | 0 | 2237.29 | 0 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 1801.02 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_366 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_240 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_142 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_78 |  |  | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 | 1152.7358 |  |  | 2975.59 |  |  | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1510.1347 |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_403 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_378 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_205 |  | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 2745.153 | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 |  | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_70 | 1535.2988 | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 30202.6331 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | 3659.643 | 7107.6802 | 5542.1786 | 10293.1526 | 15.102 | 8235.459 | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.949 | 1258.47 | 1152.765 | 251.694 | 3019.5821 | 2975.59 | 3019.5821 | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 | 4529.3771 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_392 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_328 | [19 empty] | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [7 empty] | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 503.3782
V_447 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_251 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_304 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_298 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_87 | 1535.2988 | [10 empty] | 30202.6331 |  |  | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 | 1152.7358 | 251.694 | 3019.5821 | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [5 empty] | 0 | 0 | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 |  |  |  |  | 1677.97
V_573 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 413.7962 | 0 | 0 | 4598.19 | 402.71 | 5000.34 | 3227.29 | 13211.18 | 0 | 1925.4197 | 0 | 2975.515 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8578.59 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 9665.08 | 2516.3184 | 7550.85 | 6711.86 | 0 | 2237.29 | 0 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 1801.02 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_394 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_230 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_5 | 852.965 | 2097.45 | 2237.29 | 1381.53 | 7773.5988 | 2796.61 | 7768.97 | 0 | 10599.46 | 6622.37 | 17764.07 | 16779.66 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 1283.645 | 0 | 9665.08 | 0 | 0 | 2033.135 | 3948.81 | 3079.065 | 5718.4181 | 8.39 | 4575.255 | 20443.22 | 3635.595 | 94614.91 | 4737.46 | 25169.49 | 2796.61 | 4821.355 | 1398.305 | 699.15 | 640.425 | 139.83 | 1677.965 | 2975.59 | 1677.5456 | 5033.9 | 6711.86 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.9 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.96 | 1789.83 | 838.985 | 5593.22 | 0 | 2516.3206 | 12305.07 | 16220.34 | 1677.96 | 1677.97
V_264 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_342 | [19 empty] | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [7 empty] | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 503.3782
V_477 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.5825 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_540 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 413.7962 | 0 | 0 | 4598.19 | 402.71 | 1677.97 | 0 | 13211.18 | 0 | 1925.4197 | 0 | 2975.515 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 9665.08 | 2516.3184 | 7550.85 | 6711.86 | 0 | 2237.29 | 0 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 1801.02 | 0 | 0 | 0 | 5000.34 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 3227.29
V_577 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 413.7962 | 0 | 0 | 4598.19 | 402.71 | 5000.34 | 3227.29 | 13211.18 | 0 | 1925.4197 | 0 | 2975.515 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 9665.08 | 2516.3184 | 7550.85 | 6711.86 | 0 | 2237.29 | 0 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 1801.02 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_248 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_98 | 1535.2988 | [10 empty] | 30202.6331 |  |  | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 | 1152.7358 | 251.694 | 3019.5821 | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [5 empty] | 0 | 0 | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 |  |  |  |  | 1677.97
V_20 | 852.9438 | 2096.9256 | 2237.29 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 16779.2406 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 1283.6131 | 0 | 9665.08 | 0 | 0 | 2033.135 | 3948.7112 | 3078.9881 | 5718.4181 | 8.39 | 4575.255 | 20443.22 | 3635.595 | 94614.91 | 4737.46 | 25169.49 | 2796.61 | 4821.355 | 1398.305 | 699.15 | 640.425 | 139.83 | 1677.5456 | 2975.59 | 1677.5456 | 5033.9 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 838.9638 | 5593.08 | 0 | 2516.3206 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_425 | [25 empty] | 0 | 0 | [6 empty] | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | [6 empty] | 2975.59
V_219 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_481 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.5825 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_129 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_3 |  | 2097.45 | 2237.29 | 1381.53 | 7773.5988 | 2796.61 | 7768.97 | 0 | 10599.46 | 6622.37 | 17764.07 | 16779.66 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 1283.645 | 0 | 9665.08 | 0 | 0 | 2033.135 | 3948.81 | 3079.065 | 5718.4181 | 8.39 | 4575.255 | [11 empty] | 1677.965 | 2975.59 | 1677.5456 | 5033.9 | 6711.86 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.9 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 |  | 1677.96 | 1789.83 |  |  | 0 | 2516.3206 | 12305.07 | 16220.34 | 1677.96 | 1677.97
V_68 | 1535.2988 | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 30202.6331 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | 3659.643 | 7107.6802 | 5542.1786 | 10293.1526 | 15.102 | 8235.459 | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.949 | 1258.47 | 1152.765 | 251.694 | 3019.5821 | 2975.59 | 3019.5821 | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 | 4529.3771 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_288 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_64 | 1535.2988 | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 30202.6331 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | 3659.643 | 7107.6802 | 5542.1786 | 10293.1526 | 15.102 | 8235.459 | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.949 | 1258.47 | 1152.765 | 251.694 | 3019.5821 | 2975.59 | 3019.5821 | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 | 4529.3771 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_402 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_574 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 413.7962 | 0 | 0 | 4598.19 | 402.71 | 5000.34 | 3227.29 | 13211.18 | 0 | 1925.4197 | 0 | 2975.515 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8578.59 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 9665.08 | 2516.3184 | 7550.85 | 6711.86 | 0 | 2237.29 | 0 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 1801.02 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_482 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.5825 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_234 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_187 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_171 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_282 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_420 | [25 empty] | 0 | 0 | [6 empty] | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | [6 empty] | 2975.59
V_520 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4598.19 | 402.71 | 1677.97 | 3227.29 | 13211.18 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6711.86 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 1677.96 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 0 | 5000.34
V_561 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | [9 empty] | 1925.4197 |  |  |  | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 |  | 2516.3184 | 7550.85 | 6711.86 | 0 |  |  |  |  | 564.91 | [8 empty] | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 |  | 0 |  |  | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96
V_565 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | [9 empty] | 1925.4197 |  |  |  | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 |  | 2516.3184 | 7550.85 | 6711.86 | 0 |  |  |  |  | 564.91 | [8 empty] | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 |  | 0 |  |  | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96
V_239 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_183 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_450 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.8787 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56764.7512 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_484 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.5825 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_370 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_463 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.5825 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_514 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4598.19 | 402.71 | 1677.97 | 3227.29 | 13211.18 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6711.86 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 1677.96 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 0 | 5000.34
V_556 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 413.7962 | 0 | 0 | 4598.19 | 402.71 | 1677.97 | 3227.29 | 13211.18 | 0 | 1925.4197 | 0 | 2975.515 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 9665.08 | 2516.3184 | 7550.85 | 6711.86 | 0 | 2237.29 | 0 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 1801.02 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 5000.34
V_361 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_379 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_590 | 1279.4475 | 3146.175 | 3355.935 | 1381.53 | 7774.57 | 2796.61 | 7768.97 | 0 | 10599.99 | 6622.37 | 17764.07 | 25169.49 | 3887.29 | 413.9 | 0 | 0 | 4598.19 | 402.71 | 5000.34 | 3227.29 | 13211.18 | 0 | 1925.4675 | 0 | 1789.83 | 0 | 0 | 3049.7025 | 5923.215 | 4618.5975 | 8578.59 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141922.365 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.4575 | 1048.725 | 960.6375 | 209.745 | 2516.9475 | 9665.08 | 2516.9475 | 7550.85 | 6711.86 | 0 | 2237.29 | 0 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 1801.02 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.96 | 2975.59 | 1258.4775 | 8389.83 | 0 | 3775.425 | 12305.07 | 16220.34 | 1677.96 | 1677.97
V_10 |  |  | 2237.29 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 | 3635.595 | 94614.91 | 4737.46 | 25169.49 | 2796.61 | 4821.355 | 1398.305 | 699.15 | 640.425 | 139.83 |  | 2975.59 |  |  | 6711.6637 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 838.985 |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_339 | [19 empty] | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [7 empty] | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 503.3782
V_330 | [19 empty] | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [7 empty] | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 503.3782
V_427 | [25 empty] | 0 | 0 | [6 empty] | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | [6 empty] | 2975.59
V_178 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_30 | 852.9438 | [10 empty] | 16779.2406 |  | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 1283.6131 | 0 | 9665.08 | 0 | 0 | 2033.135 | 3948.7112 |  |  |  |  | 20443.22 | 3635.595 | 94610.1794 | 4737.46 | 25169.49 | 2796.61 | 4821.355 | 1398.305 | 699.15 | 640.425 | 139.83 | 1677.5456 | 2975.59 | 1677.5456 |  |  |  | 0 | 2237.29 | 2796.61 | 2852.48 |  | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 |  |  |  | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 838.9638 | 5593.08 | 0 | 2516.3206 |  |  | 1677.96 | 1677.97
V_563 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | [9 empty] | 1925.4197 |  |  |  | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 |  | 2516.3184 | 7550.85 | 6711.86 | 0 |  |  |  |  | 564.91 | [8 empty] | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 |  | 0 |  |  | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96
V_57 | 1535.2988 | [10 empty] | 30202.6331 | [7 empty] | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | 3659.643 | 7107.6802 | 5542.1786 | 10293.1526 | 15.102 |  | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.949 | 1258.47 | 1152.765 | 251.694 | 3019.5821 | 2975.59 | 3019.5821 | 9061.02 |  |  |  |  | 2796.61 | 2852.48 | [7 empty] | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 | 4529.3771 |  |  |  | 1677.97
V_312 | [19 empty] | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [7 empty] | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 503.3782
V_443 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_43 | 852.9438 | 2096.9256 | 2237.29 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 16779.2406 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 1283.6131 | 0 | 9665.08 | 0 | 0 | 2033.135 | 3948.7112 | 3078.9881 | 5718.4181 | 8.39 | 4575.255 | 20443.22 | 3635.595 | 94610.1794 | 4737.46 | 25169.49 | 2796.61 | 4821.355 | 1398.305 | 699.15 | 640.425 | 139.83 | 1677.5456 | 2975.59 | 1677.5456 | 5033.9 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 838.9638 | 5593.08 | 0 | 2516.3206 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_164 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_340 | [19 empty] | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [7 empty] | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 503.3782
V_283 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_387 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | [7 empty] | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 |  | 1677.54 | 1789.83 |  | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_319 | [19 empty] | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [7 empty] | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 503.3782
V_522 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4598.19 | 402.71 | 1677.97 | 3227.29 | 13211.18 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6711.86 | 0 | 2237.29 | 0 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 5000.34
V_81 | 1535.2988 | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 30202.6331 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | 3659.643 | 7107.6802 | 5542.1786 | 10293.1526 | 15.102 | 8235.459 | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 | 1152.7358 | 251.694 | 3019.5821 | 2975.59 | 3019.5821 | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 | 4529.3771 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_195 |  | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 2745.153 | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 |  | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_460 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.5825 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_16 |  |  | 2237.29 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 | 3635.595 | 94614.91 | 4737.46 | 25169.49 | 2796.61 | 4821.355 | 1398.305 | 699.15 | 640.425 | 139.83 |  | 2975.59 |  |  | 6711.6637 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 838.985 |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_226 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_140 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_305 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_381 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | [7 empty] | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 |  | 1677.54 | 1789.83 |  | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_79 | 1535.2988 | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 30202.6331 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | 3659.643 | 7107.6802 | 5542.1786 | 10293.1526 | 15.102 | 8235.459 | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 | 1152.7358 | 251.694 | 3019.5821 | 2975.59 | 3019.5821 | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 | 4529.3771 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_469 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.5825 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_216 |  | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 2745.153 | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 |  | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_120 | 1535.2988 | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 30202.6331 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | 3659.643 | 7107.6802 | 5542.1786 | 10293.1526 | 15.102 | 8235.459 | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 | 1152.7358 | 251.694 | 3019.5821 | 2975.59 | 3019.5821 | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 | 4529.3771 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_367 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_452 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.8787 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56764.7512 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_528 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4598.19 | 402.71 | 1677.97 | 3227.29 | 13211.18 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6711.86 | 0 | 2237.29 | 0 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 5000.34
V_157 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_290 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_9 | 852.9438 | 2096.9256 | 2237.29 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 16779.2406 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 1283.6131 | 0 | 9665.08 | 0 | 0 | 2033.135 | 3948.7112 | 3078.9881 | 5718.4181 | 8.39 | 4575.255 | 20443.22 | 3635.595 | 94614.91 | 4737.46 | 25169.49 | 2796.61 | 4821.355 | 1398.305 | 699.15 | 640.425 | 139.83 | 1677.5456 | 2975.59 | 1677.5456 | 5033.9 | 6711.6637 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 838.985 | 5593.08 | 0 | 2516.3206 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_505 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.5825 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_169 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_448 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_145 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_562 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | [9 empty] | 1925.4197 |  |  |  | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 |  | 2516.3184 | 7550.85 | 6711.86 | 0 |  |  |  |  | 564.91 | [8 empty] | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 |  | 0 |  |  | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96
V_275 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_150 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_307 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_458 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.5825 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56754.7538 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.515 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_198 |  | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 2745.153 | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 |  | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_22 | 852.9438 | 2096.9256 | 2237.29 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 16779.2406 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 1283.6131 | 0 | 9665.08 | 0 | 0 | 2033.135 | 3948.7112 | 3078.9881 | 5718.4181 | 8.39 | 4575.255 | 20443.22 | 3635.595 | 94614.91 | 4737.46 | 25169.49 | 2796.61 | 4821.355 | 1398.305 | 699.15 | 640.425 | 139.83 | 1677.5456 | 2975.59 | 1677.5456 | 5033.9 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 838.9638 | 5593.08 | 0 | 2516.3206 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_42 | 852.9438 | 2096.9256 | 2237.29 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 16779.2406 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 1283.6131 | 0 | 9665.08 | 0 | 0 | 2033.135 | 3948.7112 | 3078.9881 | 5718.4181 | 8.39 | 4575.255 | 20443.22 | 3635.595 | 94610.1794 | 4737.46 | 25169.49 | 2796.61 | 4821.355 | 1398.305 | 699.15 | 640.425 | 139.83 | 1677.5456 | 2975.59 | 1677.5456 | 5033.9 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 838.9638 | 5593.08 | 0 | 2516.3206 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_49 | 852.9438 | 2096.9256 | 2237.29 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 16779.2406 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 1283.6131 | 0 | 9665.08 | 0 | 0 | 2033.135 | 3948.7112 | 3078.9881 | 5718.4181 | 8.39 | 4575.255 | 20443.22 | 3635.595 | 94610.1794 | 4737.46 | 25169.49 | 2796.61 | 4821.355 | 1398.305 | 699.15 | 640.425 | 139.83 | 1677.5456 | 2975.59 | 1677.5456 | 5033.9 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 838.9638 | 5593.08 | 0 | 2516.3206 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_411 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_581 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 413.7962 | 0 | 0 | 4598.19 | 402.71 | 5000.34 | 3227.29 | 13211.18 | 0 | 1925.4197 | 0 | 2975.515 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 9665.08 | 2516.3184 | 7550.85 | 6711.86 | 0 | 2237.29 | 0 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 1801.02 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_153 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_200 |  | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 2745.153 | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 |  | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_97 | 1535.2988 | [10 empty] | 30202.6331 |  |  | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 | 1152.7358 | 251.694 | 3019.5821 | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [5 empty] | 0 | 0 | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 |  |  |  |  | 1677.97
V_533 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 413.7962 | 0 | 0 | 4598.19 | 402.71 | 1677.97 | 3227.29 | 13211.18 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6711.86 | 0 | 2237.29 | 0 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 1801.02 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 5000.34
V_377 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_56 | 1535.2988 | [10 empty] | 30202.6331 | [7 empty] | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | 3659.643 | 7107.6802 | 5542.1786 | 10293.1526 | 15.102 |  | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.949 | 1258.47 | 1152.765 | 251.694 | 3019.5821 | 2975.59 | 3019.5821 | 9061.02 |  |  |  |  | 2796.61 | 2852.48 | [7 empty] | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 | 4529.3771 |  |  |  | 1677.97
V_58 | 1535.2988 | [10 empty] | 30202.6331 | [7 empty] | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | 3659.643 | 7107.6802 | 5542.1786 | 10293.1526 | 15.102 |  | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.949 | 1258.47 | 1152.765 | 251.694 | 3019.5821 | 2975.59 | 3019.5821 | 9061.02 |  |  |  |  | 2796.61 | 2852.48 | [7 empty] | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 | 4529.3771 |  |  |  | 1677.97
V_151 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_194 |  | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 2745.153 | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 |  | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_545 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 413.7962 | 0 | 0 | 4598.19 | 402.71 | 1677.97 | 3227.29 | 13211.18 | 0 | 1925.4197 | 0 | 2975.515 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 9665.08 | 2516.3184 | 7550.85 | 6711.86 | 0 | 2237.29 | 0 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 1801.02 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 5000.34
V_492 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.5825 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_276 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_173 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_349 | [19 empty] | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [7 empty] | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 503.3782
V_13 |  |  | 2237.29 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 | 3635.595 | 94614.91 | 4737.46 | 25169.49 | 2796.61 | 4821.355 | 1398.305 | 699.15 | 640.425 | 139.83 |  | 2975.59 |  |  | 6711.6637 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 838.985 |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_303 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_33 | 852.9438 | [10 empty] | 16779.2406 |  | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 1283.6131 | 0 | 9665.08 | 0 | 0 | 2033.135 | 3948.7112 |  |  |  |  | 20443.22 | 3635.595 | 94610.1794 | 4737.46 | 25169.49 | 2796.61 | 4821.355 | 1398.305 | 699.15 | 640.425 | 139.83 | 1677.5456 | 2975.59 | 1677.5456 |  |  |  | 0 | 2237.29 | 2796.61 | 2852.48 |  | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 |  |  |  | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 838.9638 | 5593.08 | 0 | 2516.3206 |  |  | 1677.96 | 1677.97
V_348 | [19 empty] | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [7 empty] | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 503.3782
V_401 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_189 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_215 |  | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 2745.153 | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 |  | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_424 | [25 empty] | 0 | 0 | [6 empty] | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | [6 empty] | 2975.59
V_583 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 413.7962 | 0 | 0 | 4598.19 | 402.71 | 5000.34 | 3227.29 | 13211.18 | 0 | 1925.4197 | 0 | 2975.515 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 9665.08 | 2516.3184 | 7550.85 | 6711.86 | 0 | 2237.29 | 0 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 1801.02 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_52 | 852.9438 | [10 empty] | 16779.2406 | [7 empty] | 3227.29 | 13210.52 | 0 | 1283.6131 | 0 | 9665.08 | 0 | 0 | 2033.135 | 3948.7112 | 3078.9881 | 5718.4181 | 8.39 |  | 20443.22 | 3635.595 | 94610.1794 | 4737.46 | 25169.49 | 2796.61 | 4821.355 | 1398.305 | 699.15 | 640.425 | 139.83 | 1677.5456 | 2975.59 | 1677.5456 | 5033.9 |  |  |  |  | 2796.61 | 2852.48 | [7 empty] | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 838.9638 | 5593.08 | 0 | 2516.3206 |  |  |  | 1677.97
V_76 |  |  | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 | 1152.7358 |  |  | 2975.59 |  |  | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1510.1347 |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_46 | 852.9438 | 2096.9256 | 2237.29 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 16779.2406 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 1283.6131 | 0 | 9665.08 | 0 | 0 | 2033.135 | 3948.7112 | 3078.9881 | 5718.4181 | 8.39 | 4575.255 | 20443.22 | 3635.595 | 94610.1794 | 4737.46 | 25169.49 | 2796.61 | 4821.355 | 1398.305 | 699.15 | 640.425 | 139.83 | 1677.5456 | 2975.59 | 1677.5456 | 5033.9 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 838.9638 | 5593.08 | 0 | 2516.3206 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_504 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.5825 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_489 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.5825 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_96 | 1535.2988 | [10 empty] | 30202.6331 |  |  | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 | 1152.7358 | 251.694 | 3019.5821 | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [5 empty] | 0 | 0 | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 |  |  |  |  | 1677.97
V_93 | 1535.2988 | [10 empty] | 30202.6331 |  |  | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 | 1152.7358 | 251.694 | 3019.5821 | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [5 empty] | 0 | 0 | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 |  |  |  |  | 1677.97
V_258 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_237 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_201 |  | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 2745.153 | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 |  | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_154 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_334 | [19 empty] | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [7 empty] | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 503.3782
V_478 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.5825 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_85 | 1535.2988 | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 30202.6331 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | 3659.643 | 7107.6802 | 5542.1786 | 10293.1526 | 15.102 | 8235.459 | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 | 1152.7358 | 251.694 | 3019.5821 | 2975.59 | 3019.5821 | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 | 4529.3771 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_526 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4598.19 | 402.71 | 1677.97 | 3227.29 | 13211.18 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6711.86 | 0 | 2237.29 | 0 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 5000.34
V_218 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_172 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_566 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | [9 empty] | 1925.4197 |  |  |  | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 |  | 2516.3184 | 7550.85 | 6711.86 | 0 |  |  |  |  | 564.91 | [8 empty] | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 |  | 0 |  |  | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96
V_559 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | [9 empty] | 1925.4197 |  |  |  | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 |  | 2516.3184 | 7550.85 | 6711.86 | 0 |  |  |  |  | 564.91 | [8 empty] | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 |  | 0 |  |  | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96
V_436 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_88 | 1535.2988 | [10 empty] | 30202.6331 |  |  | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 | 1152.7358 | 251.694 | 3019.5821 | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [5 empty] | 0 | 0 | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 |  |  |  |  | 1677.97
V_225 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_50 | 852.9438 | [10 empty] | 16779.2406 | [7 empty] | 3227.29 | 13210.52 | 0 | 1283.6131 | 0 | 9665.08 | 0 | 0 | 2033.135 | 3948.7112 | 3078.9881 | 5718.4181 | 8.39 |  | 20443.22 | 3635.595 | 94610.1794 | 4737.46 | 25169.49 | 2796.61 | 4821.355 | 1398.305 | 699.15 | 640.425 | 139.83 | 1677.5456 | 2975.59 | 1677.5456 | 5033.9 |  |  |  |  | 2796.61 | 2852.48 | [7 empty] | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 838.9638 | 5593.08 | 0 | 2516.3206 |  |  |  | 1677.97
V_431 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_462 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.5825 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_90 | 1535.2988 | [10 empty] | 30202.6331 |  |  | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 | 1152.7358 | 251.694 | 3019.5821 | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [5 empty] | 0 | 0 | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 |  |  |  |  | 1677.97
V_130 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_294 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_245 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_415 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_580 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 413.7962 | 0 | 0 | 4598.19 | 402.71 | 5000.34 | 3227.29 | 13211.18 | 0 | 1925.4197 | 0 | 2975.515 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 9665.08 | 2516.3184 | 7550.85 | 6711.86 | 0 | 2237.29 | 0 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 1801.02 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_418 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_457 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.5825 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56754.7538 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.515 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_550 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 413.7962 | 0 | 0 | 4598.19 | 402.71 | 1677.97 | 3227.29 | 13211.18 | 0 | 1925.4197 | 0 | 2975.515 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 9665.08 | 2516.3184 | 7550.85 | 6711.86 | 0 | 2237.29 | 0 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 1801.02 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 5000.34
V_385 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | [7 empty] | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 |  | 1677.54 | 1789.83 |  | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_135 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_54 | 1535.2988 | [10 empty] | 30202.6331 | [7 empty] | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | 3659.643 | 7107.6802 | 5542.1786 | 10293.1526 | 15.102 |  | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.949 | 1258.47 | 1152.765 | 251.694 | 3019.5821 | 2975.59 | 3019.5821 | 9061.02 |  |  |  |  | 2796.61 | 2852.48 | [7 empty] | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 | 4529.3771 |  |  |  | 1677.97
V_383 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | [7 empty] | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 |  | 1677.54 | 1789.83 |  | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_190 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_101 | 1535.2988 | [10 empty] | 30202.6331 |  |  | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 | 1152.7358 | 251.694 | 3019.5821 | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [5 empty] | 0 | 0 | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 |  |  |  |  | 1677.97
V_309 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_167 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_95 | 1535.2988 | [10 empty] | 30202.6331 |  |  | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 | 1152.7358 | 251.694 | 3019.5821 | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [5 empty] | 0 | 0 | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 |  |  |  |  | 1677.97
V_543 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 413.7962 | 0 | 0 | 4598.19 | 402.71 | 1677.97 | 0 | 13211.18 | 0 | 1925.4197 | 0 | 2975.515 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 9665.08 | 2516.3184 | 7550.85 | 6711.86 | 0 | 2237.29 | 0 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 1801.02 | 0 | 0 | 0 | 5000.34 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 3227.29
V_141 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_534 | [25 empty] | 0 | 0 | [6 empty] | 20443.22 | [11 empty] | 2975.515
V_124 | 1535.2988 | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 30202.6331 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | 3659.643 | 7107.6802 | 5542.1786 | 10293.1526 | 15.102 | 8235.459 | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 | 1152.7358 | 251.694 | 3019.5821 | 2975.59 | 3019.5821 | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 | 4529.3771 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_210 |  | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 2745.153 | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 |  | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_67 | 1535.2988 | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 30202.6331 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | 3659.643 | 7107.6802 | 5542.1786 | 10293.1526 | 15.102 | 8235.459 | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.949 | 1258.47 | 1152.765 | 251.694 | 3019.5821 | 2975.59 | 3019.5821 | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 | 4529.3771 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_278 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_59 | 1535.2988 | [10 empty] | 30202.6331 | [7 empty] | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | 3659.643 | 7107.6802 | 5542.1786 | 10293.1526 | 15.102 |  | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.949 | 1258.47 | 1152.765 | 251.694 | 3019.5821 | 2975.59 | 3019.5821 | 9061.02 |  |  |  |  | 2796.61 | 2852.48 | [7 empty] | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 | 4529.3771 |  |  |  | 1677.97
V_6 | 852.965 | 2097.45 | 2237.29 | 1381.53 | 7773.5988 | 2796.61 | 7768.97 | 0 | 10599.46 | 6622.37 | 17764.07 | 16779.66 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 1283.645 | 0 | 9665.08 | 0 | 0 | 2033.135 | 3948.81 | 3079.065 | 5718.4181 | 8.39 | 4575.255 | 20443.22 | 3635.595 | 94614.91 | 4737.46 | 25169.49 | 2796.61 | 4821.355 | 1398.305 | 699.15 | 640.425 | 139.83 | 1677.965 | 2975.59 | 1677.5456 | 5033.9 | 6711.86 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.9 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.96 | 1789.83 | 838.985 | 5593.22 | 0 | 2516.3206 | 12305.07 | 16220.34 | 1677.96 | 1677.97
V_390 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_185 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_111 | 1535.2988 | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 30202.6331 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | 3659.643 | 7107.6802 | 5542.1786 | 10293.1526 | 15.102 | 8235.459 | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 | 1152.7358 | 251.694 | 3019.5821 | 2975.59 | 3019.5821 | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 | 4529.3771 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_373 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_212 |  | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 2745.153 | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 |  | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_432 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_196 |  | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 2745.153 | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 |  | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_168 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_531 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 413.7962 | 0 | 0 | 4598.19 | 402.71 | 1677.97 | 3227.29 | 13211.18 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6711.86 | 0 | 2237.29 | 0 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 1801.02 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 5000.34
V_359 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_256 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_197 |  | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 2745.153 | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 |  | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_7 | 852.965 | 2097.45 | 2237.29 | 1381.53 | 7773.5988 | 2796.61 | 7768.97 | 0 | 10599.46 | 6622.37 | 17764.07 | 16779.66 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 1283.645 | 0 | 9665.08 | 0 | 0 | 2033.135 | 3948.81 | 3079.065 | 5718.4181 | 8.39 | 4575.255 | 20443.22 | 3635.595 | 94614.91 | 4737.46 | 25169.49 | 2796.61 | 4821.355 | 1398.305 | 699.15 | 640.425 | 139.83 | 1677.965 | 2975.59 | 1677.5456 | 5033.9 | 6711.86 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.9 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.96 | 1789.83 | 838.985 | 5593.22 | 0 | 2516.3206 | 12305.07 | 16220.34 | 1677.96 | 1677.97
V_384 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | [7 empty] | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 |  | 1677.54 | 1789.83 |  | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_2 |  | 2097.45 | 2237.29 | 1381.53 | 7773.5988 | 2796.61 | 7768.97 | 0 | 10599.46 | 6622.37 | 17764.07 | 16779.66 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 1283.645 | 0 | 9665.08 | 0 | 0 | 2033.135 | 3948.81 | 3079.065 | 5718.4181 | 8.39 | 4575.255 | [11 empty] | 1677.965 | 2975.59 | 1677.5456 | 5033.9 | 6711.86 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.9 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 |  | 1677.96 | 1789.83 |  |  | 0 | 2516.3206 | 12305.07 | 16220.34 | 1677.96 | 1677.97
V_147 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_439 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_180 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_109 | 1535.2988 | [10 empty] | 30202.6331 |  |  | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 | 1152.7358 | 251.694 | 3019.5821 | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [5 empty] | 0 | 0 | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 |  |  |  |  | 1677.97
V_8 | 852.965 | 2097.45 | 2237.29 | 1381.53 | 7773.5988 | 2796.61 | 7768.97 | 0 | 10599.46 | 6622.37 | 17764.07 | 16779.66 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 1283.645 | 0 | 9665.08 | 0 | 0 | 2033.135 | 3948.81 | 3079.065 | 5718.4181 | 8.39 | 4575.255 | 20443.22 | 3635.595 | 94614.91 | 4737.46 | 25169.49 | 2796.61 | 4821.355 | 1398.305 | 699.15 | 640.425 | 139.83 | 1677.965 | 2975.59 | 1677.5456 | 5033.9 | 6711.86 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.9 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.96 | 1789.83 | 838.985 | 5593.22 | 0 | 2516.3206 | 12305.07 | 16220.34 | 1677.96 | 1677.97
V_400 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_551 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 413.7962 | 0 | 0 | 4598.19 | 402.71 | 1677.97 | 3227.29 | 13211.18 | 0 | 1925.4197 | 0 | 2975.515 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 9665.08 | 2516.3184 | 7550.85 | 6711.86 | 0 | 2237.29 | 0 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 1801.02 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 5000.34
V_393 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_391 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_281 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_191 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_567 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | [9 empty] | 1925.4197 |  |  |  | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 |  | 2516.3184 | 7550.85 | 6711.86 | 0 |  |  |  |  | 564.91 | [8 empty] | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 |  | 0 |  |  | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96
V_217 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_73 | 1535.2988 | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 30202.6331 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | 3659.643 | 7107.6802 | 5542.1786 | 10293.1526 | 15.102 | 8235.459 | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 | 1152.7358 | 251.694 | 3019.5821 | 2975.59 | 3019.5821 | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 | 4529.3771 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_314 | [19 empty] | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [7 empty] | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 503.3782
V_149 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_521 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4598.19 | 402.71 | 1677.97 | 3227.29 | 13211.18 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6711.86 | 0 | 2237.29 | 0 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 5000.34
V_92 | 1535.2988 | [10 empty] | 30202.6331 |  |  | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 | 1152.7358 | 251.694 | 3019.5821 | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [5 empty] | 0 | 0 | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 |  |  |  |  | 1677.97
V_516 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4598.19 | 402.71 | 1677.97 | 3227.29 | 13211.18 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6711.86 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 1677.96 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 0 | 5000.34
V_491 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.5825 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_518 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4598.19 | 402.71 | 1677.97 | 3227.29 | 13211.18 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6711.86 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 1677.96 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 0 | 5000.34
V_295 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_238 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_252 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_322 | [19 empty] | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [7 empty] | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 503.3782
V_444 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_434 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_503 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.5825 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_15 |  |  | 2237.29 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 | 3635.595 | 94614.91 | 4737.46 | 25169.49 | 2796.61 | 4821.355 | 1398.305 | 699.15 | 640.425 | 139.83 |  | 2975.59 |  |  | 6711.6637 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 838.985 |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_269 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_229 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_587 | 1279.4475 | 3146.175 | 3355.935 | 1381.53 | 7774.57 | 2796.61 | 7768.97 | 0 | 10599.99 | 6622.37 | 17764.07 | 25169.49 | 3887.29 | 413.9 | 0 | 0 | 4598.19 | 402.71 | 5000.34 | 3227.29 | 13211.18 | 0 | 1925.4675 | 0 | 1789.83 | 0 | 0 | 3049.7025 | 5923.215 | 4618.5975 | 8578.59 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141922.365 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.4575 | 1048.725 | 960.6375 | 209.745 | 2516.9475 | 9665.08 | 2516.9475 | 7550.85 | 6711.86 | 0 | 2237.29 | 0 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 1801.02 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.96 | 2975.59 | 1258.4775 | 8389.83 | 0 | 3775.425 | 12305.07 | 16220.34 | 1677.96 | 1677.97
V_441 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_148 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_352 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_277 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_568 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | [9 empty] | 1925.4197 |  |  |  | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 |  | 2516.3184 | 7550.85 | 6711.86 | 0 |  |  |  |  | 564.91 | [8 empty] | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 |  | 0 |  |  | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96
V_227 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_320 | [19 empty] | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [7 empty] | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 503.3782
V_542 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 413.7962 | 0 | 0 | 4598.19 | 402.71 | 1677.97 | 0 | 13211.18 | 0 | 1925.4197 | 0 | 2975.515 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 9665.08 | 2516.3184 | 7550.85 | 6711.86 | 0 | 2237.29 | 0 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 1801.02 | 0 | 0 | 0 | 5000.34 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 3227.29
V_235 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_65 | 1535.2988 | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 30202.6331 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | 3659.643 | 7107.6802 | 5542.1786 | 10293.1526 | 15.102 | 8235.459 | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.949 | 1258.47 | 1152.765 | 251.694 | 3019.5821 | 2975.59 | 3019.5821 | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 | 4529.3771 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_25 | 852.9438 | 2096.9256 | 2237.29 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 16779.2406 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 1283.6131 | 0 | 9665.08 | 0 | 0 | 2033.135 | 3948.7112 | 3078.9881 | 5718.4181 | 8.39 | 4575.255 | 20443.22 | 3635.595 | 94610.1794 | 4737.46 | 25169.49 | 2796.61 | 4821.355 | 1398.305 | 699.15 | 640.425 | 139.83 | 1677.5456 | 2975.59 | 1677.5456 | 5033.9 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 838.9638 | 5593.08 | 0 | 2516.3206 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_84 | 1535.2988 | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 30202.6331 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | 3659.643 | 7107.6802 | 5542.1786 | 10293.1526 | 15.102 | 8235.459 | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 | 1152.7358 | 251.694 | 3019.5821 | 2975.59 | 3019.5821 | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 | 4529.3771 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_246 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_128 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_174 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_496 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.5825 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_110 | 1535.2988 | [10 empty] | 30202.6331 |  |  | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 | 1152.7358 | 251.694 | 3019.5821 | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [5 empty] | 0 | 0 | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 |  |  |  |  | 1677.97
V_351 | [19 empty] | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [7 empty] | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 503.3782
V_263 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_207 |  | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 2745.153 | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 |  | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_284 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_232 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_184 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_306 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_502 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.5825 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_280 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_360 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_544 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 413.7962 | 0 | 0 | 4598.19 | 402.71 | 1677.97 | 0 | 13211.18 | 0 | 1925.4197 | 0 | 2975.515 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 9665.08 | 2516.3184 | 7550.85 | 6711.86 | 0 | 2237.29 | 0 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 1801.02 | 0 | 0 | 0 | 5000.34 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 3227.29
V_44 | 852.9438 | 2096.9256 | 2237.29 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 16779.2406 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 1283.6131 | 0 | 9665.08 | 0 | 0 | 2033.135 | 3948.7112 | 3078.9881 | 5718.4181 | 8.39 | 4575.255 | 20443.22 | 3635.595 | 94610.1794 | 4737.46 | 25169.49 | 2796.61 | 4821.355 | 1398.305 | 699.15 | 640.425 | 139.83 | 1677.5456 | 2975.59 | 1677.5456 | 5033.9 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 838.9638 | 5593.08 | 0 | 2516.3206 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_75 |  |  | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 | 1152.7358 |  |  | 2975.59 |  |  | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1510.1347 |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_18 |  |  | 2237.29 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 | 3635.595 | 94614.91 | 4737.46 | 25169.49 | 2796.61 | 4821.355 | 1398.305 | 699.15 | 640.425 | 139.83 |  | 2975.59 |  |  | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 838.9638 |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_17 |  |  | 2237.29 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 | 3635.595 | 94614.91 | 4737.46 | 25169.49 | 2796.61 | 4821.355 | 1398.305 | 699.15 | 640.425 | 139.83 |  | 2975.59 |  |  | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 838.9638 |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_204 |  | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 2745.153 | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 |  | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_363 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_530 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 413.7962 | 0 | 0 | 4598.19 | 402.71 | 1677.97 | 3227.29 | 13211.18 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6711.86 | 0 | 2237.29 | 0 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 1801.02 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 5000.34
V_485 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.5825 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_413 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_362 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_228 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_4 | 852.965 | 2097.45 | 2237.29 | 1381.53 | 7773.5988 | 2796.61 | 7768.97 | 0 | 10599.46 | 6622.37 | 17764.07 | 16779.66 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 1283.645 | 0 | 9665.08 | 0 | 0 | 2033.135 | 3948.81 | 3079.065 | 5718.4181 | 8.39 | 4575.255 | 20443.22 | 3635.595 | 94614.91 | 4737.46 | 25169.49 | 2796.61 | 4821.355 | 1398.305 | 699.15 | 640.425 | 139.83 | 1677.965 | 2975.59 | 1677.5456 | 5033.9 | 6711.86 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.9 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.96 | 1789.83 | 838.985 | 5593.22 | 0 | 2516.3206 | 12305.07 | 16220.34 | 1677.96 | 1677.97
V_347 | [19 empty] | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [7 empty] | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 503.3782
V_249 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_317 | [19 empty] | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [7 empty] | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 503.3782
V_53 | 1535.2988 | [10 empty] | 30202.6331 | [7 empty] | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | 3659.643 | 7107.6802 | 5542.1786 | 10293.1526 | 15.102 |  | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.949 | 1258.47 | 1152.765 | 251.694 | 3019.5821 | 2975.59 | 3019.5821 | 9061.02 |  |  |  |  | 2796.61 | 2852.48 | [7 empty] | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 | 4529.3771 |  |  |  | 1677.97
V_465 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.5825 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_208 |  | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 2745.153 | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 |  | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_297 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_344 | [19 empty] | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [7 empty] | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 503.3782
V_26 | 852.9438 | 2096.9256 | 2237.29 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 16779.2406 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 1283.6131 | 0 | 9665.08 | 0 | 0 | 2033.135 | 3948.7112 | 3078.9881 | 5718.4181 | 8.39 | 4575.255 | 20443.22 | 3635.595 | 94610.1794 | 4737.46 | 25169.49 | 2796.61 | 4821.355 | 1398.305 | 699.15 | 640.425 | 139.83 | 1677.5456 | 2975.59 | 1677.5456 | 5033.9 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 838.9638 | 5593.08 | 0 | 2516.3206 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_170 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_86 | 1535.2988 | [10 empty] | 30202.6331 |  |  | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 | 1152.7358 | 251.694 | 3019.5821 | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [5 empty] | 0 | 0 | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 |  |  |  |  | 1677.97
V_313 | [19 empty] | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [7 empty] | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 503.3782
V_499 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.5825 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_386 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | [7 empty] | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 |  | 1677.54 | 1789.83 |  | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_329 | [19 empty] | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [7 empty] | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 503.3782
V_143 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_578 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 413.7962 | 0 | 0 | 4598.19 | 402.71 | 5000.34 | 3227.29 | 13211.18 | 0 | 1925.4197 | 0 | 2975.515 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 9665.08 | 2516.3184 | 7550.85 | 6711.86 | 0 | 2237.29 | 0 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 1801.02 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_558 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | [9 empty] | 1925.4197 |  |  |  | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 |  | 2516.3184 | 7550.85 | 6711.86 | 0 |  |  |  |  | 564.91 | [8 empty] | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 |  | 0 |  |  | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96
V_475 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.5825 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_1 |  | 2097.45 | 2237.29 | 1381.53 | 7773.5988 | 2796.61 | 7768.97 | 0 | 10599.46 | 6622.37 | 17764.07 | 16779.66 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 1283.645 | 0 | 9665.08 | 0 | 0 | 2033.135 | 3948.81 | 3079.065 | 5718.4181 | 8.39 | 4575.255 | [11 empty] | 1677.965 | 2975.59 | 1677.5456 | 5033.9 | 6711.86 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.9 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 |  | 1677.96 | 1789.83 |  |  | 0 | 2516.3206 | 12305.07 | 16220.34 | 1677.96 | 1677.97
V_517 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4598.19 | 402.71 | 1677.97 | 3227.29 | 13211.18 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6711.86 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 1677.96 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 0 | 5000.34
V_519 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4598.19 | 402.71 | 1677.97 | 3227.29 | 13211.18 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6711.86 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 1677.96 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 0 | 5000.34
V_327 | [19 empty] | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [7 empty] | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 503.3782
V_410 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_166 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_220 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_353 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_39 | 852.9438 | 2096.9256 | 2237.29 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 16779.2406 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 1283.6131 | 0 | 9665.08 | 0 | 0 | 2033.135 | 3948.7112 | 3078.9881 | 5718.4181 | 8.39 | 4575.255 | 20443.22 | 3635.595 | 94610.1794 | 4737.46 | 25169.49 | 2796.61 | 4821.355 | 1398.305 | 699.15 | 640.425 | 139.83 | 1677.5456 | 2975.59 | 1677.5456 | 5033.9 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 838.9638 | 5593.08 | 0 | 2516.3206 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_486 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.5825 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_221 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_549 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 413.7962 | 0 | 0 | 4598.19 | 402.71 | 1677.97 | 3227.29 | 13211.18 | 0 | 1925.4197 | 0 | 2975.515 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 9665.08 | 2516.3184 | 7550.85 | 6711.86 | 0 | 2237.29 | 0 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 1801.02 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 5000.34
V_126 | 1535.2988 | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 30202.6331 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 2310.5036 | 0 | 9665.08 | 0 | 0 | 3659.643 | 7107.6802 | 5542.1786 | 10293.1526 | 15.102 | 8235.459 | 20443.22 | 6544.071 | 170298.3229 | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 | 1152.7358 | 251.694 | 3019.5821 | 2975.59 | 3019.5821 | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1510.1347 | 10067.544 | 0 | 4529.3771 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_576 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 413.7962 | 0 | 0 | 4598.19 | 402.71 | 5000.34 | 3227.29 | 13211.18 | 0 | 1925.4197 | 0 | 2975.515 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8578.59 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 9665.08 | 2516.3184 | 7550.85 | 6711.86 | 0 | 2237.29 | 0 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 1801.02 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_321 | [19 empty] | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 |  |  | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 |  |  |  | 2975.59 | [6 empty] | 2796.61 | 2852.48 | [7 empty] | 0 | 4698.31 | [8 empty] | 0 | 1677.54 | 1789.83 | 503.3782
V_41 | 852.9438 | 2096.9256 | 2237.29 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 16779.2406 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 1283.6131 | 0 | 9665.08 | 0 | 0 | 2033.135 | 3948.7112 | 3078.9881 | 5718.4181 | 8.39 | 4575.255 | 20443.22 | 3635.595 | 94610.1794 | 4737.46 | 25169.49 | 2796.61 | 4821.355 | 1398.305 | 699.15 | 640.425 | 139.83 | 1677.5456 | 2975.59 | 1677.5456 | 5033.9 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 838.9638 | 5593.08 | 0 | 2516.3206 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_223 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_472 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.5825 | 0 | 1925.4197 | 0 | 9665.08 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 2975.515 | 2516.3184 | 7550.85 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_47 | 852.9438 | 2096.9256 | 2237.29 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 16779.2406 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 1283.6131 | 0 | 9665.08 | 0 | 0 | 2033.135 | 3948.7112 | 3078.9881 | 5718.4181 | 8.39 | 4575.255 | 20443.22 | 3635.595 | 94610.1794 | 4737.46 | 25169.49 | 2796.61 | 4821.355 | 1398.305 | 699.15 | 640.425 | 139.83 | 1677.5456 | 2975.59 | 1677.5456 | 5033.9 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 838.9638 | 5593.08 | 0 | 2516.3206 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_299 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_188 |  | 3774.4661 | 4027.122 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [5 empty] | 8235.459 | 20443.22 |  |  | 4737.46 | 25169.49 | 5033.898 | 8678.439 | 2516.886 | 1258.47 |  |  |  | 2975.59 |  | 9061.02 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 |  |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_553 | 1279.4156 | 3145.3884 | 3355.935 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 25168.8609 | 3886.3187 | 413.7962 | 0 | 0 | 4598.19 | 402.71 | 1677.97 | 3227.29 | 13211.18 | 0 | 1925.4197 | 0 | 2975.515 | 0 | 0 | 3049.7025 | 5923.0669 | 4618.4822 | 8577.6272 | 12.585 | 6862.8825 | 20443.22 | 5453.3925 | 141886.8844 | 4737.46 | 25169.49 | 4194.915 | 7232.0325 | 2097.405 | 1048.725 | 960.6131 | 209.745 | 2516.3184 | 9665.08 | 2516.3184 | 7550.85 | 6711.86 | 0 | 2237.29 | 0 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 1801.02 | 0 | 0 | 0 | 0 | 4698.31 | 1677.96 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 1258.4456 | 8389.62 | 0 | 3774.4809 | 12304.7625 | 16216.285 | 1677.96 | 5000.34
V_397 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.725 | 6622.37 | 17763.6263 | 10067.5444 | 3886.3187 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6710.1825 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.7625 | 16216.285 | 1677.96 | 1677.97
V_36 | 852.9438 | 2096.9256 | 2237.29 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 16779.2406 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 1283.6131 | 0 | 9665.08 | 0 | 0 | 2033.135 | 3948.7112 | 3078.9881 | 5718.4181 | 8.39 | 4575.255 | 20443.22 | 3635.595 | 94610.1794 | 4737.46 | 25169.49 | 2796.61 | 4821.355 | 1398.305 | 699.15 | 640.425 | 139.83 | 1677.5456 | 2975.59 | 1677.5456 | 5033.9 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 838.9638 | 5593.08 | 0 | 2516.3206 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_279 | 511.7663 | 1258.1554 | 1342.374 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 | 10067.5444 | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 | 770.1679 | 0 | 9665.08 | 0 | 0 | 1219.881 | 2369.2267 | 1847.3929 | 3431.0509 | 5.034 | 2745.153 | 20443.22 | 2181.357 | 56766.1076 | 4737.46 | 25169.49 | 1677.966 | 2892.813 | 838.962 | 419.49 | 384.2452 | 83.898 | 1006.5274 | 2975.59 | 1006.5274 | 3020.34 | 6711.525 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 503.3782 | 3355.848 | 0 | 1509.7924 | 12304.455 | 16219.5287 | 1677.96 | 1677.97
V_14 |  |  | 2237.29 | 1381.53 | 7772.815 | 2796.61 | 7768.7762 | 0 | 10599.46 | 6622.37 | 17763.1813 |  | 3887.0963 | 1801.02 | 0 | 0 | 4597.04 | 402.71 | 5000.34 | 3227.29 | 13210.52 | 0 |  | 0 | 9665.08 | 0 | 0 | [6 empty] | 20443.22 | 3635.595 | 94614.91 | 4737.46 | 25169.49 | 2796.61 | 4821.355 | 1398.305 | 699.15 | 640.425 | 139.83 |  | 2975.59 |  |  | 6711.6637 | 0 | 0 | 2237.29 | 2796.61 | 2852.48 | 564.91 | 1320 | 2237.29 | 413.7962 | 0 | 0 | 0 | 0 | 4698.31 | 1677.54 | 0 | 1208.13 | 8949.15 | 0 | 0 | 1113.05 | 0 | 0 | 1677.54 | 1789.83 | 838.985 |  |  |  | 12304.455 | 16219.5287 | 1677.96 | 1677.97